## Treatment_tracker
Name | Owner | Date of SME session | Workshop Progress | Migration Strategy | Remarks | Date for Treatment Document completion (ETA) | Recorded Session URL | Peer Review Ownership | Peer Review Completion | Peer review completion - ETA | Ready for SDM Sign Off (Yes/No) | Status | SDM signed off email sent date | SDM Signoff received | Sox Governed | Gxp Governed | Complexity | Business Criticality | Peer Review Completed | Peer Review Pending
Abacus | Saurabh | 2020-08-21 | 100% | Replatform | Out Of Scope |  |  | Nihal | Yes |  | Yes | Completed | 2020-09-09 | 2020-09-16 | No | No | Medium | Medium | 1 | 0 | #N/A | #N/A
Active Directory |  | None | 100% | Out Of Scope | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
Adams |  | 2020-07-28 | 100% | Out Of Scope | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
ADFS (Active Directory Federation Services) |  | None | 100% | Out Of Scope |  |  | https://web.microsoftstream.com/video/73c0d14c-1e80-486b-99e5-86d95a313cab |  |  |  | NA | Out of Scope | [6 empty] | 0 | 0
Agile PLM | Razak | 2020-07-14 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/e10ef2f2-75fa-4d85-ba70-a720be10e5ae | Saurabh | Yes | 2020-08-12 | Yes | Completed | 2020-08-14 | 2020-09-25 | No | Yes | High | High | 1 | 0
AIMS (China) |  | None | 100% | Retirement | [6 empty] | NA | Out of Scope |  |  | No |  |  |  | 0 | 0
Alteryx | Nihal | 2020-08-18 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/714ebf7f-93dd-481a-b81c-57628859ab9f | Saurabh | Yes | 2020-08-27 | Yes | Completed | 2020-08-31 | 2020-12-08 | No | Yes | Medium | Medium | 1 | 0
Altium Designer | Nihal | 2020-07-28 | 100% | Rehost (L/S) | Application is out of scope, license server migration is in scope |  | https://web.microsoftstream.com/video/cc0b7fbb-d3da-4052-ba00-3a515492ea2d | Saurabh | Yes |  | Yes | Completed | 2020-08-21 | 2020-09-25 | No | No | Low | Low | 1 | 0
Ancile uPerform |  | None | 100% | Out Of Scope |  |  | https://web.microsoftstream.com/video/f5da5711-2a50-47e7-b283-f613e14c9e46 |  |  |  | NA | Out of Scope |  |  | No |  |  |  | 0 | 0
ANZPowerBI | Nihal | 2020-08-27 | 80% | Rehost (L/S) |  |  |  | Saurabh | Yes |  | Yes | Completed | 2020-09-10 | 2020-09-30 | No | No | Medium | Medium | 1 | 0
ASSIST4 | Nihal | 2020-07-10 | 100% | Rehost (L/S) |  |  |  | Saurabh | Yes |  | Yes | Completed | 2020-08-21 | 2020-09-14 | No | No | Low | Low | 1 | 0
Auftragsverwaltung (Loaner Pool) |  | None | 100% | Retirement | [6 empty] | NA | Out of Scope |  |  | No |  |  |  | 0 | 0
AutoCAD | Razak | 2020-07-14 | 100% | Replatform |  |  | https://web.microsoftstream.com/video/e10ef2f2-75fa-4d85-ba70-a720be10e5ae | Saurabh | Yes | 2020-08-28 | Yes | Completed | 2020-09-02 | 2020-09-25 | No | Yes | Medium | Medium | 1 | 0
Automic |  | 2020-07-15 | 100% | Retirement |  |  | https://web.microsoftstream.com/video/8f4ea89a-062b-4115-8e21-8a53f8ab5e39 | Saurabh | Yes |  | Yes | Out of Scope |  |  | No | Yes | High | High | 1 | 0
AVON |  | None | 100% | Retirement | [6 empty] | NA | Out of Scope |  |  | No |  |  |  | 0 | 0
AWM Data Warehouse | Nihal | 2020-07-13 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/fbf9973d-bbc1-4ac7-8d57-e57ca121978f | Saurabh | Yes |  | Yes | Completed | 2020-08-26 | 2020-09-30 | No | No | High | High | 1 | 0
Axapta 2009 (China) |  | None | 100% | Retirement | [6 empty] | NA | Out of Scope |  |  | No |  |  |  | 0 | 0
Axapta 2009 (Dubai) | Raju | 2020-10-07 | 100% | Out Of Scope |  |  |  | Saurabh | Yes |  | Yes | Out of Scope |  |  | No |  |  |  | 1 | 0
Axapta 2009 (India) | Raju | 2020-10-07 | 100% | Out Of Scope |  |  |  | Saurabh | Yes |  | Yes | Out of Scope |  |  | No |  |  |  | 1 | 0
Axapta 2009 (Malaysia & Thailand) | Raju | 2020-10-08 | 100% | Out Of Scope |  |  |  | Saurabh | Yes |  | Yes | Out of Scope |  |  | No |  |  |  | 1 | 0
Axapta 2009 (Singapore) | Raju | 2020-10-08 | 100% | Out Of Scope |  |  |  | Saurabh | Yes |  | Yes | Out of Scope |  |  | No |  |  |  | 1 | 0
Axway | Deepak | 2020-09-04 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/42d88d5f-4e3d-47ba-acae-e18662c1da4c | Saurabh | Yes |  | Yes | Completed | 2020-09-25 | 2020-10-20 | No |  |  |  | 1 | 0
BackupExec(OSIRIS) |  | None | 100% | Retirement | [6 empty] | NA | Out of Scope |  |  | No |  |  |  | 0 | 0
Bartender(OSIRIS) | Saurabh | 2020-08-27 | 100% | Rehost (L/S) |  |  |  | Nihal | Yes |  | Yes | Completed | 2020-09-02 | 2020-09-23 | No | No | Low | Low | 1 | 0
BAS |  | None | 100% | Out Of Scope | [6 empty] | NA | Out of Scope |  |  | No |  |  |  | 0 | 0
BI (CHINA) | Razak | 2020-07-09 | 100% | Rehost (L/S) |  | 2020-08-27 | https://web.microsoftstream.com/video/7f617777-e1f9-42ac-84c5-654c7c2a457d | Saurabh | Yes | 2020-09-01 | Yes | Completed | 2020-09-02 | 2020-09-03 | No | No | Medium | High | 1 | 0
BPCS - Japan |  | None | 100% | Retirement | [6 empty] | NA | Out of Scope |  |  | No |  |  |  | 0 | 0
Bugzilla | Raju | 2020-07-31 | 100% | Rehost (L/S) |  | 2020-09-03 | https://web.microsoftstream.com/video/2132a16c-0a7e-40cf-b62d-4bb4a5ef163d | Nihal | Yes |  | Yes | Completed | 2020-09-08 | 2020-09-25 | No | Yes | Medium | Medium | 1 | 0
Business Objects (IRAMEA) | Vidit | 2020-07-13 | 100% | Rehost (L/S) | review changes completed | 2020-08-28 | https://web.microsoftstream.com/video/971823ae-9465-40ee-9927-691f4c228df6 | Razak | Yes |  | Yes | Completed | 2020-09-08 | 2020-10-13 | Yes | No | Medium | Medium | 1 | 0
Calibration Manager(OSIRIS) |  | 2020-08-10 | 100% | Out Of Scope |  |  |  | Nihal | Yes |  | Yes | Out of Scope |  |  | No | No | Medium | Medium | 1 | 0
CardAccess 3000 |  | 2020-07-24 | 100% | Retirement | [6 empty] | NA | Out of Scope |  |  | No |  |  |  | 0 | 0
Central FTP | Razak | 2020-09-03 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/636aa985-f155-4e60-b7af-ae74cec386ee | Nihal | Yes | 2020-09-15 | Yes | Completed | 2020-09-18 | 2020-10-20 | No |  |  |  | 1 | 0
Cimco china | Saurabh | 2020-07-30 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/19e5fe6a-8602-47b2-8e2e-c7a9853551c2 | Nihal | Yes |  | Yes | Completed | 2020-08-13 | 2020-08-25 | No | Yes | Medium | Medium | 1 | 0
Cimco Mansfield | Saurabh | 2020-07-30 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/19e5fe6a-8602-47b2-8e2e-c7a9853551c2 | Nihal | Yes |  | Yes | Completed | 2020-08-13 | 2020-08-25 | No | Yes | Medium | High | 1 | 0
Cimco Memphis | Saurabh | 2020-07-30 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/19e5fe6a-8602-47b2-8e2e-c7a9853551c2 | Nihal | Yes |  | Yes | Completed | 2020-08-13 | 2020-08-25 | No | Yes | Medium | High | 1 | 0
Cisco System Unity VM and unified messaging |  | 2020-08-18 | 100% | Out Of Scope | [6 empty] | NA | Out of Scope |  |  | No |  |  |  | 0 | 0
CISCO Umbrella |  | None | 100% | Retirement | [6 empty] | NA | Out of Scope |  |  | No |  |  |  | 0 | 0
Cockpit | Razak | 2020-07-28 | 100% | Rehost (L/S) | Infra inventory validation pedning. | 2020-08-19 | https://web.microsoftstream.com/video/200f3f18-5a2d-4700-b754-b3c53c38a929 | Nihal | Yes | 2020-08-24 | Yes | Completed | 2020-08-26 | 2020-09-25 | No | No | Low | Low | 1 | 0
Cognos (STRATPLAN) | Saurabh | 2020-08-11 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/200f3f18-5a2d-4700-b754-b3c53c38a929 | Nihal | Yes |  | Yes | Completed | 2020-08-26 | 2020-09-30 | Yes | No | Medium | Medium | 1 | 0
Cognos BI (SoNAR Sales Dashboards & Standard Reporting) |  | None | 100% | Out Of Scope | [6 empty] | NA | Out of Scope |  |  | No |  |  |  | 0 | 0
Cognos Demand Planning |  | None | 100% | Retirement | [6 empty] | NA | Out of Scope |  |  | No |  |  |  | 0 | 0
Cognos Performance Mgmt (STGP) | Saurabh | 2020-08-13 | 100% | Rehost (L/S) |  |  |  | Nihal | Yes |  | Yes | Completed | 2020-08-26 | 2020-09-30 | No | No | Medium | High | 1 | 0
CONNECT |  | None | 100% | Retirement | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
Connect Plus |  | 2020-07-22 | 100% | Retirement |  |  | https://web.microsoftstream.com/video/8764116a-6fe7-47c3-b30a-6008031895e6 |  |  |  | NA | Out of Scope | [6 empty] | 0 | 0
Connect Ship (UPS/DHL) | Razak | 2020-07-08 | 100% | Rehost (L/S) |  | 2020-08-28 | https://web.microsoftstream.com/video/255b90e0-e8b9-46f6-94c2-358fe0e6b05f | Saurabh | Yes | 2020-09-02 | Yes | Completed | 2020-09-18 | 2020-09-21 | No | No | High | High | 1 | 0
CVS Concurrent Version System | Raju | 2020-07-30 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/ac03b481-9676-4b31-9987-45f747700c0e | Razak | Yes | 2020-09-07 | Yes | Completed | 2020-09-08 | 2020-09-25 | No | No | Low | Medium | 1 | 0
CyberArk EPM (Endpoint Privilege Management) |  | None | 100% | Out Of Scope | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
CyberArk PAM (Privileged Access Management) |  | None | 100% | Out Of Scope | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
dataSTOR | Deepak | 2020-07-16 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/79289f19-dcb7-4370-bc3f-15c99f21d86f | Razak | Yes | 2020-08-09 | Yes | Completed | 2020-08-14 | 2020-08-17 | No | No | Low | Medium | 1 | 0
DNC5000 | Razak | 2020-07-27 | 100% | Rehost (L/S) |  | 2020-08-28 | https://web.microsoftstream.com/video/538764ff-bb86-4477-8a00-7620e30a8058 | Saurabh | Yes | 2020-09-04 | Yes | Completed | 2020-08-10 | 2020-09-25 | No | No | High | High | 1 | 0
Dr.Sum | Raju | 2020-08-06 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/a3391b8c-c5c5-4507-befb-1cbe6e7217cc | Razak | Yes | 2020-08-24 | Yes | Completed | 2020-08-31 | 2020-09-16 | No | No | Low | Medium | 1 | 0
E-Adept | Razak | 2020-08-11 | 100% | Rehost (L/S) |  | 2020-08-28 | https://web.microsoftstream.com/video/d7a658de-d3d6-4840-b5d1-69ccf6dc9e65 | Saurabh | Yes | 2020-09-10 | Yes | Completed | 2020-09-15 | 2020-09-16 | No | Yes | Low | Low | 1 | 0
Eagle RF Express | Saurabh | 2020-08-26 | 100% | Rehost (L/S) | Sme as QAD ERP |  |  | Nihal | Yes |  | Yes | Completed | 2020-09-10 | 2020-09-10 | Yes | Yes | High | Medium | 1 | 0
ECAP |  | None | 100% | Retirement | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
eDiscovery |  | None | 100% | Retirement | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
Eflow | Razak | 2020-07-28 | 100% | Rehost (L/S) |  | 2020-08-28 | https://web.microsoftstream.com/video/d8230eb6-1cbc-4444-b857-e5e4e06b9734 | Saurabh | Yes | 2020-09-01 | Yes | Completed | 2020-09-02 | 2020-10-14 | No | No | High | High | 1 | 0
Electronic Instructions for Use | Deepak | 2020-07-07 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/27e3fec5-ea65-4be3-a269-f4efdc1b62f8 | Saurabh | Yes |  | Yes | Completed | 2020-08-21 | 2020-09-11 | No | Yes | Medium | High | 1 | 0
Embarcadero/Erwin Studio |  | 2020-08-25 | 100% | Retirement | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
ENCORE |  | None | 100% | Retirement | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
END NOTE |  | 2020-07-30 | 100% | Out Of Scope |  |  | https://web.microsoftstream.com/video/576ad3dc-018d-4d23-9b97-06e07f9d8d4d |  |  |  | NA | Out of Scope | [6 empty] | 0 | 0
Endo Loans | Vidit | 2020-07-17 | 100% | Rehost (L/S) | review changes completed |  | https://web.microsoftstream.com/video/8daee401-1283-4ac4-b599-43bfc0078604 | Nihal | Yes |  | Yes | Completed | 2020-08-21 | 2020-08-22 | No | No | Low | Low | 1 | 0
Enterprise Business Objects Reporting | Razak | 2020-08-05 | 100% | Rehost (L/S) |  | 2020-08-28 | https://web.microsoftstream.com/video/d34cf669-5837-460c-9d6d-19f34870a2b6 | Saurabh | Yes | 2020-09-03 | Yes | Completed | 2020-09-08 | 2020-10-20 | No | No | High | High | 1 | 0
Epats | Razak | 2020-07-31 | 100% | Rehost (L/S) |  | 2020-08-29 | https://web.microsoftstream.com/video/48c4afd9-2931-4023-9ddd-b5fc9564e536 | Saurabh | Yes | 2020-09-10 | Yes | Completed | 2020-09-18 | 2020-09-18 | No | No | High | Medium | 1 | 0
EpiServer | Razak | 2020-08-06 | 100% | Out Of Scope |  | 2020-08-29 | https://web.microsoftstream.com/video/3003abbd-dd72-46d6-8c02-87c6c4d65333 | Saurabh | Yes | 2020-09-10 | Yes | Out of Scope |  |  | No | No | Medium | Medium | 1 | 0
eRoom | Deepak | 2020-09-28 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/e58052c4-f61b-44a8-ada9-6e63bd5e13e8 | Vidit | Yes | 2020-10-10 | Yes | Completed | 2020-10-13 | 2020-10-10 | No | No | Medium | Low | 1 | 0
ERP LN |  | 2020-09-28 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/5e0470d6-e648-4723-b79c-0ffca9eb0737 | Saurabh | Yes |  | Yes | Out of Scope |  |  | Yes | No | High | High | 1 | 0
Euro log |  | None | 100% | Retirement | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
Event Manager |  | None | 100% | Out Of Scope | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
Evisense | Vidit | 2020-08-20 | 100% | Rehost (L/S) | review changes completed |  |  | Razak | Yes | 2020-08-30 | Yes | Completed | 2020-09-09 | 2020-09-25 | No | Yes | Medium | Low | 1 | 0
Exactus Payroll Application (Costa Rica) | Raju | 2020-08-17 | 100% | Rehost (L/S) |  |  |  | Saurabh | Yes |  | Yes | Completed | 2020-09-02 | 2020-09-04 | No | Yes | Low | Low | 1 | 0
Expert Document Imaging (EDI) | Razak | 2020-08-24 | 100% | Rehost (L/S) |  | 2020-08-29 | https://web.microsoftstream.com/video/bfb9bc31-6dfc-45a0-bba7-8bf741511f8f | Saurabh | Yes | 2020-09-03 | Yes | Completed | 2020-09-04 | 2020-10-02 | No | No | Low | Medium | 1 | 0
Express Implants | Razak | 2020-08-19 | 100% | Replatform |  | 2020-08-29 | https://web.microsoftstream.com/video/ebcefab7-920c-4409-895e-a5a8147e490e?list=studio | Saurabh | Yes | 2020-09-15 | Yes | Completed | 2020-09-15 | 2020-10-21 | No | Yes | High | Medium | 1 | 0
Express Instruments | Razak | 2020-08-19 | 100% | Replatform |  | 2020-08-29 | https://web.microsoftstream.com/video/ebcefab7-920c-4409-895e-a5a8147e490e?list=studio | Saurabh | Yes | 2020-09-15 | Yes | Completed | 2020-09-15 | 2020-10-21 | No | Yes | High | Medium | 1 | 0
Express Visionaire | Razak | 2020-08-03 | 100% | Replatform | Waiting for information from SME/SDM | 2020-08-31 | https://web.microsoftstream.com/video/0a37a515-6176-4c02-95d3-c0c0ea14bdc2 | Nihal | Yes | 2020-09-15 | Yes | Completed | 2020-09-18 | 2020-10-21 | No | Yes | Medium | Low | 1 | 0
FAS 500 -Sage | Razak | 2020-07-06 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/63dfc378-e1c0-496a-abc4-ffb53f6dd8d8 | Saurabh | Yes |  | Yes | Completed | 2020-08-26 | 2020-08-28 | No | No | Low | Low | 1 | 0
Fax to EDI - Order 2 Cash |  | None | 100% | Retirement | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
FileMaker | Vidit | 2020-08-04 | 100% | Rehost (L/S) | review changes completed |  | https://web.microsoftstream.com/video/facd9bd4-2de5-4c89-b0ea-4465230aebb9 | Saurabh | Yes |  | Yes | Completed | 2020-08-13 | 2020-08-14 | No | No | Low | Low | 1 | 0
Filezilla FTP Server | Nihal | 2020-08-04 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/9859c4c6-005f-49a7-9afb-4ac587f8c958 | Razak | Yes | 2020-08-16 | Yes | Completed | 2020-08-26 | 2020-10-13 | No | No | Medium | Medium | 1 | 0
Fishbowl |  | None | 100% | Retirement | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
Flex LM | Razak | 2020-08-04 | 100% | Rehost (L/S) |  | 2020-08-27 | https://web.microsoftstream.com/video/f8887c4e-59ab-44bf-b5c9-2509e6dbfbfe | Saurabh | Yes | 2020-08-29 | Yes | Completed | 2020-09-02 | 2020-09-25 | No | No | Medium | Medium | 1 | 0
Gentran Server for Unix |  | 2020-08-20 | 100% | Out Of Scope | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
Geomagic | Deepak | 2020-08-05 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/abaf826e-c3dd-458c-a288-1b0c2b339989 | Razak | Yes |  | Yes | Completed | 2020-09-04 | 2020-09-25 | No | Yes | Low | Medium | 1 | 0
Georgia Softworks | Saurabh | 2020-08-19 | 100% | Rehost (L/S) | Planned at 2:30 PM on Aug 19 |  | https://web.microsoftstream.com/video/1ab3b055-f9d9-4102-adce-d221672ea48c | Nihal | Yes |  | Yes | Completed | 2020-09-09 | 2020-10-13 | No | Yes | High | High | 1 | 0
Git Version control |  | 2020-08-20 | 100% | Retirement | Planned at 2 AM on Aug 21 |  | https://web.microsoftstream.com/video/895741cf-5703-4c15-bcbd-a51c363d2206 |  |  |  | NA | Out of Scope | [6 empty] | 0 | 0
Global Business Information Platform |  | 2020-07-24 | 100% | Out Of Scope | Planned at 3 AM on Aug 20 | [5 empty] | NA | Out of Scope | [6 empty] | 0 | 0
Global Data Warehouse | Nihal | 2020-07-24 | 100% | Rehost (L/S) | Planned at 1 AM on Aug 13 |  | https://web.microsoftstream.com/video/bbc118f9-b571-4b88-8e0a-fa36696a4dcf | Razak | Yes | 2020-08-16 | Yes | Completed | 2020-08-26 | 2020-09-30 | No | No | Medium | Low | 1 | 0
Global Market Monitoring | Nihal | 2020-07-24 | 100% | Rehost (L/S) | Planned at 5:30 PM on Aug 14 |  | https://web.microsoftstream.com/video/bf9c21f7-58c6-4534-a55b-af3a693ada77 | Razak | Yes | 2020-08-16 | Yes | Completed | 2020-08-26 | 2020-09-30 | No | No | Medium | Low | 1 | 0
Global Protect VPN |  | None | 100% | Out Of Scope | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
Global Regulatory Submissions | Nihal | 2020-07-20 | 100% | Rehost (L/S) | Planned at 5 PM on Aug 17 |  | https://web.microsoftstream.com/video/c7bbb18e-6250-414b-ba10-155f3b18126c | Saurabh | Yes |  | Yes | Completed | 2020-08-31 | 2020-09-10 | No | No | Medium | Low | 1 | 0
Global Returns Disposition Tool | Nihal | 2020-08-07 | 100% | Rehost (L/S) | Planned at 1 PM on Aug 20 |  | https://web.microsoftstream.com/video/c9e26a13-e490-4852-a422-4bc5e0cdffe7 | Saurabh | Yes |  | Yes | Completed | 2020-08-26 | 2020-09-11 | No | No | Low | Low | 1 | 0
GSC Data Warehouse Admin Tool | Nihal | 2020-07-24 | 100% | Rehost (L/S) | Planned at 3 PM on Aug 20 |  | https://web.microsoftstream.com/video/40dbcdbd-ef55-4d4e-ad19-4de4f0477b7d | Saurabh | Yes |  | Yes | Completed | 2020-09-02 | 2020-10-23 | No | No | Medium | Low | 1 | 0
HR Notification | Vidit | 2020-07-27 | 100% | Replatform | review changes completed |  | https://web.microsoftstream.com/video/b01b1083-818a-456d-b046-fed789072f65 | Razak | Yes | 2020-08-09 | Yes | Completed | 2020-08-18 | 2020-08-19 | No | No | Low | Low | 1 | 0
Hydra (Tuttlingen) | Saurabh | 2020-07-16 | 100% | Rehost (L/S) | Planned at 7:30 PM on Aug 19 |  | https://web.microsoftstream.com/video/98619d33-41ae-4895-ad41-23743b797f3d | Nihal | Yes |  | Yes | Completed | 2020-08-13 | 2020-08-31 | No | Yes | Low | High | 1 | 0
ID Prove | Deepak | 2020-08-11 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/ca85f395-b6a0-4af5-ad4e-a23477cbcb02 | Saurabh | Yes |  | Yes | Completed | 2020-08-31 | 2020-09-14 | No | No | Medium | Medium | 1 | 0
InfinityQS ProFicient (SPC software) | Razak | 2020-07-24 | 100% | Rehost (L/S) |  | 2020-08-30 | https://web.microsoftstream.com/video/c7aa29d2-a5f7-4693-b941-bba379dc6c6d | Saurabh | Yes | 2020-09-03 | Yes | Completed | 2020-09-04 | 2020-09-10 | No | No | Low | Medium | 1 | 0
Informatica (SoNAR Data Intergration) |  | 2020-08-24 | 100% | Out Of Scope | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
Informatica (Wound Data Intergration) | Razak | 2020-07-29 | 100% | Rehost (L/S) |  | 2020-08-30 | https://web.microsoftstream.com/video/31bd2469-2de3-4c7c-a4e4-6bb975f5a36f | Saurabh | Yes | 2020-09-03 | Yes | Completed | 2020-09-04 | 2020-10-05 | No | No | High | High | 1 | 0
Informatica MDM Data Quality | Razak | 2020-07-30 | 100% | Rehost (L/S) |  | 2020-08-30 | https://web.microsoftstream.com/video/fd1ec44b-e7fe-45fc-bb5f-1f9dc712dfa1 | Saurabh | Yes | 2020-09-03 | Yes | Completed | 2020-09-04 | 2020-09-30 | No | No | High | High | 1 | 0
Informatica P360 | Saurabh | None | 100% | TBD |  |  | https://web.microsoftstream.com/video/f3101242-04ad-41bc-a867-254b545ba7f5 | Nihal | Yes |  | Yes | Completed | 2020-09-15 | 2020-10-19 | No | Yes | High | Medium | 1 | 0
Interform/400 |  | None | 100% | Out Of Scope | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
Inventures (SCAMPI) Web App | Razak | None | 100% | TBD | Same as express instruments |  | https://web.microsoftstream.com/video/ebcefab7-920c-4409-895e-a5a8147e490e?list=studio | Saurabh | Yes | 2020-09-15 | Yes | Completed | 2020-09-15 | 2020-10-21 | No | Yes | High | Medium | 1 | 0
IQ-Soft (Aarau) | Deepak | 2020-08-19 | 100% | Rehost (L/S) |  |  |  | Saurabh | Yes |  | Yes | Completed | 2020-09-08 | 2020-09-08 | No | Yes | Medium | Low | 1 | 0
IRAMEA-LATAM Data Warehouse (South Africa) | Saurabh | 2020-08-12 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/424870cf-a267-4c43-95aa-9935d955cea1 | Nihal | Yes |  | Yes | Completed | 2020-08-31 | 2020-10-13 | No | No | Medium | Medium | 1 | 0
iScala (Hong Kong) |  | None | 100% | Retirement | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
iStability | Razak | 2020-07-23 | 100% | Rehost (L/S) | Aileen to complete questiniare and server validation. | 2020-09-01 | https://web.microsoftstream.com/video/9f531892-cc42-452c-ae23-b87ea656d70b | Saurabh | Yes |  | Yes | Completed | 2020-09-15 | 2020-09-16 | No | Yes | Medium | Low | 1 | 0
IXI UMS Fax Server |  | 2020-08-18 | 100% | Out Of Scope | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
Jobrouter | Nihal | 2020-07-16 | 100% | Out Of Scope |  |  | https://web.microsoftstream.com/video/79289f19-dcb7-4370-bc3f-15c99f21d86f | Saurabh | Yes |  | Yes | Out of Scope |  |  | No | No | Medium | Medium | 1 | 0
Kaba Elostar | Saurabh | 2020-08-21 | 100% | Rehost (L/S) |  |  |  | Nihal | Yes |  | Yes | Completed | 2020-09-04 | 2020-10-20 | No | No | Medium | Low | 1 | 0
KepServerEx (Amsterdam & USA) | Deepak | 2020-08-12 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/37c0f09f-a2e9-44f6-97e5-65d32158cf9d | Razak | Yes |  | Yes | Completed | 2020-09-04 | 2020-10-28 | No | No | Low | Low | 1 | 0
KepServerEx (China) |  | 2020-08-12 | 100% | Out Of Scope | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
Lasernet / Nemhandel | Nihal | 2020-07-30 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/a1cbd0c1-461e-419d-9803-6646b9fcfe49 | Saurabh | Yes |  | Yes | Completed | 2020-09-04 | 2020-10-23 | No | No | Low | Medium | 1 | 0
LDAPUpdate | Deepak | 2020-08-21 | 90% | Replatform |  |  | https://web.microsoftstream.com/video/f1f0fac7-c59f-499a-8de4-e1da7d1b7d8d | Saurabh | Yes |  | Yes | Completed | 2020-09-04 | 2020-10-02 | No | No | Low | Low | 1 | 0
LIFEMOD BIOMECHANICS SYS |  | 2020-08-04 | 100% | Retirement | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
Loaners/OSC |  | None | 100% | Retirement | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
LogicMonitor |  | None | 100% | Out Of Scope | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
Logility Voyager (SCP) |  | None | 100% | Out Of Scope | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
Logility Voyager (SCP) - Data Integration |  | None | 100% | Out Of Scope | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
Lutron | Raju | 2020-08-25 | 100% | Rehost (L/S) |  |  |  | Saurabh | Yes |  | Yes | Completed | 2020-09-22 | 2020-09-23 |  |  |  |  | 1 | 0
Magic X |  | 2020-08-14 | 100% | Out Of Scope | Removed from Network License Server |  | https://web.microsoftstream.com/video/e2c4299e-27b2-432b-83e0-28ffab75a52c |  |  |  | NA | Out of Scope | [6 empty] | 0 | 0
Mainsaver CMMS (UK) | Razak | 2020-08-11 | 100% | Rehost (L/S) |  | 2020-09-01 | https://web.microsoftstream.com/video/c83f4b2f-bd52-49a5-aeb7-9a29e63589bd | Saurabh | Yes |  | Yes | Completed | 2020-09-15 | 2020-09-17 | No | Yes | Medium | Low | 1 | 0
MASK |  | None | 100% | Out Of Scope |  |  |  | Razak |  |  | NA | Out of Scope | [6 empty] | 0 | 0
MATLAB | Saurabh | 2020-08-10 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/01770347-2701-4e5a-ba13-25f027d7c73f | Nihal | Yes |  | Yes | Completed | 2020-09-02 | 2020-09-25 | No | No | Medium | Medium | 1 | 0
McAfee ePO Console |  | 2020-09-04 | 100% | Out of Scope | [7 empty] | Out of Scope | [6 empty] | 0 | 0
Mcosomos | Saurabh | 2020-08-26 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/b94f1533-8e87-471f-8073-81f5fd36bdbf | Razak | Yes |  | Yes | Completed | 2020-09-15 | 2020-09-16 | No | No | Medium | Medium | 1 | 0
Metasys | Saurabh | 2020-07-17 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/f5da5711-2a50-47e7-b283-f613e14c9e46 | Razak | Yes |  | Yes | Completed | 2020-08-13 | 2020-08-17 | No | Yes | Medium | Medium | 1 | 0
Microsoft CRM |  | None | 100% | Retirement | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
Microsoft Dynamics CRM 2016 (ANZ) |  | 2020-07-28 | 100% | Retirement | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
MIMICS | Razak | 2020-07-31 | 100% | Rehost (L/S) |  | 2020-09-01 | https://web.microsoftstream.com/video/74501093-aa15-41ce-af1e-f2b1628043af | Nihal | Yes | 2020-09-15 | Yes | Completed | 2020-09-18 | 2020-09-25 | No | Yes | Low | Low | 1 | 0
Minitab | Razak | 2020-07-20 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/24b8a62b-dff8-464d-908c-4140fe9c4fe6 | Saurabh | Yes |  | Yes | Completed | 2020-08-21 | 2020-08-31 | Yes | Yes | Low | Low | 1 | 0
MLE (China) |  | None | 100% | Out Of Scope | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
MLE (Hull) |  | None | 100% | Out Of Scope | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
Mobile Inventory Management System | Deepak | 2020-07-21 | 100% | Rehost (L/S) | Completed the review comment changes and uploaded the doc |  | https://web.microsoftstream.com/video/bf1b9d0e-d442-4bf7-b3c9-49fffec54f94 | Nihal | Yes |  | Yes | Completed | 2020-08-13 | 2020-08-21 | Yes | Yes | Medium | High | 1 | 0
Motion Board | Raju | 2020-08-06 | 100% | Rehost (L/S) |  |  |  | Razak | Yes | 2020-08-25 | Yes | Completed | 2020-08-31 | 2020-09-16 | No | No | Low | Medium | 1 | 0
Myriad | Vidit | 2020-07-31 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/6a601a6b-ca9e-4284-9873-4f75bc7e3bc6 | Razak | Yes | 2020-08-30 | Yes | Completed | 2020-08-31 | 2020-09-01 | No | No | Low | Low | 1 | 0
Nexpose Metasploit |  | None | 100% | Out Of Scope | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
Nomino Security | Vidit | 2020-08-14 | 100% | Rehost (L/S) | review changes completed |  |  | Saurabh | Yes |  | Yes | Completed | 2020-08-26 | 2020-09-11 | No | No | Low | Low | 1 | 0
Non-Employee Database | Vidit | 2020-07-27 | 100% | Rehost (L/S) | review changes completed |  | https://web.microsoftstream.com/video/b01b1083-818a-456d-b046-fed789072f65 | Saurabh | Yes |  | Yes | Completed | 2020-08-18 | 2020-08-19 | No | No | Low | Low | 1 | 0
NPWT Tracker | Saurabh | 2020-08-31 | 100% | Rehost (L/S) |  |  |  | Nihal | Yes |  | Yes | Completed | 2020-09-10 | 2020-09-11 | No | No | Medium | High | 1 | 0
OEE | Saurabh | 2020-07-21 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/cdc1d134-23e5-42ab-a4da-2fdacab64989 | Nihal | Yes |  | Yes | Completed | 2020-09-04 | 2020-10-28 | No | No | Low | Low | 1 | 0
Offline Counting | Nihal | 2020-08-25 | 100% | Replatform |  |  |  | Saurabh | Yes |  | Yes | Completed | 2020-09-15 | 2020-09-16 | Yes | No | Medium | Low | 1 | 0
OLMEC - UDI Printing | Razak | 2020-08-19 | 100% | Rehost (L/S) | Planned at 3 AM on Aug 20 | 2020-09-15 | https://web.microsoftstream.com/video/ebcefab7-920c-4409-895e-a5a8147e490e?list=studio | Nihal | Yes |  | Yes | Completed | 2020-09-18 | 2020-09-25 | No | No | Medium | High | 1 | 0
Oracle Enterprise Manager | Saurabh | 2020-08-14 | 100% | Rehost (L/S) | Planned at 1 AM on Aug 13 |  | https://web.microsoftstream.com/video/2ae39d43-53f9-4240-8fd4-dcc5392fb6e6 | Razak | Yes |  | Yes | Completed | 2020-09-15 | 2020-09-30 | No | No | Medium | Medium | 1 | 0
Oracle Hyperion | Nihal | 2020-07-27 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/2adcec08-77c3-409b-bad8-cb764ec1bab1 | Saurabh | Yes |  | Yes | Completed | 2020-08-31 | 2020-09-07 | No | No | Medium | Low | 1 | 0
OSISoft PI System | Razak | 2020-08-13 | 100% | Replatform | Planned at 1 AM on Aug 13 | 2020-09-01 | https://web.microsoftstream.com/video/3ced8476-0dde-4c2c-a189-7a0b4fd6a208 | Saurabh | Yes |  | Yes | Completed | 2020-09-15 | 2020-10-21 | No | No | High | Low | 1 | 0
Palo Alto DNS Filtering |  | None | 100% | Out Of Scope | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
PanelBuilder |  | None | 100% | Out Of Scope | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
Panorama (Palo Alto Firewall Management Platform) |  | None | 100% | Out Of Scope | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
PartMaker | Saurabh | 2020-07-29 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/b9cafeb4-c99f-4d43-b35a-228f4e8c95b0 | Nihal | Yes |  | Yes | Completed | 2020-09-02 | 2020-10-28 | No | Yes | Low | Low | 1 | 0
Paymetric Application System | Saurabh | 2020-08-21 | 100% | Rehost (L/S) | Planned at 5:30 PM on Aug 14 |  |  | Nihal | Yes |  | Yes | Completed | 2020-09-04 | 2020-10-16 | No | No | Medium | High | 1 | 0
Payroll - Softland (Colombia) |  | None | 100% | Retirement | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
PCM (procurement) |  | None | 100% | Retirement | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
PMPA | Nihal | 2020-07-31 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/cfeba761-099b-4377-acad-be9cc2664a98 | Saurabh | Yes |  | Yes | Completed | 2020-08-26 | 2020-09-30 | No | Yes | Medium | Medium | 1 | 0
Power BI (China) | Razak | 2020-08-14 | 100% | Rehost (L/S) | IT Architecure with complex integration |  |  | Saurabh | Yes |  | Yes | Completed | 2020-08-18 | 2020-08-31 | No | Yes | Low | High | 1 | 0
PricingTool | Deepak | 2020-08-17 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/91fe1881-f0c5-4301-8ca3-f1fed556a708 | Saurabh | Yes |  | Yes | Completed | 2020-09-18 | 2020-09-18 | No | No | Medium | Medium | 1 | 0
Primion | Saurabh | 2020-08-05 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/8b736fba-664e-4fc6-a6a4-335dffcf4b14 | Nihal | Yes |  | Yes | Completed | 2020-09-04 | 2020-10-23 | No | No | Medium | Low | 1 | 0
Procurement Spend Management |  | 2020-07-22 | 100% | Out Of Scope |  |  | https://web.microsoftstream.com/video/da2cf8bb-460b-49f2-ab7d-dfb9be739796 |  |  |  | NA | Out of Scope | [6 empty] | 0 | 0
PTC Creo | Deepak | 2020-09-03 | 90% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/fe4a3d00-ee7f-4cb7-a8d8-6e5a0d0b8bfa | Razak | Yes |  | Yes | Completed | 2020-09-04 | 2020-09-25 | No | No | Low | Medium | 1 | 0
QA Change Control | Vidit | 2020-09-03 | 100% | Rehost (L/S) | New app came into scope as part of Azure Migration along with co hosted other apps. |  |  | Razak | Yes |  | yes | Completed | 2021-01-18 | 2021-01-21 | Yes | No | Low | Medium
QAD ERP | Saurabh | 2020-08-26 | 100% | Rehost (L/S) | Same as Eagle RF Express |  | https://web.microsoftstream.com/video/2d402d6f-550e-4c43-b608-86f99151b5e0 | Nihal | Yes |  | Yes | Completed | 2020-09-10 | 2020-09-10 | Yes | Yes | High | Medium | 1 | 0
RADB | Nihal | 2020-08-03 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/394e704a-73cf-4bb0-a276-6c5cd45bf7c5 | Saurabh | Yes | Yes | Yes | Completed | 2020-09-10 | 2020-09-16 | No | No | Medium | High | 1 | 0
RAMS (China) | Razak | 2020-08-11 | 100% | Rehost (L/S) | Same as eFlow |  | https://web.microsoftstream.com/video/d8230eb6-1cbc-4444-b857-e5e4e06b9734 | Saurabh | Yes |  | Yes | Completed | 2020-09-04 | 2020-09-09 | No | No | High | High | 1 | 0
Recon LaunchPad (SSO) | Deepak | 2020-08-18 | 90% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/4f581ad6-0d46-4124-ad8c-953f5cef9167 | Nihal | Yes |  | Yes | Completed | 2020-09-04 | 2020-09-09 | No | No | Medium | High | 1 | 0
Reflections (AS400 emulator for AWMANZ BPCS) |  | None | 100% | Retirement | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
Reimbursement | Nihal | 2020-07-13 | 100% | Rehost (L/S) |  |  |  | Saurabh | Yes |  | Yes | Completed | 2020-08-13 | 2020-08-14 | No | No | Low | Low | 1 | 0
Sales Request Forms | Deepak | 2020-07-13 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/4c075843-a4de-405a-82e4-08d4ecfbdbd7 | Nihal | Yes |  | Yes | Completed | 2020-08-31 | 2020-08-31 | No | No | Medium | Low | 1 | 0
Salient |  | None | 100% | Retirement | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
SAP Business One |  | None | 100% | Retirement | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
SAP Business Warehouse |  | None | 100% | Out Of Scope | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
SEAL Application | Nihal | 2020-08-05 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/5987bfc6-989e-4a54-ab6e-ac8722ba4cb5 | Saurabh | Yes |  | Yes | Completed | 2020-09-02 | 2020-09-24 | No | Yes | Medium | Medium | 1 | 0
Skillsoft (Percipio) |  | None | 100% | Out Of Scope | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
Smart EHL | Nihal | 2020-08-18 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/755ccad3-cb00-46e3-b49f-49e0cf56d389 | Saurabh | Yes |  | Yes | Completed | 2020-09-08 | 2020-09-16 | No | No | Medium | Low | 1 | 0
SmartGit |  | 2020-08-20 | 100% | Retirement |  |  | https://web.microsoftstream.com/video/895741cf-5703-4c15-bcbd-a51c363d2206 |  |  |  | NA | Out of Scope | [6 empty] | 0 | 0
SNID Archived Shipping Documents | Nihal | 2020-08-19 | 100% | Replatform |  |  | https://web.microsoftstream.com/video/72b0195a-1c7d-4f39-9202-c598178cb43f | Saurabh | Yes |  | Yes | Completed | 2020-09-08 | 2020-10-13 | No | No | Medium | Low | 1 | 0
Solarwinds |  | None | 100% | Out Of Scope | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
Solidworks | Razak | 2020-07-17 | 100% | Rehost (L/S) | Matt to confirm Server to Srikanth |  |  | Saurabh | Yes |  | Yes | Completed | 2020-08-13 | 2020-09-25 | No | No | Low | Low | 1 | 0
Solidworks PDM Professional | Razak | 2020-08-19 | 100% | Rehost (L/S) |  | 2020-08-31 | https://web.microsoftstream.com/video/79b5e3e3-dd30-4f4b-b75d-b9f94c70ccff | Saurabh | Yes |  | Yes | Completed | 2020-09-15 | 2020-09-25 | No | No | High | High | 1 | 0
Solidworks PDM Workgroup | Razak | 2020-08-19 | 100% | Rehost (L/S) |  | 2020-08-31 | https://web.microsoftstream.com/video/79b5e3e3-dd30-4f4b-b75d-b9f94c70ccff | Saurabh | Yes |  | Yes | Completed | 2020-09-15 | 2020-09-25 | No | Yes | Low | Low | 1 | 0
SOTI | Saurabh | 2020-07-15 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/4ecd55e8-b362-4fe4-be06-51ec3e859d31 | Nihal | Yes |  | Yes | Completed | 2020-08-13 | 2020-08-25 | No | No | Medium | Medium | 1 | 0
Spectrum 10 | Razak | 2020-08-17 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/e47694c9-7425-46b8-bd5d-cfdb489e5bb1 | Saurabh | Yes | 2020-09-07 | Yes | Completed | 2020-09-04 | 2020-09-09 | No | Yes | Low | Medium | 1 | 0
SVN - Subversion Configuration Management |  | 2020-08-13 | 100% | Retirement |  |  | https://web.microsoftstream.com/video/2cb18ee0-c673-4d42-8bc6-0c7eac7d0efc |  |  |  | NA | Out of Scope | [6 empty] | 0 | 0
SVN Tortoise |  | 2020-09-18 | 100% | Out Of Scope | [6 empty] | No | Out of Scope | [6 empty] | 0 | 0
Symon Jumpstart |  | 2020-07-28 | 100% | Retirement | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
Syngistix | Razak | 2020-08-20 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/f0b60403-78ff-44a8-83ee-9f76c65e3f78 | Saurabh | Yes | 2020-09-07 | Yes | Completed | 2020-09-04 | 2020-09-30 | No | Yes | Medium | Medium | 1 | 0
System Center Configuration Manager (SCCM) |  | 2020-08-31 | 100% | Out Of Scope | Planned at 5 PM on Aug 17 | [5 empty] | No | Out of Scope | [6 empty] | 0 | 0
Tableau Bridge | Saurabh | 2020-08-20 | 100% | Rehost (L/S) | Planned at 1 PM on Aug 20 |  |  | Nihal | Yes |  | Yes | Completed | 2020-08-31 | 2020-09-30 | No | No | Medium | Medium | 1 | 0
Tarife | Saurabh | 2020-08-20 | 100% | Rehost (L/S) | Planned at 3 PM on Aug 20 |  |  | Nihal | Yes |  | Yes | Completed | 2020-09-04 | 2020-09-14 | No | No | Low | Low | 1 | 0
Tenable VMS |  | None | 100% | Out Of Scope | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
TIAMO | Razak | 2020-08-17 | 100% | Rehost (L/S) |  | 2020-08-27 | https://web.microsoftstream.com/video/16d63594-24f1-446b-afa7-08bc00e8bdf5 | Saurabh | Yes | 2020-09-01 | Yes | Completed | 2020-09-02 | 2020-09-02 | Yes | Yes | Low | Low | 1 | 0
TM1 (Global Cost Visibility) | Saurabh | 2020-08-06 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/dc0aa6a1-698d-43cc-972f-5a98dba35aeb | Nihal | Yes |  | Yes | Completed | 2020-08-17 | 2020-09-30 | Yes | No | Medium | High | 1 | 0
TM1 (Transfer Pricing) | Saurabh | 2020-08-07 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/a520eb7a-39d5-4965-abdd-73465eec4dd0 | Nihal | Yes |  | Yes | Completed | 2020-08-17 | 2020-09-30 | Yes | No | Medium | High | 1 | 0
TM1 Cognos Configuration | Saurabh | 2020-08-12 | 100% | Rehost (L/S) |  |  | No Video | Nihal | Yes |  | Yes | Completed | 2020-08-17 | 2020-09-30 | No | No | Medium | High | 1 | 0
Tops Pro | Raju | 2020-08-13 | 100% | Rehost (L/S) | Planned at 2:30 AM on Aug 13 |  | https://web.microsoftstream.com/video/2cb18ee0-c673-4d42-8bc6-0c7eac7d0efc | Saurabh | Yes |  | Yes | Completed | 2020-09-15 | 2020-09-17 | No | No | Low | Low | 1 | 0
TotalChrom |  | None | 100% | Retirement | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
TOTVS | Saurabh | None | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/bf370b95-4181-47ab-918c-e1871de9cb58 | Nihal | Yes |  | Yes | Completed | 2020-08-26 | 2020-09-16 | No | Yes | High | High | 1 | 0
Trackwise (EU) | Saurabh | 2020-08-19 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/d7e691fe-bff2-4da4-85e2-3d1ed8b0f3e9 | Nihal | Yes |  | Yes | Completed | 2020-09-09 | 2020-09-10 | No | No | Low | Medium | 1 | 0
Trackwise (US) |  | 2020-07-29 | 100% | Retirement | Planned at 7:30 PM on Aug 19 |  |  | Razak |  |  |  | Out of Scope |  |  | No | No | Medium | Low | 0 | 0
Trios Guardian | Razak | 2020-07-21 | 100% | Rehost (L/S) | 7/22 - Waiting for inputs from Aileen | 2020-08-27 | https://web.microsoftstream.com/video/507da32f-8ad7-4944-8af0-6327c02d9928 | Saurabh | Yes | 2020-09-01 | Yes | Completed | 2020-09-02 | 2020-09-02 | No | No | Low | Low | 1 | 0
Unified Functional Testing | Raju | 2020-08-20 | 100% | Replatform |  |  |  | Saurabh | Yes |  | Yes | Completed | 2020-09-02 | 2020-09-30 | No | No | Low | Low | 1 | 0
Unigraphics | Saurabh | 2020-08-04 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/bee9f0c4-7883-411b-b5d9-dec87b88eb8d | Nihal | Yes |  | Yes | Completed | 2020-09-04 | 2020-09-25 | No | No | Low | Medium | 1 | 0
VEI Label Verification | Vidit | 2020-08-19 | 50% | Rehost (L/S) | review changes completed |  | https://web.microsoftstream.com/video/5acb1f64-50e4-4558-b7cb-7a37b6ee63ca | Razak | Yes | 2020-09-15 | Yes | Completed | 2020-09-15 | 2020-10-28 | No | Yes | Medium | High | 1 | 0
Vericut | Nihal | 2020-07-27 | 100% | Rehost (L/S) |  |  |  | Saurabh | Yes |  | Yes | Completed | 2020-09-08 | 2020-09-09 | No | No | Low | Low | 1 | 0
Vertex - Q Series |  | None | 100% | Out Of Scope | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
Vertex - Q Series Returns |  | None | 100% | Out Of Scope | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
Vertex - Rate Locator |  | None | 100% | Out Of Scope | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
Vertex - Tax Decision Maker |  | None | 100% | Out Of Scope | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
Vertex Sales & Use Tax Returns |  | None | 100% | Out Of Scope | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
Vertex Sales Tax Q Series |  | None | 100% | Out Of Scope | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
Visionaire Case Management (VCM) |  | 2020-08-17 | 100% | Out Of Scope |  |  | https://web.microsoftstream.com/video/0c7c6e71-24c7-44ab-a24a-55326c02fb5a https://web.microsoftstream.com/video/75d9852c-2348-4ff9-8086-c20963873620 |  |  |  | NA | Out of Scope | [6 empty] | 0 | 0
Visionaire Case Processing of Images | Razak | 2020-08-19 | 100% | Rehost (L/S) |  | 2020-08-31 | https://web.microsoftstream.com/video/ceaf78cd-b215-4392-bc96-cf06bfffdc67 | Saurabh | Yes | 2020-09-15 | Yes | Completed | 2020-09-18 | 2020-09-25 | No | Yes | High | High | 1 | 0
Visual SVN | Deepak | 2020-08-20 | 100% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/895741cf-5703-4c15-bcbd-a51c363d2206 | Razak | Yes | 2020-09-07 | Yes | Completed | 2020-09-08 | 2020-10-21 | No | No | Low | Medium | 1 | 0
WebOps |  | None | 100% | Out Of Scope | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
Windchill PLM |  | None | 100% | Out Of Scope | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
Winflex | Deepak | 2020-08-20 | 90% | Rehost (L/S) |  |  | https://web.microsoftstream.com/video/15fbd908-4ce5-47d7-989e-94db8a5f2a86 | Razak | Yes |  | Yes | Completed | 2020-09-04 | 2020-09-14 | No | No | Low | Low | 1 | 0
Winshuttle | Vidit | 2020-08-25 | 100% | Rehost (L/S) | Review changes completed |  | https://web.microsoftstream.com/video/f488c966-4247-4346-88c2-a4ff8c35ade6 | Saurabh | Yes | 2020-09-09 | Yes | Completed | 2020-09-09 | 2020-10-27 | Yes | Yes | Medium | High | 1 | 0
zScaler Private Access (ZPA) |  | 2020-08-25 | 100% | Retirement | [6 empty] | NA | Out of Scope | [6 empty] | 0 | 0
High
Medium
Simple
| Razak | Planned
| Nihal | Out of Scope
| Saurabh | In-Progress
| Vidit | Resheduled
| Deepak | Completed
| Raju | Not Started
Formulas:
Date of SME session = IF(VLOOKUP([Name],'Waves of question forms'!$A2:N214,13) = "",VLOOKUP([Name],'Waves of question forms'!$A2:N214,12),VLOOKUP([Name],'Waves of question forms'!$A2:N214,13))

## Waves of question forms
Name | Description | Sanitized business domain | Cloud Possible | Questions order | IT Application Owner | Service Delivery Manager | IT Application SME | Business Application Owner | Business Application SME | estemated best timezone | Original workshop date | Rescheduled workshop date | 2nd workshop date | 3rd workshop date | Needed SME's confirmed | Questionare Ready for meeting date | Questonare % complete | HCL Meeting prep completed date | Workshop progress (%) | Hosting target | If retiring date | If DCaaS - why? | Cloud migration model | High level migration plan in place | Migrate key points list in place | Comments | RISK & Mitigation | Closing Date | SDM Sign-Off Email Sent Date | SDM Sign-Off Status | SDM Sign-Off Received Date | Reminder to SDM | Application Complexity by HCL
Abacus |  | Group Functions | yes |  | Philip Sedgwick | Paul Davison |  |  |  | eu | 2020-08-13 | 2020-08-21 |  |  | Yes | Yes | 100% | 2020-08-21 | 100% | SNI Azure |  |  | Replatform | Yes - complete | Yes - complete | Assessment work in completed. |  | 2020-09-04 | 2020-09-09 | Sign-Off Received | 2020-09-16 |  | Medium
Active Directory | Domain Controller, DNS, DHCP Services | ET | Yes | 2 - July 13 | Roman Wojtasik | Roman Wojtasik | Sathish Kumar | Patryk Bromirski | Sathish Kumar | eu | 2020-07-16 | None | None | None | None | None | None | None | 100% | Infrastructure service - out of scope |  |  | Out Of Scope | Not needed | Not needed | Patryk - I was just on the phone with Przemyslaw from the Cloud team trying to explain that I don’t believe that we should be doing this exercise for AD. AD includes core services such as at DNS, DHCP. They are already extending into our Cloud. But if there’s further work to be done, then I think we just need a technical conversation, but this would have been done during the design phase. |  | 2020-07-16
Adams | Ortho Research and Product Development. 12/3/13 - Updated name from "LifeMod and Adams" to "Adams" per Randall Reavis. | R&D | Yes | 1 - July 6 | Ian Bennett | Matthew Stephens | Sumanth Arigela | Brian McKinnon |  | us | 2020-07-09 | 2020-07-28 | None | None | None | None | None | None | 100% | Other - comments |  |  | Out Of Scope | Not needed | Not needed | Hi Deepak- The Altium questionnaire is updated on the teams site. We need to move the Adams discussion out a couple of weeks as the business has decided to close the offices where that software development team is located and mostly likely, those apps will be migrated to the Robotics team’s AWS cloud. We have a meeting this week to discuss this new development. Matt |  | 2020-08-25
ADFS (Active Directory Federation Services) | End-user authentication services; Current: Exchange Online, InTune (Company Portal), Lync, Yammer, Sharepoint (Online and Compass) | ET | Yes | 2 - July 13 | Jakub Keler | Paul Funk | Patryk Bromirski | Anna Falbogowska |  | eu | 2020-07-17 | None | None | None | None | None | None | None | 100% | Infrastructure service - out of scope |  |  | Out Of Scope | Not needed | Not needed | Patryk - I was just on the phone with Przemyslaw from the Cloud team trying to explain that I don’t believe that we should be doing this exercise for AD. AD includes core services such as at DNS, DHCP. They are already extending into our Cloud. But if there’s further work to be done, then I think we just need a technical conversation, but this would have been done during the design phase. |  | 2020-07-21
Agile PLM | PLM system for ex-Arthrocare products | R&D | Yes | 1 - July 6 | Ian Bennett | Matthew Stephens | Sumanth Arigela | Al Torabi |  | us | 2020-07-09 | 2020-07-14 |  |  | Yes | Yes | 100% | 2020-07-14 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. | - cateorised as Complex application with mutiple env, LB, DR, BCP (dependencies). - No Vendor Support - BCP dependecies (out of scope) needs to be taken care. | 2020-08-17 | 2020-08-14 | Sign-Off Received | 2020-09-25 | 2020-08-24 | Complex
AIMS (China) | Asset Instrument Management Systems - SC management of instrument sets Product Vendor Support=UNSUPPORTED Delivery Manager Cert:22JUN17 | Supply Chain | Yes | 1 - July 6 | Benny Xu | Benny Xu | Benny Xu | Mona Li | KiKi Liu | ap | 2020-07-06 | None | None | None | None | None | None | None | 100% | Retirement | 2020-07-01 |  | Retirement | Not needed | Not needed | Hello Nihal, Benny will be leaving us 3rd July also AX2009 / AIMS have ben replaces with POWER AX 2012 which we went live yesterday. Best Regards Massimo |  | 2020-06-30
Alteryx | Alteryx is a BI application which will be used by Supply Chain for loading and manipulating data sets which will then be published through Tableau Online. | Data & Analytics | Yes | 2 - July 13 | Stuart Robinson | Sathiamurthy Samidurai |  | Alexander Meijer |  | ap | 2020-07-30 | 2020-08-18 |  |  | Yes | Yes | 100% | 2020-08-18 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | assessment work is complete. |  | 2020-08-24 | 2020-08-31 | Pending with SDM |  | 2020-09-10 | Medium
Altium Designer | Bluebelt An electrical CAD package for electrical design schematics capture and printed circuit boards layout. | R&D | Yes | 2 - July 13 | Ian Bennett | Matthew Stephens | Sumanth Arigela | James Moody |  | us | 2020-07-16 | 2020-07-28 |  |  | Yes | Yes | 100% | 2020-07-28 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed |  | 2020-08-21 | 2020-08-21 | Sign-Off Received | 44099 | 2020-08-24 | incomplete assessment
Ancile uPerform | Training Development tool for SAP. uPerform has been used extensively since 2006 (when it was a prior application called Infopak). It is a completely different type of tool than Learncenter. There are great synergies between the two but they are very different. uPerform at the highest level is a documentation creation tool that allows SMEs to record training documentation - effectively reducing/eliminating the requirement to have consultants or specialized training developers to create documentation. Once the documentation is created using the desktop application by the authors, the resulting documentation can be published to uPerform's End User website. Anyone who is on the SN network has visibility to the documentation. One work instruction document created by an author creates multiple outputs: html based, pdf, and a html-based simulation. One document with multiple outputs. In addition to transactional-based documentation, uPerform also offers the development of a document output called a Course. These are similar to "powerpoint" type courses that can contain embedded simulations with the option to include a knowledge check as well. It is a very robust application and has been used for all NAPO/EPO/GPO implementations as well as multiple training reference materials for many other areas - Ortho's Customer Service for example has all our training reference materials stored there. | Group Functions | Yes | 1 - July 6 | Philip Sedgwick | Paul Davison |  | Robin Curry | Robin Curry | eu | 2020-07-07 | None | None | None | None | None | None | None | 100% | SNI AWS |  |  | Out Of Scope | Not needed | Not needed | Update From Paul on 8-Jul-20: Carla confirmed that Ancile uPerform is already on AWS. |  | 2020-07-08
ANZPowerBI | Reporting tool that accesses SAP PR1, SoNar and End User Data Sources | Data & Analytics | Yes | 3 - July 20 | Stuart Robinson | Sathiamurthy Samidurai |  | Rohit Gupta |  |  | 2020-07-20 | 2020-08-27 |  |  | Yes | Yes | 100% | 2020-09-04 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-04 | 2020-09-10 | Sign-Off Received | 44104
ASSIST4 | Customs Clearance | Supply Chain | Yes | 1 - July 6 | Manas Singha | Yvonne Braun | Yvonne Braun | Josef Horstmann | Birgit Meihack | eu | 2020-07-10 |  | None | None | None | None | 100% | 2020-07-10 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed |  | 2020-08-21 | 2020-08-21 | Sign-Off Received | 44089 | 2020-08-24 | Simple
Auftragsverwaltung (Loaner Pool) | Loaner application | Supply Chain | Yes | 1 - July 6 | Manas Singha | Amit Shokeen | Sebastian Pasch | Peter Heinemann |  | us | 2020-07-08 | None | None | None | None | None | None | None | 100% | Retirement | 2020-06-30 |  | Retirement | Not needed | Not needed | Done with the meeting with Amit.As per the discussion the application is going to be decommissioned in Q1 or Q2 of 2021. |  | 2020-07-08
AutoCAD | Facilities Drawings, manufacturing shop floor layouts; vendor supplied drawings and models for Case Development AUTODESK POWERSHAPE PREMIUM SUBSCRIPTION -- 3,280.00 AUTODESK POWERSHAPE PREMIUM SUBSCRIPTION -- 3,280.00 AUTODESK POWERMILL PREMIUM SUBSCRIPTIon -- 9,225.00 AUTODESK POWERMILL PREMIUM SUBSCRIPTION -- 9,225.00 AUTODESK POWERSHAPE PREMIUM SUBSCRIPTION -- 3,280.00 ANNUAL RENEWAL References S/N: 564-47864651 Expires: 6/19/2019 S/N:564-44606441 Expires: 6/10/2019 S/N: 564-44606342 Expires: 6/10/2019 S/N: 564-43092548 Expires: 6/7/2019 S/N: 564-43090172 Expires: 6/7/2019 | R&D | Yes | 2 - July 13 | Ian Bennett | Matthew Stephens |  | Mark Powers |  | us | 2020-07-14 |  |  |  | Yes | Yes | 100% | 2020-07-14 | 100% | SNI Azure |  |  | Replatform | Yes - complete | Yes - complete | 15/7/2020 SME session completed.Sent email for few action items. ---------------- 20/7/2020 Got the confirmation for server details.One action is pending. |  | 2020-08-31 | 2020-09-02 | Sign-Off Received | 44099 |  | Medium
Automic | Tool to automate batch Job Scheduling and monitoring in SAP PR1 & EPR and Informatica GBIP & Logility | ERP | Yes | 2 - July 13 | Jacek Karas | Krzysztof Gaik | Pablo Iradier | Jacek Karas | Jacek Karas | eu | 2020-07-15 |  |  |  | Yes | Yes | 100% | 2020-07-15 | 100% | Retirement |  |  | Retirement | Not needed | Not needed | Assessment is completed |  | 2020-09-04 |  | NA
AVON | Remote app for AVON users (Finance) - for HP remote access to local SW. | Group Functions | Yes | 5 - Aug 3 | Philip Sedgwick | Paul Davison | Paul Davison | Jose Canton | Jose Canton | eu | None | None | None | None | None | None | None | None | 100% | Retirement | 2020-07-10 |  | Retirement | Not needed | Not needed | AVON (RDP servers) are retired and servers have been turned off. This session is not required. Regards, Paul. |  | 2020-07-27
AWM Data Warehouse | Invoiced Sales, Sales Orders and Inventory interfaced from US BPCS, HUB BPCS and Wound SAP ITLT Cert:26-JUN-17 | Data & Analytics | Yes | 1 - July 6 | Chris Cook | Sathiamurthy Samidurai | Michael Herd | Donann Fowler |  | ap | 2020-07-08 | 2020-07-13 |  |  | Yes | Yes | 100% | 2020-07-13 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Done with session.Sent action items to Sathya Murthy and Sai. Got reply from Sai for Server details.Waiting for other response from Sathya Murthy. |  | 2020-08-21 | 2020-08-26 | Sign-Off Received | 44104 | 2020-09-10 | Complex
Axapta 2009 (China) | China, Malaysia, Thailand, Singapore. Finance / SCM; 06/24/2014 - Update from Shaban - iScala (Malaysia) and iScala (Thailand) retired, functionality moved to this application. Product Vendor Support=Supported Delivery Manager Cert=22JUN17 | ERP | Yes | 1 - July 6 | Massimo Trambaioli | Benny Xu | Benny Xu | Ala Ahram | Mona Li | ap | 2020-07-06 | None | None | None | None | None | None | None | 100% | Retirement | 2020-07-01 |  | Retirement | Not needed | Not needed | Massimo - Benny will be leaving us 3rd July also AX2009 / AIMS have ben replaces with POWER AX 2012 which we went live yesterday. |  | 2020-06-30
Axapta 2009 (Dubai) | ERP system Support Knowledge=100% System Documentation=50% Maint Agreement=Yes Product Vendor Support=Supported Delivery Manager Cert=22JUN17 | ERP | Yes | 2 - July 13 | Massimo Trambaioli | Swapnil Kelaiya | Fahad Ummer | Basel AbouJalala | Pravin Pinto |  | 2020-07-14 | 2020-10-07 |  |  | Yes | Yes | 1899-12-31 | 2020-10-07 | 100% | Retirement |  |  | Out Of Scope | Not needed | Not needed | assessment work is completed. |  | 2020-10-12 | 2020-10-12 | NA
Axapta 2009 (India) | ERP System Product Vendor Support Level: Supported Delivery Manager Certified: 26-MAY-17 | ERP | Yes | 2 - July 13 | Massimo Trambaioli | Swapnil Kelaiya | Sushant Pawar | Badhri Iyengar | Badhri Iyengar |  | 2020-07-14 | 2020-10-07 |  |  | Yes | Yes | 1899-12-31 | 2020-10-07 | 100% | Retirement |  |  | Out Of Scope | Not needed | Not needed | assessment work is completed. |  | 2020-10-12 | 2020-10-13 | NA
Axapta 2009 (Malaysia & Thailand) | Operations for Malaysia & Thailand | ERP | Yes | 3 - July 20 | Massimo Trambaioli | Mulyanto Ng | Mulyanto Ng | Badhri Iyengar |  | ap | 2020-07-22 | 2020-10-08 |  |  | Yes | Yes | 1899-12-31 | 2020-10-07 | 100% | Retirement |  |  | Out Of Scope | Not needed | Not needed | assessment work is completed. |  | 2020-10-12 | 2020-10-12 | NA
Axapta 2009 (Singapore) | Singapore Commercial | ERP | Yes | 3 - July 20 | Massimo Trambaioli | Mulyanto Ng | Mulyanto Ng | Badhri Iyengar |  | ap | 2020-07-22 | 2020-10-08 |  |  | Yes | Yes | 1899-12-31 | 2020-10-08 | 100% | Retirement |  |  | Out Of Scope | Not needed | Not needed | assessment work is completed. |  | 2020-10-12 | 2020-10-12 | NA
Axway | GHX EDI Sales Orders | ERP | Yes | 5 - Aug 3 | Firas Almahamid | Pawel Pietrzyk |  | Darlene Balzotti |  | eu | 2020-08-12 | 2020-09-04 |  |  | Yes | Yes | 100% | 2020-09-09 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | assessment work is completed. |  | 2020-09-25 | 2020-09-25 | Sign-Off Received | 44124
BackupExec(OSIRIS) | Windows Backup | ET | Yes | 4 - July 27 | Roman Wojtasik | Jacob Goitom | Muhammad Hamza | Muhammad Hamza | Muhammad Hamza | us | None | None | None | None | None | None | None | None | 100% | Retirement | 2020-09-01 |  | Retirement | Not needed | Not needed | Per Jacob will be retired mid Aug 2020 |  | 2020-07-06
Bartender(OSIRIS) | Barcoding Software | RAQA | Yes | 4 - July 27 | Derek Spillane | Jacob Goitom | Muhammad Hamza | Heather Hill | Christine Walters | us | 2020-08-10 | 2020-08-27 |  |  | Yes | Yes | 100% | 2020-08-27 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment is completed |  | 2020-09-02 | 2020-09-02 | Sign-Off Received | 44097 |  | Simple
BAS | Order management, Sales, MRP. Original Name: "OMS, BAS". Per Yvonne, OMS was the vendor name. However, vendor is no longer in business. 01/20/16 - Yvonne sent email indicating this is GxP. | ERP | Yes | 2 - July 13 | Massimo Trambaioli | Yvonne Braun | Yvonne Braun | Josef Horstmann | Meinrad Riedinger | eu | 2020-07-14 | None | None | None | None | None | None | None | 100% | AS400 - out of scope |  |  | Out Of Scope | Not needed | Not needed | Yvonne - I thought we agreed with Ken that AS400 applications cannot be migrated to cloud? BAS is an application which is running on the AS400 |  | 2020-07-03
BI (CHINA) | Local managerial reporting system | Data & Analytics | Yes | 1 - July 6 | Jerry Li | Jinble Li | Jinble Li | Las Lu | Jinble Li | ap | 2020-07-06 | 2020-07-09 |  |  | None | No | 50% | 2020-07-09 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Jinble to complete the questionnaire form and submit. Follow-up sessions may be required. |  | 2020-08-31 | 2020-09-02 | Sign-Off Received | 44077 |  | Medium
BPCS - Japan | ERP Application Product vendor support: Supported | ERP | Yes | 3 - July 20 | Tsutomu Hirooka | Tsutomu Hirooka | Tsutomu Hirooka | Shinji Hosoda | Shinji Hosoda | ap | 2020-07-22 | None | None | None | None | None | 30% | 2020-07-22 | 100% | Retirement | 31-Sep-21 |  | Retirement | Not needed | Not needed | BPCS - Only Japanese supported - OS400 can’t be migrate to cloud - BPCS will be retired after POWeR project go-live (in 2021) Tsutomu HIROOKA ¦ IT Director ¦ |  | 2020-07-22
Bugzilla | Bluebelt "Maintains records related to product and design history file investigations and actions on performance issues identified on Robotics products. Used for Navio Product Development" | R&D | Yes | 2 - July 13 | Ian Bennett | Matthew Stephens | Sumanth Arigela | Costa Nikou |  | us | 2020-07-16 | 2020-07-31 |  |  | Yes | Yes | 100% | 2020-07-31 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-04 | 2020-09-08 | Sign-Off Received | 44099 |  | Medium
Business Objects (IRAMEA) | Sales Figures | Data & Analytics | Yes | 1 - July 6 | Stuart Robinson | Mark Elliott |  | Mark Elliott |  | eu | 2020-07-09 | 2020-07-13 |  |  | Part - not enough | Yes | 100% | 2020-07-13 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-04 | 2020-09-08 | Sign-Off Received | 44117 |  | Medium
Calibration Manager(OSIRIS) | Calibration Management Tool | RAQA | Yes | 4 - July 27 | Danielle Blackwell | Jacob Goitom | Muhammad Hamza | Keith Smiley | Keith Smiley | us | 2020-08-10 |  |  |  | Yes | Yes | 100% | 2020-08-28 | 100% | DCaaS |  |  | Out Of Scope | Not needed | Not needed | It won’t be a cloud migration |  | 2020-09-14 |  |  |  |  | Medium
CardAccess 3000 | Building Card Access System used in Costa Rica. 05/31/16 - Adding per request from Mark Beal. | Group Functions | Yes | 3 - July 20 | Philip Sedgwick | Paul Davison | Marcos Obando | Miguel Montero |  | eu | 2020-07-16 | 2020-07-24 | None | None | None | None | None | None | 100% | Retirement | 2020-07-31 |  | Retirement | Not needed | Not needed | Out of scope We are in the middle of replacing this application for a new one. (the new one is a feature of an existing application) So. Once the migration is completed, we can get rid of CardAccess 3000. I think this could be done by middle of July |  | 2020-07-21
Central FTP | Internal and External FTP (file transfer) servcies. External (DMZ) leverages AS2 encryption (Axway, WS_FTP). Supports many internal business applications and processes. SAP, BPCS, PRMS, etc. ITLT Cert: 26-JUN-17 Del Cert:26JUN17 | ERP | Yes | 1 - July 6 | Jacek Karas | Pawel Pietrzyk | Pablo Iradier | Tjebbes Feenstra | Tjebbes Feenstra | eu | 2020-07-06 | 2020-09-03 |  |  | Yes | Yes | 100% | 2020-09-03 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-14 | 2020-09-18 | Sign-Off Received | 44124 |  | Complex
CIMCO (China) |  | Manufacturing | Yes | 4 - July 27 | Derek Spillane | Carla Morris |  |  |  | us | 2020-07-30 |  |  |  | Yes | Yes | 100% | 2020-07-30 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed |  | 2020-08-04 | 2020-08-13 | Sign-Off Received | 2020-08-25 | 2020-08-24 | Medium
CIMCO (Mansfield) |  | Manufacturing | Yes | 4 - July 27 | Derek Spillane | Carla Morris |  |  |  | us | 2020-07-30 |  |  |  | Yes | Yes | 100% | 2020-07-30 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed |  | 2020-08-04 | 2020-08-13 | Sign-Off Received | 2020-08-25 | 2020-08-24 | Medium
CIMCO (Memphis) |  | Manufacturing | Yes | 4 - July 27 | Derek Spillane | Carla Morris |  |  |  | us | 2020-07-30 |  |  |  | Yes | Yes | 100% | 2020-07-30 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed |  | 2020-08-04 | 2020-08-13 | Sign-Off Received | 2020-08-25 | 2020-08-24 | Medium
Cisco System Unity VM and unified messaging | Phone software | ET | Yes | 1 - July 6 | Patryk Bromirski | Roman Wojtasik | William Brock | Anna Falbogowska |  | eu | 2020-07-10 | 2020-08-18 | None | None | None | None | None | None | 100% | DCaaS |  | many dependencies and Global SIP project it is not eligible for cloud migration | Out Of Scope | Not needed | Not needed | As per Pawel "We had technical session with our voice support team regarding possibilities to move Cisco System Unity VM and unified messaging and IXI UMS Fax Server to Cloud. Because of many dependencies and Global SIP project it is not eligible for cloud migration. Please be so kind to remove it form list and cancel both meetings tomorrow." |  | 2020-08-17
CISCO Umbrella | Public DNS using Webfiltering. Proxy for internet browsing. Umbrella filters the traffic and blocks/whitelists sites. Has a deployed agent on end user compute Support vendor is Cisco | Security | Yes | 4 - July 27 | Jody Jenkins | Paul Funk | Paul Funk | Jody Jenkins | Paul Funk | us | 2020-08-06 | None | None | None | None | None | None | None | 100% | Retirement | 2021-07-31 |  | Retirement | Not needed | Not needed | • Cisco Umbrella – Will be replaced by PaloAlto’s web filtering |  | 2020-07-29
Cockpit | Bluebelt Web-application that manages product requirement specifications, test plans, risk assessments, summary test reports and requirement-to-test report traces. Used for Navio Product Development to record and maintain design history file documents. | R&D | Yes | 2 - July 13 | Ian Bennett | Matthew Stephens | Sumanth Arigela | Stephen Wetzel |  | us | 2020-07-16 | 2020-07-28 |  |  | Yes | Yes | 90% | 2020-07-28 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | 7/28/2020 Matt need to confirm like the decision to be made by mid of August 2020, if SNI wants to choose one of the below application Product Development Platform ( Jama , Cognition cockpit ) |  | 2020-08-17 | 2020-08-26 | Sign-Off Received | 44099 | 2020-09-10 | Simple
Cognos (STRATPLAN) | TM1 Strategic Planning Application | Data & Analytics | Yes | 4 - July 27 | Stuart Robinson | Sathiamurthy Samidurai |  | Nick Hatfield |  | ap | 2020-08-11 |  |  |  | Yes | Yes | 100% | 2020-08-11 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | The Session is done. |  | 2020-08-26 | 2020-08-26 | Sign-Off Received | 44104 | 2020-09-10 | Medium
Cognos BI (SoNAR Sales Dashboards & Standard Reporting) | Cognos instances for Enterprise Data Warehouse (GBIP) environment. ITLT Cert:26-JUN-17 | Data & Analytics | Yes | 4 - July 27 | Stuart Robinson | Sathiamurthy Samidurai |  | Nick Hatfield |  | ap | 2020-08-12 | None | None | None | None | None | None | None | 100% | Complex - separate project |  |  | Out Of Scope | Not needed | Not needed | As discussed with Sathia all Cognos and Informatica apps will be under discussion and for time being these are out of scope. |  | 2020-08-12
Cognos Demand Planning | Used for demand planning of the former Plus products. Update from Lucie: "Manu produces a plan for the Plus parts that is passed to SAP PRD. Those forecasts are then netted to create the production plan. The result is then passed to Cognos for further forecast intelligence and the final result is passed to Movex." Demand Planning: "All countries use the web interface with Cognos to enter their forecast changes. Always have. These forecasts go directly into the Cognos system the demand planners use in Baar Switzerland. THose forecasts in Cognos pass into Movex - the Aarau manufcturing system. " | Supply Chain | Yes | 3 - July 20 | Manas Singha | Antoine d'Overschie | Antoine d'Overschie | Dragomir Lakic | Matthias Felder | eu | 2020-07-20 | None | None | None | None | None | None | None | 100% | Retirement | 2020-12-31 |  | Retirement | Not needed | Not needed | Cognos Demand planning is in a process of decommissioning, therefore no reason to migrate to Cloud Regards Antoine |  | 2020-07-16
Cognos Performance Mgmt (STGP) | STGP and RUBIK are the new Sales Reporting using Cognos BI front-end using Cognos TM1 data source; 03/03/15 - Merging the "Cognos TM1" entry into this entry. ITLT Cert:26-JUN-17 | Data & Analytics | Yes | 4 - July 27 | Stuart Robinson | Sathiamurthy Samidurai |  | Nick Hatfield |  | ap | 2020-08-13 |  |  |  | Yes | Yes | 100% | 2020-08-13 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | action items sent to Sathia |  | 2020-08-26 | 2020-08-26 | Sign-Off Received | 44104 | 2020-09-10 | Medium
CONNECT | The portal allows External S&N Customers to access usage information reguarding the CONNECT NPWT pump from S&N. These devices are rented to patients, and the device reports back information related to it's use via AT&T's 3G machine to machine network. This usage information is then used for billing purposes. Engineering Contact: Allan Macrae in the UK | R&D | Yes | 4 - July 27 | Ian Bennett | Matthew Stephens |  | Rebecca Ford |  | us | 2020-07-30 | None | None | None | None | None | None | None | 100% | Retirement |  |  | Retirement | Not needed | Not needed | End Note is uploaded although it’s a desktop app only with no servers that we’ll be migrating to a SaaS at some point. CVS is also uploaded. CONNECT is being retired. Matt |  | 2020-07-30
Connect Plus | ETL for Dr.sum, Web Customer Support and Shipping Slip Management from SAP | ERP | Yes | 3 - July 20 | Tsutomu Hirooka | Tsutomu Hirooka | Tsutomu Hirooka | Tsutomu Hirooka | Tsutomu Hirooka | ap | 2020-07-22 |  |  |  | Part - enough | None | 30% | 2020-07-22 | 100% | Retirement | 31-Sep-21 |  | Retirement | Not needed | Not needed | Connect Plus - Only Japanese supported - Extract data from SAP (EPR) - ConnectPlus will be retired after POWeR project go-live (in 2021) Tsutomu HIROOKA ¦ IT Director ¦ |  | 2020-07-22
Connect Ship (UPS/DHL) | Shipping System for UPS/DHL. 01/21/16 - Update from Al. Non-FedEx Shipping software for XPS Ship in SAP Licensed through Catalyst - Licensed for Connectship and 2 carriers - UPS, DHL. Removing DHL Connect and Progistics to combine into this one entry. | Supply Chain | Yes | 1 - July 6 | Manas Singha | Amit Shokeen | Danyelle Johnson |  |  | us | 2020-07-08 |  |  |  | Yes | Yes | 100% | 2020-07-08 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-04 | 2020-09-18 | Sign-Off Received | 44096 |  | Complex
CVS Concurrent Version System | Bluebelt "Source code for product software development is maintained in CVS. CVS provides configuration management for source-code files for Navio Implant Databases and the Navio System (GUI) Language Pack. Used for Navio Product Development" | R&D | Yes | 4 - July 27 | Ian Bennett | Matthew Stephens | Sumanth Arigela | Costa Nikou |  | us | 2020-07-30 |  |  |  | Yes | Yes | 80% | 2020-07-30 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Action items sent. | The url (dynomite.sncorp.smith-nephew.com.) Matt provided, still have to be clarified how it is connected with CVS and function? | 2020-08-17 | 2020-09-08 | Sign-Off Received | 44099 |  | Simple
CyberArk EPM (Endpoint Privilege Management) | Provides privilege elevation for non-privileged users on workstations removing the need for local admin privileges. | Security | Yes | 5 - Aug 3 | Jody Jenkins | Paul Funk | Paul Funk | Jody Jenkins | Paul Funk | us | 2020-08-04 | None | None | None | None | None | None | None | 100% | DCaaS |  | Recommendation from vendor to keep in DCs | Out Of Scope | Not needed | Not needed | • CyberArk EPM (Endpoint Privilege Management) – Recommendation from vendor to keep in DCs – may add items in cloud if required |  | 2020-07-29
CyberArk PAM (Privileged Access Management) | Manages passwords for privileged accounts in the S&N environment. | Security | Yes | 4 - July 27 | Jody Jenkins | Paul Funk | Paul Funk | Jody Jenkins | Paul Funk | us | None | None | None | None | None | None | None | None | 100% | DCaaS |  | Recommendation from vendor to keep in DCs | Out Of Scope | Not needed | Not needed | • CyberArk PAM (Privileged Access Management) - Recommendation from vendor to keep in DCs – may add items in cloud if required |  | 2020-07-29
dataSTOR | This application is used to store an electronic copy of PODs, Invoices, Statements and other forms which might be needed to be located and sent to customers, auditors, suppliers etc. at a later stage | ERP | Yes | 2 - July 13 | Dave Cranny | Sebastian Pasch | Mpho Gwala | Maria Areal | Mpho Gwala | eu | 2020-07-16 |  |  |  | Yes | Yes | 100% | 2020-07-16 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-07-31 | 2020-08-14 | Sign-Off Received | 2020-08-17 |  | Simple
DNC5000 | Procution CNC sofware | Manufacturing | Yes | 3 - July 20 | Derek Spillane | Antoine d'Overschie | Antoine d'Overschie | Josef Horstmann | Martin Senn | eu | 2020-07-20 | 2020-07-27 |  |  | Yes | Yes | 90% | 2020-08-05 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Session finished but we have lots of action items which are sent to Antoine. 5-Aug, Antoine, replied to most of the questions, so we will document in the Assessment the complexity of the application. | Complex appliction, server/client architecture on .NET remoting, SQL Server, ftp server, shared drive, SMB, Cimco NFS Server for Heidenhain controls and network adapter with ftp client for machines with serial interface. Has latency requirements. Many network adapters and machines have fixed IPs, DNC Server has also a fixed IP. | 2020-08-17 | 2020-09-08 | Sign-Off Received | 44099 |  | Complex
Dr.Sum | Business Intelligence for sales amount and inventory | Data & Analytics | Yes | 1 - July 6 | Jerry Li | Chika Ishii | Chika Ishii | Shinya Dobashi |  | us | 2020-07-07 | 2020-08-06 |  |  | Yes | Yes | 100% | 2020-08-06 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | The Session partially completed.Questionnaire was also incomplete.Chika will complete the Questionnaire and will send it back. ----------------------------- 10/8/2020 Chika has completed and sent the questionnaire . Will start doing the assessment |  | 2020-08-31 | 2020-08-31 | Sign-Off Received | 44090 | 2020-09-10 | Simple
E-Adept | CRM interfaces Tenders, repairs, prices | Commercial | Yes | 2 - July 13 | Santhosh Nair | Andres Bernard | Oriol Morral | Carles Ferrer |  | us | 2020-07-17 | 2020-08-11 |  |  | Part - not enough | 2020-08-11 | 10% |  | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Action items sent to Andres and Team. |  | 2020-09-09 | 2020-09-15 | Sign-Off Received | 44090 |  | Simple
Eagle RF Express | Eagle RF Express RF-Gun Software | Supply Chain | Yes | 4 - July 27 | Derek Spillane | Jacob Goitom | Muhammad Hamza | Samson Tom | Dan Chisnell | us | 2020-08-10 | 2020-08-26 |  |  | Yes | Yes | 20% | 2020-08-26 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-04 | 2020-09-10 | Sign-Off Received | 2020-09-10 |  | Complex
ECAP | External web based entry form to be used by Smith & Nephew customer accounts. This will gather product information from surgeries to help facilitate warranties and warranty claims for PICO. Users need to be able to enter information into the website which will then be reviewable by internal Smith & Nephew employees through an internal admin site. External users do not need to be able to retrieve this information from website at a later time. | RAQA | Yes | 2 - July 13 | Santhosh Nair | Amit Shokeen | Andres Bernard | Rich Szulewski | Rich Szulewski | us | None | None | None | None | None | None | None | None | 100% | Retirement | 2020-07-31 |  | Retirement | Not needed | Not needed | Andres confirmed It can be retired right now. |  | 2020-07-16
eDiscovery |  | Group Functions | Yes |  | Philip Sedgwick | Paul Davison |  |  |  | eu | None | None | None | None | None | None | None | None | 100% | Retirement | 2020 Q3 |  | Retirement | Not needed | Not needed | will be retiring per Paul D |  | 2020-07-14
Eflow | workflow for master data (item master, customer master and vendor master) | Data & Analytics | Yes | 1 - July 6 | Massimo Trambaioli | Las Lu | Las Lu | Ala Ahram |  | ap | 2020-07-07 | 2020-07-28 |  |  | Part - enough | Yes | 100% | 2020-07-28 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Action items sent on mail. |  | 2020-08-31 | 2020-09-02 | Sign-Off Received | 44118 |  | Complex
Electronic Instructions for Use | This is a public facing website to allow health care professionals download electronic PDF versions of our product instruction for use documents (IFUs). Healthcare product manufacturers are required to produce and provide Instructions for Use (IFU) documents for their reusable surgical instruments, medical devices and equipment and implantable biologics, materials and devices. | Commercial | Yes | 1 - July 6 | Santhosh Nair | Andres Bernard | Jamie McShan | Laurie Jordan | Laurie Jordan | us | 2020-07-07 |  |  |  | Yes | Yes | 100% | 2020-07-07 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed |  | 2020-07-31 | 2020-08-21 | Sign-Off Received | 2020-09-11 | 2020-08-24 | Medium
Embarcadero/Erwin Studio | Data & Analytics Engineers Data Modelling tool | R&D | Yes | 5 - Aug 3 | Stuart Robinson | Sathiamurthy Samidurai |  | Linda Rosser |  | ap | 2020-08-14 | 2020-08-25 | None | None | None | None | None | None | 100% | Retirement | 2020-12-31 |  | Retirement | Not needed | Not needed | Hi Vidit, Erwin Studio is out of scope as this application is considered for elimination. Regards Sathia |  | 2020-08-24
ENCORE | Web-based application to allow European markets to log their own complaints relating to product delivery - Dependent on A 305 | Supply Chain | Yes | 5 - Aug 3 | Sri Tupil | Amit Shokeen | Maagedha Shajahan | Paul Gagg |  |  | None | None | None | None | None | None | None | None | 100% | Retirement | 4/31/2020 |  | Retirement | Not needed | Not needed | Yes this is the case of another orphan app which was passing around with no information. After few weeks of looking around , I found that Its old warehouse house app so fall under SCM and I am the SDM . I had informed Team in May that belong to me . No action required for this app as this is no longer used by business . There are other apps “not from my area” running on this server so cannot shutdown the server but application link has been turned off. |  | 2020-07-30
END NOTE | Commercial reference management software for managing bibliographies and references | R&D | Yes | 2 - July 13 | Ian Bennett | Matthew Stephens | Sumanth Arigela |  |  | us | 2020-07-16 | 2020-07-30 | None | None | None | None | None | None | 100% | Desktop App |  |  | Out Of Scope | Not needed | Not needed | We are moving all 13th and 20th week R&D applications into future scope. We will further reschedule all these. --------------------------------------------------------- 30/07/2020 As per the discussion with Matt its a Desktop application and dont have any servers and any connection with external systems |  | 2020-07-30
Endo Loans | Internal web form to allow sales reps to request orders electronically on their mobile device for Visualization Tower evaluations. It will be accessed through webaccess on their iPad. | Commercial | Yes | 2 - July 13 | Santhosh Nair | Andres Bernard | Jamie McShan | Alex Lamont | Alex Lamont | us | 2020-07-17 |  |  |  | Yes | Yes | 100% | 2020-07-17 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed |  | 2020-07-31 | 2020-08-21 | Sign-Off Received | 2020-08-22 |  | Simple
Enterprise Business Objects Reporting | Reporting tool that accesses GDW, ODW, and EPO Ax data sources | Data & Analytics | Yes | 5 - Aug 3 | Stuart Robinson | Sathiamurthy Samidurai | Michael Herd | Donann Fowler |  | ap | 2020-08-05 |  |  |  | Yes | Yes | 100% | 2020-08-05 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Session completed.Need to send the action items. | Dependencies with 4 integrated application | 2020-08-17 | 2020-09-08 | Sign-Off Received | 44124 |  | Complex
Epats | NPWT - monitor & manage patients requirement | Data & Analytics | Yes | 2 - July 13 | Stuart Robinson | Mark Elliott | Mark Elliott | Mark Elliott |  | eu | 2020-07-17 | 2020-07-31 |  |  | Yes | Yes | 100% | 2020-07-31 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-14 | 2020-09-18 | Sign-Off Received | 44092 |  | Complex
EpiServer | Regulatory Affairs. 07/28/16 - Identified by Joy Du (App registered by Tom Steels). This system in externally (Internet) exposed. | RAQA | Yes | 4 - July 27 | Sri Tupil | Aileen Diola | Tom Steels | Joy Du |  | us | 2020-07-24 | 2020-08-06 |  |  | Yes | Yes | 100% | 2020-08-06 | 100% | Retirement |  |  | Out Of Scope | Not needed | Not needed | Assessment work is completed. |  | 2020-09-14 | 2020-09-18 | NA |  |  | Complex
ERP LN | ERP application for Biotherapeutics. Includes both Finance and Manufacturing modules. 1-6-16: Delivery Manager was Steve McNeill. Changed to Robert Jones Support Knowledge = 75% System Documentation=50% Maint agreement =YES Product vendor support level=Supported Delivery Mangager CERT: 9-JUN-17 | ERP | Yes | 1 - July 6 | Massimo Trambaioli | Carla Morris | Carey Clement | Guillermo Santiago | Kunal Purkar | us | 2020-07-08 | 2020-07-29 |  |  | Yes | Yes | 100% |  | 100% | Retirement |  |  | Out Of Scope | Not needed | Not needed | ig ERP System. SQL Server upgrade is required. Vendor support needed |  | 2020-08-31 | 2020-08-31 | NA |  | 2020-09-10 | Complex
eRoom | This application is used to store the documents for AWM data warehouse application. The application is retired. As the business need the data for next 5 years it is going to retain the data for next 5 years. When ever the order comes the user will run the eRoom application in the server to access the old history data and send the report. | Commercial | Yes | 37838 | Santhosh Nair | Andres Bernard |  |  |  | us | 2020-09-28 | 2020-09-28 |  |  | Yes | Yes | 100% | 2020-09-28 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment is completed. |  | 2020-10-12 | 2020-10-13 | Sign-Off Received | 44114
Euro log | Logistics Loaners software | Supply Chain | Yes | 2 - July 13 | Manas Singha | Amit Shokeen | Sumanth Arigela | Axel Girod | Axel Girod | us | 2020-07-14 | None | None | None | None | None | None | None | 100% | Retirement | 2020-12-31 |  | Retirement | Not needed | Not needed | This app will decom after this year so no need to move to cloud Amit Shokeen |  | 2020-07-06
Event Manager | sdfsa | Supply Chain | Yes | 2 - July 13 | Manas Singha | Amit Shokeen | Lucie Horowitz | Dawn Pollard |  | us | 2020-07-14 | None | None | None | None | None | None | None | 100% | Complex - separate project |  |  | Out Of Scope | Not needed | Not needed | As per Amit this application is out of scope .Event Manager also its all part of MLE application. |  | 2020-07-23
Evisense | Refrigeration monitoring for lab environments. | R&D | Yes | 2 - July 13 |  | Matthew Stephens | Antoine d'Overschie | Lynsey Yardley | David Langton | us | 2020-07-16 | 2020-08-20 |  |  | Yes | Yes | 95% | 2020-08-20 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is complete |  | 2020-08-27 | 2020-09-09 | Sign-Off Received | 2020-09-25 |  | Medium
Exactus Payroll Application (Costa Rica) | CostaRica finance | Group Functions | Yes |  | Philip Sedgwick | Paul Davison |  |  |  | eu | 2020-08-17 |  |  |  | Yes | Yes | 100% | 2020-08-17 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | action items sent to Paul. After that we will start assessment work |  | 2020-08-18 | 2020-09-02 | Sign-Off Received | 44078 |  | Simple
Expert Document Imaging (EDI) | Provides document managing solution to electronically store all surgery cases and AWM customer orders paperwork. System stores electronically patient surgery case information as well as accounts receivables documentation. | Commercial | Yes | 5 - Aug 3 | Roberto Pujol | Eduardo Lima | Keyla Garcia | Maritere Diez |  |  | 2020-08-19 | 2020-08-24 |  |  | Yes | Yes | 100% | 2020-08-24 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-04 | 2020-09-04 | Sign-Off Received | 44106 |  | Simple
Express Implants | Used to gather custom implant information and schedule/track custom implant manufacturing for surgeons | R&D | Yes | 2 - July 13 | Manas Singha | Matthew Stephens | Danyelle Johnson | Daniel Stehle |  | us | 2020-07-16 | 2020-08-19 |  |  | Yes | Yes | 100% | 2020-08-21 | 100% | SNI Azure |  |  | Replatform | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-14 | 2020-09-15 | Sign-Off Received | 44125 |  | Complex
Express Instruments | Used to gather custom implant information and schedule/track custom implant manufacturing for surgeons | R&D | Yes | 3 - July 20 | Manas Singha | Matthew Stephens | Sumanth Arigela | Rodney Overall |  | us | 2020-07-24 | 2020-08-19 |  |  | Yes | Yes | 100% | 2020-08-19 | 100% | SNI Azure |  |  | Replatform | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-14 | 2020-09-15 | Sign-Off Received | 44125 |  | Complex
Express Visionaire | 04/10/14 - Reported as an application missing from EAP by Randall Reavis team during WARP. Visionaire case flow website. | R&D | Yes | 2 - July 13 | Ian Bennett | Matthew Stephens | Derrick Givens | Derrick Givens | Derrick Givens | us | 2020-07-16 | 2020-08-03 |  |  | Yes | Yes | 80% | 2020-08-03 | 100% | SNI Azure |  |  | Replatform | Yes - complete | Yes - complete | Assessment work is completed. | a. MEMSRV491 is on OS 2003 with SQL 2005, b. Server USMANSMDBPCW4B is OS 2008, SQL 2005 c. CMDB /Cloudscape inventory not consistent Matt, Derrick to verify the server inventory d. Link to Isilon (Storage Device) for data usage to be clarified. e. 2 url are being used hitting to 2 didderent server based on cut of data date, April 3rd 2014. f. QA environment (MEMSRV491) is being used to host PROD data. g. MEMSRV491 also have other application hosted (not related to Express Visionaire) | 2020-09-14 | 2020-09-18 | Sign-Off Received | 2020-10-21 |  | Complex
FAS 500 -Sage | Fixed Assets. 6 users in the U.S. (3 Florida; 3 Memphis). This application is accessed via a remote desktop connection and not from the users pc - via RDP server USMAN-SMTSPW01. This has the client Sage software installed. USMAN-SMAPPVW52 is the Windows 2012 server which has the server (and client) Sage software installed and holds the data. | Group Functions | Yes | 1 - July 6 | Philip Sedgwick | Paul Davison | Ritesh Prakash | Frankie Brooks | Frankie Brooks | eu | 2020-07-06 |  |  |  | Yes | Yes | 1899-12-31 | 2020-07-06 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Hi Matt, Below apps are still pending to schedule/re-schedule. Please let us know when you will be able to complete the questionnaire for below applications? Magic X MASK MATLAB Evisense LIFEMOD BIOMECHANICS SYS SVN - Subversion Configuration Management |  | 2020-07-06 | 2020-09-04 | Sign-Off Received | 44071 |  | Simple
Fax to EDI - Order 2 Cash | Currently in AWM, Germany only ITLT Cert: 26-MAY-17 | Supply Chain | Yes | 2 - July 13 | Jacek Karas | Pablo Iradier | Pablo Iradier | Yvonne Eckert | Yvonne Eckert |  | 2020-07-15 | None | None | None | None | None | None | None | 100% | Retirement |  |  | Retirement | Not needed | Not needed | Hello Vidit, Fax to EDI functionality has been replaced by Esker which is a SaaS application. Therefore, there is no need to migrate FAX to EDI to Cloud |  | 2020-07-03
FileMaker | Software to support Professional Education Training Equipment process and team in EUCAN. | Commercial | Yes | 2 - July 13 | Santhosh Nair | Andres Bernard |  | Beat Leimgruber | Beat Leimgruber | us | 2020-08-04 |  |  |  | Part - enough | Yes | 100% | 2020-08-04 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed |  | 2020-08-17 | 2020-09-04 | Sign-Off Received | 44057 |  | Simple
Filezilla FTP Server | Transfering files into Business Objects server in South Africa. Not vendor supported. | Data & Analytics | Yes | 2 - July 13 | Stuart Robinson | Mark Elliott | Wen Han Som | Lukman Haryanto |  | eu | 2020-07-17 | 2020-08-04 |  |  | Yes | Yes | 1899-12-31 | 2020-08-04 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Hi Matt, Below apps are still pending to schedule/re-schedule. Please let us know when you will be able to complete the questionnaire for below applications? Magic X MASK MATLAB Evisense LIFEMOD BIOMECHANICS SYS SVN - Subversion Configuration Management |  | 2020-08-26 | 2020-09-04 | Sign-Off Received | 44117 |  | Medium
Fishbowl | Inventory Management –Tracks all components, WIP, FG, & Field Inventory. Lot, revision, and expiration date traceability. -ACQ SOURCE: ROTATION MEDICAL | ERP | Yes | 3 - July 20 | Manas Singha | Amit Shokeen | Sumanth Arigela | Gonzalo Mata | Gonzalo Mata | us | None | None | None | None | None | None | None | None | 100% | retirement | 2021-07-01 |  | Retirement | Not needed | Not needed | Hi Maciek, Yes , we will need Sathia & team to join the call so please forward invite to Sathia. Logility and Infor MLE is out of scope for now due to the nature of complexity of the application and investment required . They don’t fit the criteria of lift and shift and more fall into large project category due to the complexity of application. Fishbowl is out of scope as Site which is using this application will be closed . . Ken mentioned that any application which is going to be shut down in 2021 does not need to migrate as those application will stay in Data Center. Thanks Amit |  | 2020-07-06
Flex LM | FlexLM3 (CPS Data Collector Only) | R&D | Yes | 3 - July 20 | Ian Bennett | Matthew Stephens | Sumanth Arigela | Jason Jordan | Derrick Givens | us | 2020-08-04 |  |  |  | Yes | Yes | 50% | 2020-08-04 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | SVN - Subversion Configuration Management |  | 2020-08-17 | 2020-09-04 | Sign-Off Received | 44099 |  | Medium
Gentran Server for Unix | EDI; EDIFACTS (Component) ITLT Cert: 26-JUN-17 | ERP | Yes | 4 - July 27 | Jacek Karas | Krzysztof Gaik | Pablo Iradier | Tjebbes Feenstra | Tjebbes Feenstra | eu | 2020-08-07 | 2020-08-20 | None | None | None | None | 100% | None | 100% | SAP on HP-UX - out of scope |  |  | Out Of Scope | Not needed | Not needed | this application is running on HP-UX so OoO. |  | 2020-08-20
Geomagic | 3-D design and engineering technology that streamlines a wide range of inspection and manufacturing processes | R&D | Yes | 4 - July 27 | Ian Bennett | Matthew Stephens | Sumanth Arigela | Kyle Lonidier | Derrick Givens | us | 2020-08-05 |  |  |  | Yes | Yes | 100% | 2020-08-05 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete |  | - Co-hosted license server apps (MEMSRV236) - Mac Address would have to stay the same for the licesing to continue working. If we can't emulate mac address then the server would have to go to DCaaS. | 2020-08-17 | 2020-09-04 | Sign-Off Received | 44099 |  | Simple
Georgia Softworks | Enables Telnet SAP Console for Easykit RFID system | ERP | Yes | 4 - July 27 | Jacek Karas | Krzysztof Gaik | Pablo Iradier | Jacek Karas | Jacek Karas | eu | 2020-08-10 | 2020-08-19 |  |  | Yes | Yes | 100% | 2020-08-19 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-09 | 2020-09-09 | Sign-Off Received | 44117 |  | Complex
Git Version control | Git Version control is used to maintain source code for product software development. Git provides configuration management for source code files used to develop Navio product software. | R&D | Yes | 4 - July 27 | Ian Bennett | Matthew Stephens | Sumanth Arigela | Costa Nikou |  | us | 2020-08-06 | 2020-08-20 |  |  | Yes | Yes | 1899-12-31 | 2020-08-20 | 100% | Retirement | 2020-12-31 |  | Retirement | Not needed | Not needed | Matt confirmed on SME Session his plan to retire GIT on Aug 20th 2020 (ETA by end of 2020). ------------ Reschedule again from 08/06/20 to 08/20/20 |  | 2020-08-20
Global Business Information Platform | Oracle instances for Enterprise Data Warehouse (GBIP) environment. Name changed to Global Business Information Platform (RUBIK). 22-MAR-17 Per Troy Seals and Robert Heide ITLT Cert:26-JUN-17 | Data & Analytics | Yes | 2 - July 13 | Stuart Robinson | Sathiamurthy Samidurai | John Samuel John | Nick Hatfield |  | ap | 2020-07-20 | 2020-07-24 | None | None | None | None | None | None | 100% | Complex - separate project |  |  | Out Of Scope | Not needed | Not needed | This application can not be migrated to Azure now due to high investment requirement for replatform effort |  | 2020-07-23
Global Data Warehouse | Microsoft SQL - Global Business Warehouse system for Sales, Inventory, Contracts, Products. GDW is the data source for US, Japan, China, and ANZ ASD Endo reporting and analytics environment. Business Objects is the reporting tool interface. ITLT Cert:26-JUN-17 | Data & Analytics | Yes | 2 - July 13 | Stuart Robinson | Sathiamurthy Samidurai |  | Donann Fowler |  | ap | 2020-07-20 | 2020-07-24 |  |  | Yes | Yes | 100% | 2020-07-24 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Action-items sent to get few information about application. |  | 2020-08-24 | 2020-09-04 | Sign-Off Received | 44104 |  | Medium
Global Market Monitoring | 03/07 - TS - Received request to add this application to portfolio. | Data & Analytics | Yes | 1 - July 6 | Stuart Robinson | Sathiamurthy Samidurai | Michael Herd | Richard Newlove | Richard Newlove | ap | 2020-07-31 | 2020-07-24 |  |  | Yes | Yes | 1899-12-31 | 2020-07-24 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Few action items sent to Sathia. He will response those. |  | 2020-08-26 | 2020-09-04 | Sign-Off Received | 44104 |  | Medium
Global Protect VPN | Full VPN | Security | Yes | 4 - July 27 | Jody Jenkins | Paul Funk | Paul Funk | Jody Jenkins | Paul Funk |  | 2020-08-07 | None | None | None | None | None | None | None | 100% | Infrastructure service - out of scope |  |  | Out Of Scope | Not needed | Not needed | Paul Funk is the SDM, but again this is part of the Firewall and cannot be migrated to the cloud. |  | 2020-07-29
Global Regulatory Submissions | Regulatory Affairs | RAQA | Yes | 1 - July 6 | Sri Tupil | Aileen Diola | Sumanth Arigela | Bradley Heil |  | us | 2020-07-09 | 2020-07-20 |  |  | Part - enough | Yes | 100% | 2020-07-20 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete |  |  | 2020-08-31 | 2020-09-02 | Sign-Off Received | 2020-09-11 |  | Complex
Global Returns Disposition Tool | Approval or rejection of Sports Med and Ortho goods requested for return to the global distribution center. | Commercial | Yes | 4 - July 27 | Santhosh Nair | Andres Bernard | RK Seelam | Susan Farnsworth | Susan Farnsworth | us | 2020-08-07 |  |  |  | Yes | Yes | 100% | 2020-08-07 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Session is done.Will send the action items . |  | 2020-08-26 | 2020-09-04 | Sign-Off Received | 44085 |  | Simple
GSC Data Warehouse Admin Tool | Web-based admin screens to allow Global Supply Chain users to manage elements of the data in the Data Warehouse. Arlene has documentation from Paul Davison. | Data & Analytics | Yes | 3 - July 20 | Manas Singha | Amit Shokeen | Dave Roberts | Sarah Armitage | Sarah Armitage | us | 2020-07-24 |  |  |  | Yes | Yes | 100% | 2020-07-24 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work in progress |  | 2020-08-17 | 2020-09-02 | Sign-Off Received | 2020-10-23 |  | Medium
HR Notification | Web based application that notifies key departments of a new hire via e-mail. In House Application. URL: http://orthonet.smith-nephew.com/NonEmpNotification/default.aspx | Group Functions | Yes | 3 - July 20 | Philip Sedgwick | Paul Davison |  | Carla Crockett |  | eu | 2020-07-16 | 2020-07-27 |  |  | Part - enough | Yes | 100% | 2020-07-27 | 100% | SNI Azure |  |  | Replatform | Yes - complete | Yes - complete | Assessment work is completed |  | 2020-08-19 | 2020-08-18 | Sign-Off Received | 2020-08-19 |  | Simple
Hydra (Tuttlingen) | ADE: Shop Floor Control, PZE: Time recording and ZKS: Access control. 01/20/16 - Criticality, RTO, DR Plan - Updated from email request from Yvonne. | RAQA | Yes | 1 - July 6 | Sri Tupil | Aileen Diola | Yvonne Braun | Josef Horstmann |  | us | 2020-07-09 | 2020-07-16 |  |  | Yes | Yes | 90% | 2020-07-16 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed |  | 2020-07-31 | 2020-08-13 | Sign-Off Received | 44074 | 2020-08-24 | Simple
ID Prove | Sanctions list checking softawre. 01/20/16 - RTO, DR Plan - Updated from email request from Yvonne. | Supply Chain | Yes | 4 - July 27 | Manas Singha | Yvonne Braun | Yvonne Braun | Josef Horstmann | Yvonne Braun | eu | 2020-08-11 |  |  |  | Yes | Yes | 100% | 2020-08-11 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is complete. | 44067 | 2020-08-31 | 2020-08-31 | Sign-Off Received | 2020-09-15 | 44084 | Medium
InfinityQS ProFicient (SPC software) | SPC Software. Statistical Process Control. 03/29/16 - Per Al Whitney, this is a desktop app and has limited IT support. | RAQA | Yes | 4 - July 27 | Sri Tupil | Aileen Diola |  | Gary Lynch |  | us | 2020-07-22 | 2020-07-24 |  |  | Part - not enough | No | 0.2 | 2020-07-24 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-04 | 2020-09-04 | Sign-Off Received | 44085 |  | Simple
Informatica (SoNAR Data Intergration) | Informatica instance for Enterprise Data Warehouse (GBIP) environment. ITLT Cert:26-JUN-17 Name Formally Informatica (GBIP) Changed per SRR0082319 to reflect current name | Data & Analytics | Yes | 2 - July 13 | Stuart Robinson | Sathiamurthy Samidurai | Chaitanya Pogula | Nick Hatfield |  | ap | 2020-07-20 | 2020-08-24 | None | None | None | None | None | None | 100% | Complex - separate project |  |  | Out Of Scope | Not needed | Not needed | Hi Vidit, SoNAR data integration is out of scope as of now As we discussed before, this requires huge re-platform effort Regards Sathia |  | 2020-08-24
Informatica (Wound Data Intergration) | ETA tool. Mainly used to load data between BPCS, ERP, WMD Data Warehouse and MLE planning system Name Formally Informatica (Hull) Changed per SRR0082319 to reflect current name | Data & Analytics | Yes | 1 - July 6 | Stuart Robinson | Sathiamurthy Samidurai |  | Laura Marshall |  | ap | 2020-07-29 |  |  |  | Yes | Yes | 100% | 2020-07-28 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-04 | 2020-09-04 | Sign-Off Received | 44109 |  | Complex
Informatica MDM Data Quality | Data quality tool allows business users to monitor data quality and perform data set discovery | Data & Analytics | Yes | 5 - Aug 3 | Stuart Robinson | Sathiamurthy Samidurai |  | Nick Hatfield |  | ap | 2020-07-30 |  |  |  | Yes | Yes | 1899-12-31 | 2020-07-30 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-04 | 2020-09-04 | Sign-Off Received | 44104 |  | Complex
Informatica P360 | GDSN is a Global GS1-driven initiative to provide a standardized data format / repository design to allow manufacturers and customers to efficiently exchange product data (at SKU-level). This is done using GDSN Data pool companies assigned in each market, or globally at company level. Our customers subscribe to get access to various data sources from that pool (paid). We subscribe to get access to customer metadata from the data pool. The objective is to drive efficiency and transparency in the Healthcare supply chain. This project will put in place a single, global, integrated approach to e-commerce which incorporates the immediate GS1/GDSN requirements and a business as usual standardized process to support future customer needs & market requirements either in response to a mandate or proactively to enhance our customers' experience. | Data & Analytics | Yes | 3 - July 20 | Stuart Robinson | Sathiamurthy Samidurai |  | Stephen Roan |  | ap | 2020-07-24 | None | None | None | Yes | Yes | 1899-12-31 | 2020-08-24 | 100% | SNI Azure |  |  | Replatform | Yes - complete | Yes - complete | SDM opinion to directly install Latest version to cloud and running on-prem app parallel till cloud based app is validated and go live.During detailing migration, decision to made to move along with near integrated application and/or isolate non related application from the servers. SDM can explore the option to host on exclusive server for IDQ (VM). |  | 2020-08-24 | 2020-09-15 | Sign-Off Received | 44123 |  | Complex
Interform/400 | Printout Design. 01/20/16 - RTO, DR Plan - Updated from email request from Yvonne. | ERP | Yes | 4 - July 27 | Massimo Trambaioli | Yvonne Braun | Yvonne Braun | Josef Horstmann | Yvonne Braun | eu | 2020-08-06 | None | None | None | None | None | None | None | 100% | AS400 - out of scope |  |  | Out Of Scope | Not needed | Not needed | As Yuonne Confirmed Hi All, yes, Massimo is right, Interform/400 is an AS400 application, please put it out of scope. Best regards |  | 2020-07-29
Inventures (SCAMPI) Web App | Site used by R&D and Marketing to track new prodcut ideas. Update from Doug C.: "The main application (Scampi) is used by the Inventures team to manage new product ideas. This is an internal application and is on mmpsrv046 and is scheduled to move to USMAN-SMWSPVW12 the weekend of Feb. 13th. There is a public facing application (this is a one page form) for Inventures called New Ideas and is public facing and hosted on mmpsrv023. This application is used by doctors, nurses, Sales Reps, … to submit new product ideas." | R&D | Yes | 4 - July 27 | Sri Tupil | Matthew Stephens | Arunkumar Palanimuthu | Jeff Wyman |  | us | 2020-08-18 | 2020-08-31 |  |  | Yes | Yes | 100% | 2020-08-31 | 100% | SNI Azure |  |  | Replatform | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-14 | 2020-09-15 | Sign-Off Received | 2020-10-21 |  | Complex
IQ-Soft (Aarau) | This software have two modules; 1. Calibration Management used by Quality Management 2. Operating Equipment Management used by Downstream Engineering | RAQA | Yes | 4 - July 27 | Sri Tupil | Aileen Diola | Antoine d'Overschie | Roger Schaller | Antoine d'Overschie | us | 2020-07-09 | 2020-08-19 |  |  | Yes | Yes | 95% | 2020-08-19 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | 8/19/2020 Aileen, the only action item on you for this is to let us know how license is being handled for Desktop and Server? Aileen : 2nd modul is being used by Engg (Carla), so Aileen will work with Carla to decide on next course of action. ------------ Needs to be rescheduled. Its rescheduled again from 07/16/2020 to 08/05/2020 ----------------- 8/5/2020 Once again since the questionnaire is not filled the session got canceled.Aileen said like will send it to the vendor for filling. Meeting has been rescheduled again from 05 aug to 25 aug -------- |  | 2020-08-19 | 2020-09-08 | Sign-Off Received | 44083 |  | Simple
IRAMEA-LATAM Data Warehouse (South Africa) | Data Warehouse for the SABO reporting System | Data & Analytics | Yes | 4 - July 27 | Stuart Robinson | Mark Elliott |  | Firas Almahamid |  | eu | 2020-08-07 | 2020-08-12 |  |  | Yes | Yes | 1899-12-31 | 2020-08-12 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Done with the session.Sent the action items. |  | 2020-08-31 | 2020-08-31 | Sign-Off Received | 44117 | 44084 | Medium
iScala (Hong Kong) | ERP Product Vendor Support= UNSUPPORTED Delivery Manager Cert:22JUN17 | ERP | Yes | 4 - July 27 | Massimo Trambaioli | Magnus Chen | Magnus Chen | Priscilla Chan |  | ap | None | None | None | None | None | None | None | None | 100% | Retirement | 2020-12-31 |  | Retirement | Not needed | Not needed | Massimo - The Apac roadmap we are filing CER, and already discussed with management, aims at replacing within 2021-2022 following systems: 1) SAP Business ONE in S. Korea 2) Iscala in HongKong 3) AX 2009 for ASEAN (Singapore, Malaysia, Indonesia, Thailand) 4) AX 2009 India 5) AX 2009 UAE / Saudi Arabia Japan BPICS + SAP will be replace in P5/2021 as part of POWER Japan project |  | 2020-07-15
iStability | Business Only Application - No IT support - Application provides stability testing against product samples | RAQA | Yes | 2 - July 13 | Sri Tupil | Aileen Diola | Aileen Diola | Blake Hemmel |  | us | 2020-07-13 | 2020-07-23 |  |  | Part - not enough | No | 0.5 | 2020-07-23 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-14 | 2020-09-15 | Sign-Off Received | 44090 |  | Simple
IXI UMS Fax Server | Fax Server solution for inbound fax services, integrated in our CISCO VOIP/IPT | ET | Yes | 5 - Aug 3 | Roman Wojtasik | Patryk Bromirski | Michael Schatten | Chris Cook |  | eu | 2020-08-07 | 2020-08-18 | None | None | None | None | None | None | 100% | DCaaS |  | many dependencies and Global SIP project it is not eligible for cloud migration | Out Of Scope | Not needed | Not needed | As per Pawel "We had technical session with our voice support team regarding possibilities to move Cisco System Unity VM and unified messaging and IXI UMS Fax Server to Cloud. Because of many dependencies and Global SIP project it is not eligible for cloud migration. Please be so kind to remove it form list and cancel both meetings tomorrow." |  | 2020-08-17
Jobrouter | Workflow tool for document management system - deals with approvals etc | ERP | Yes | 2 - July 13 | Dave Cranny | Sebastian Pasch | Alexandra Jauch | Josef Horstmann | Alexandra Jauch | eu | 2020-07-16 |  |  |  | Yes | Yes | 100% | 2020-07-16 | 100% | Retirement |  |  | Out Of Scope | Not needed | Not needed | We are not migrating Docuware because of the physical and workflow limitation. The plan is that this will either be replaced by eQMS Document management system. |  | 2020-09-04 |  | NA | NA |  | Medium
Kaba Elostar | Software that manages key entry. Used at Aarau. | Group Functions | Yes | 3 - July 20 | Ken Holton | Antoine d'Overschie | Antoine d'Overschie | Patrick Groth | Werner Fischer | eu | 2020-07-20 | 2020-08-21 |  |  | Yes | Yes | 100% | 2020-08-21 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-04 | 2020-09-04 | Sign-Off Received | 44124 |  | Medium
KepServerEx (Amsterdam & USA) | KEPServerEX enables users to connect, manage, monitor, and control diverse automation devices and software applications through a single-server interface. ' Application called Tulip. | Manufacturing | Yes | 1 - July 6 | Derek Spillane | Carla Morris | John Thomas | Dan Meyer | Dan Meyer | us | 2020-07-15 | 2020-08-12 |  |  | Yes | Yes | 1899-12-31 | 2020-08-12 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-04 | 2020-09-04 | Sign-Off Received | 44132 |  | Simple
KepServerEx (China) | KEPServerEX enables users to connect, manage, monitor, and control diverse automation devices and software applications through a single-server interface. ' Application called Tulip. | Manufacturing | Yes | 1 - July 6 | Derek Spillane | Carla Morris | John Thomas | Dan Meyer | Dan Meyer | us | 2020-07-15 | 2020-08-12 | None | None | None | None | None | None | 100% | SNI AWS |  |  | Out Of Scope | Not needed | Not needed | Per the meeting notes from Ken and Carla - already SaaS |  | 2020-07-13 |  |  |  |  | Simple
Lasernet / Nemhandel | EDI system - receiving orders from customers and send electronic invoices to customers | ERP | Yes | 3 - July 20 | Dave Cranny | Sebastian Pasch | Thue Lang | Henrik Jakobsen | Thue Lang | eu | 2020-07-23 | 2020-07-30 |  |  | Yes | Yes | 100% | 2020-07-30 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-04 | 2020-09-04 | Sign-Off Received | 44125 |  | Simple
LDAPUpdate | .Net Application that runs daily to update the LDAP database on USMAN-SMDBPVW12 | Commercial | Yes | 5 - Aug 3 | Santhosh Nair | Andres Bernard | Andres Bernard |  |  | us | 2020-08-07 | 2020-08-21 |  |  | Yes | Yes | 100% | 2020-08-21 | 100% | SNI Azure |  |  | Replatform | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-04 | 2020-10-01 | Sign-Off Received | 44106
LIFEMOD BIOMECHANICS SYS | Engineering software for biomechanics which quickly creates accurate, dynamic human models which can be analyzed for contacts, displacements, velocity, acceleration, muscle and joint forces, muscle timings, control functions and energetics. | R&D | Yes | 3 - July 20 | Ian Bennett | Matthew Stephens | Sumanth Arigela | Jason Jordan | Derrick Givens | us | 2020-08-04 |  |  |  | Yes | Yes | 1899-12-31 | 2020-08-04 | 100% | Retirement |  |  | Retirement | Not needed | Not needed | LIFEMOD BIOMECHANICS SYS- Matt to follow up with SME and confirm SME session Date/time ---------------------------- Aug-4: As per Matt its Out of Scope - office is being closed and there is no decision about the servers yet |  | 2020-08-04
Loaners/OSC | Schedule Surgical Cases by Procedure and Loaner Orders by Procedure/Catalog/Kit - Order, Pick, Pack, Ship, Receive, Inspect, Replenish. June 2, 2020: Being replaced by Movemedical next year. That's phase two. ============================= Being Replaced by SAP. 03/09/16 - Per Dave M, this is now in scope for SOX. ITLT Cert:26-JUN-17 USASHSMDBQVW01 is the TEST OSC server for Visionaire | Commercial | Yes | 5 - Aug 3 | Santhosh Nair | Andres Bernard | David Bradley | Matthew Yeomans |  | us | None | None | None | None | None | None | None | None | 100% | Retirement | 31-Jun-21 |  | Retirement | Not needed | Not needed | Hi, Loaners/OSC is scheduled to be replaced OS by Q2 2021. Please remove from the Cloud Migration list. Thanks, Andres |  | 2020-07-09
LogicMonitor | Middleware for Network monitoring with VOLOGY | ET | Yes | 1 - July 6 | Roman Wojtasik | Roman Wojtasik | Marcin Berkowicz | Anna Falbogowska |  | eu | 2020-07-10 | None | None | None | None | None | None | None | 100% | Infrastructure service - out of scope |  |  | Out Of Scope | Not needed | Not needed | The meeting needs to be rescheduled. Roman is the owner but not the SME/SDM. I’ll have the team work on the questionnaire and we can reschedule the meeting once it’s complete. Also LogicMonitor should not be in scope and needs to be removed from the list. It’s a Monitoring tool used by Vology to Monitor our Network environment. Thanks, Patryk" |  | 2020-07-10
Logility Voyager (SCP) | Global Supply Chain planning and inventory optimization. Implemented as part of project: Sudoku. | Supply Chain | Yes | 3 - July 20 | Manas Singha | Amit Shokeen | Dianne Dalton | Todd Smith | Dianne Dalton | us | 2020-07-24 | None | None | None | None | None | None | None | 100% | Complex - separate project |  |  | Out Of Scope | Not needed | Not needed | Hi Maciek, Yes , we will need Sathia & team to join the call so please forward invite to Sathia. Logility and Infor MLE is out of scope for now due to the nature of complexity of the application and investment required . They don’t fit the criteria of lift and shift and more fall into large project category due to the complexity of application. Fishbowl is out of scope as Site which is using this application will be closed . . Ken mentioned that any application which is going to be shut down in 2021 does not need to migrate as those application will stay in Data Center. Thanks Amit |  | 2020-07-23
Logility Voyager (SCP) - Data Integration | Global Supply Chain planning and inventory optimization | Supply Chain | Yes | 4 - July 27 | Manas Singha | Amit Shokeen | Dianne Dalton | Alexander Meijer | Alexander Meijer | us | None | None | None | None | None | None | None | None | 100% | Complex - separate project |  |  | Out Of Scope | Not needed | Not needed | Hi Maciek, Yes , we will need Sathia & team to join the call so please forward invite to Sathia. Logility and Infor MLE is out of scope for now due to the nature of complexity of the application and investment required . They don’t fit the criteria of lift and shift and more fall into large project category due to the complexity of application. Fishbowl is out of scope as Site which is using this application will be closed . . Ken mentioned that any application which is going to be shut down in 2021 does not need to migrate as those application will stay in Data Center. Thanks Amit |  | 2020-07-23
Lutron | Building Automation in Costa Rica | Group Functions | Yes | 2 - July 13 | Philip Sedgwick | Paul Davison | Marcos Obando | Marcos Obando |  | eu | 2020-07-16 | 2020-08-25 |  |  | Yes | Yes | 90% | 2020-08-28 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment is comleted |  | 2020-09-22 | 2020-09-22 | Sign-Off Received | 44096 |  | Medium
Magic X | Real time design rule checking software. Application for the plastic and metal sintering machines | R&D | Yes | 3 - July 20 | Ian Bennett | Matthew Stephens | Sumanth Arigela | Robin Defries | Derrick Givens | us | 2020-08-04 | 2020-08-14 |  |  | Yes | Yes | 100% | 2020-08-14 | 100% | Desktop App |  |  | Out Of Scope | Not needed | Not needed | Thu 06/08/2020 21:00 Hi Matt, Below apps are still pending to schedule/re-schedule. Please let us know when you will be able to complete the questionnaire for below applications? Magic X - Razak to replace with Unigraphics 14-Aug (Done) MASK MATLAB Evisense LIFEMOD BIOMECHANICS SYS SVN - Subversion Configuration Management ----------- 01/08/2020 - Razak has reschduled all the above. Mask and Lifemod are OOS. |  | 2020-08-14
Mainsaver CMMS (UK) | Manufacturing Maintenance and Repair management software; Mainsaiver CMMS is used in Hull only | Manufacturing | Yes | 1 - July 6 | Derek Spillane | Carla Morris | James Sharpe | Dave Chamberlain |  | us | 2020-07-08 | 2020-08-11 |  |  | Yes | Yes | 1899-12-31 | 2020-08-11 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-14 | 2020-09-15 | Sign-Off Received | 44091 |  | Simple
MASK | Used by engineers to measure patient x rays and compare to patients MRI's. Used by Visionaire designers to manipulate MRI's. Creates 3d pictures of paitents bones | R&D | Yes | 3 - July 20 | Ian Bennett | Matthew Stephens |  | Kyle Lonidier |  | us | 2020-08-03 | None | None | None | None | None | None | None | 100% | Desktop App |  |  | Out Of Scope | Not needed | Not needed | Out of Scope (reason Desktop app only), Matt confirmed this. |  | 2020-08-11
MATLAB | Serves as the foundation for all MathWorksª products. It includes a programming language and tools for algorithm development, data analysis, data visualization, and numeric computation. Local install only | R&D | Yes | 3 - July 20 | Ian Bennett | Matthew Stephens | Sumanth Arigela | Kyle Lonidier | Derrick Givens | us | 2020-08-03 | 2020-08-10 |  |  | Yes | Yes | 100% | 2020-08-10 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-02 | 2020-09-02 | Sign-Off Received | 44099 |  | Medium
McAfee ePO Console | Antivirus software system for desktops and servers. Product Vedor Support Level: Supported Delivery Manager Certified - 26-MAY-17 Updated ITLT and Support Manager due Org changes | Security | Yes | 3 - July 20 | Jody Jenkins | Jody Jenkins | Paul Funk | Jody Jenkins | Paul Funk | us | 2020-07-23 | 2020-09-04 | None | None | None | None | None | None | 100% | Retirement | 2021-12-31 |  | Retirement | Not needed | Not needed | It is confirmed McAfee will retire until end of 2021 |  | 2020-10-10
Mcosomos | Coordinate Measuring Machine (CMM) Software https://ecatalog.mitutoyo.com/MCOSMOS-Coordinate-Measuring-Machine-Software-C1019.aspx Hardware that runs this software is purchased directly by the vendor. | Manufacturing | Yes | 2 - July 13 | Derek Spillane | Aileen Diola | Christian Nitschke | Christian Nitschke |  | us | 2020-07-13 | 2020-08-26 |  |  | Yes | Yes | 100% | 2020-08-26 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-04 | 2020-09-15 | Sign-Off Received | 2020-09-16 |  | Medium
Metasys | The Metasys System controls the complete site. That include the Air Handler Units, Temperature Control and monitoring, Pressure Control and monitoring(Manufacturing Rooms), Humidity monitoring, Chillers, Boiler, etc. Manages the connection and oversite of the manufacturing equipment utilized in our Ft Worth manufacturing plant. | Group Functions | Yes | 1 - July 6 | Philip Sedgwick | Paul Davison | Sumanth Arigela | Brad Poston | Martin Pichardo | eu | 2020-07-07 | 2020-07-17 |  |  | Yes | Yes | 1899-12-31 | 2020-07-17 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed |  | 2020-08-17 | 2020-08-13 | Sign-Off Received | 44060 |  | Medium
Microsoft CRM | CRM software Entire Organization / Sales /Cust Serv | Commercial | Yes | 2 - July 13 | Santhosh Nair | Andres Bernard | David Bradley | Vassie Ponsamy | Vassie Ponsamy | us | 2020-08-13 | None | None | None | None | None | None | None | 100% | Retirement | 2020-12-31 |  | Retirement | Not needed | Not needed | Hi, I’m in the process of “Retiring” this application. Thanks, Andres The request for retiring is scheduled for August 13’s CAB. |  | 2020-08-04
Microsoft Dynamics CRM 2016 (ANZ) | CRM System for ANZ Copied from Microsoft Dynamics CRM 2011 (ANZ) per Troy 30-JAN-17. | Commercial | Yes | 1 - July 6 | Rohit Gupta | Rohit Gupta | Darrell Jackson | Nina Fan | Nina Fan | ap | 2020-07-10 | 2020-07-28 | None | None | None | None | None | None | 100% | Retirement | 2021-12-31 |  | Retirement | Not needed | Not needed | ANZ CRM is not in scope of migration Aligned with Commercial IT leadership To be replaced by Salesforce in 2021 Regards Rohit Gupta ¦ Business Partner IT ¦ Smith and Nephew – Australia and New Zealand Sydney , Australia |  | 2020-07-23
MIMICS | Segmentation tools to convert your scanner data to a range of output formats, or perform a variety of design and engineering operations directly on your 3D model | R&D | Yes | 4 - July 27 | Ian Bennett | Matthew Stephens | Sumanth Arigela | Kyle Lonidier | Derrick Givens | us | 2020-07-31 |  |  |  | Yes | Yes | 100% | 2020-07-31 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-14 | 2020-09-18 | Sign-Off Received | 2020-09-25 |  | Simple
Minitab | Several different Licences for each GBU | RAQA | Yes | 4 - July 27 | Sri Tupil | Aileen Diola |  |  |  | us | 2020-07-20 |  |  |  | Yes | Yes | 0.95 | 2020-07-20 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed | Server has OEE co-host application that needs to be isolated during move phase. | 2020-07-20 | 2020-08-21 | Sign-Off Received | 44074 | 44067 | Simple
MLE (China) | Supply Chain: Forecasting & Demand Management, Replenishment Planning & RCCP | Supply Chain | Yes | 4 - July 27 | Manas Singha | Amit Shokeen | Kamal Mishra | Raj Narasimhan |  | us | None | None | None | None | None | None | None | None | 100% | Complex - separate project |  |  | Out Of Scope | Not needed | Not needed | Hi Maciek, Yes , we will need Sathia & team to join the call so please forward invite to Sathia. Logility and Infor MLE is out of scope for now due to the nature of complexity of the application and investment required . They don’t fit the criteria of lift and shift and more fall into large project category due to the complexity of application. Fishbowl is out of scope as Site which is using this application will be closed . . Ken mentioned that any application which is going to be shut down in 2021 does not need to migrate as those application will stay in Data Center. Thanks Amit |  | 2020-07-24
MLE (Hull) | Supply Chain: Forecasting & Demand Management, Replenishment Planning & RCCP | Supply Chain | Yes | 4 - July 27 | Manas Singha | Amit Shokeen | Kamal Mishra | Dawn Pollard |  | us | None | None | None | None | None | None | None | None | 100% | Complex - separate project |  |  | Out Of Scope | Not needed | Not needed | Hi Maciek, Yes , we will need Sathia & team to join the call so please forward invite to Sathia. Logility and Infor MLE is out of scope for now due to the nature of complexity of the application and investment required . They don’t fit the criteria of lift and shift and more fall into large project category due to the complexity of application. Fishbowl is out of scope as Site which is using this application will be closed . . Ken mentioned that any application which is going to be shut down in 2021 does not need to migrate as those application will stay in Data Center. Thanks Amit |  | 2020-07-24
Mobile Inventory Management System | Long Description: The MIMS application allows our field sales reps visibility into their current inventory, customer accounts and delivered order status. A rep can use the application to create an order for their customer for inventory that they currently have in hand and are physically delivering to the customer. Each night the system data including inventory, accounts, sales districts are repopulated from feeds out of SAP. After the information is updated, any Draft or Pending PO order inventory is updated to reflect what has been allocated by the MIMS system but not yet in SAP. Key Interfaces: 'MobileOrderFormExtractLoad' Interface - executes SSIS packages to import data from SAP, the program then loads the data tables and executes some data maintenance stored procedures. 'MobileImsOutput' Interface - creates EDI order files to be placed in a shared folder where they can be retrieved and processed by Gentran for SAP. Short Description: Order entry system for sales reps providng delivered orders to customers. 03/09/16 - Per Dave M, this is now in scope for SOX. | Commercial | Yes | 3 - July 20 | Santhosh Nair | Andres Bernard | Jamie McShan | Johanna Perez | Adriana Zamora | us | 2020-07-21 |  |  |  | Yes | Yes | 100% | 2020-07-21 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed |  | 2020-08-17 | 2020-08-13 | Sign-Off Received | 44064 |  | Medium
Motion Board | Dashboard Application | Data & Analytics | Yes | 4 - July 27 | Tsutomu Hirooka | Chika Ishii | Chika Ishii | Hiroaki Sugamoto |  |  | 2020-08-06 | 2020-08-06 |  |  | Yes | No | 100% | 2020-08-06 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Questionnaire is incomplete.Both the applications Dr.Sum and Motion Board are in the same server and Motion Board is a BI for the Dr.Sum data. Chika will complete the Questionnaire and will send it back. ----------------------------- 10/8/2020 Chika has completed and sent the questionnaire . Will start doing the assessment |  | 2020-08-31 | 2020-08-31 | Sign-Off Received | 2020-09-16 | 44084 | Simple
Myriad | Viewing software used for AutoCAD drawings | R&D | Yes | 5 - Aug 3 | Ian Bennett | Matthew Stephens | Sumanth Arigela | Mark Powers | Rob Cooper | us | 2020-07-31 | 2020-07-31 |  |  | Yes | Yes | 1899-12-31 | 2020-07-31 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | The sesion has been completed and also got response for the action items sent.Started working on the assessment document. | No vendor Support, License authentication to be tested on Temporary Test Server before PROD, Server is co-hosted with other apps - Solidworks - Unigraphics - Flex LM - MATLAB | 2020-08-31 | 2020-08-31 | Sign-Off Received | 44075 |  | Simple
Nexpose Metasploit | email phishing | Security | Yes | 3 - July 20 | Jody Jenkins | Jody Jenkins | Paul Funk | Jody Jenkins | John Briggs | us | 2020-07-22 | None | None | None | None | None | None | None | 100% | Infrastructure service - out of scope |  |  | Out Of Scope | Not needed | Not needed | As Jody confirmed this will not move to Azure -• Nexpose Metasploit – Used to verify penetration testing with in DCs |  | 2020-07-29
Nomino Security | Sets access for legacy Nomino applications (eg. Shipping docs, Encore); | Commercial | Yes | 5 - Aug 3 | Santhosh Nair | Andres Bernard |  | Santhosh Nair |  | us | 2020-08-14 |  |  |  | Yes | Yes | 100% | 2020-08-14 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | assessment work is complete. |  | 2020-08-24 | 2020-08-26 | Sign-Off Received | 2020-09-11 | 44084 | Simple
Non-Employee Database | Web Application used to maintain NonEmployee data and send data extract to Learn.com | Group Functions | Yes | 3 - July 20 | Philip Sedgwick | Paul Davison | Paul Davison | Kevin Cousins |  | eu | 2020-07-16 | 2020-07-27 |  |  | Yes | Yes | 100% | 2020-07-27 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed |  | 2020-08-19 | 2020-08-18 | Sign-Off Received | 2020-08-19 |  | Simple
NPWT Tracker | Web based app for tracking NPWT sales (AWM npwt devices); retired w/ EPO Release. 1/11/16 - Per Chris Cook "Data is incorrect – it SHOULD have been replaced by SAP but that is not the case and it remains in use; managed out of a third party in Germany. Transfer that one to me please." Removed Linda Rosser as the Delivery Manager. ITLT Cert: 26-MAY-17 Business Owner is TBD - ECMDB Cannot Remove due to sec perm. | Commercial | Yes | 3 - July 20 | Santhosh Nair | Andres Bernard | Sebastian Jaschinski | Thorsten Kreuser | Thorsten Kreuser | us | 2020-07-21 | 2020-08-31 |  |  | Yes | Yes | 100% | 2020-08-31 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-04 | 2020-09-10 | Sign-Off Received | 44085 |  | Medium
OEE | Virtulized | Manufacturing | Yes | 3 - July 20 | Derek Spillane | Carla Morris | John Thomas | Thomas Spradlin | Thomas Spradlin | us | 2020-07-21 |  |  |  | Yes | Yes | 100% | 2020-08-21 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment is complete |  | 2020-07-31 | 2020-09-04 | Sign-Off Received | 44132 |  | Simple
Offline Counting | Application used to perform stock audits at customer premises Support manager updated per Paul D and Francisco M. 16-NOV-17 | Supply Chain | Yes | 5 - Aug 3 | Manas Singha | Amit Shokeen | Oliver Thomi | Carles Ferrer | Oliver Thomi | us | 2020-08-17 | 2020-08-25 |  |  | Yes | Yes | 100% | 2020-08-25 | 100% | SNI Azure |  |  | Replatform | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-04 | 2020-09-15 | Sign-Off Received | 44090 |  | Medium
OLMEC - UDI Printing | Server authenticates user AD accounts to allow access to the OLMEC UDI Printing software | R&D | Yes | 5 - Aug 3 | Ian Bennett | Matthew Stephens | Antoine d'Overschie |  |  | us | 2020-08-07 | 2020-08-19 |  |  | Yes | Yes | 100% | 2020-08-19 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-14 | 2020-09-18 | Sign-Off Received | 44099 |  | Medium
Oracle Enterprise Manager | Environmental and database monitoring of GBIP SoNAR servers | Data & Analytics | Yes | 2 - July 13 | Stuart Robinson | Sathiamurthy Samidurai | Andy Challen |  |  | ap | 2020-07-20 | 2020-08-14 |  |  | Yes | Yes | 100% | 2020-08-14 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-04 | 2020-09-15 | Sign-Off Received | 2020-09-30 |  | Medium
Oracle Hyperion | Financial reporting aka. ESSBASE. Ex-ARTC application. | Group Functions | Yes | 2 - July 13 | Philip Sedgwick | Paul Davison | Dhinagaran Kuppusamy | Rick Florence | Karen Noffsinger | eu | 2020-07-17 | 2020-07-27 |  |  | Part - not enough | Yes | 100% | 2020-07-24 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Few action items sent to Paul and Dina. |  | 2020-08-31 | 2020-08-31 | Sign-Off Received | 44081 |  | Medium
OSISoft PI System | OSIsoft software is used to capture, process, analyze, and store data. It is used as lab software and is not GxP. | Manufacturing | Yes | 3 - July 20 | Ian Bennett | Matthew Stephens | Dave Chamberlain | John Hodgson | John Hodgson | us | 2020-08-10 | 2020-08-13 |  |  | Yes | 2020-08-13 | 0.9 | 2020-08-13 | 100% | SNI Azure |  | Leagcy OS , No vendor support | Replatform | Yes - complete | Yes - complete | Rescheduled from 08/10/20 to 08/13/20 ------------------ 13-Aug-2020 - Matt/Adrina to laise with Ken on feasibilty to move to Azure with legacy OS or to retain it AS IS current platform or Upgrade to newer version (as seperate proejct) | Windows 2003 server, No Vendor Support | 2020-08-17 | 2020-09-15 | Sign-Off Received | 44125 |  | Complex
Palo Alto DNS Filtering | Used to whitelist/blacklist URLs in the Palo Alto DNS filter protection component. | Security | Yes | 4 - July 27 | Lawrence Zorio | Paul Funk | John Briggs | Jody Jenkins |  | us | 2020-08-17 | None | None | None | None | None | None | None | 100% | Infrastructure service - out of scope |  |  | Out Of Scope | Not needed | Not needed | • Palo Alto DNS Filtering – Internet Web Filter (just an app in the firewalls) |  | 2020-07-29
PanelBuilder |  | Manufacturing | Yes | 4 - July 27 | Derek Spillane | Carla Morris |  |  |  | us | 2020-07-29 | None | None | None | None | None | None | None | 100% | Desktop App |  |  | Out Of Scope | Not needed | Not needed | Hi Deepak, We can cancel the PanelBuilder SME session. We have discovered that that PanelBuilder is a pc based application. It would not be suitable for cloud. |  | 2020-07-29
Panorama (Palo Alto Firewall Management Platform) | Used to manage the Palo Alto firewalls throughout the S+N environment. | Security | Yes | 4 - July 27 | Jody Jenkins | Paul Funk | John Briggs | Jody Jenkins | Paul Funk | us | 2020-08-12 | None | None | None | None | None | None | None | 100% | Infrastructure service - out of scope |  |  | Out Of Scope | Not needed | Not needed | • Panorama (Palo Alto Firewall Management Platform) – management console for firewalls |  | 2020-07-29
PartMaker | CAM system for automating the programming of mutli-axis Turn-Mill centers and Swiss-type lathes. | Manufacturing | Yes | 3 - July 20 | Ian Bennett | Carla Morris |  | Michael Barnes |  | us | 2020-07-29 |  |  |  | Yes | Yes | 100% | 2020-07-29 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is complete. |  | 2020-08-04 | 2020-09-02 | Sign-Off Received | 44132 |  | Simple
Paymetric Application System | Credit Card Authorization processing interfaced with SAP EPR and PRD system. 12/1/15 - Paul Wilson requested delivery manager - was set to Tauseef. | ERP | Yes | 5 - Aug 3 | Jacek Karas | Pablo Iradier | Pablo Iradier | Steve Horgan | Siva Govender |  | 2020-08-14 | 2020-08-21 |  |  | Yes | Yes | 1899-12-31 | 2020-08-21 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-04 | 2020-09-04 | Sign-Off Received | 44120 |  | Medium
Payroll - Softland (Colombia) | Columbia finance app | Group Functions | Yes | 3 - July 20 | Philip Sedgwick | Paul Davison |  |  |  | eu | None | None | None | None | None | None | None | None | 100% | Retirement |  |  | Retirement | Not needed | Not needed | Hi All, I’ve noticed on looking back that the Softland and Uno payroll applications in Colombia are not active and only used for historical purposes. The data is required for 5 years and we are on year 2, so I’ve asked the business to put in an archive request so the data can be archived into Serrala and the applications can be decommissioned. Therefore, I recommend these be removed from scope. Regards, Paul. |  | 2020-07-22
PCM (procurement) | Procurement software | Supply Chain | Yes | 3 - July 20 | Manas Singha | Antoine d'Overschie | Antoine d'Overschie | René Baumann | Silvia Carlino | eu | 2020-07-20 | None | None | None | None | None | None | None | 100% | Retirement | 2021-06-30 |  | Retirement | Not needed | Not needed | PCM (procurement), Movex ERP will migrate to SAP in Q1-Q2 2021, with this migration several application will decommission, PCM is one of these application. Regards Antoine |  | 2020-07-16
PMPA | PMPA hosts post market product performance information. Structured data as well as unstructured data including advance search and full-text search. It will include all CER's and PMS reports for the S&N company for all products. | Data & Analytics | Yes | 3 - July 20 | Stuart Robinson | Sathiamurthy Samidurai | Roger Pearson | James Huckle |  | ap | 2020-07-24 | 2020-07-31 |  |  | Yes | Yes | 100% | 2020-07-31 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | 31/7/2020 Session is done.Will send the action items and do the follow-up. |  | 2020-08-26 | 2020-08-26 | Sign-Off Received | 2020-09-30 | 2020-09-10 | Medium
Power BI (China) | Run all relevant PowerBI reports for business department | Data & Analytics | Yes | 3 - July 20 | Jerry Li | Jinble Li | Jinble Li | Las Lu | Jinble Li |  | 2020-07-21 | 2020-08-14 |  |  | Part - not enough | No | 90% | 2020-08-14 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed | SDM input suggest there is no dependencies with other application, however the IT architecure shared seems to suggest otherwise, this warrants through analysis of entire application intergration during actual migration. | 2020-08-17 | 2020-08-18 | Sign-Off Received | 44074 | 44067 | Simple
PricingTool | Comercial forecast for princings conditions | Commercial | Yes | 3 - July 20 | Santhosh Nair | Andres Bernard | Oriol Morral | Maria Ferrer |  | us | 2020-07-21 | 2020-08-17 |  |  | Yes | Yes | 100% | 2020-08-17 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-04 | 2020-09-18 | Sign-Off Received | 44092 |  | Medium
Primion | PRIMION is time capture system used in Germany commercial business. We have time capture terminals in both Marl and Hamburg. Also this is the former vacation planning system. Also this system manages the access to the building in Marl and is coupled with the Alarm system. The user-interface is a Website: http://ukrthsmappvw23/primeweb/index.jsp NOTES from Sebastian: This was introduced in July 2014. Business Owner is Udo Jensen (HR Director Germany). This is vendor supported application. The server is running a local SQL Express database. It does run IE11 native and no web-plugins/add-ons required. There is also a full client software to program key-cards, to my knowledge. | Group Functions | Yes | 2 - July 13 | Philip Sedgwick | Paul Davison | Sebastian Pasch | Udo Jensen | Dirk Giezenaar | eu | 2020-07-17 | 2020-08-05 |  |  | Yes | Yes | 100% | 2020-08-05 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed.But still there is a open pending action items from SDM side. |  | 2020-09-04 | 2020-09-04 | Sign-Off Received | 44127 |  | Medium
Procurement Spend Management | Business Objects Spend Performance Management and Supplier Scorecards. Business owner update per:SRR0079440 | Supply Chain | Yes | 1 - July 6 | Stuart Robinson | Sathiamurthy Samidurai |  | Andrew Croston |  | ap | 2020-07-22 |  |  |  | Part - enough | Yes | 100% | 2020-07-21 | 100% | SAP on HP-UX - out of scope |  |  | Out Of Scope | Not needed | Not needed | SAP PSM package which is deployed on HP-UX box |  | 2020-07-22
PTC Creo | Bluebelt Used to generate the 3 dimensional models of our products. These 3d model are then converted to two dimensional prints within Creo and exported as ODSs and .STEP files. These documents become part of the Design History file. | R&D | Yes | 4 - July 27 | Ian Bennett | Matthew Stephens | Sumanth Arigela | Branko Jaramaz |  | us | 2020-08-11 | 2020-09-03 |  |  | Yes | Yes | 100% | 2020-08-19 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-04 | 2020-09-04 | Sign-Off Received | 2020-09-25 |  | Simple
QAD ERP | Manufacturing ERP SDM: Jacob Goitom pending add to group | Manufacturing | Yes | 4 - July 27 | Derek Spillane | Jacob Goitom | Muhammad Hamza | Samson Tom | Dan Chisnell | us | 2020-08-10 | 2020-08-26 |  |  | Yes | Yes | 100% | 2020-08-26 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-04 | 2020-09-10 | Sign-Off Received | 44084 |  | Complex
RADB | Reg Subs, Labeling System. Product Vendor Support=Supported Delivery Manager Cert: 22JUN17 | RAQA | Yes | 1 - July 6 | Sri Tupil | Aileen Diola | Guoliang Wu | Alex Jiang |  | us | 2020-07-09 | 2020-08-03 |  |  | Yes | Yes | 100% | 2020-08-03 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | There are few action items are stil pending to complete. Waiting for response on follow-up email. |  | 2020-08-04 | 2020-09-10 | Sign-Off Received | 2020-09-16 |  | Medium
RAMS (China) | RARRS, Regulatory Submission; Manages the process of new/renew Registration request for China Commercial. Including the approval management, document management and tracking records. | RAQA | Yes | 1 - July 6 | Sri Tupil | Aileen Diola | Las Lu | Amber Wang |  | us | 2020-07-09 | 2020-08-11 |  |  | Part - enough | Yes | 100% | 2020-07-28 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-04 | 2020-09-04 | Sign-Off Received | 2020-09-09 |  | Complex
Recon LaunchPad (SSO) | Used by Memphis and Aarau. The application basically provides single sign-on functionality by redirecting the users to another web site passing the user credentials to authenticate to the web site. | Commercial | Yes | 4 - July 27 | Santhosh Nair | Andres Bernard | Andres Bernard | Alan Kee | Alan Kee | us | 2020-07-31 | 2020-08-18 |  |  | Yes | Yes | 1899-12-31 | 2020-08-18 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-04 | 2020-09-04 | Sign-Off Received | 44083 |  | Medium
Reflections (AS400 emulator for AWMANZ BPCS) | BPCS/AS400 Emulator | Commercial | Yes | 3 - July 20 | Firas Almahamid | Firas Almahamid | Joe Szili | Firas Almahamid |  | ap | 2020-07-24 | None | None | None | None | None | None | None | 100% | Retirement | 2015-12-31 |  | Retirement | Not needed | Not needed | BPCS AS400 application has been retired in 2015 and this application kept for supporting historical reporting, we do not need to migrate this to Cloud as this may be retired once we have an alternative cloud based solution for historical reporting. |  | 2020-07-23
Reimbursement | Web based application - Informational. Per Doug C, Internet exposed b/c accessed by sales reps AND office admins for doctors that use our products. In production since 2006. "There is an internal web application called ReimbursementAdmin which is on mmpsrv046 and being moved this weekend to USMAN-SMWSPVW12. This application is used by Michelle Lowe to update the Content on the Public Facing web application, Reimbursement, on mmpsrv023." | Commercial | Yes | 2 - July 13 | Santhosh Nair | Andres Bernard | Andres Bernard | Michelle Lowe | Michelle Lowe | us | 2020-07-13 |  |  |  | Yes | Yes | 100% | 2020-07-14 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed |  | 2020-08-17 | 2020-08-13 | Sign-Off Received | 2020-08-14 |  | Simple
Sales Request Forms | Sales Request Forms | Commercial | Yes | 2 - July 13 | Santhosh Nair | Andres Bernard | Andres Bernard | Kenneth Stiles | Brenda Groves | us | 2020-07-13 |  |  |  | Yes | Yes | 1899-12-31 | 2020-07-14 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | follow up session with Michel and Maagedha (HCL) is required to clarify its working, flows, issues and most importantly how many application are being hosted on the each server (dependencies) on the infra movement, and also how many database of other application are in the SQL server (treatment needs to be laid out based on how to extract this for Reimbursement and Sales Request form application). |  | 2020-08-31 | 2020-08-31 | Sign-Off Received | 44074 |  | Medium
Salient | Salient calculates sales incentive compensation for the US Sports Med and ENT sales forces based upon actual sales data, and business rules managed by Finance. | Commercial | Yes | 1 - July 6 | Santhosh Nair | Andres Bernard | Andres Bernard | Akhil Radhakrishnan | Akhil Radhakrishnan | us | None | None | None | None | None | None | None | None | 100% | Retirement | 2021-07-01 |  | Retirement | Not needed | Not needed | Per Andre: Donann and I discussed and agreed that we should not plan for Salient migration to Azure. We are working on another project to set up a database repository for US Commission data (probably in AWS) and hence we plan to decommission Salient by Q2 next year. |  | 2020-07-09
SAP Business One | ERP South Korea Product Vendor Support Level: Supported Support Knowledge: 0% Delivery Manager Cert: 14-JUN-17 | ERP | Yes | 3 - July 20 | Massimo Trambaioli | Chang Keun Oh | Chang Keun Oh | Sun Young Kim |  | ap | 2020-07-20 | None | None | None | None | None | None | None | 100% | Retirement | 2020-12-31 |  | Retirement | Not needed | Not needed | Massimo - The Apac roadmap we are filing CER, and already discussed with management, aims at replacing within 2021-2022 following systems: 1) SAP Business ONE in S. Korea 2) Iscala in HongKong 3) AX 2009 for ASEAN (Singapore, Malaysia, Indonesia, Thailand) 4) AX 2009 India 5) AX 2009 UAE / Saudi Arabia Japan BPICS + SAP will be replace in P5/2021 as part of POWER Japan project |  | 2020-07-15
SAP Business Warehouse | SAP Business Intelligence BWP sends data to TM1, PSM, Pilgrim, Endo Varicent and other apps. | Data & Analytics | Yes | 5 - Aug 3 | Stuart Robinson | Sathiamurthy Samidurai |  | Nick Hatfield |  | ap | 2020-07-29 | None | None | None | None | None | None | None | 100% | SAP on HP-UX - out of scope |  |  | Out Of Scope | Not needed | Not needed | SAP Business warehouse is out of scope. Since it is running on HP UX |  | 2020-07-29
SEAL Application | SEAL application manages printed content for the AWM DMS System - Applying watermarking and other information based on document status. Used in Europe and Asia. | ERP | Yes | 3 - July 20 | Jacek Karas | Krzysztof Gaik | Rabindra Mishra | Wilson Kennedy | Chris Green | eu | 2020-07-22 | 2020-08-05 |  |  | Yes | Yes | 1899-12-31 | 2020-08-05 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Session is done.Action Items sent .Waiting for the response. |  | 2020-08-04 | 2020-09-02 | Sign-Off Received | 44097 |  | Medium
Skillsoft (Percipio) | Corporate Learning / Development | Group Functions | Yes | 4 - July 27 | Philip Sedgwick | Paul Davison |  | James Hegarty |  | eu | 2020-08-06 | None | None | None | None | None | None | None | 100% | SaaS |  |  | Out Of Scope | Not needed | Not needed | Skillsoft is a SaaS application and should be removed from the list of applications. |  | 2020-07-20
Smart EHL |  | Group Functions | Yes | 37838 | Philip Sedgwick | Paul Davison |  |  |  | eu | 2020-08-18 |  |  |  | Yes | Yes | 100% | 2020-08-18 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | assessment work is complete |  | 2020-08-24 | 2020-09-08 | Sign-Off Received | 44090 |  | Medium
SmartGit | Bluebelt ""SmartGit" is an interface to "Git". SmartGit is an alternative GUI client that is friendlier than the command-line Git client. Used for Navio Product Development " | R&D | Yes | 2 - July 13 | Ian Bennett | Matthew Stephens | Sumanth Arigela | Costa Nikou |  | us | 2020-07-16 | 2020-08-20 |  |  | Yes | Yes | 100% | 2020-08-20 | 100% | Retirement | 2020-12-31 |  | Retirement | Not needed | Not needed | Matt confirmed on SME Session his plan to retire SmartGIT on Aug 20th 2020 (ETA by end of 2020). ------------ |  | 2020-08-20
SNID Archived Shipping Documents | Repository of archived shipping documententation for orders shipped from the Movianto and UDG 3PLs. Developed internally. | Supply Chain | Yes | 5 - Aug 3 | Manas Singha | Amit Shokeen | Archana Sekar | Joanne Ball | Joanne Ball | us | 2020-08-19 |  |  |  | Yes | Yes | 1899-12-31 | 2020-08-19 | 100% | SNI Azure |  |  | Replatform | Yes - complete | Yes - complete | Assesement work is complete. |  | 2020-08-24 | 2020-09-08 | Sign-Off Received | 44117 |  | Medium
Solarwinds | Network Performance monitor | ET | Yes | 5 - Aug 3 | Roman Wojtasik | Patryk Bromirski |  | Anna Falbogowska |  | eu | 2020-08-14 | None | None | None | None | None | None | None | 100% | Infrastructure service - out of scope |  |  | Out Of Scope | Not needed | Not needed | Solarwinds - Networking monitoring tool, will remain on prem. This is out of scope for the Cloud migration, as discussed with Roman Wojtasik. |  | 2020-08-10
Solidworks | Computer Aided Design ITLT Cert:26-JUN-17 | R&D | Yes | 5 - Aug 3 | Ian Bennett | Matthew Stephens | Sumanth Arigela | Christopher Spencer | Petra Millberg | us | 2020-07-09 | 2020-07-17 |  |  | Yes | Yes | 95% | 2020-07-17 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed |  | 2020-08-13 | 2020-08-13 | Sign-Off Received | 44099 | 44067 | Simple
Solidworks PDM Professional | Product Data Management Software. Secures Solidworks files and metadata. | R&D | Yes | 4 - July 27 | Ian Bennett | Matthew Stephens | Sumanth Arigela | Vishal Jayakumar |  | us | 2020-07-09 | 2020-08-19 |  |  | Yes | Yes | 95% | 2020-08-19 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-14 | 2020-09-15 | Sign-Off Received | 44099 |  | Medium
Solidworks PDM Workgroup | Solidworks PDM Workgroup stores CAD models in a secure vault. | R&D | Yes | 1 - July 6 | Ian Bennett | Matthew Stephens | Sumanth Arigela | Christopher Spencer | Petra Millberg | us | 2020-07-09 | 2020-08-19 |  |  | Yes | Yes | 50% | 2020-08-19 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-14 | 2020-09-15 | Sign-Off Received | 2020-09-25 |  | Simple
SOTI | RF Gun Management Console and configuration tool for Manufacturing ADC is Product vendor | Manufacturing | Yes | 1 - July 6 | Francisco Marconcini | Carla Morris | John Thomas | Mick Leazer | Keith White | us | 2020-07-08 | 2020-07-15 |  |  | Yes | Yes | 100% | 2020-07-15 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed |  | 2020-07-31 | 2020-08-13 | Sign-Off Received | 2020-08-25 | 44067 | Medium
Spectrum 10 | Spectroscopic data collection and analysis Name updated due to new release and configuration | RAQA | Yes | 2 - July 13 | Sri Tupil | Aileen Diola |  | Tim Colley |  | us | 2020-07-13 | 2020-08-17 |  |  | None | No | 40% | 2020-08-17 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | assessment work is complete | Latency | 2020-08-27 | 2020-09-04 | Sign-Off Received | 44083 |  | Simple
SVN - Subversion Configuration Management | Bluebelt "Binary product software is managed on the SVN. Used for Navio Product Development" | R&D | Yes | 1 - July 6 | Ian Bennett | Matthew Stephens | Sumanth Arigela | Costa Nikou |  | us | 2020-07-09 | 2020-08-13 |  |  | Yes | 2020-08-13 | 100% | 2020-08-13 | 100% | Retirement | 2020-12-01 |  | Retirement | Not needed | Not needed | SVN - Subversion Configuration Management - Rescheduled from 07/14/20 to 08/13/20 |  | 2020-08-13
SVN Tortoise | Atracsys document repository, documentation revision controlling software | Commercial | Yes | 5 - Aug 3 | Kevin Ponce | Kevin Ponce |  | Kevin Ponce |  |  | 2020-08-14 | 2020-09-18 |  |  | Yes | 44057 | 1 | 44057 | 100% | Other - comments |  |  | Out Of Scope | Not needed | Not needed | Hi everyone, After a review it has been agreed to mark this app as remaining on-prem. Can we please update the trackers to reflect decision this and cancel the session. Thanks, Adrian Caines |  | 2020-09-17
Symon Jumpstart | 03/16/16 - According to the directory, Russell Dodd is part of MedEd. Chris C suggested TJ/Sam would be the owners - TJ asked Sam to work with business to identify IT contact. Symon Jumpstart is a utility that scans sub nets for the ip addresses of the SDA's. It is not a critical application and should not interfere with the operation of the digital sign system. Symon as a whole is a digital sign system that controls the content of the LED signs that are used at Smith and Nephew facilities in the Memphis area. Also, Nicolas Bussey (desktop) has RDP access to this system. | Group Functions | Yes | 3 - July 20 | Philip Sedgwick | Paul Davison | Nicholas Bussey | Russell Dodd | Nicholas Bussey | eu | 2020-07-24 | 2020-07-28 | None | None | None | None | None | None | 100% | Retirement | 2020-12-31 |  | Retirement | Not needed | Not needed | All, see below. We can remove Symon Jumpstart from the scope. Regards, Paul. It will be replaced by the end of this year for sure. Philip Meeker ¦ GBS AV and Executive Technical Service Delivery |  | 2020-07-22
Syngistix | LAB Application | RAQA | Yes | 3 - July 20 | Sri Tupil | Aileen Diola |  | Tim Colley |  | us | 2020-07-13 | 2020-08-20 |  |  | Yes | Yes | 95% | 2020-08-20 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | assessment work is complete |  | 2020-08-27 | 2020-09-04 | Sign-Off Received | 44104 |  | Simple
System Center Configuration Manager (SCCM) | IT tool for inventory,remote takeover,patch management,software distribution | ET | Yes | 5 - Aug 3 | Jakub Keler | Bartosz Ostrowski | Evangelos Kontis | Alison Conlon |  | eu | 2020-08-17 | 2020-08-31 | None | None | None | None | None | None | 100% | Other - comments |  |  | Out Of Scope | Not needed | Not needed | As discussed this application will still on-prem. |  | 2020-09-14
Tableau Bridge | Tableau Bridge will act as an interface between Alteryx (on prem) and Tableau Online (web-based), in order that Supply Chain can publish datasets into Tableau. | Supply Chain | Yes | 5 - Aug 3 | Manas Singha | Sathiamurthy Samidurai | Ritesh Verma | Rachael Lear | Rachael Lear | us | 2020-08-13 | 2020-08-20 |  |  | Yes | Yes | 100% | 2020-08-20 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Action items sent to Yuonne. |  | 2020-08-31 | 2020-08-31 | Sign-Off Received | 44104 | 44084
Tarife | Customs Tariff No. Administration | Supply Chain | Yes | 5 - Aug 3 | Manas Singha | Yvonne Braun | Yvonne Braun | Josef Horstmann | Birgit Meihack | eu | 2020-08-20 |  |  |  | Yes | 2020-08-20 | 1899-12-31 | 2020-08-20 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-04 | 2020-09-04 | Sign-Off Received | 44089 |  | Simple
Tenable VMS | Tenable VMS | Security | Yes | 4 - July 27 | Jody Jenkins | Paul Funk | Mekkos Beech | Jody Jenkins | Mekkos Beech | us | 2020-08-13 | None | None | None | None | None | None | None | 100% | DCaaS |  | vulnerabilities scanners – will require to keep in DCs | Out Of Scope | Not needed | Not needed | • Tenable VMS – Our vulnerabilities scanners – we may add some in the cloud but we will require to keep in DCs as well |  | 2020-07-29
TIAMO | control and database software for titrators, dosing devices and sample changers that allows complete laboratory automation | Manufacturing | Yes | 5 - Aug 3 | Sri Tupil | Aileen Diola |  | John Rose |  | us | 2020-07-13 | 2020-08-17 |  |  | None | No | 40% | 2020-08-17 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | assessment work is complete | Latency | 2020-08-27 | 2020-09-02 | Sign-Off Received | 44076 |  | Simple
TM1 (Global Cost Visibility) | TM1 Global Cost Visibility Application | Data & Analytics | Yes | 3 - July 20 | Stuart Robinson | Sathiamurthy Samidurai |  | Ian Melling |  | ap | 2020-07-24 | 2020-08-06 |  |  | Yes | Yes | 100% | 2020-08-06 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed |  | 2020-08-17 | 2020-08-17 | Sign-Off Received | 44104 | 2020-08-24 | Medium
TM1 (Transfer Pricing) | TM1 Transfer Pricing Application | Data & Analytics | Yes | 3 - July 20 | Stuart Robinson | Sathiamurthy Samidurai |  | Roger Horwood |  | ap | 2020-07-24 | 2020-08-07 |  |  | Yes | Yes | 100% | 2020-08-07 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed |  | 2020-08-17 | 2020-08-17 | Sign-Off Received | 44104 | 2020-08-24 | Medium
TM1 Cognos Configuration | Cognos EPO Ax aplication retired in 2018. The old EPO Ax cognos servers repurposed for TM1 Cognos configuration and TM1 development. | Data & Analytics | Yes | 5 - Aug 3 | Stuart Robinson | Sathiamurthy Samidurai |  | Nick Hatfield |  | ap | 2020-08-12 |  |  |  | Yes | Yes | 100% | 2020-08-12 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed |  | 2020-08-17 | 2020-08-17 | Sign-Off Received | 44104 | 44067 | Medium
Tops Pro | Packaging Design | R&D | Yes | 5 - Aug 3 | Ian Bennett | Matthew Stephens | Matthew Stephens | Jean Woloszko | Matt Stephenson | us | 2020-08-13 |  |  |  | Yes | 44056 | 1 | 44056 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-07 | 2020-09-15 | Sign-Off Received | 44091 |  | Simple
TotalChrom | A COTS application that is use for chromatography data handling by the quality business unit. | RAQA | Yes | 5 - Aug 3 | Danielle Blackwell | Aileen Diola |  | John Rose |  | us | 2020-07-29 | None | None | None | None | None | None | None | 100% | Retirement | 2011-01-01 |  | Retirement | Not needed | Not needed | Aileen: As per conversation with John Rose and Wallace Puckett just now, they said that they have stopped using TotalChrom and the Chromatography equipment that was connected to it last 2011 and they have informed people prior to us of the same thing. |  | 2020-07-28
TOTVS | ERP Platform for Brazil Product Vendor Support=Supported Users Internal is set to YES, & not number Delivery Manager Certification = 14-Jun-17 | ERP | Yes | 4 - July 27 | Manas Singha | Eduardo Lima | Eduardo Lima | Guilherme Costa | Eduardo Lima |  | 2020-08-10 | None | None | None | None | None | 100% | 2020-08-10 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | This is azure to azure migration. |  | 2020-08-26 | 2020-08-26 | Sign-Off Received | 2020-09-16 | 44084 | Complex
Trackwise (EU) | TrackWise is a web-based tracking software tool for electronically logging, managing, and trending CAPA, Audit and Change at Aarau and Tuttlingen | RAQA | Yes | 3 - July 20 | Sri Tupil | Aileen Diola | Antoine d'Overschie | Roger Schaller | Benjamin Hinterberger | us | 2020-07-24 | 2020-08-19 |  |  | Yes | Yes | 1 | 44062 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-04 | 2020-09-09 | Sign-Off Received | 44084 |  | Medium
Trackwise (US) | Legacy Complaints management tool for the Plus business. TrackWise is a web-based tracking software tool for electronically logging, managing, and trending quality and compliance issues and action items in accordance with cGxP standards. Used by Fort Worth and Curacao. 1-6-16: Delivery Manager was Steve McNeill. Changed to Robert Jones | RAQA | Yes | 5 - Aug 3 | Sri Tupil | Aileen Diola | Robert Jones | Blake Hemmel |  | us | 2020-07-29 |  | None | None | None | None | None | None | 100% | Retirement | 2020-12-31 |  | Retirement | Not needed | Not needed | As per Aileen "Yes on archiving and yes in turning off the system by end of this year." |  | 2020-07-27
Trios Guardian | Lab Application | RAQA | Yes | 3 - July 20 | Sri Tupil | Aileen Diola |  | Tim Colley |  | us | 2020-07-20 | 2020-07-21 |  |  | Yes | Yes | 100% | 2020-08-21 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Action items sent to Aileen to get data from vendor. |  | 2020-08-27 | 2020-09-02 | Sign-Off Received | 44076 |  | Simple
Unified Functional Testing | UFT provides regression testing functionality for application testers | Data & Analytics | Yes | 5 - Aug 3 | Chris Cook | Sathiamurthy Samidurai | Adam Brunt | Roger Pearson |  | eu | 2020-08-20 |  |  |  | Yes | Yes | 100% | 2020-08-20 | 100% | SNI Azure |  |  | Replatform | Yes - complete | Yes - complete |  |  | 2020-08-24 | 2020-09-02 | Sign-Off Received | 44104
Unigraphics | CAD Modeling, Assembly, Drawing Creation, CAM Programming,CMM programming | R&D | Yes | 4 - July 27 | Ian Bennett | Matthew Stephens | Sumanth Arigela | Dean Hughes | Jason Jordan | us | 2020-08-04 |  |  |  | Yes | Yes | 100% | 2020-08-04 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-04 | 2020-09-04 | Sign-Off Received | 44099 |  | Simple
VEI Label Verification | Confirm the contents of the label match the shop order Support Vendor: Vision Engineering, INC. | Manufacturing | Yes | 2 - July 13 | Derek Spillane | Carla Morris | John Thomas | Laurie Jordan | Zachary Wells | us | 2020-07-27 | 2020-08-19 |  |  | Yes | Yes | 100% | 2020-08-19 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-14 | 2020-09-15 | Sign-Off Received | 2020-10-28 |  | Medium
Vericut | CNC Program Optimizer | Manufacturing | Yes | 2 - July 13 | Derek Spillane | Carla Morris | Sumanth Arigela | Brad Dacus | Trey Hubbard | us | 2020-07-27 |  |  |  | Part - enough | Yes | 1899-12-31 | 2020-07-27 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-04 | 2020-09-08 | Sign-Off Received | 44083 |  | Simple
Vertex - Q Series | Q Series ITLT Cert:26-JUN-17 | ERP | Yes | 5 - Aug 3 | Jacek Karas | Krzysztof Gaik | Dorothy Hoyland | Rick Florence | Debbie Gangi | eu | 2020-08-12 | None | None | None | None | None | None | None | 100% | SAP on HP-UX - out of scope |  |  | Out Of Scope | Not needed | Not needed | Vertex is in HP UX. So all 6 Vertex applications are OoS because they are HPUX/ SAP intergrated. |  | 2020-08-10
Vertex - Q Series Returns | Q Series Returns | ERP | Yes | 5 - Aug 3 | Jacek Karas | Krzysztof Gaik | Krzysztof Gaik | Rick Florence | Debbie Gangi | eu | 2020-08-12 | None | None | None | None | None | None | None | 100% | SAP on HP-UX - out of scope |  |  | Out Of Scope | Not needed | Not needed | Vertex is in HP UX. So all 6 Vertex applications are OoS because they are HPUX/ SAP intergrated. |  | 2020-08-10
Vertex - Rate Locator | Rate Locator | ERP | Yes | 5 - Aug 3 | Jacek Karas | Krzysztof Gaik | Krzysztof Gaik | Rick Florence | Debbie Gangi | eu | 2020-08-12 | None | None | None | None | None | None | None | 100% | SAP on HP-UX - out of scope |  |  | Out Of Scope | Not needed | Not needed | Vertex is in HP UX. So all 6 Vertex applications are OoS because they are HPUX/ SAP intergrated. |  | 2020-08-10
Vertex - Tax Decision Maker | Tax Decision Maker | ERP | Yes | 5 - Aug 3 | Jacek Karas | Krzysztof Gaik | Krzysztof Gaik | Rick Florence | Debbie Gangi | eu | 2020-08-12 | None | None | None | None | None | None | None | 100% | SAP on HP-UX - out of scope |  |  | Out Of Scope | Not needed | Not needed | Vertex is in HP UX. So all 6 Vertex applications are OoS because they are HPUX/ SAP intergrated. |  | 2020-08-10
Vertex Sales & Use Tax Returns | Vertex Quantum Sales & Use Tax Returns. 05/09/16 - Updated name from "QUANTUM RETURNS" to "Vertex Sales & Use Tax Returns" per request/approval from Dorothy/Paul W. | ERP | Yes | 1 - July 6 | Jacek Karas | Krzysztof Gaik | Krzysztof Gaik | Frankie Brooks | Debbie Gangi | eu | 2020-08-12 | None | None | None | None | None | None | None | 100% | SAP on HP-UX - out of scope |  |  | Out Of Scope | Not needed | Not needed | Vertex is in HP UX. So all 6 Vertex applications are OoS because they are HPUX/ SAP intergrated. |  | 2020-08-10
Vertex Sales Tax Q Series | Sales and use tax calculation | ERP | Yes | 1 - July 6 | Jacek Karas | Krzysztof Gaik | Krzysztof Gaik | Maureen Judd | Debbie Gangi | eu | 2020-08-12 | None | None | None | None | None | None | None | 100% | SAP on HP-UX - out of scope |  |  | Out Of Scope | Not needed | Not needed | Vertex is in HP UX. So all 6 Vertex applications are OoS because they are HPUX/ SAP intergrated. |  | 2020-08-10
Visionaire Case Management (VCM) | Patient matched solutions. ASD-Recon custom cutting block specification tool | R&D | Yes | 4 - July 27 | Ian Bennett | Matthew Stephens | David Bradley | Eric Morris | Eric Morris | us | 2020-08-17 |  |  |  | Yes | yes | 100% | 2020-08-17 | 100% | Complex - separate project |  |  | Out Of Scope | Not needed | Not needed | As per conversation with Matt,VCM will be out of scope due to the project and total rearchitecting of the application. VCM will undergo overhaul transformation (upgrade [replacing legacy workloads] + migrate [eventually to Azure]) by end of this 2020 in a separate capital budget program of itself, and no need to include this as part of our migration program for now. |  | 2020-08-17
Visionaire Case Processing of Images | Central storage for all patient case files (EMC Isilon) and applications that automate case processing (Segway and Initialize) and the Remote Sites (Aarau, Sydney, Noida). ITLT Cert:26-JUN-17 | R&D | Yes | 5 - Aug 3 | Ian Bennett | Matthew Stephens | Derrick Givens | Alan Kee |  | us | 2020-08-19 |  |  |  | Yes | Yes | 95% | 2020-08-19 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. | Have latency issues with Remote Sites (Aarau, Sydney, Noida). | 2020-09-14 | 2020-09-18 | Sign-Off Received | 44099 |  | Complex
Visual SVN | Apache Subversion service | R&D | Yes | 2 - July 13 | Ian Bennett | Matthew Stephens |  | Ryan Cho |  | us | 2020-07-16 | 2020-08-20 |  |  | Yes | Yes | 0.5 | 2020-08-20 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-04 | 2020-09-08 | Sign-Off Received | 44125 |  | Simple
WebOps | Loaners and Consignments Application Support Manager=Mohamed Dawood Product Support Level=Supported Delivery Manager Cert: 14-JUN-17 | Supply Chain | Yes | 5 - Aug 3 | Massimo Trambaioli | Balvant Kelaiya | Mohamed Dawood | Pierre Palassian |  |  | 2020-08-17 | None | None | None | None | None | None | None | 100% | SaaS |  |  | Out Of Scope | Not needed | Not needed | Massimo confirmed "Webops is Saas". |  | 2020-07-28
Windchill PLM | Product Lifeycle Management | R&D | Yes | 1 - July 6 | Ian Bennett | Matthew Stephens | Matthew Stephens | Alex Jiang |  | us | 2020-07-09 | None | None | None | None | None | None | None | 100% | SNI AWS |  |  | Out Of Scope | Not needed | Not needed | Upated by Ken - Already in AWS |  | 2020-07-13
Winflex | DNC software. 01/20/16 - RTO, GxP - Updated from email request from Yvonne. | Manufacturing | Yes | 5 - Aug 3 | Derek Spillane | Yvonne Braun | Yvonne Braun | Michael Stoerk | Goran Markovic | eu | 2020-08-20 |  |  |  | Yes | Yes | 100% | 2020-08-20 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-04 | 2020-09-04 | Sign-Off Received | 44089 |  | Simple
Winshuttle | Workflow automation solution for master data management in SAP and mass uploads in to SAP. Not supported for transactional data extracts. | ERP | Yes | 5 - Aug 3 | Stuart Robinson | Melissa Hollingsworth | Mahmood Mohammed | Melissa Hollingsworth |  | eu | 2020-08-11 | 2020-08-25 |  |  | Yes | Yes | 1899-12-31 | 2020-08-25 | 100% | SNI Azure |  |  | Rehost (L/S) | Yes - complete | Yes - complete | Assessment work is completed. |  | 2020-09-04 | 2020-09-09 | Sign-Off Received | 44131 |  | Medium
zScaler Private Access (ZPA) | Network Remote Access | Security | Yes | 5 - Aug 3 | Jody Jenkins | Paul Funk | Paul Funk | Jody Jenkins | Paul Funk | us | 2020-08-14 | None | None | None | None | None | None | None | 100% | Retirement | 4440800% |  | Retirement | Not needed | Not needed | • zScaler Private Access (ZPA) – will be replaced by Global Protect VPN |  | 44041
Pending with SDM
[15 empty] | Yes |  |  |  |  | SNI Azure |  |  | Rehost (L/S) | Not needed | [5 empty] | Sign-Off Received
[15 empty] | None |  |  |  |  | SNI AWS |  |  | Replatform | No | [5 empty] | Discussion Required
[15 empty] | Part - not enough |  |  |  |  | DCaaS |  |  | Redeply swing | WIP | [5 empty] | Not Sent
[15 empty] | Part - enough |  |  |  |  | Retirement |  |  | Upgrade and migrate | Yes - complete | [5 empty] | NA
|  |  |  | 1 - July 6 | [15 empty] | Other - comments |  |  | Retirement
|  |  |  | 2 - July 13 | [15 empty] | SaaS |  |  | Out Of Scope
|  |  |  | 3 - July 20 | [15 empty] | Desktop App |  |  | WIP
|  |  |  | 4 - July 27 | [15 empty] | Infrastructure service - out of scope
|  |  |  | 5 - Aug 3 | [15 empty] | AS400 - out of scope
SAP on HP-UX - out of scope
[20 empty] | WIP |  |  |  | put application front end 'off line'
[20 empty] | Complex - separate project |  | blead out LB |  | azure migrate web server
[20 empty] | Pending information from SDM |  | azure migrate web node 1 |  | azure migrate sql server
[20 empty] | No workshop |  | azure migrate sql |  | modift LB
[22 empty] | sync DB |  | test
[22 empty] | reloadbalnce |  | enable app
blead out DC node connection
migrate web node 2
final LB config
LB test
test
/
Note on L1: Holton, Ken:
Note on M1: Holton, Ken: the date of the 1st workshop
Note on N1: Holton, Ken: the date of the follow up 2nd workshop - for not needed enter 'none'
Note on O1: Holton, Ken: data of the follow up 3rd workshop - if not needed enter 'none'
Note on P1: Holton, Ken: pull down answers:
Note on Q1: Holton, Ken: the date the questonare is completed enough to have the workshop - the save date from the SDM NOT the date reviewed by HCL
Note on R1: Holton, Ken: the percent of questions answered in the pre meeting questomare
Note on S1: Holton, Ken: the date HCL has completed their prep for the meeting to include full review of the questomare
Note on T1: Holton, Ken: how close to complete - including the deliverables for the respective application

## Tracker
Count of Name
Row Labels | Deepak | Nihal | Razak | Saurabh | Vidit | (blank) | Raju | Grand Total | Row Labels | Sum of Peer Review Completed | Sum of Peer Review Pending
Completed | 16 | 21 | 37 | 32 | 11 |  | 8 | 125 | Nihal | 40 | 0
Out of Scope |  | 1 | 1 |  |  | 84 | 4 | 90 | Razak | 20 | 0
Grand Total | 16 | 22 | 38 | 32 | 11 | 84 | 12 | 215 | Saurabh | 72 | 0
[9 empty] | (blank) | 0 | 0
[9 empty] | Vidit | 1 | 0
[9 empty] | Grand Total | 133 | 0
[9 empty] | Row Labels | Count of SDM signed off email sent date | Count of SDM Signoff received
[9 empty] | Deepak | 16 | 16
Automic | [8 empty] | Nihal | 21 | 21
Calibration Manager(OSIRIS) | [8 empty] | Raju | 8 | 8
ERP LN | [8 empty] | Razak | 37 | 37
[9 empty] | Saurabh | 32 | 32
Axapta | [8 empty] | Vidit | 11 | 11
Jobrouter | [8 empty] | (blank)
[9 empty] | Grand Total | 125 | 125