## App Details
S.No | Applications | Environment | SDM | ITLT | Flexible schedule | Cutover ID | Cutover Scheduled Date | Original planned date | Out of scope | Out of scope - comment | Migration preparation RAG status | Migration Preparation RAG Status Comments | HCL Migration App SME | HCL Migration Infra SME | On Prem App Server/s | On Prem DB Server/s | Target DB Servers for SQL 2019 consolidation | Migration Strategy | Domain | Speciality | Region | Original Wave | App Strategic Grouping | Application Grouping Theme | Original Month | Original MoveGroup | SOX | GxP | Migration Effort | Criticality | SDM Opinion | User Base | OS Platform | Apps Developer | Database | Environments | Apps Servers Counts | Co-Host | Integrations/Dependencies | Risk | SDM Feedback for the Move Group | Migration Scheduled | MS-Planned Date | MS-Actual Date | Cutover Planning Complete | CPC-Planned Date | CPC-Actual Date | Business Owner Approval Complete | BOAC-Planned Date | BOAC-Actual Date | UAT, Data, Performance testers nominated | UDPTN planned date | UDPTN actual date | UAT, Data, Performance Test Plan Ready | UDPPR-Planned Date | UDPPR-Actual Date | UAT, Data, Performance tests ready in DevOps and approved | UDPPRD-Planned Date | UDPPRD-Actual Date | CR Submitted | CS-Planned Date | CS--Actual Date | CR Approved | CA--Planned Date | CA--Actual Date | Precutover Implementation Complete | PIC-Planned Date | PIC-Actual Date | SNI On Prem Testing Completed | SNI OPTC-Planned Date | SNI OPTC-Actual Date | Cutover Completed | CC-Planned Date | CC-Actual Date | HCL Azure Testing Completed | HATC-Planned Date | HATC-Actual Date | SNI Azure Testing Completed | SATC-Planned Date | SATC-Actual Date | Backup | Windows Firewall | Encryption | Log Management | Anti-Virus | PAM | WAF | Patching | AD Accounts migrated | DR test | Application Summary Document completed | ASDC-Planned Date | ASDC-Actual Date | CMDB Update Completed | CUC-Planned Date | CUC-Actual Date | On Prem Decom Completed | OPDC-Planned Date | OPDC-Actual Date | Hypercare signed off | HS Planned Date | HS Actual Date | Migration Signed Off | MSO-Planned Date | MSO-Actual Date
131 | Abacus | PROD | Paul Davison | Chris Cook |  | PW-MG1 | 2020-11-06 | 2020-11-06 | No |  | Finished (blue) |  |  |  | CHAARSMAPPW11 |  |  | RE-PLATFORM | Group Functions | Group Functions | EMEA | Pilot | Pilot | 00 - Pilot | Nov | MG2 | No | No | Moderate | Medium | Moderate migration | Switzerland, Aarau | Windows 2012 R2 Standard | COTS | DB: Actian PSQL v12 | Prod | 1 | None | 4. Connectivity to Hydra and Workday, their shared folder locations, where the files are being shared/placed, to be validated during migration. | There is a global payroll project planned for 2021 which will migrate all to payroll applications to one solution., Port 40000 used by client to access application on server |  | Done | 2020-10-05 | 2021-01-15 | Yes | 2020-10-20 | 2020-10-20 | Yes | 2020-09-17 | 2020-09-17 | Yes | 2020-09-17 | 2020-09-17 | Yes | 2020-09-24 | 2020-09-24 | Yes | 2020-09-28 | 2020-09-28 | Yes | 2020-09-21 | 2020-09-21 | Yes | 2020-09-24 | 2020-09-24 | Yes | 2020-10-04 | 2020-10-04 | Yes | 2020-10-04 | 2020-10-04 | Yes | 2020-10-05 | 2021-01-15 | Yes | 2020-10-07 | 2020-10-07 | Yes | 2020-10-07 | 2020-10-07 | Done, no evidence provided | N/A | N/A | Done, no evidence provided | Done, no evidence provided | N/A | N/A | N/A | N/A | N/A | Yes | 2020-11-02 | 2021-01-02 | Yes | 2020-11-02 | 2021-02-08 | No | 2020-11-02 |  | No | 2020-11-02 |  | Yes | 2020-11-02 | 2021-01-15
58 | Agile PLM | DEV | Requalann Pereira | Sri Tupil |  | W6-MG1 | 2021-06-04 | 2021-04-30 | No |  | Not started (grey) |  |  |  | USASHSMAPDVW02; USASHSMAPDVW03; USASHSMAPDVW06; | USASHSMDBDVW06 |  | RE-HOST | R&D | R&D, PLM system for ex-Arthrocare products | US | 4 | 11 | 11 - US Medium/Complex Application | Apr | MG1 | No | Yes | Complex Migration | High | - Investing within 2 years 2 times, now move to SNI Azure & another for Platform change in year 2022 (to PTC Wind Chill), will bring cost overhead to SNI. - Application has high numbr of VM, with F5 LB in place, DR and BCP all needs to be planned, which may make this 4-6 months exercise for 1 move and another Platfrom Change will be again migration effort for 4-6 months. | Costa Rica, Memphis, Mansfield and Austin | Windows Server 2012 R2 | COTS | Oracle 12c | PROD, DEV, QA, BCP | 15 | None | SAP P01 | Platform change in year 2022 (to PTC Wind Chill), No Oracle Vendor Support,BCP Repository has been set up on the server \\T167dmxl6220y28 |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
58 | Agile PLM | QA | Requalann Pereira | Sri Tupil |  | W6-MG1 | 2021-06-04 | 2021-04-30 | No |  | Not started (grey) |  |  |  | USASHSMAPQVW03; USASHSMAPQVW04; USASHSMAPQVW06; USASHSMAPQVW07; | USASHSMDBQVW02 |  | RE-HOST | R&D | R&D, PLM system for ex-Arthrocare products | US | 4 | 11 | 11 - US Medium/Complex Application | Apr | MG1 | No | Yes | Complex Migration | High | - Investing within 2 years 2 times, now move to SNI Azure & another for Platform change in year 2022 (to PTC Wind Chill), will bring cost overhead to SNI. - Application has high numbr of VM, with F5 LB in place, DR and BCP all needs to be planned, which may make this 4-6 months exercise for 1 move and another Platfrom Change will be again migration effort for 4-6 months. | Costa Rica, Memphis, Mansfield and Austin | Windows Server 2012 R2 | COTS | Oracle 12c | PROD, DEV, QA, BCP | 15 | None | SAP P01 | Platform change in year 2022 (to PTC Wind Chill), No Oracle Vendor Support,BCP Repository has been set up on the server \\T167dmxl6220y28 |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
58 | Agile PLM | PROD | Requalann Pereira | Sri Tupil |  | W7-MG1 | 2021-07-09 | 2021-04-30 | No |  | Not started (grey) |  |  |  | USMEMSMAPPVW22; USASHSMAPPVW14; USASHSMAPPVW15; USASHSMAPPVW16; USASHSMAPPVW17; | USASHSMDBPVW07 |  | RE-HOST | R&D | R&D, PLM system for ex-Arthrocare products | US | 4 | 11 | 11 - US Medium/Complex Application | Apr | MG1 | No | Yes | Complex Migration | High | - Investing within 2 years 2 times, now move to SNI Azure & another for Platform change in year 2022 (to PTC Wind Chill), will bring cost overhead to SNI. - Application has high numbr of VM, with F5 LB in place, DR and BCP all needs to be planned, which may make this 4-6 months exercise for 1 move and another Platfrom Change will be again migration effort for 4-6 months. | Costa Rica, Memphis, Mansfield and Austin | Windows Server 2012 R2 | COTS | Oracle 12c | PROD, DEV, QA, BCP | 15 | None | SAP P01 | Platform change in year 2022 (to PTC Wind Chill), No Oracle Vendor Support,BCP Repository has been set up on the server \\T167dmxl6220y28 |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
59 | Alteryx | DEV | Sathiamurthy Samidurai | Stuart Robinson |  | W4-MG1 | 2021-04-09 | 2021-04-30 | No |  | On track (green) | waiting for Chaitanya's response | Isha/Venkat/Sirisha | Rahul/Saurabh | USMEMSMAPDVW21 | USMEMSMAPDVW21 |  | RE-HOST | Data & Analytics | Data & Analytics | US | 4 | 11 | 11 - US Medium/Complex Application | Apr | MG1 | No | Yes | Moderate Migration | Medium | Upgrade Required | USA | Window Server 2016 Standard | COTS | SQL Server 2017 | Dev, Prod | 3 | Tableau Bridge | Shared Server with Tableau Bridge. Has integration with (IDQ, Logility) to pull data | For business support, there is high possibility to increase new on-premise connections, SME need to share upcoming plan in this context | SDM to decide on overall Roadmap and planning | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
59 | Alteryx | PROD | Sathiamurthy Samidurai | Stuart Robinson |  | W4-MG2 | 2021-04-23 | 2021-04-30 | No |  | On track (green) | waiting for Chaitanya's response | Isha/Venkat/Sirisha | Rahul/Saurabh | USMEMSMAPPVW34 | USMEMSMAPPVW35 |  | RE-HOST | Data & Analytics | Data & Analytics | US | 4 | 11 | 11 - US Medium/Complex Application | Apr | MG1 | No | Yes | Moderate Migration | Medium | Upgrade Required | USA | Window Server 2016 Standard | COTS | SQL Server 2017 | Dev, Prod | 3 | Tableau Bridge | Shared Server with Tableau Bridge. Has integration with (IDQ, Logility) to pull data | For business support, there is high possibility to increase new on-premise connections, SME need to share upcoming plan in this context | SDM to decide on overall Roadmap and planning | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
12 | Altium Designer | PROD | Requalann Pereira | Sri Tupil |  | W6-MG1 | 2021-06-04 | 2021-01-30 | No |  | Not started (grey) |  |  |  | BBTAPP01 |  |  | RE-HOST | R&D | R&D | US | 1 | 1 | 01 - Network License Server - Batch 1 | Jan | MG1 | No | No | Simple Migration | Low | Moderate Migration | USA | Window 2012 R2 Server | COTS | NA | Prod | 1 |  | License Server | Dependency - License Server, Associated workload migration |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  | 2021-01-21 | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
95 | ANZPowerBI | PREPROD | Jerry Li | Firas Almahamid |  | W6-MG1 | 2021-06-04 | 2021-06-30 | No |  | Not started (grey) |  |  |  | SGDCSMDBPVW05; | SGDCSMDBPVW05 |  | RE-HOST | Data & Analytics | Data & Analytics | APAC | 6 | 19 | 19 - APAC Complex Group | Jun | MG2 | No | No | Moderate Migration | Medium | Moderate Migration | USA | Window Server 2012 R2 Standard | SNI developed | SQL Server 2016 | Pre-Prod, Prod | 2 | None | Has dependency on hybrid model and third-party (ActiveX & JRM) | Server Sharing:Clean-up Microsoft dynamic CRM dependency |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
95 | ANZPowerBI | PROD | Jerry Li | Firas Almahamid |  | W6-MG2 | 2021-06-18 | 2021-06-30 | No |  | Not started (grey) |  |  |  | SGDCSMDBPVW04 | SGDCSMDBPVW04 |  | RE-HOST | Data & Analytics | Data & Analytics | APAC | 6 | 19 | 19 - APAC Complex Group | Jun | MG2 | No | No | Moderate Migration | Medium | Moderate Migration | USA | Window Server 2012 R2 Standard | SNI developed | SQL Server 2016 | Pre-Prod, Prod | 2 | None | Has dependency on hybrid model and third-party (ActiveX & JRM) | Server Sharing:Clean-up Microsoft dynamic CRM dependency |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
81 | ASSIST4 | PROD | Yvonne Braun | Massimo Trambaioli | X | W5-MG1 | 2021-05-07 | 2021-04-23 | No |  | Not started (grey) | Propose to move to April 23rd |  |  | DETUTSMAPPW02 | DETUTSMAPPW02 | EUAZRSMDBPVW01, EUAZRSMDBPVW02 | RE-HOST(App)/RE-PLATFORM(DB) | Supply Chain | Supply Chain | EMEA | 5 | 15 | 15 - EMEA Medium Application REHOST Only Group | May | MG2 | No | No | Simple | Low | Based on vendor's response, it is possible to run the application in the vendor's datacenter, but not in a public cloud. If it is decided to move to the cloud, we will loose any vendor support. | Tuttlingen, Germany | Windows Server 2012 R2 | COTS | Sql Server 2012 | Prod | 1 | ID Prove Werma-Win Tarife | None | IP Address changes |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
8 | AutoCAD | PROD | Requalann Pereira | Sri Tupil |  | W4-MG1 | 2021-04-09 | 2021-01-30 | No |  | Risk of delay (amber) | New server details to be assessed | Shweta | Srikanth | MEMSRV236; CNBDACADS01; |  |  | RE-PLATFORM | R&D | R&D, Facilities Drawings, manufacturing shop floor layouts; | US | 1 | 2 | 02 - Network License Server - Batch 2 | Jan | MG1 | No | Yes | Moderate Migration | Medium | Plans: AutoCAD to be integrated with PLM products | SNI Internal Globally | Windows server 2003/2008/2012 | COTS | NA | PROD | 4 | Adams (Out of Scope), Flex LM, Geomagic, LIFEMOD BIOMECHAICS SYS (Out of Scope), PartMaker, Solidworks & Unigraphics | Co-Hosted application License manager for Flex LM, Geomagic, PartMaker, Solidworks & Unigraphics. | Replatform, Shared Server with Flex LM, Geomagic,PartMaker, Solidworks,Unigraphics |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  | 2021-01-21 | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
50 | AWD Tracker | PROD | Andres Bernard | Firas Almahamid |  | W3-MG2 | 2021-03-19 | 2021-03-30 | No |  | On track (green) |  | Raju | Rahul/Saurabh | CHAARSMAPPW02 | CHAARSMDBPW01 | EUAZRSMDBPVW01, EUAZRSMDBPVW02 | RE-HOST(App)/RE-PLATFORM(DB) | Commercial | Commercial | EMEA | 3 | 8 | 08 - Full Throttle EMEA Application - Batch 1 | Mar | MG2 | No | No | Medium | High | Moderate migration | Germany | Window Server 2008 R2 | SNI developed | Sql Server 2008 R2 | Prod | 1 | None | None | Required support needed from Thorsten and Third Party Contractor during Azure Migration Database Performance to be validate during migration. Indexing to be validate Downtime needs to be aligned with Business. The application has High Impact on Business. There is a plan to migrate this application to a new solution. But no tentative date yet. |  | Yes | 2020-01-25 | 2021-01-28 | No | 2020-02-08 |  | No |  |  | No |  |  | No |  |  | No |  |  | No | 2021-02-24 |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
78 | AWM Data Warehouse | PROD | Sathiamurthy Samidurai | Stuart Robinson |  | W3-MG2 | 2021-03-19 | 2021-03-05 | No |  | On track (green) |  | Deepak | Rahul/Saurabh | NA | UKRTH-SMDBPVW32 |  | RE-HOST | Data & Analytics | Data & Analytics | US | 1 | 3 | 03 - SNI Developed + Co-Hosted Apps | Mar | MG2 | No | No | Complex Migration | High | Complex Migration | USA | Windows Server 2012 R2 Standard | SNI developed | SQL Server 2012 | Dev, Prod | 4 | GSC DataWare House Admin Tool | Application Dependency BOBJ Server Dependency - Database Server sharing Applications GBIS Data Staging Process ISIS Data Staging Process Ortho Data Warehouse Application Server sharing Applications GSC Data Warehouse Admin Tool | Informatica Platform Dependency This is an Informatica application not compatible with Azure rather can be hosted on AWS as per recommendation from the software vendor | AWM and Informatica need to move together in Jan or Feb | Yes | 2020-01-25 | 2021-01-28 | No | 2020-02-08 |  | No |  |  | No |  |  | No |  |  | No |  |  | No | 2021-02-10 |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
78 | AWM Data Warehouse | DEV | Sathiamurthy Samidurai | Stuart Robinson |  | W1-MG2 | 2021-01-22 | 2021-01-22 | No |  | Finished (blue) |  | Deepak | Rahul/Saurabh | UKHUL-SMAPPVW20 | USMAN-SMAPPVW54 |  | RE-HOST | Data & Analytics | Data & Analytics | US | 1 | 3 | 03 - SNI Developed + Co-Hosted Apps | Jan | MG2 | No | No | Complex Migration | High | Complex Migration | USA | Windows Server 2012 R2 Standard | SNI developed | SQL Server 2012 | Dev, Prod | 4 | GSC DataWare House Admin Tool | Application Dependency BOBJ Server Dependency - Database Server sharing Applications GBIS Data Staging Process ISIS Data Staging Process Ortho Data Warehouse Application Server sharing Applications GSC Data Warehouse Admin Tool | Informatica Platform Dependency This is an Informatica application not compatible with Azure rather can be hosted on AWS as per recommendation from the software vendor | AWM and Informatica need to move together in Jan or Feb | Done | 2020-12-11 | 2021-01-22 | Yes | 2020-12-30 | 2021-01-22 | No | 2021-01-13 | 2021-01-13 | Yes | 2021-01-04 | 2021-01-04 | Yes | 2021-01-11 | 2021-01-11 | Yes | 2021-01-15 | 2021-01-15 | Yes | 2021-01-08 | 2021-01-08 | Yes | 2021-01-13 | 2021-01-13 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-22 | 2021-01-22 | Yes | 2021-01-24 | 2021-01-24 | Yes | 2021-01-24 | 2021-01-24 | Done, no evidence provided | N/A | N/A | Done, no evidence provided | Done, no evidence provided | N/A | N/A | N/A | N/A | N/A | No | 2021-02-19 |  | Yes | 2021-02-19 | 2021-02-08 | No | 2021-02-19 |  | No | 2021-02-19 |  | No | 2021-02-19
103 | Axapta 2009 (Dubai) | QA | Swapnil Kelaiya | Massimo Trambaioli |  |  | 2021-06-30 | 2021-06-30 | Yes | Out of scope - confirmed by Ken | Out of scope (dark grey) |  | Shweta | Rahul/Saurabh | DUFS16 |  |  | RE-HOST | ERP | ERP | APAC | 6 | 20 | 20 - APAC Complex Group | Jun | MG2 | No | No | Complex Migration | High | Complex Migration | Dubai | Windows server 2008 | COTS | Sql Server 2008 R2 | Prod, Test | 3 | None | None | IP Address |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
103 | Axapta 2009 (Dubai) | PROD | Swapnil Kelaiya | Massimo Trambaioli |  |  | 2021-06-30 | 2021-06-30 | Yes | Out of scope - confirmed by Ken | Out of scope (dark grey) |  | Vidit | Srikanth/Rajesh | DUFS17; DUFS18; |  |  | RE-HOST | ERP | ERP | APAC | 6 | 20 | 20 - APAC Complex Group | Jun | MG2 | No | No | Complex Migration | High | Complex Migration | Dubai | Windows server 2008 | COTS | Sql Server 2008 R2 | Prod, Test | 3 | None | None | IP Address |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
104 | Axapta 2009 (India) | QA | Swapnil Kelaiya | Massimo Trambaioli |  |  | 2021-06-30 | 2021-06-30 | Yes | Out of scope - confirmed by Ken | Out of scope (dark grey) |  | Vidit | Srikanth/Rajesh | MUS03; MUS10 |  |  | RE-HOST | ERP | ERP | APAC | 6 | 20 | 20 - APAC Complex Group | Jun | MG2 | No | No | Complex Migration | High | Complex Migration | India | Windows server 2009 | COTS | Sql Server 2008 R3 | Prod, Test | 4 | None | None | IP Address |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
104 | Axapta 2009 (India) | PROD | Swapnil Kelaiya | Massimo Trambaioli |  |  | 2021-06-30 | 2021-06-30 | Yes | Out of scope - confirmed by Ken | Out of scope (dark grey) |  | Venkat/Isha/Shirisha | Praveen | MUS02; MUS04; MUS05; MUS07 |  |  | RE-HOST | ERP | ERP | APAC | 6 | 20 | 20 - APAC Complex Group | Jun | MG2 | No | No | Complex Migration | High | Complex Migration | India | Windows server 2009 | COTS | Sql Server 2008 R3 | Prod, Test | 4 | None | None | IP Address |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
104 | Axapta 2009 (India) | DR | Swapnil Kelaiya | Massimo Trambaioli |  |  | 2021-06-30 | 2021-06-30 | Yes | Out of scope - confirmed by Ken | Out of scope (dark grey) |  | Venkat/Isha/Shirisha | Praveen | MUSDR |  |  | RE-HOST | ERP | ERP | APAC | 6 | 20 | 20 - APAC Complex Group | Jun | MG2 | No | No | Complex Migration | High | Complex Migration | India | Windows server 2009 | COTS | Sql Server 2008 R3 | Prod, Test | 4 | None | None | IP Address |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
120 | Axapta 2009 (Malaysia & Thailand) | PROD | Mulyanto Ng | Massimo Trambaioli |  |  | 2021-07-30 | 2021-07-30 | Yes | Out of scope - confirmed by Ken | Out of scope (dark grey) |  | Venkat/Isha/Shirisha | Praveen | CNSHAAXASEAN01; CNSHAASEANRDP01 | CNSHAAXASEAN02 |  | RE-HOST | ERP | ERP | APAC | 7 | 22 | 22 - Final EMEA/APAC application | Jul | MG2 | No | No | Complex Migration | High | Complex Migration | Malaysia | Windows server 2010 | COTS | Sql Server 2008 R4 | Prod, Test | 4 | None | None | IP Address |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
120 | Axapta 2009 (Malaysia & Thailand) | DR | Mulyanto Ng | Massimo Trambaioli |  |  | 2021-07-30 | 2021-07-30 | Yes | Out of scope - confirmed by Ken | Out of scope (dark grey) |  | Venkat/Isha/Shirisha | Praveen | CNSHAAXQA-APP02; CNSHAAXDEV02 | CNSHAAXQA-DB02 |  | RE-HOST | ERP | ERP | APAC | 7 | 22 | 22 - Final EMEA/APAC application | Jul | MG2 | No | No | Complex Migration | High | Complex Migration | Malaysia | Windows server 2010 | COTS | Sql Server 2008 R4 | Prod, Test | 4 | None | None | IP Address |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
121 | Axapta 2009 (Singapore) | QA | Mulyanto Ng | Massimo Trambaioli |  |  | 2021-07-30 | 2021-07-30 | Yes | Out of scope - confirmed by Ken | Out of scope (dark grey) |  | Venkat/Isha/Shirisha | Praveen | SGDCSMAPPVW03 | SGDCSMDBPVW02 |  | RE-HOST | ERP | ERP | APAC | 7 | 22 | 22 - Final EMEA/APAC application | Jul | MG2 | No | No | Complex Migration | High | Complex Migration | Singapore | Windows server 2011 | COTS | Sql Server 2008 R5 | Prod, Test | 4 | None | None | IP Address |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
121 | Axapta 2009 (Singapore) | PROD | Mulyanto Ng | Massimo Trambaioli |  |  | 2021-07-30 | 2021-07-30 | Yes | Out of scope - confirmed by Ken | Out of scope (dark grey) |  | Venkat/Isha/Shirisha | Praveen | SGDCSMTSPW01; SGDCSMAPPVW04; SGDCSMAPPVW05; SGDCSMAPPVW06 | SGDCSMDBPVW03 |  | RE-HOST | ERP | ERP | APAC | 7 | 22 | 22 - Final EMEA/APAC application | Jul | MG2 | No | No | Complex Migration | High | Complex Migration | Singapore | Windows server 2011 | COTS | Sql Server 2008 R5 | Prod, Test | 4 | None | None | IP Address |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
114 | Axway | QA | Pawel Pietrzyk | Massimo Trambaioli |  | W7-MG1 | 2021-07-09 | 2021-07-30 | No |  | Not started (grey) |  |  |  | MEMSRV254Q |  |  | RE-HOST | ERP | ERP | US | 7 | 23 | 23 - High Critical Application | Jul | MG1 | No | No | Complex Migration | High | Complex Migration | USA | Windows Server 2012 R2 | COTS | NA | Prod , QA | 2 | Central FTP | Many firewall/IP dependencies both internally and external third parties that connect to S&N | 1) Has significant firewall rules that can impact functionality if changes are made 2) IIS is running on the same server which is a FTP server accessed by some Asia business units. | Axway is not with Amit. Need to check the email from him. | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
114 | Axway | PROD | Pawel Pietrzyk | Massimo Trambaioli |  | W7-MG2 | 2021-07-23 | 2021-07-30 | No |  | Not started (grey) |  |  |  | MEMSRV254 |  |  | RE-HOST | ERP | ERP | US | 7 | 23 | 23 - High Critical Application | Jul | MG1 | No | No | Complex Migration | High | Complex Migration | USA | Windows Server 2012 R2 | COTS | NA | Prod , QA | 2 | Central FTP | Many firewall/IP dependencies both internally and external third parties that connect to S&N | 1) Has significant firewall rules that can impact functionality if changes are made 2) IIS is running on the same server which is a FTP server accessed by some Asia business units. | Axway is not with Amit. Need to check the email from him. | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
71 | Bartender | PROD | Amit Shokeen |  | X | W5-MG2 | 2021-05-21 | 2021-05-30 | No |  | Not started (grey) |  |  |  | USMAN-SMPRPVW03 |  |  | RE-HOST | ET | Manufacturing - Inventory | US | 5 | 14 | 14 - Shop Floor Medium/Complex Application | May | MG1 | No | No | Moderate Migration | Medium | Moderate Migration | US-MD/Columbia | Windows 2012 | COTS | NA | 1 for Prod | 1 | NA | Print Server | Printer Configuration, Third Party Drivers. | Revalidate the dependency as the application was moved to a different server. Check if this can be re-platformed. | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
96 | BI (CHINA) | DEV | Jinble Li | Firas Almahamid |  | W6-MG1 | 2021-06-04 | 2021-06-30 | No |  | Not started (grey) |  |  |  | CNSHABIDEV01 | CNSHABIDEV02 | China servers TBD | RE-HOST(App)/RE-PLATFORM(DB) | Data & Analytics | Data & Analytics | APAC | 6 | 19 | 19 - APAC Complex Group | Jun | MG2 | No | No | Complex Migration | Medium | Integration with WeChat Enterprise, SFDC | APAC | Windows 2012 R2 Standard,Windows 2008 R2 Enterprise | COTS | Microsoft SQL Server 2012 | Prod,QA,Dev,Test | 7 | None | WeChat, SFDC | Commercial team's monthly closing time is critical for this application. During this period, they need these reports. Migration of this application should be avoided on Frist and last week of any given month. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
96 | BI (CHINA) | TEST | Jinble Li | Firas Almahamid |  | W6-MG1 | 2021-06-04 | 2021-06-30 | No |  | Not started (grey) |  |  |  | CNSHAETLQADB01 | CNSHABIQADB01 | China servers TBD | RE-HOST(App)/RE-PLATFORM(DB) | Data & Analytics | Data & Analytics | APAC | 6 | 19 | 19 - APAC Complex Group | Jun | MG2 | No | No | Complex Migration | Medium | Integration with WeChat Enterprise, SFDC | APAC | Windows 2012 R2 Standard,Windows 2008 R2 Enterprise | COTS | Microsoft SQL Server 2012 | Prod,QA,Dev,Test | 7 | None | WeChat, SFDC | Commercial team's monthly closing time is critical for this application. During this period, they need these reports. Migration of this application should be avoided on Frist and last week of any given month. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
96 | BI (CHINA) | QA | Jinble Li | Firas Almahamid |  | W6-MG1 | 2021-06-04 | 2021-06-30 | No |  | Not started (grey) |  |  |  | CNSHAQVS01 | CNSHAQVS01 | China servers TBD | RE-HOST(App)/RE-PLATFORM(DB) | Data & Analytics | Data & Analytics | APAC | 6 | 19 | 19 - APAC Complex Group | Jun | MG2 | No | No | Complex Migration | Medium | Integration with WeChat Enterprise, SFDC | APAC | Windows 2012 R2 Standard,Windows 2008 R2 Enterprise | COTS | Microsoft SQL Server 2012 | Prod,QA,Dev,Test | 7 | None | WeChat, SFDC | Commercial team's monthly closing time is critical for this application. During this period, they need these reports. Migration of this application should be avoided on Frist and last week of any given month. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
96 | BI (CHINA) | PROD | Jinble Li | Firas Almahamid |  | W6-MG2 | 2021-06-18 | 2021-06-30 | No |  | Not started (grey) |  |  |  |  | CNSHABIDB01; CNSHAETLDB01 | China servers TBD | RE-HOST(App)/RE-PLATFORM(DB) | Data & Analytics | Data & Analytics | APAC | 6 | 19 | 19 - APAC Complex Group | Jun | MG2 | No | No | Complex Migration | Medium | Integration with WeChat Enterprise, SFDC | APAC | Windows 2012 R2 Standard,Windows 2008 R2 Enterprise | COTS | Microsoft SQL Server 2012 | Prod,QA,Dev,Test | 7 | None | WeChat, SFDC | Commercial team's monthly closing time is critical for this application. During this period, they need these reports. Migration of this application should be avoided on Frist and last week of any given month. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
22 | Bugzilla | PROD | Requalann Pereira | Sri Tupil |  | W7-MG1 | 2021-07-09 | 2021-02-28 | No |  | Not started (grey) |  |  |  | DYNOMITE |  |  | RE-HOST | R&D | R&D,Defect/bug Tracking for Navio Product Development team | US | 2 | 5 | 05 - Simple/Medium Apps | Feb | MG1 | No | Yes | Moderate Migration | Medium | Moderate Migration | USA,SNI Internal | Linux10.0.4 | COTS | NA | Prod | 1 | CVS Concurrent Version System | Both Bugzilla and CVS are cohosted on the same server | Nothing Found |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
46 | Business Objects (IRAMEA) | PROD | Mark Elliott | Stuart Robinson |  | W4-MG2 | 2021-04-23 | 2021-04-30 | No |  | Imminent Delay (red) | Potential Latency issue. Mark Elliot is proposing a different solution, Mat Pie to confirm | Isha/Venkat/Sirisha | Rahul/Saurabh | ZAEMBO | ZASNFS2; ZAORCLEM |  | RE-HOST | Data & Analytics | Sales Figures -BI reporting and analytical tool | EMEA | 4 | 10 | 10 - Full Throttle EMEA Application - Batch 1 | Apr | MG2 | No | No | Medium | Medium | Medium Migration | SNI Internal | Windows Server 2008 R2 Standard | COTS | SQL Server 2008 R2 | Prod | 3 | dataStor | Server ‘ZASNFS2’ also co-host dataSTOR application. | Reporting (Sql) and DB (Oracle) server are shared across other applications in SNI |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
110 | Central FTP | QA | Pawel Pietrzyk | Massimo Trambaioli |  | W7-MG1 | 2021-07-09 | 2021-07-30 | No |  | Not started (grey) |  |  |  | MEMSRV042T |  |  | RE-HOST | ERP | ERP - File Transfer | US | 7 | 23 | 23 - High Critical Application | Jul | MG1 | No | No | Complex Migration | High | Complex Migration | SNI Internal Globally | Windows 2016 Standard | COTS | NA | PROD, QA | 2 | Axway | External Partner, Service Now, many SNI internal application, Share Folders. | Firewall changes can directly impact and stop jobs from working, IP Changes, Testing are Manual and requires internal and external partner participation. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
110 | Central FTP | PROD | Pawel Pietrzyk | Massimo Trambaioli |  | W7-MG2 | 2021-07-23 | 2021-07-30 | No |  | Not started (grey) |  |  |  | MEMSRV042 |  |  | RE-HOST | ERP | ERP - File Transfer | US | 7 | 23 | 23 - High Critical Application | Jul | MG1 | No | No | Complex Migration | High | Complex Migration | SNI Internal Globally | Windows 2016 Standard | COTS | NA | PROD, QA | 2 | Axway | External Partner, Service Now, many SNI internal application, Share Folders. | Firewall changes can directly impact and stop jobs from working, IP Changes, Testing are Manual and requires internal and external partner participation. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
97 | China commercial Eflow | QA | Oswin Liao |  | X | W6-MG1 | 2021-06-04 | 2021-06-30 | No |  | Not started (grey) |  |  |  | CNSHABPMQADB01 | CNSHABPMQADB01 | China servers TBD | RE-HOST(App)/RE-PLATFORM(DB) | Data & Analytics | Data & Analytics | APAC | 6 | 19 | 19 - APAC Complex Group | Jun | MG2 | No | No | Complex Migration | High | DMZ server, SDM expecting HA & LB to be implemented on new cloud environment, Latency Sensitive, External facing Server Utilization goes over 90%, Lots of DB jobs. | APAC | Windows 2012 R2 Standard Windows 2008 R2 Enterprise | COTS | MS SQL Server 2012 | Prod,QA,DR | 6 | Both E-Flow & RAMS(China) applications will be covered in one application migration. | Data warehouse (Hospital data, Distributor TSA, Report), POWeR AX2012(MMDM,VMDM), Salesforce(DRM,DMDM), Biz talk(DMDM), WeChat, SFDC. | Risk 1 - DMZ server Mitigation 1 - Public facing url to be tested when move of DMZ server is made. Risk 2 - Hardcoded IP in source code Mitigation 2 - Some web page is using the hardcoded IP address in the application. SDM/SME need confirm with the vendor before migration to either change it and test in lower Env., before the same is replicated to PROD Risk 3 - SDM project team expecting HA & LB to be implemented on new cloud environment. Mitigation 3 - SDM needs to talk to their VP/Ken/Chris to initiate the talk, and work on the plan & cost of the same. Note: To be cognizant that these may not be part of this migration budget. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
97 | China commercial Eflow | PROD | Oswin Liao |  | X | W6-MG2 | 2021-06-18 | 2021-06-30 | No |  | Not started (grey) |  |  |  | CNSHABPM02; CNSHABPMQA01; CNSHABPM01 | CNSHABPMDB01 | China servers TBD | RE-HOST(App)/RE-PLATFORM(DB) | Data & Analytics | Data & Analytics | APAC | 6 | 19 | 19 - APAC Complex Group | Jun | MG2 | No | No | Complex Migration | High | DMZ server, SDM expecting HA & LB to be implemented on new cloud environment, Latency Sensitive, External facing Server Utilization goes over 90%, Lots of DB jobs. | APAC | Windows 2012 R2 Standard Windows 2008 R2 Enterprise | COTS | MS SQL Server 2012 | Prod,QA,DR | 6 | Both E-Flow & RAMS(China) applications will be covered in one application migration. | Data warehouse (Hospital data, Distributor TSA, Report), POWeR AX2012(MMDM,VMDM), Salesforce(DRM,DMDM), Biz talk(DMDM), WeChat, SFDC. | Risk 1 - DMZ server Mitigation 1 - Public facing url to be tested when move of DMZ server is made. Risk 2 - Hardcoded IP in source code Mitigation 2 - Some web page is using the hardcoded IP address in the application. SDM/SME need confirm with the vendor before migration to either change it and test in lower Env., before the same is replicated to PROD Risk 3 - SDM project team expecting HA & LB to be implemented on new cloud environment. Mitigation 3 - SDM needs to talk to their VP/Ken/Chris to initiate the talk, and work on the plan & cost of the same. Note: To be cognizant that these may not be part of this migration budget. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
97 | China commercial Eflow | DR | Oswin Liao |  | X | W6-MG2 | 2021-06-18 | 2021-06-30 | No |  | Not started (grey) |  |  |  | CNSHADRDB03 | CNSHADRDB04 | China servers TBD | RE-HOST(App)/RE-PLATFORM(DB) | Data & Analytics | Data & Analytics | APAC | 6 | 19 | 19 - APAC Complex Group | Jun | MG2 | No | No | Complex Migration | High | DMZ server, SDM expecting HA & LB to be implemented on new cloud environment, Latency Sensitive, External facing Server Utilization goes over 90%, Lots of DB jobs. | APAC | Windows 2012 R2 Standard Windows 2008 R2 Enterprise | COTS | MS SQL Server 2012 | Prod,QA,DR | 6 | Both E-Flow & RAMS(China) applications will be covered in one application migration. | Data warehouse (Hospital data, Distributor TSA, Report), POWeR AX2012(MMDM,VMDM), Salesforce(DRM,DMDM), Biz talk(DMDM), WeChat, SFDC. | Risk 1 - DMZ server Mitigation 1 - Public facing url to be tested when move of DMZ server is made. Risk 2 - Hardcoded IP in source code Mitigation 2 - Some web page is using the hardcoded IP address in the application. SDM/SME need confirm with the vendor before migration to either change it and test in lower Env., before the same is replicated to PROD Risk 3 - SDM project team expecting HA & LB to be implemented on new cloud environment. Mitigation 3 - SDM needs to talk to their VP/Ken/Chris to initiate the talk, and work on the plan & cost of the same. Note: To be cognizant that these may not be part of this migration budget. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
102 | Cimco china | DEV | Carla Morris |  |  | W6-MG1 | 2021-06-04 | 2021-06-30 | No |  | Not started (grey) |  |  |  | USMEM-SMAPPVW24; | USMEM-SMAPPVW24; |  | RE-HOST | Manufacturing | Manufacturing | APAC | 6 | 19 | 19 - APAC Complex Group | Jun | MG2 | No | Yes | Moderate Migration | Medium | Moderate Migration | China, Beijing | Windows Server 2019 for Apps | COTS | CIMCO Maria DB | Prod,Dev,Test | 3 | None | IP Address change - Some FTP and SMB CNC controllers will need to be repointed to the new server. | Risk 1 - During Upgrade Cloud testing in AWS. Internal traffic was getting NATed. It was breaking FTP and SMB connections. Mitigation 1 - Application uses FTP and SMB and other unique protocols like FOCAS to transfer programs to and from machines. While migrating to Azure, IP address change needs to be taken care in the Client machines to point them to correct FTP and SMB configurations. Migration will be minimal but system needs to be tested to ensure file transfers still work as expected. Risk 2 - IP Address Change Mitigation 2 - Some FTP and SMB CNC controllers will need to be repointed to the new server. Risk 3 - Latency Sensitivity Mitigation 3 - The application was tested during AWS Upgrade and latency observed was around 90-120 ms which was high compared to the on prem 1-2 ms. Expected Latency is 60 ms max. Risk 4 - There will be an upgrade of the software to support automation and to interface with Tulip by end of 2020. Mitigation 4 - This needs to be planned and detail analysis to be done if this integration impacts Azure move. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
102 | Cimco china | PROD | Carla Morris |  |  | W6-MG2 | 2021-06-18 | 2021-06-30 | No |  | Not started (grey) |  |  |  | CNBDACIMCOS01 | CNBDACIMCOS02 |  | RE-HOST | Manufacturing | Manufacturing | APAC | 6 | 19 | 19 - APAC Complex Group | Jun | MG2 | No | Yes | Moderate Migration | Medium | Moderate Migration | China, Beijing | Windows Server 2019 for Apps | COTS | CIMCO Maria DB | Prod,Dev,Test | 3 | None | IP Address change - Some FTP and SMB CNC controllers will need to be repointed to the new server. | Risk 1 - During Upgrade Cloud testing in AWS. Internal traffic was getting NATed. It was breaking FTP and SMB connections. Mitigation 1 - Application uses FTP and SMB and other unique protocols like FOCAS to transfer programs to and from machines. While migrating to Azure, IP address change needs to be taken care in the Client machines to point them to correct FTP and SMB configurations. Migration will be minimal but system needs to be tested to ensure file transfers still work as expected. Risk 2 - IP Address Change Mitigation 2 - Some FTP and SMB CNC controllers will need to be repointed to the new server. Risk 3 - Latency Sensitivity Mitigation 3 - The application was tested during AWS Upgrade and latency observed was around 90-120 ms which was high compared to the on prem 1-2 ms. Expected Latency is 60 ms max. Risk 4 - There will be an upgrade of the software to support automation and to interface with Tulip by end of 2020. Mitigation 4 - This needs to be planned and detail analysis to be done if this integration impacts Azure move. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
70 | CIMCO Mansfield | DEV | Carla Morris |  |  | W5-MG1 | 2021-05-07 | 2021-05-30 | No |  | Not started (grey) |  |  |  | USASHSMAPQVW11 | USASHSMAPQVW11 |  | RE-HOST | Manufacturing | Manufacturing - Shop Floor | US | 5 | 14 | 14 - Shop Floor Medium/Complex Application | May | MG1 | No | Yes | Moderate Migration | High | Moderate Migration | Mansfield | Windows 2016 | COTS | Maria DB | 2 Environments, 1 for Prod and 1 for QA . Both CIMCO App and CIMCO Maria Db on same VM. | 2 | NA | FTP, SMB | Possible Latency issues when migrated to Cloud. Tried once with AWS. SMF and FTP File transfer potential issues. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
70 | CIMCO Mansfield | PROD | Carla Morris |  |  | W5-MG2 | 2021-05-21 | 2021-05-30 | No |  | Not started (grey) |  |  |  | USASHSMAPPVW45 | USASHSMAPPVW45 |  | RE-HOST | Manufacturing | Manufacturing - Shop Floor | US | 5 | 14 | 14 - Shop Floor Medium/Complex Application | May | MG1 | No | Yes | Moderate Migration | High | Moderate Migration | Mansfield | Windows 2016 | COTS | Maria DB | 2 Environments, 1 for Prod and 1 for QA . Both CIMCO App and CIMCO Maria Db on same VM. | 2 | NA | FTP, SMB | Possible Latency issues when migrated to Cloud. Tried once with AWS. SMF and FTP File transfer potential issues. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
69 | CIMCO Memphis | DEV | Carla Morris |  |  | W6-MG1 | 2021-06-04 | 2021-05-30 | No |  | Not started (grey) |  |  |  | USMEM-SMAPPVW24; | USMEM-SMAPPVW24 | USAZRSMDBDVW03 | RE-HOST(App)/RE-PLATFORM(DB) | Manufacturing | Manufacturing - Shop Floor | US | 5 | 14 | 14 - Shop Floor Medium/Complex Application | May | MG1 | No | Yes | Moderate Migration | High | Moderate Migration | Memphis | Windows 2016 | COTS | MS SQL 2017 | 2 Environments, 1 for Prod and 1 for QA. Both CIMCO App and SQL Db on same VM. | 2 | NA | FTP, SMB | Possible Latency issues when migrated to Cloud. Tried once with AWS. SMF and FTP File transfer potential issues. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
69 | CIMCO Memphis | PROD | Carla Morris |  |  | W6-MG2 | 2021-06-18 | 2021-05-30 | No |  | Not started (grey) |  |  |  | USMEMSMDBPVW19 | USMEMSMDBPVW19 | USAZRSMDBPVW04, USAZRSMDBPVW05 | RE-HOST(App)/RE-PLATFORM(DB) | Manufacturing | Manufacturing - Shop Floor | US | 5 | 14 | 14 - Shop Floor Medium/Complex Application | May | MG1 | No | Yes | Moderate Migration | High | Moderate Migration | Memphis | Windows 2016 | COTS | MS SQL 2017 | 2 Environments, 1 for Prod and 1 for QA. Both CIMCO App and SQL Db on same VM. | 2 | NA | FTP, SMB | Possible Latency issues when migrated to Cloud. Tried once with AWS. SMF and FTP File transfer potential issues. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
27 | Cockpit | PROD | Requalann Pereira | Sri Tupil |  | W8-MG1 | 2021-08-06 | 2021-08-06 | No |  | Not started (grey) |  |  |  | BBTCPT01 |  |  | RE-HOST | R&D | R&D, Web Application | US | 2 | 5 | 05 - Simple/Medium Apps | Feb | MG1 | No | No | Simple | Low | Simple | SNI Internal Globally | Windows Server 2008 R2 | COTS | Inbuilt | PROD | 1 | None | NA | Upgrade planned Cockpit 9.2 |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
109 | Cognos STGP | DEV | Sathiamurthy Samidurai | Stuart Robinson |  | W3-MG2 | 2021-03-19 | 2021-03-30 | No |  | On track (green) |  | Venkat/Isha/Shirisha | Srikanth Venkatasen | USMEM-SMAPEVW35 | NA |  | RE-HOST | Data & Analytics | Cognos | US | 3 | 9 | 09 - High Critical Application | Mar | MG2 | Yes | No | Moderate Migration | High | Moderate Migration | Globally SNI Internal | Windows 2016 | SNI Dev'ed | TM1 Cubes | 1 for Prod, 1 for QA, 1 for Dev | 3 | 1. All 5 TM1 applications are sharing these servers, Migration needs to be planned accordingly. | GBIP, SAP BW, Non SAP - Flat Files | IP Address, Enhancements going on. Finance Team involvement. |  | Yes | 2020-01-25 | 2021-01-28 | No | 2020-02-08 |  | No |  |  | No |  |  | No |  |  | No |  |  | No | 2021-02-24 |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
109 | Cognos STGP | QA | Sathiamurthy Samidurai | Stuart Robinson |  | W4-MG2 | 2021-04-23 | 2021-03-30 | No |  | On track (green) | ticket for docker to remain open. Need to wait for W3-MG2 cutover | Venkat/Isha/Shirisha | Srikanth/Rajesh | USATL-SMAPQUW05 |  |  | RE-HOST | Data & Analytics | Cognos | US | 3 | 9 | 09 - High Critical Application | Mar | MG2 | Yes | No | Moderate Migration | High | Moderate Migration | Globally SNI Internal | Windows 2016 | SNI Dev'ed | TM1 Cubes | 1 for Prod, 1 for QA, 1 for Dev | 3 | 1. All 5 TM1 applications are sharing these servers, Migration needs to be planned accordingly. | GBIP, SAP BW, Non SAP - Flat Files | IP Address, Enhancements going on. Finance Team involvement. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
109 | Cognos STGP | PROD | Sathiamurthy Samidurai | Stuart Robinson |  | W5-MG2 | 2021-05-21 | 2021-03-30 | No |  | Not started (grey) |  |  |  | USATLSMAPPPW07 |  |  | RE-HOST | Data & Analytics | Cognos | US | 3 | 9 | 09 - High Critical Application | Mar | MG2 | Yes | No | Moderate Migration | High | Moderate Migration | Globally SNI Internal | Windows 2016 | SNI Dev'ed | TM1 Cubes | 1 for Prod, 1 for QA, 1 for Dev | 3 | 1. All 5 TM1 applications are sharing these servers, Migration needs to be planned accordingly. | GBIP, SAP BW, Non SAP - Flat Files | IP Address, Enhancements going on. Finance Team involvement. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
108 | Cognos_STRATPLAN | DEV | Sathiamurthy Samidurai | Stuart Robinson |  | W3-MG2 | 2021-03-19 | 2021-03-30 | No |  | On track (green) |  | Venkat/Isha/Shirisha | Srikanth Venkatasen | USMEM-SMAPEVW35 | NA |  | RE-HOST | Data & Analytics | Cognos | US | 3 | 9 | 09 - High Critical Application | Mar | MG2 | Yes | No | Moderate Migration | High | Moderate Migration | Globally SNI Internal | Windows 2016 | SNI Dev'ed | TM1 Cubes | 1 for Prod, 1 for QA, 1 for Dev | 3 | 1. All 5 TM1 applications are sharing these servers, Migration needs to be planned accordingly. | GBIP - Datahub, Non SAP Sources | IP Address, Enhancements going on. Finance Team involvement. |  | Yes | 2020-01-25 | 2021-01-28 | No | 2020-02-08 |  | No |  |  | No |  |  | No |  |  | No |  |  | No | 2021-02-24 |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
108 | Cognos_STRATPLAN | QA | Sathiamurthy Samidurai | Stuart Robinson |  | W4-MG2 | 2021-04-23 | 2021-03-30 | No |  | On track (green) | ticket for docker to remain open. Need to wait for W3-MG2 cutover | Venkat/Isha/Shirisha | Srikanth/Rajesh | USATL-SMAPQUW05 |  |  | RE-HOST | Data & Analytics | Cognos | US | 3 | 9 | 09 - High Critical Application | Mar | MG2 | Yes | No | Moderate Migration | High | Moderate Migration | Globally SNI Internal | Windows 2016 | SNI Dev'ed | TM1 Cubes | 1 for Prod, 1 for QA, 1 for Dev | 3 | 1. All 5 TM1 applications are sharing these servers, Migration needs to be planned accordingly. | GBIP - Datahub, Non SAP Sources | IP Address, Enhancements going on. Finance Team involvement. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
108 | Cognos_STRATPLAN | PROD | Sathiamurthy Samidurai | Stuart Robinson |  | W5-MG2 | 2021-05-21 | 2021-03-30 | No |  | Not started (grey) |  |  |  | USATLSMAPPPW07 |  |  | RE-HOST | Data & Analytics | Cognos | US | 3 | 9 | 09 - High Critical Application | Mar | MG2 | Yes | No | Moderate Migration | High | Moderate Migration | Globally SNI Internal | Windows 2016 | SNI Dev'ed | TM1 Cubes | 1 for Prod, 1 for QA, 1 for Dev | 3 | 1. All 5 TM1 applications are sharing these servers, Migration needs to be planned accordingly. | GBIP - Datahub, Non SAP Sources | IP Address, Enhancements going on. Finance Team involvement. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
126 | Connect Ship (UPS/DHL) | QA | Amit Shokeen | Massimo Trambaioli |  | W3-MG1 | 2021-03-05 | 2021-03-30 | No |  | On track (green) |  | Kishore Balimidi | Rahul Sarin | USMAN-SMAPDVW32 | USMANSMDBDUW01 | USAZRSMDBQVW02 | RE-HOST(App)/RE-PLATFORM(DB) | Supply Chain | Supply Chain | US | 3 | 8 | 08 - Full Throttle EMEA Application - Batch 1 | Mar | MG2 | No | No | Complex Migration | High | Complex Migration | SNI Internal Globally | Windows Server 2012 R2 | COTS | Sql Server 2008 | PROD, QA | 5 | None | SAP and Shipping Printer | SAP side web service call that Connect Ship has hardcoded IP address pointing to current On-Perm server IP , Multi Location Printer Spools , Server also host VCM application |  | Yes | 2020-01-25 | 2021-01-28 | No | 2020-02-08 | 2020-02-10 | No |  |  | No |  |  | No |  |  | No |  |  | Yes | 2021-02-10 | 2021-02-11 | Yes | 2021-02-17 | 2021-02-17 | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
126 | Connect Ship (UPS/DHL) | PROD | Amit Shokeen | Massimo Trambaioli |  | W3-MG2 | 2021-03-19 | 2021-03-30 | No |  | On track (green) |  | Kishore Balimidi | Rahul Sarin | USMAN-SMAPPVW51 | USMANSMDBPCW08; USMANSMDBPCW07 | USAZRSMDBPVW04, USAZRSMDBPVW05 | RE-HOST(App)/RE-PLATFORM(DB) | Supply Chain | Supply Chain | US | 3 | 8 | 08 - Full Throttle EMEA Application - Batch 1 | Mar | MG2 | No | No | Complex Migration | High | Complex Migration | SNI Internal Globally | Windows Server 2012 R2 | COTS | Sql Server 2008 | PROD, QA | 5 | None | SAP and Shipping Printer | SAP side web service call that Connect Ship has hardcoded IP address pointing to current On-Perm server IP , Multi Location Printer Spools , Server also host VCM application |  | Yes | 2020-01-25 | 2021-01-28 | No | 2020-02-08 |  | No |  |  | No |  |  | No |  |  | No |  |  | No | 2021-02-24 |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
23 | CVS Concurrent Version System | PROD | Requalann Pereira | Sri Tupil |  | W7-MG1 | 2021-07-09 | 2021-02-28 | No |  | Not started (grey) |  |  |  | DYNOMITE |  |  | RE-HOST | R&D | R&D,Defect/bug Tracking for Navio Product Development team | US | 2 | 5 | 05 - Simple/Medium Apps | Feb | MG1 | No | No | Simple Migration | Medium | Complex Migration | USA-Costa Rica,SNI Internal | Linux12.04.2 | COTS | NA | Prod | 1 | Bugzilla | Both Bugzilla and CVS are cohosted on the same server | Nothing Found |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
47 | dataSTOR | PROD | Sebastian Pasch |  |  | W4-MG1 | 2021-04-09 | 2021-03-30 | No |  | On track (green) | Infra and DB team to share cutover steps | Saurabh | Praveen | ZASNFS2 | ZASNFS2 | EUAZRSMDBPVW01, EUAZRSMDBPVW02 | RE-HOST(App)/RE-PLATFORM(DB) | ERP | ERP Application -This application is used to store an electronic copy of PODs, Invoices, Statements | EMEA | 3 | 8 | 08 - Full Throttle EMEA Application - Batch 1 | Mar | MG2 | No | No | Simple Migration | Medium | Medium Migration | SNI Internal | Windows Server 2008 R2 Standard | COTS | SQL Server 2008 R2 | Prod | 1 | Business Objects (IRAMEA) | Server ‘ZASNFS2’ also co-host dataSTOR application. | Licenses are mapped to the MAC ID of the Client machines |  | Yes | 2020-01-25 | 2021-01-28 | No | 2020-02-08 |  | No |  |  | No |  |  | No |  |  | No |  |  | No | 2021-02-24 |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
48 | DNC5000 | PROD | Antoine d'Overschie | Massimo Trambaioli | X | W7-MG1 | 2021-07-09 | 2021-07-30 | No |  | Not started (grey) | Propose to move to April 23rd |  |  | AAR-SW197 | AAR-SW197 | EUAZRSMDBPVW01, EUAZRSMDBPVW02 | RE-HOST(App)/RE-PLATFORM(DB) | Manufacturing | Manufacturing -to communicate/control CNC machine | EMEA | 7 | 21 | 21 - Final EMEA/APAC application | Jul | MG2 | No | No | Complex Migration | Complex | Latency requirement & SAP integration being planned in Q1 and Q2 2021 | SNI Internal | Windows 2012 R2 Standard | COTS | Sql Server 2014 | Prod | 1 | NA | None | Vendor confirmed use latest OS (Replatform) | Antoine d’Overschie (22-Oct)- Fr the application DNC5000 in column J, I can find March. Keeping in mind that we will be live with SAP EPR in Q1 2021, if it’s the planed migration, may I politely ask for a delay, I would appreciate being in Wave 6 or 7, if wave represents the month. | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
62 | E-Adept | PROD | Andres Bernard | Firas Almahamid | X | W4-MG2 | 2021-04-23 | 2021-04-30 | No |  | Imminent Delay (red) | Meeting today, March 5th | Shweta | Rahul/Saurabh | ESBARSMEAPW01 | ESBARSMDBPW01 |  | RE-HOST | Commercial | Commercial | EMEA | 4 | 10 | 10 - Full Throttle EMEA Application - Batch 2 | Apr | MG2 | No | Yes | Simple Migration | Low | SDM: Server Hosted in Barcelona site, with challenge with Local User. | Spain, Barcelona | Windows Server 2008 Enterprise | COTS | Sql Server 2008 R2 | Prod | 2 | None | None | Application & DB server physical location at user site , Amsterdam DC (ESX server) vCenter shows this 2 server registered. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
73 | Eagle RF Express | DEV | Jacob Goitom | Chris Cook |  | W5-MG1 | 2021-05-07 | 2021-05-30 | No |  | Not started (grey) |  |  |  | QAD01 |  |  | RE-HOST | Supply Chain | Manufacturing - Inventory | US | 5 | 14 | 14 - Shop Floor Medium/Complex Application | May | MG1 | No | Yes | Complex Migration | Medium | Complex Migration | US-MD/Columbia | Linux 6.9 | COTS | Progress Database | 4 Environments, Prod, Test, Dev, Val – Total 4 Instances on same VM - QAD01 - VM | 4 | Both QAD ERP & Eagle RF Express applications will be covered in one application migration. | SAP, Eagle RF Express Guns. | Printer Configuration, Third Party Drivers. COTS version compatibility |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
73 | Eagle RF Express | TEST | Jacob Goitom | Chris Cook |  | W5-MG1 | 2021-05-07 | 2021-05-30 | No |  | Not started (grey) |  |  |  | QAD01 |  |  | RE-HOST | Supply Chain | Manufacturing - Inventory | US | 5 | 14 | 14 - Shop Floor Medium/Complex Application | May | MG1 | No | Yes | Complex Migration | Medium | Complex Migration | US-MD/Columbia | Linux 6.9 | COTS | Progress Database | 4 Environments, Prod, Test, Dev, Val – Total 4 Instances on same VM - QAD01 - VM | 4 | Both QAD ERP & Eagle RF Express applications will be covered in one application migration. | SAP, Eagle RF Express Guns. | Printer Configuration, Third Party Drivers. COTS version compatibility |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
73 | Eagle RF Express | VAL | Jacob Goitom | Chris Cook |  | W5-MG1 | 2021-05-07 | 2021-05-30 | No |  | Not started (grey) |  |  |  | QAD01 |  |  | RE-HOST | Supply Chain | Manufacturing - Inventory | US | 5 | 14 | 14 - Shop Floor Medium/Complex Application | May | MG1 | No | Yes | Complex Migration | Medium | Complex Migration | US-MD/Columbia | Linux 6.9 | COTS | Progress Database | 4 Environments, Prod, Test, Dev, Val – Total 4 Instances on same VM - QAD01 - VM | 4 | Both QAD ERP & Eagle RF Express applications will be covered in one application migration. | SAP, Eagle RF Express Guns. | Printer Configuration, Third Party Drivers. COTS version compatibility |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
73 | Eagle RF Express | PROD | Jacob Goitom | Chris Cook |  | W5-MG1 | 2021-05-07 | 2021-05-30 | No |  | Not started (grey) |  |  |  | QAD01 |  |  | RE-HOST | Supply Chain | Manufacturing - Inventory | US | 5 | 14 | 14 - Shop Floor Medium/Complex Application | May | MG1 | No | Yes | Complex Migration | Medium | Complex Migration | US-MD/Columbia | Linux 6.9 | COTS | Progress Database | 4 Environments, Prod, Test, Dev, Val – Total 4 Instances on same VM - QAD01 - VM | 4 | Both QAD ERP & Eagle RF Express applications will be covered in one application migration. | SAP, Eagle RF Express Guns. | Printer Configuration, Third Party Drivers. COTS version compatibility |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
32 | Electronic Instructions for Use | PROD | Carla Morris | Derek Spillane |  | W2-MG2 | 2021-02-19 | 2021-02-19 | No |  | Finished (blue) |  |  |  | USASHSMWSPVW13; USASHSMWSPVW14 | USASHSMDBPPW02; USASHSMDBPPW04 | USAZRSMDBPVW02, USAZRSMDBPVW03 | RE-HOST(App)/RE-PLATFORM(DB) | Commercial | Commercial | US | 2 | 5 | 05 - Simple/Medium Apps | Feb | MG2 | No | Yes | Simple | Medium | Easy Migration | USA | Windows Server 2016 | SNI Dev | Sql Server 2016 | Prod , QA , Dev , DR | 12 | No |  |  |  | Yes | 2020-12-23 | 2020-12-23 | Yes | 2021-01-29 | 2021-01-29 | Yes | 2021-01-21 | 2021-01-25 | Yes | 2021-02-01 | 2021-01-18 | Yes | 2021-02-08 | 2021-01-25 | Yes | 2021-02-12 | 2021-01-29 | Yes | 2021-01-29 | 2021-01-29 | Yes | 2021-02-03 | 2021-02-03 | Yes | 2021-02-19 | 2021-02-19 | No | 2021-02-18 |  | Yes | 2021-02-19 | 2021-02-19 | No | 2021-02-21 | 2021-02-21 | No | 2021-02-21 |  | Done, no evidence provided | N/A | N/A | Done, no evidence provided | Done, no evidence provided | N/A | Done, no evidence provided | N/A | N/A | N/A | Yes | 2021-03-19 |  | No | 2021-03-19 |  | No | 2021-03-19 |  | No | 2021-03-19 |  | No | 2021-03-19
32 | Electronic Instructions for Use | DEV | Carla Morris | Derek Spillane |  | W2-MG1 | 2021-02-05 | 2021-02-05 | No |  | Finished (blue) |  |  |  | USASHSMWSDVW06 | USASHSMDBDVW12 | USAZRSMDBDVW02 | RE-HOST(App)/RE-PLATFORM(DB) | Commercial | Commercial | US | 2 | 5 | 05 - Simple/Medium Apps | Feb | MG1 | No | Yes | Simple | Medium | Easy Migration | USA | Windows Server 2016 | SNI Dev | Sql Server 2016 | Prod , QA , Dev , DR | 12 | No |  |  |  | Yes | 2020-12-23 | 2020-12-23 | Yes | 2021-01-18 | 2021-01-15 | No | 2021-01-18 |  | Yes | 2021-01-18 | 2021-01-18 | Yes | 2021-01-25 | 2021-01-25 | Yes | 2021-01-29 | 2021-01-29 | Yes | 2021-01-15 | 2021-01-15 | Yes | 2021-01-20 | 2021-01-20 | Yes | 2021-02-05 | 2021-02-05 | Yes | 2021-02-04 | 2021-02-04 | Yes | 2021-02-05 | 2021-02-05 | Yes | 2021-02-07 | 2021-02-07 | Yes | 2021-02-07 | 2021-02-07 | Done, no evidence provided | N/A | N/A | Done, no evidence provided | Done, no evidence provided | N/A | Not done | N/A | N/A | N/A | No | 2021-03-05 |  | No | 2021-03-05 |  | No | 2021-03-05 |  | No | 2021-03-05 |  | No | 2021-03-05
32 | Electronic Instructions for Use | QA | Carla Morris | Derek Spillane |  | W2-MG1 | 2021-02-05 | 2021-02-05 | No |  | Finished (blue) |  |  |  | USASHSMWSQVW06; USASHSMWSQVW07 | USASHSMDBTVW01 | USAZRSMDBQVW01 | RE-HOST(App)/RE-PLATFORM(DB) | Commercial | Commercial | US | 2 | 5 | 05 - Simple/Medium Apps | Feb | MG1 | No | Yes | Simple | Medium | Easy Migration | USA | Windows Server 2016 | SNI Dev | Sql Server 2016 | Prod , QA , Dev , DR | 12 | No |  |  |  | Yes | 2020-12-23 | 2020-12-23 | Yes | 2021-01-18 | 2021-01-15 | No | 2021-01-18 |  | Yes | 2021-01-18 | 2021-01-18 | Yes | 2021-01-25 | 2021-01-25 | Yes | 2021-01-29 | 2021-01-29 | Yes | 2021-01-15 | 2021-01-15 | Yes | 2021-01-20 | 2021-01-20 | Yes | 2021-02-05 | 2021-02-05 | Yes | 2021-02-04 | 2021-02-04 | Yes | 2021-02-05 | 2021-02-05 | Yes | 2021-02-07 | 2021-02-07 | Yes | 2021-02-07 | 2021-02-07 | Done, no evidence provided | N/A | N/A | Done, no evidence provided | Done, no evidence provided | N/A | Not done | N/A | N/A | N/A | No | 2021-03-05 |  | No | 2021-03-05 |  | No | 2021-03-05 |  | No | 2021-03-05 |  | No | 2021-03-05
32 | Electronic Instructions for Use | DR | Carla Morris | Derek Spillane |  |  |  |  | Yes | DR environment at On prem to be decomissioned as Azure PROD will take care of HA & DR requirement. | Out of scope (dark grey) |  |  |  | USASHSMWSPVW13; USASHSMWSPVW14 | USMEMSMDBQPW01 | USAZRSMDBPVW02, USAZRSMDBPVW03 | RE-HOST(App)/RE-PLATFORM(DB) | Commercial | Commercial | US | 2 | 5 | 05 - Simple/Medium Apps | Feb | MG2 | No | Yes | Simple | Medium | Easy Migration | USA | Windows Server 2016 | SNI Dev | Sql Server 2016 | Prod , QA , Dev , DR | 12 | No |  |  |  | Yes | 2020-12-23 | 2020-12-23 | Yes | 2021-01-29 | 2021-01-29 | No |  |  | Yes |  | 2021-01-18 | Yes |  | 2021-01-25 | Yes |  | 2021-01-29 | Yes | 2021-01-29 | 2021-01-29 | Yes | 2021-02-03 | 2021-02-03 | Yes | 2021-02-19 | 2021-02-19 | No |  |  | No |  |  | No |  |  | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No |  |  | No |  |  | No |  |  | No |  |  | No
5 | Endo Loans | PROD | Andres Bernard | Firas Almahamid |  | W3-MG1 | 2021-03-05 | 2021-03-05 | No |  | On track (green) |  | Vidit Kumar | Rahul Sarin | USMAN-SMWSPVW12 | USMAN-SMDBPVW12 | USAZRSMDBPVW02, USAZRSMDBPVW03 | RE-HOST(App)/RE-PLATFORM(DB) | Commercial | Commercial | US | 1 | 3 | 03 - SNI Developed + Co-Hosted Apps | Jan | MG2 | No | No | Simple | Low | Easy Migration | Globally SNI Internal | Windows Server 2012 | SNI Dev'ed | Sql Server 2012 | Dev, Test, Prod | 4 | "SNID Archived shipping documents ECAP ENCORE HR Notification Global Return Disposition Tool GSC Datawarehouse Admin Tool Inventures Web App Nomino Security QA Change Control Recon LaunchPad(SSO) Reimbursement Sales Request Forms Non-Employee Database " | NA | App and DB servers are shared across other applications in SNI, IP Address Change – Hardcoding |  | Yes | 2020-01-25 | 2021-01-28 | Yes | 2020-02-08 | 2020-02-10 | Yes | 2021-02-08 | 2020-02-10 | No |  |  | No |  |  | No |  |  | Yes | 2021-02-10 | 2021-02-11 | Yes | 2021-02-17 | 2021-02-17 | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
5 | Endo Loans | QA | Andres Bernard | Firas Almahamid |  | W1-MG2 | 2021-01-22 | 2021-01-22 | No |  | Finished (blue) |  |  |  | USMAN-SMWSQVW05 | USMAN-SMDPDVW16 | USAZRSMDBQVW01 | RE-HOST(App)/RE-PLATFORM(DB) | Commercial | Commercial | US | 1 | 3 | 03 - SNI Developed + Co-Hosted Apps | Jan | MG2 | No | No | Simple | Low | Easy Migration | Globally SNI Internal | Windows Server 2012 | SNI Dev'ed | Sql Server 2012 | Dev, Test, Prod | 4 | "SNID Archived shipping documents ECAP ENCORE HR Notification Global Return Disposition Tool GSC Datawarehouse Admin Tool Inventures Web App Nomino Security QA Change Control Recon LaunchPad(SSO) Reimbursement Sales Request Forms Non-Employee Database " | NA | App and DB servers are shared across other applications in SNI, IP Address Change – Hardcoding |  | Done | 2020-12-11 | 2020-12-11 | Yes | 2020-12-30 | 2021-01-22 | No | 2021-01-13 | 2021-01-13 | Yes | 2021-01-04 | 2021-01-04 | Yes | 2021-01-11 | 2021-01-11 | Yes | 2021-01-15 | 2021-01-15 | Yes | 2021-01-08 | 2021-01-08 | Yes | 2021-01-13 | 2021-01-13 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-22 | 2021-01-22 | Yes | 2021-01-24 | 2021-01-24 | Yes | 2021-01-24 | 2021-01-24 | Done, no evidence provided | N/A | N/A | Done, no evidence provided | Done, no evidence provided | N/A | N/A | N/A | N/A | N/A | No | 2021-02-19 |  | Yes | 2021-02-19 | 2021-02-08 | No | 2021-02-19 |  | No | 2021-02-19 |  | No | 2021-02-19
76 | Enterprise Business Objects Reporting | PROD | Sathiamurthy Samidurai | Stuart Robinson |  | W3-MG2 | 2021-03-19 | 2021-03-19 | No |  | Imminent Delay (red) | Decision pending on either DB servers will be consolidated or will have dedicated Cluster in Azure. QA Testing is still pending that ensures the path for a successful migration. | Shirisha | Srikanth Venkatasen | USMANSMAPPUW16 | USMANSMDBPUW35(SQL Cluster Address);USMANSMDBPUW31; USMANSMDBPUW32 |  | RE-HOST | Data & Analytics | Data & Analytics | US | 2 | 6 | 6 - Data Warehouse Application | Mar | MG2 | No | No | Complex Migration | High | Complex Migration | US , EUC ,APAC | Windows Server 2012 R2 | COTS | Sql Server 2012 | PROD, DEV | 4 | New server (non CMDB) USMANSMDBPUW35 Co-host application to be confirmed, If not, then no Co-Host. | SAP | Integration with Global data warehouse (GWD), Wound data warehouse, SAP Business warehouse and Global Market Monitoring solutions. Co-hosted application on the server. |  | Yes | 2020-01-25 | 2021-01-28 | No | 2020-02-08 |  | No |  |  | No |  |  | No |  |  | No |  |  | No | 2021-02-24 |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
76 | Enterprise Business Objects Reporting | DEV | Sathiamurthy Samidurai | Stuart Robinson |  | W1-MG2 | 2021-01-22 | 2021-01-22 | No |  | Finished (blue) |  |  |  | USMAN-SMAPDVW34 | USMAN-SMAPPVW54 |  | RE-HOST | Data & Analytics | Data & Analytics | US | 2 | 6 | 6 - Data Warehouse Application | Jan | MG2 | No | No | Complex Migration | High | Complex Migration | US , EUC ,APAC | Windows Server 2012 R2 | COTS | Sql Server 2012 | PROD, DEV | 4 | New server (non CMDB) USMANSMDBPUW35 Co-host application to be confirmed, If not, then no Co-Host. | SAP | Integration with Global data warehouse (GWD), Wound data warehouse, SAP Business warehouse and Global Market Monitoring solutions. Co-hosted application on the server. |  | Done | 2020-12-11 | 2021-01-22 | Yes | 2020-12-30 | 2021-01-22 | No | 2021-01-13 | 2021-01-13 | Yes | 2021-01-04 | 2021-01-04 | Yes | 2021-01-11 | 2021-01-11 | Yes | 2021-01-15 | 2021-01-15 | Yes | 2021-01-08 | 2021-01-08 | Yes | 2021-01-13 | 2021-01-13 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-22 | 2021-01-22 | Yes | 2021-01-24 | 2021-01-24 | Yes | 2021-01-24 | 2021-01-24 | Done, no evidence provided | N/A | N/A | Done, no evidence provided | Done, no evidence provided | N/A | N/A | N/A | N/A | N/A | No | 2021-02-19 |  | Yes | 2021-02-19 | 2021-02-08 | No | 2021-02-19 |  | No | 2021-02-19 |  | No | 2021-02-19
63 | Epats | PROD | Mark Elliott | Stuart Robinson |  | W6-MG2 | 2021-06-18 | 2021-06-30 | No |  | Not started (grey) |  |  |  | ZAORACLE | ZAORACLE |  | RE-HOST | Data & Analytics | Data & Analytics | EMEA | 6 | 17 | 17 - Full Throttle EMEA Application - Batch 2 | Jun | MG2 | No | No | Complex Migration | Medium | Action items pending with SDM | Europe | Window Server 2008 R2 | COTS | Oracle 11g | Prod | 1 | IRAMEA-LATAM Data Warehouse (South Africa) Global Data Warehouse Epats | None | Application had DR, External (or internal) facing URL using bluecoat forward proxy to allow users to access Epats site | Need to check if in Azure it will allow additional processes for Oracle DB. | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
61 | eRoom | PROD | Andres Bernard | Firas Almahamid | X | W4-MG1 | 2021-04-09 | 2021-04-30 | Yes | Potential mothball pilot solution - AVS | Out of scope (dark grey) | Out of Scope |  |  | HP-EROOMS |  |  | RE-HOST | RAQA | Commercial | US | 4 | 11 | 11 - US Medium/Complex Application | Apr | MG1 | No | No | Simple Migration | Low | Moderate migration | USA | Windows Server 2008 | COTS | Sql Server 2008 | Prod | 1 | None | None | IP Address Change |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
84 | Evisense | PROD | Requalann Pereira | Sri Tupil |  | W4-MG1 | 2021-04-09 | 2021-05-30 | No |  | Risk of delay (amber) | Req needs to confirm if this applciation is in scope by Friday March 5th | Raju | Rahul/Saurabh | UKRTH-SMAPDVW31 |  |  | RE-HOST | R&D | R&D | EMEA | 5 | 15 | 15 - EMEA Medium Application REHOST Only Group | May | MG2 | No | Yes | Moderate Migration | Low | Moderate migration | Europe | Windows Server 2012 DataCenter | COTS | in-built | Prod | 1 | None | None | Temperature probes are on the refrigeration units and connected to the wireless networks and will need to make sure they can communicate with the server |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
24 | Exactus Payroll Application (Costa Rica) | PROD | Paul Davison | Chris Cook |  |  |  |  | No |  | Reverted (light orange) | Migrated and reverted back to ON Prem due to Latency concerns from business |  |  | CRCOSSMDBPVW01 |  |  | RE-HOST | Group Functions | Group Functions,used in Costa Rica by the Payroll department | US | 2 | 5 | 05 - Simple/Medium Apps | Feb | MG1 | No | Yes | Moderate Migration | Low | Easy Migration | USA,SNI Internal | Window Server 2016 Standard | COTS | SQL Server version is 2016 | Prod | 1 | NA | Nothing. | Nothing Found |  | Yes | 2020-12-23 | 2020-12-23 | Yes | 2021-01-18 | 2021-01-15 | Yes | 2021-01-14 | 2021-01-14 | Yes | 2021-01-18 | 2021-01-18 | Yes | 2021-01-25 | 2021-01-25 | Yes | 2021-01-29 | 2021-01-29 | Yes | 2021-01-15 | 2021-01-15 | Yes | 2021-01-20 | 2021-01-20 | Yes | 2021-02-05 | 2021-02-05 | No | 2021-02-04 |  | No | 2021-02-05 |  | No | 2021-02-07 | 2021-02-07 | No | 2021-02-07 |  | Not done | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No |  |  | No | 2021-03-05 |  | No | 2021-03-05 |  | No | 2021-03-05 |  | No | 2021-03-05
41 | Expert Document Imaging (EDI) | PROD | Eduardo Lima | Firas Almahamid |  | W6-MG2 | 2021-06-18 | 2021-03-30 | No |  | Not started (grey) |  |  |  | PRSEDI |  | USAZRSMDBPVW02, USAZRSMDBPVW03 | RE-HOST(App)/RE-PLATFORM(DB) | Commercial | Commercial | US | 3 | 7 | 07 - Simple/Medium Apps - Moving to EMEA | Mar | MG1 | No | No | Simple | Medium | Complex Migration | Europe (Server is US) | Windows Server 2008 Enterprise | COTS | Sql Server 2008 | PROD | 1 | None | NA | Local network upgrade program may impact the migration. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
89 | Express Implants | QA | Requalann Pereira | Sri Tupil |  | W4-MG2 | 2021-04-23 | 2021-06-30 | No |  | On track (green) |  | Deepak | Rahul/Saurabh | USMEM-SMAPDVW28 | MEMSRV491 |  | RE-PLATFORM | R&D | R&D, Gather Schedule & Track | US | 6 | 18 | 18 - Complex Application Group | Jun | MG1 | No | Yes | Complex Migration | Medium | Complex Migration | US | Windows Server 2003 Enterprise x64/2008 Datacenter | Vendor Developed | Sql Server 2005 | PROD, DEV | 4 | Express Instruments, Express Visionaire, Opentext ECM | Integration with Matrix (reading information of UDI data) and sending information to Prisym and SAP. Co-Hosted with Express Instruments application. | DEV/QA server OS is 2003 |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
89 | Express Implants | PROD | Requalann Pereira | Sri Tupil |  | W5-MG2 | 2021-05-21 | 2021-06-30 | No |  | Not started (grey) |  |  |  | USMEM-SMWSPVW11 | VMSCSSQL2K501 |  | RE-PLATFORM | R&D | R&D, Gather Schedule & Track | US | 6 | 18 | 18 - Complex Application Group | Jun | MG1 | No | Yes | Complex Migration | Medium | Complex Migration | US | Windows Server 2003 Enterprise x64/2008 Datacenter | Vendor Developed | Sql Server 2005 | PROD, DEV | 4 | Express Instruments, Express Visionaire, Opentext ECM | Integration with Matrix (reading information of UDI data) and sending information to Prisym and SAP. Co-Hosted with Express Instruments application. | DEV/QA server OS is 2003 |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
91 | Express Instruments | QA | Requalann Pereira | Sri Tupil |  | W4-MG2 | 2021-04-23 | 2021-06-30 | No |  | On track (green) |  | Deepak | Rahul/Saurabh | USMEM-SMAPDVW28; | MEMSRV491 |  | RE-PLATFORM | R&D | R&D, Custom implant manufacturing | US | 6 | 18 | 18 - Complex Application Group | Jun | MG1 | No | Yes | Complex Migration | Medium | Complex Migration | US | Windows Server 2016 Standard | Vendor Developed | Sql Server 2016 | PROD, DEV | 4 | Express Implants, Express Visionaire, Opentext ECM. | Integration with Matrix (reading information of UDI data) and sending information to Prisym and SAP. Co-Hosted with Express Implants application. | Both Express Instruments & Inventures (SCAMPI) Web App applications as we learnt during the SME sessions are one and the same. These are duplicate entries in the CMDB. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
91 | Express Instruments | PROD | Requalann Pereira | Sri Tupil |  | W5-MG2 | 2021-05-21 | 2021-06-30 | No |  | Not started (grey) |  |  |  | USMEM-SMWSPVW11 | VMSCSSQL2K501 |  | RE-PLATFORM | R&D | R&D, Custom implant manufacturing | US | 6 | 18 | 18 - Complex Application Group | Jun | MG1 | No | Yes | Complex Migration | Medium | Complex Migration | US | Windows Server 2016 Standard | Vendor Developed | Sql Server 2016 | PROD, DEV | 4 | Express Implants, Express Visionaire, Opentext ECM. | Integration with Matrix (reading information of UDI data) and sending information to Prisym and SAP. Co-Hosted with Express Implants application. | Both Express Instruments & Inventures (SCAMPI) Web App applications as we learnt during the SME sessions are one and the same. These are duplicate entries in the CMDB. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
42 | Express Visionaire | PROD | Requalann Pereira | Sri Tupil |  |  | 2021-05-30 | 2021-03-30 | Yes | To be retired - Adrian Caines | Out of scope (dark grey) |  |  |  | USMEMSMAPDVW28; USMANSMDBPCW4B | MEMSRV491 |  | RE-PLATFORM | R&D | R&D, Visionaire case flow website. | US | 3 | 7 | 07 - Simple/Medium Apps - Moving to EMEA | Mar | MG1 | No | Yes | Moderate Migration | Low | Moderate Migration | US | Windows Server 2003/08/12 Enterprise | Vendor Developed | Sql Server 2005 | PROD, QA | 3 | QA Server: Express Instruments, Express Visionaire, Opentext ECM PROD Server: Visionaire Case Management (Legacy) | Co-host application Visionaire Case Management (Legacy), Express Implant and Express Instruments & Opentext ECM. | Application and DB are hosted on Legacy OS , PROD server hosting other application,Server USMANSMDBPCW4B is OS 2008 & SQL DB 2005 |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
28 | FAS 500 -Sage | TEST | Paul Davison | Chris Cook |  | W2-MG1 | 2021-02-05 | 2021-02-05 | No |  | Finished (blue) |  |  |  | USMAN-SMAPDVW33 | USMAN-SMAPDVW33 |  | RE-HOST | Group Functions | Group Functions | US | 2 | 5 | 05 - Simple/Medium Apps | Feb | MG1 | No | No | Simple | Low | SDM reuest for RE-PLATFORM | US | Windows Server 2008 R2 | COTS | Sql Server 2014 | PROD, DEV, RDP | 3 | None | RDP server is Windows 2008 R2, Application servers are Windows 2012 | Replatform - Server will upgrade |  | Yes | 2020-12-23 | 2020-12-23 | Yes | 2021-01-18 | 2021-01-15 | No | 2021-01-18 |  | Yes | 2021-01-18 | 2021-01-18 | Yes | 2021-01-25 | 2021-01-25 | Yes | 2021-01-29 | 2021-01-29 | Yes | 2021-01-15 | 2021-01-15 | Yes | 2021-01-20 | 2021-01-20 | Yes | 2021-02-05 | 2021-02-05 | Yes | 2021-02-04 | 2021-02-04 | Yes | 2021-02-05 | 2021-02-05 | Yes | 2021-02-07 | 2021-02-07 | Yes | 2021-02-07 | 2021-02-07 | Done, no evidence provided | N/A | N/A | Done, no evidence provided | Done, no evidence provided | N/A | N/A | N/A | N/A | N/A | No | 2021-03-05 |  | No | 2021-03-05 |  | No | 2021-03-05 |  | No | 2021-03-05 |  | No | 2021-03-05
28 | FAS 500 -Sage | PROD | Paul Davison | Chris Cook |  | W2-MG2 | 2021-02-19 | 2021-02-19 | No |  | Finished (blue) |  |  |  | USMAN-SMAPPVW52; USMAN-SMTSPW01 | USMAN-SMAPPVW52 |  | RE-HOST | Group Functions | Group Functions | US | 2 | 5 | 05 - Simple/Medium Apps | Feb | MG2 | No | No | Simple | Low | SDM reuest for RE-PLATFORM | US | Windows Server 2008 R2 | COTS | Sql Server 2014 | PROD, DEV, RDP | 3 | None | RDP server is Windows 2008 R2, Application servers are Windows 2012 | Replatform - Server will upgrade |  | Yes | 2020-12-23 | 2020-12-23 | Yes | 2021-01-29 | 2021-01-29 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-02-01 | 2021-01-18 | Yes | 2021-02-08 | 2021-01-25 | Yes | 2021-02-12 | 2021-01-29 | Yes | 2021-01-29 | 2021-01-29 | Yes | 2021-02-03 | 2021-02-03 | Yes | 2021-02-19 | 2021-02-19 | No | 2021-02-18 |  | Yes | 2021-02-19 | 2021-02-19 | No | 2021-02-21 | 2021-02-21 | No | 2021-02-21 |  | Done, no evidence provided | N/A | Done with evidence provided | Done, no evidence provided | Done, no evidence provided | N/A | N/A | Not done | N/A | N/A | Yes | 2021-03-19 |  | No | 2021-03-19 |  | No | 2021-03-19 |  | No | 2021-03-19 |  | No | 2021-03-19
35 | FileMaker | PROD | Andres Bernard | Firas Almahamid |  |  | 2021-02-28 | 2021-02-28 | No |  | Risk of delay (amber) |  |  |  | NLAMSSMAPPVW24 |  |  | RE-HOST | Commercial | Commercial | EMEA | 2 | 5 | 05 - Simple/Medium Apps | Feb | MG1 | No | No | Simple Migration | Low | Low | Europe | Windows 2012 R2 Standard | COTS | FileMaker db | Prod | 1 | None | None | IP Address changes |  | Yes | 2020-12-23 |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
98 | Filezilla FTP Server | PROD | Mark Elliott | Stuart Robinson |  |  | 2021-04-30 | 2021-04-30 | Yes | Retired | Out of scope (dark grey) |  |  |  | MEMSRV042; SNS02; |  |  | RE-HOST | Data & Analytics | Data & Analytics | APAC | 4 | 12 | 12 - APAC Complex Group | Apr | MG2 | No | No | Not Possible | Medium | Not Possible | APAC/Africa | Windows Server 2012 | COTS | NA | Prod | 7 | None | IP Hardcoding | Risk 1 - Test cases are not available Mitigation 1 - SNI team provides ahead of migration phase start. Risk 2 - Hardcoded IP in source code Mitigation 2 - Change configuration before migration phase start Risk 3 - Missing – all list of Clients, Users, Systems (in configuration or code) connecting to FTP server Mitigation 3 - Its critical to make sure all the Clients, User or Systems are identified and communication are send to them (ALL) on the change of the new IP server (instances), so that they change the same that they have mentioned in their configuration or source code. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
9 | Flex LM | PROD | Requalann Pereira | Sri Tupil |  | W5-MG1 | 2021-05-07 | 2021-01-30 | No |  | Not started (grey) |  |  |  | MEMSRV403; MEMSRV434; |  |  | RE-PLATFORM | R&D | R&D | US | 1 | 2 | 02 - Network License Server - Batch 2 | Jan | MG1 | No | No | Moderate Migration | Medium | Moderate Migration | US | Windows Server 2008 & 2008 R2 | COTS | NA | PROD | 3 | MIMICS, Simulia Abaqus, MATLAB, MyRiad, PartMaker, Geomagic, AutoCAD & Adams (Out of scope). | Co-Hosted application License manager for MIMICS, Simulia Abaqus, MATLAB, MyRiad, PartMaker, Geomagic, AutoCAD & Adams (Out of scope). | Multiple co-hosted application Network License Server |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  | 2021-01-21 | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
18 | Geomagic | PROD | Requalann Pereira | Sri Tupil |  | W4-MG1 | 2021-04-09 | 2021-01-30 | No |  | Risk of delay (amber) | Cohosted with other apps, Req needs to confirm. MAC address binding for Licensing. No vendor support | Shweta | Rahul/Saurabh | MEMSRV236 |  |  | RE-HOST | R&D | R&D | US | 1 | 2 | 02 - Network License Server - Batch 2 | Jan | MG1 | No | Yes | Moderate migration | Low | Moderate Migration | USA | Windows Server 2012 R2 | COTS | NA | Prod | 1 | Server also host Network License Manager for PartMaker, AutoCAD, Flex LM, LIFEMOD BIOMECHANICS SYS (Out of Scope) & Adams (Out of Scope).Mac Address would have to stay the same for the licensing to continue working. If we can't emulate mac address then the server would have to go to DCaaS. | 1) - Server also host Network License Manager for PartMaker, AutoCAD, Flex LM, LIFEMOD BIOMECHANICS SYS (Out of Scope) & Adams (Out of Scope) 2) Mac Address would have to stay the same for the licensing to continue working. If we can't emulate mac address then the server would have to go to DCaaS. | 1) Mac Address would have to stay the same for the licensing to continue working. If we can't emulate mac address then the server would have to go to DCaaS.Also have a confirmation from Microsoft that we cannot retain MAC address while migrating VM to Azure. > we have to stand up a new test VM to test out the Mac address dependency. > During migration if there is any concern with Mac address not working with the license server ,new license need to be occurred from the vendor. > If not then roll back |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  | 2021-01-21 | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
74 | Georgia Softworks | PROD | Krzysztof Gaik | Massimo Trambaioli |  | W5-MG2 | 2021-05-21 | 2021-05-30 | No |  | Not started (grey) |  |  |  | USMAN-SMAPPVW53 |  |  | RE-HOST | ERP | Manufacturing - Warehouse | US | 5 | 14 | 14 - Shop Floor Medium/Complex Application | May | MG1 | No | No | Complex Migration | High | Complex Migration | US SNI Internal | Windows 2012 | COTS | NA | Prod | 8 | VM shared with Proquis Software. | RFID Scanners, SAP | Integration points to be validated |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
79 | Global Data Warehouse | PROD | Sathiamurthy Samidurai | Stuart Robinson |  | W3-MG2 | 2021-03-19 | 2021-03-19 | No |  | Imminent Delay (red) | Decision pending on either DB servers will be consolidated or will have dedicated Cluster in Azure. QA Testing is still pending that ensures the path for a successful migration. | Venkat/Isha | Srikanth Venkatasen | NA | USMANSMDBPUW35(SQL Cluster Address); USMANSMDBPUW31; USMANSMDBPUW32 |  | RE-HOST | Data & Analytics | Data & Analytics | US | 2 | 6 | 6 - Data Warehouse Application | Mar | MG2 | No | No | Moderate Migration | Low | High | USA | Windows Server 2012 | SNI developed | SQL Server 2012 | Dev, Prod | 2 | None | SAP + Oracle | Hybrid model - Connect to SAP Need to clearly layout hybrid strategy so that this application when move to Azure should be able to pull/push data from SAP. Oracle, etc. Documentation and test cases are not available DEV OPS involvement to create one before migration | GDW GMM and Enterprise Business Objects Reports together can be clubbed together in Jan or Feb | Yes | 2020-01-25 | 2021-01-28 | No | 2020-02-08 |  | No |  |  | No |  |  | No |  |  | No |  |  | No | 2021-02-24 |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
79 | Global Data Warehouse | DEV | Sathiamurthy Samidurai | Stuart Robinson |  | W1-MG2 | 2021-01-22 | 2021-01-22 | No |  | Finished (blue) |  |  |  | USMAN-SMAPPVW54 | USMAN-SMAPPVW54 |  | RE-HOST | Data & Analytics | Data & Analytics | US | 2 | 6 | 6 - Data Warehouse Application | Jan | MG2 | No | No | Moderate Migration | Low | High | USA | Windows Server 2012 | SNI developed | SQL Server 2012 | Dev, Prod | 2 | None | SAP + Oracle | Hybrid model - Connect to SAP Need to clearly layout hybrid strategy so that this application when move to Azure should be able to pull/push data from SAP. Oracle, etc. Documentation and test cases are not available DEV OPS involvement to create one before migration | GDW GMM and Enterprise Business Objects Reports together can be clubbed together in Jan or Feb | Done | 2020-12-11 | 2021-01-22 | Yes | 2020-12-30 | 2021-01-22 | No | 2021-01-13 | 2021-01-13 | Yes | 2021-01-04 | 2021-01-04 | Yes | 2021-01-11 | 2021-01-11 | Yes | 2021-01-15 | 2021-01-15 | Yes | 2021-01-08 | 2021-01-08 | Yes | 2021-01-13 | 2021-01-13 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-22 | 2021-01-22 | Yes | 2021-01-24 | 2021-01-24 | Yes | 2021-01-24 | 2021-01-24 | Done, no evidence provided | N/A | N/A | Done, no evidence provided | Done, no evidence provided | N/A | N/A | N/A | N/A | N/A | No | 2021-02-19 |  | Yes | 2021-02-19 | 2021-02-08 | No | 2021-02-19 |  | No | 2021-02-19 |  | No | 2021-02-19
132 | Global Labeling System (PRISYM) | QA | Carla Morris | Derek Spillane |  |  |  | 2021-05-30 | No |  | Not started (grey) | [7 empty] | Manufacturing | Manufacturing | US | [5 empty] | No | Yes |  | High |  | Globally SNI Internal |  |  |  | QA , Prod | [5 empty] | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
132 | Global Labeling System (PRISYM) | PROD | Carla Morris | Derek Spillane |  |  |  | 2021-05-30 | No |  | Not started (grey) | [7 empty] | Manufacturing | Manufacturing | US | [5 empty] | No | Yes |  | High |  | Globally SNI Internal |  |  |  | QA , Prod | [5 empty] | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
80 | Global Market Monitoring | PROD | Sathiamurthy Samidurai | Stuart Robinson |  | W3-MG2 | 2021-03-19 | 2021-03-19 | No |  | Imminent Delay (red) | Decision pending on either DB servers will be consolidated or will have dedicated Cluster in Azure. QA Testing is still pending that ensures the path for a successful migration. | Venkat/Isha | Srikanth Venkatasen | NA | USMANSMDBPUW35(SQL Cluster Address ); USMANSMDBPUW31; USMANSMDBPUW32 |  | RE-HOST | Data & Analytics | Data & Analytics | US | 2 | 6 | 6 - Data Warehouse Application | Mar | MG2 | No | No | Moderate Migration | Low | Medium | USA | Windows Server 2012 R2 Standard | SNI developed | SQL Server 2012 | Dev, Prod | 3 | None | SAP + Oracle | Hybrid model Hybrid strategy implementation Documentation and test cases are not available Create test cases and ensure SME availability during migration |  | Yes | 2020-01-25 | 2021-01-28 | No | 2020-02-08 |  | No |  |  | No |  |  | No |  |  | No |  |  | No | 2021-02-24 |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
80 | Global Market Monitoring | DEV | Sathiamurthy Samidurai | Stuart Robinson |  | W1-MG2 | 2021-01-22 | 2021-01-22 | No |  | Finished (blue) |  |  |  | USMAN-SMAPPVW54 | USMAN-SMAPPVW54 |  | RE-HOST | Data & Analytics | Data & Analytics | US | 2 | 6 | 6 - Data Warehouse Application | Jan | MG2 | No | No | Moderate Migration | Low | Medium | USA | Windows Server 2012 R2 Standard | SNI developed | SQL Server 2012 | Dev, Prod | 3 | None | SAP + Oracle | Hybrid model Hybrid strategy implementation Documentation and test cases are not available Create test cases and ensure SME availability during migration |  | Done | 2020-12-11 | 2021-01-22 | Yes | 2020-12-30 | 2021-01-22 | No | 2021-01-13 | 2021-01-13 | Yes | 2021-01-04 | 2021-01-04 | Yes | 2021-01-11 | 2021-01-11 | Yes | 2021-01-15 | 2021-01-15 | Yes | 2021-01-08 | 2021-01-08 | Yes | 2021-01-13 | 2021-01-13 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-22 | 2021-01-22 | Yes | 2021-01-24 | 2021-01-24 | Yes | 2021-01-24 | 2021-01-24 | Done, no evidence provided | N/A | N/A | Done, no evidence provided | Done, no evidence provided | N/A | N/A | N/A | N/A | N/A | No | 2021-02-19 |  | Yes | 2021-02-19 | 2021-02-08 | No | 2021-02-19 |  | No | 2021-02-19 |  | No | 2021-02-19
60 | Global Regulatory Submissions | DEV | Aileen Diola | Sri Tupil |  | W8-MG1 | 2021-08-06 | 2021-08-30 | No |  | Not started (grey) |  |  |  | USMEM-SMAPDVW26; USMEMSMAPDVW17; USMEMSMAPDVW12; USMEMSMAPDVW13; USMEMSMAPDVW14; USMEMSMAPTVW01; USMEMSMAPDVW15 | USMEMSMDBDUW12; USMEMSMDBDVW07 |  | RE-HOST | RAQA | RAQA | US | 8 | 24 | 11 - US Medium/Complex Application | Aug | MG1 | No | No | Moderate Migration | Low | Need Upgrade before Migration | USA | Enovia – Window Server 2008 R2 Ent, Adlib – Window Server 2012 | COTS | Enovia – Window Server 2008 + Oracle Adlib – Window Serer 2008 + SQL Server 2008 | Dev, Test, Prod | 34 | None | SAP, LORENZ docuBridge, License server, File Share | Retiring in year 2021 Replacing with new platform is under process Documentation and SME/Vendor support Documents are partially available, and SME/vendor support is required during migration IP hard dependency - hardcoding Resolve with local DNS name. if not, validate IP and plan configuration changes accordingly. | Please also note that we have to test this application prior to actual due date, so we need the environment build at least 1 month before the migration due date. Our end-users need enough time to test. | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
60 | Global Regulatory Submissions | QA | Aileen Diola | Sri Tupil |  | W8-MG1 | 2021-08-06 | 2021-08-30 | No |  | Not started (grey) |  |  |  | USMEMSMAPQVW15; USMEMSMAPQVW12; USMEMSMAPQVW08; USMEMSMAPQVW11; USMEMSMLSQUW12; USMEMSMAPQVW09; USMANSMTSPVW01; USMANSMTSPVW02; USMANSMTSPVW03; USMEMSMAPQVW10; | USMEMSMDBDUW12; USMEMSMDBDVW07 |  | RE-HOST | RAQA | RAQA | US | 8 | 24 | 11 - US Medium/Complex Application | Aug | MG1 | No | No | Moderate Migration | Low | Need Upgrade before Migration | USA | Enovia – Window Server 2008 R2 Ent, Adlib – Window Server 2012 | COTS | Enovia – Window Server 2008 + Oracle Adlib – Window Serer 2008 + SQL Server 2008 | Dev, Test, Prod | 34 | None | SAP, LORENZ docuBridge, License server, File Share | Retiring in year 2021 Replacing with new platform is under process Documentation and SME/Vendor support Documents are partially available, and SME/vendor support is required during migration IP hard dependency - hardcoding Resolve with local DNS name. if not, validate IP and plan configuration changes accordingly. | Please also note that we have to test this application prior to actual due date, so we need the environment build at least 1 month before the migration due date. Our end-users need enough time to test. | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
60 | Global Regulatory Submissions | PROD | Aileen Diola | Sri Tupil |  | W8-MG2 | 2021-08-20 | 2021-08-30 | No |  | Not started (grey) |  |  |  | USMAN-SMAPPVW41; USMAN-SMAPPVW42; USMAN-SMAPPVW43; USMANSMAPPVW26; USMANSMAPPVW28; USMANSMAPPVW29; USMANSMAPPW06; USMANSMAPPVW27; UKRTHSMAPPVW14; USMEMSMAPPVW01 | USMANSMDBPVW23; USMANSMDBPW08 |  | RE-HOST | RAQA | RAQA | US | 8 | 24 | 11 - US Medium/Complex Application | Aug | MG1 | No | No | Moderate Migration | Low | Need Upgrade before Migration | USA | Enovia – Window Server 2008 R2 Ent, Adlib – Window Server 2012 | COTS | Enovia – Window Server 2008 + Oracle Adlib – Window Serer 2008 + SQL Server 2008 | Dev, Test, Prod | 34 | None | SAP, LORENZ docuBridge, License server, File Share | Retiring in year 2021 Replacing with new platform is under process Documentation and SME/Vendor support Documents are partially available, and SME/vendor support is required during migration IP hard dependency - hardcoding Resolve with local DNS name. if not, validate IP and plan configuration changes accordingly. | Please also note that we have to test this application prior to actual due date, so we need the environment build at least 1 month before the migration due date. Our end-users need enough time to test. | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
13 | Global Returns Disposition Tool | PROD | Andres Bernard | Firas Almahamid |  | W3-MG1 | 2021-03-05 | 2021-03-05 | No |  | On track (green) |  | Raju Pottella | Rahul Sarin | USMAN-SMWSPVW12 | USMAN-SMDBPVW12 | USAZRSMDBPVW02, USAZRSMDBPVW03 | RE-HOST(App)/RE-PLATFORM(DB) | Commercial | Commercial | US | 1 | 3 | 03 - SNI Developed + Co-Hosted Apps | Jan | MG2 | No | No | Simple Migration | Low | Easy Migration | USA | Windows Server 2012 R2 Standard | SNI developed | SQL Server 2012 R2 | Dev, Test, Prod | 6 | SNID Archived shipping documents ECAP ENCORE EndoLoans HR Notification GSC Datawarehouse Admin Tool Inventures Web App Nomino Security QA Change Control Recon LaunchPad(SSO) Reimbursement Sales Request Forms Non-Employee Database | Shared server with other apps. SNID Archived Shipping Documents, GSC Data Warehouse Admin Tool, Non-Employee Database, Nomino Security, Recon LaunchPad (SSO), Reimbursement, Sales Request Forms | IP Dependency Do configuration for IP changes Documentation and test cases are not available SNI prepare test cases and ensure SME availability |  | Yes | 2020-01-25 | 2021-01-28 | Yes | 2020-02-08 | 2020-02-10 | Yes | 2021-02-08 | 2020-02-10 | No |  |  | No |  |  | No |  |  | Yes | 2021-02-10 | 2021-02-11 | Yes | 2021-02-17 | 2021-02-17 | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
13 | Global Returns Disposition Tool | DEV | Andres Bernard | Firas Almahamid |  | W1-MG2 | 2021-01-22 | 2021-01-22 | No |  | Finished (blue) |  |  |  | USMAN-SMWSDVW07 | USMAN-SMDPDVW16 | USAZRSMDBDVW02 | RE-HOST(App)/RE-PLATFORM(DB) | Commercial | Commercial | US | 1 | 3 | 03 - SNI Developed + Co-Hosted Apps | Jan | MG2 | No | No | Simple Migration | Low | Easy Migration | USA | Windows Server 2012 R2 Standard | SNI developed | SQL Server 2012 R2 | Dev, Test, Prod | 6 | SNID Archived shipping documents ECAP ENCORE EndoLoans HR Notification GSC Datawarehouse Admin Tool Inventures Web App Nomino Security QA Change Control Recon LaunchPad(SSO) Reimbursement Sales Request Forms Non-Employee Database | Shared server with other apps. SNID Archived Shipping Documents, GSC Data Warehouse Admin Tool, Non-Employee Database, Nomino Security, Recon LaunchPad (SSO), Reimbursement, Sales Request Forms | IP Dependency Do configuration for IP changes Documentation and test cases are not available SNI prepare test cases and ensure SME availability |  | Done | 2020-12-11 | 2020-12-11 | Yes | 2020-12-30 | 2021-01-22 | No | 2021-01-13 | 2021-01-13 | Yes | 2021-01-04 | 2021-01-04 | Yes | 2021-01-11 | 2021-01-11 | Yes | 2021-01-15 | 2021-01-15 | Yes | 2021-01-08 | 2021-01-08 | Yes | 2021-01-13 | 2021-01-13 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-22 | 2021-01-22 | Yes | 2021-01-24 | 2021-01-24 | Yes | 2021-01-24 | 2021-01-24 | Done, no evidence provided | N/A | N/A | Done, no evidence provided | Done, no evidence provided | N/A | N/A | N/A | N/A | N/A | No | 2021-02-19 |  | Yes | 2021-02-19 | 2021-02-08 | No | 2021-02-19 |  | No | 2021-02-19 |  | No | 2021-02-19
13 | Global Returns Disposition Tool | QA | Andres Bernard | Firas Almahamid |  | W1-MG2 | 2021-01-22 | 2021-01-22 | No |  | Finished (blue) |  |  |  | USMAN-SMWSQVW05 | USMAN-SMDPDVW16 | USAZRSMDBQVW01 | RE-HOST(App)/RE-PLATFORM(DB) | Commercial | Commercial | US | 1 | 3 | 03 - SNI Developed + Co-Hosted Apps | Jan | MG2 | No | No | Simple Migration | Low | Easy Migration | USA | Windows Server 2012 R2 Standard | SNI developed | SQL Server 2012 R2 | Dev, Test, Prod | 6 | SNID Archived shipping documents ECAP ENCORE EndoLoans HR Notification GSC Datawarehouse Admin Tool Inventures Web App Nomino Security QA Change Control Recon LaunchPad(SSO) Reimbursement Sales Request Forms Non-Employee Database | Shared server with other apps. SNID Archived Shipping Documents, GSC Data Warehouse Admin Tool, Non-Employee Database, Nomino Security, Recon LaunchPad (SSO), Reimbursement, Sales Request Forms | IP Dependency Do configuration for IP changes Documentation and test cases are not available SNI prepare test cases and ensure SME availability |  | Done | 2020-12-11 | 2020-12-11 | Yes | 2020-12-30 | 2021-01-22 | No | 2021-01-13 | 2021-01-13 | Yes | 2021-01-04 | 2021-01-04 | Yes | 2021-01-11 | 2021-01-11 | Yes | 2021-01-15 | 2021-01-15 | Yes | 2021-01-08 | 2021-01-08 | Yes | 2021-01-13 | 2021-01-13 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-22 | 2021-01-22 | Yes | 2021-01-24 | 2021-01-24 | Yes | 2021-01-24 | 2021-01-24 | Done, no evidence provided | N/A | N/A | Done, no evidence provided | Done, no evidence provided | N/A | N/A | N/A | N/A | N/A | No | 2021-02-19 |  | Yes | 2021-02-19 | 2021-02-08 | No | 2021-02-19 |  | No | 2021-02-19 |  | No | 2021-02-19
14 | GSC Data Warehouse Admin Tool | DEV | Amit Shokeen | Massimo Trambaioli |  | W1-MG2 | 2021-01-22 | 2021-01-22 | No |  | Finished (blue) |  |  |  | USMAN-SMWSDVW07 | USMAN-SMAPPVW54 |  | RE-HOST | Data & Analytics | Data & Analytics | US | 1 | 3 | 03 - SNI Developed + Co-Hosted Apps | Jan | MG2 | No | No | Moderate Migration | Low | Moderate Migration | USA | Windows Server 2012 R2 Standard | SNI developed | SQL Server 2012 R2 | Dev, Test, Prod | 3 | SNID Archived shipping documents ECAP ENCORE EndoLoans HR Notification Global Returns Disposition Tool Inventures Web App Nomino Security QA Change Control Recon LaunchPad(SSO) Reimbursement Sales Request Forms Non-Employee Database | Sharing server with SNID Archived Shipping Documents application | Server sharing with SNID Archived Shipping Documents app Plan to migrate in same move group Legacy technology – asp classic 3.0 Replacing with new platform (Cognos TM1) is under process, tentative by 2021 Documentation and testing Create test cases and deployment documents before migration Hardcoded Database connection Plan to change hardcoded database connection info. |  | Done | 2020-12-11 | 2020-12-11 | Yes | 2020-12-30 | 2021-01-22 | No | 2021-01-13 | 2021-01-13 | Yes | 2021-01-04 | 2021-01-04 | Yes | 2021-01-11 | 2021-01-11 | Yes | 2021-01-15 | 2021-01-15 | Yes | 2021-01-08 | 2021-01-08 | Yes | 2021-01-13 | 2021-01-13 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-22 | 2021-01-22 | Yes | 2021-01-24 | 2021-01-24 | Yes | 2021-01-24 | 2021-01-24 | Done, no evidence provided | N/A | N/A | Done, no evidence provided | Done, no evidence provided | N/A | N/A | N/A | N/A | N/A | No | 2021-02-19 |  | Yes | 2021-02-19 | 2021-02-08 | No | 2021-02-19 |  | No | 2021-02-19 |  | Yes | 2021-02-19 | 2021-02-16
14 | GSC Data Warehouse Admin Tool | PROD | Amit Shokeen | Massimo Trambaioli |  | W3-MG1 | 2021-03-05 | 2021-03-05 | No |  | On track (green) |  | Raju Pottella | Rahul Sarin | USMAN-SMWSPVW12 | UKRTH-SMDBPVW32 |  | RE-HOST | Data & Analytics | Data & Analytics | US | 1 | 3 | 03 - SNI Developed + Co-Hosted Apps | Jan | MG2 | No | No | Moderate Migration | Low | Moderate Migration | USA | Windows Server 2012 R2 Standard | SNI developed | SQL Server 2012 R2 | Dev, Test, Prod | 3 | SNID Archived shipping documents ECAP ENCORE EndoLoans HR Notification Global Returns Disposition Tool Inventures Web App Nomino Security QA Change Control Recon LaunchPad(SSO) Reimbursement Sales Request Forms Non-Employee Database | Sharing server with SNID Archived Shipping Documents application | Server sharing with SNID Archived Shipping Documents app Plan to migrate in same move group Legacy technology – asp classic 3.0 Replacing with new platform (Cognos TM1) is under process, tentative by 2021 Documentation and testing Create test cases and deployment documents before migration Hardcoded Database connection Plan to change hardcoded database connection info. |  | Yes | 2020-01-25 | 2021-01-28 | Yes | 2020-02-08 | 2020-02-10 | Yes | 2021-02-08 | 2020-02-10 | No |  |  | No |  |  | No |  |  | Yes | 2021-02-10 | 2021-02-11 | Yes | 2021-02-17 | 2021-02-17 | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
125 | HR Notification | DEV | Paul Davison | Chris Cook |  | PW-MG2 | 2020-11-12 | 2020-11-12 | No |  | Finished (blue) |  |  |  | USMAN-SMWSDVW07 | USMAN-SMDPDVW16 |  | RE-PLATFORM | Group Functions | Group Functions | US | Pilot | Pilot | 00 - Pilot | Nov | MG1 | No | No | Simple | Low | Easy Migration | Memphis facility, US | Windows Server 2012 | SNI Dev'ed | Sql Server 2012 | 1 for PROD APP, 1 for PROD DB, 1 for Dev APP, 1 for Dev DB,1 for TEST APP and 1 for TEST DB | 6 | SNID Archived shipping documents ECAP ENCORE EndoLoans Global Return Disposition Tool GSC Datawarehouse Admin Tool Inventures Web App Nomino Security QA Change Control Recon LaunchPad(SSO) Reimbursement Sales Request Forms Non-Employee Database | NA | App and DB servers are shared across other applications in SNI, IP Address Change – Hardcoding |  | Done | 2020-10-05 | 2020-10-05 | Yes | 2020-10-26 | 2020-10-26 | Yes | 2020-10-26 | 2020-10-26 | Yes | 2020-10-26 | 2020-10-26 | Yes | 2020-11-02 | 2020-11-02 | Yes | 2020-11-06 | 2020-11-06 | Yes | 2020-10-30 | 2020-10-30 | Yes | 2020-11-02 | 2020-11-02 | Yes | 2020-11-12 | 2020-11-12 | Yes | 2020-11-12 | 2020-11-12 | Yes | 2020-11-13 | 2020-11-13 | Yes | 2020-11-15 | 2020-11-15 | Yes | 2020-11-15 | 2020-11-15 | Done, no evidence provided | N/A | N/A | Done, no evidence provided | Done, no evidence provided | N/A | N/A | N/A | N/A | N/A | Yes | 2020-12-11 | 2021-01-02 | Yes | 2020-12-11 | 2021-02-08 | No | 2020-12-11 |  | No | 2020-12-11 |  | Yes | 2020-12-11 | 2021-01-13
125 | HR Notification | QA | Paul Davison | Chris Cook |  | PW-MG2 | 2020-11-12 | 2020-11-12 | No |  | Finished (blue) |  |  |  | USMAN-SMWSQVW05 | USMAN-SMDPDVW16 |  | RE-PLATFORM | Group Functions | Group Functions | US | Pilot | Pilot | 00 - Pilot | Nov | MG1 | No | No | Simple | Low | Easy Migration | Memphis facility, US | Windows Server 2012 | SNI Dev'ed | Sql Server 2012 | 1 for PROD APP, 1 for PROD DB, 1 for Dev APP, 1 for Dev DB,1 for TEST APP and 1 for TEST DB | 6 | SNID Archived shipping documents ECAP ENCORE EndoLoans Global Return Disposition Tool GSC Datawarehouse Admin Tool Inventures Web App Nomino Security QA Change Control Recon LaunchPad(SSO) Reimbursement Sales Request Forms Non-Employee Database | NA | App and DB servers are shared across other applications in SNI, IP Address Change – Hardcoding |  | Done | 2020-10-05 | 2020-10-05 | Yes | 2020-10-26 | 2020-10-26 | Yes | 2020-10-26 | 2020-10-26 | Yes | 2020-10-26 | 2020-10-26 | Yes | 2020-11-02 | 2020-11-02 | Yes | 2020-11-06 | 2020-11-06 | Yes | 2020-10-30 | 2020-10-30 | Yes | 2020-11-02 | 2020-11-02 | Yes | 2020-11-12 | 2020-11-12 | Yes | 2020-11-12 | 2020-11-12 | Yes | 2020-11-13 | 2020-11-13 | Yes | 2020-11-15 | 2020-11-15 | Yes | 2020-11-15 | 2020-11-15 | Done, no evidence provided | N/A | N/A | Done, no evidence provided | Done, no evidence provided | N/A | N/A | N/A | N/A | N/A | Yes | 2020-12-11 | 2021-01-02 | Yes | 2020-12-11 | 2021-02-08 | No | 2020-12-11 |  | No | 2020-12-11 |  | Yes | 2020-12-11 | 2021-01-13
125 | HR Notification | PROD | Paul Davison | Chris Cook |  | PW-MG4 | 2020-12-04 | 2020-12-04 | No |  | Finished (blue) |  |  |  | USMAN-SMWSPVW12 | USMAN-SMDBPVW12 |  | RE-PLATFORM | Group Functions | Group Functions | US | Pilot | Pilot | 00 - Pilot | Nov | MG1 | No | No | Simple | Low | Easy Migration | Memphis facility, US | Windows Server 2012 | SNI Dev'ed | Sql Server 2012 | 1 for PROD APP, 1 for PROD DB, 1 for Dev APP, 1 for Dev DB,1 for TEST APP and 1 for TEST DB | 6 | SNID Archived shipping documents ECAP ENCORE EndoLoans Global Return Disposition Tool GSC Datawarehouse Admin Tool Inventures Web App Nomino Security QA Change Control Recon LaunchPad(SSO) Reimbursement Sales Request Forms Non-Employee Database | NA | App and DB servers are shared across other applications in SNI, IP Address Change – Hardcoding |  | Done | 2020-10-05 | 2020-10-05 | Yes | 2020-11-17 | 2020-11-17 | Yes | 2020-11-17 | 2020-11-17 | Yes | 2020-11-17 | 2020-11-17 | Yes | 2020-11-24 | 2020-11-24 | Yes | 2020-11-28 | 2020-11-28 | Yes | 2020-11-21 | 2020-11-21 | Yes | 2020-11-24 | 2020-11-24 | Yes | 2020-12-04 | 2020-12-04 | Yes | 2020-12-04 | 2020-12-04 | Yes | 2020-12-05 | 2020-12-05 | Yes | 2020-12-07 | 2020-12-07 | Yes | 2020-12-07 | 2020-12-07 | Done, no evidence provided | N/A | N/A | Done, no evidence provided | Done, no evidence provided | N/A | N/A | N/A | N/A | N/A | Yes | 2021-01-02 | 2021-01-02 | Yes | 2021-01-02 | 2021-02-08 | No | 2021-01-02 |  | No | 2021-01-02 |  | Yes | 2021-01-02 | 2021-01-13
64 | Hydra (Tuttlingen) | DEV | Aileen Diola | Sri Tupil |  | W4-MG1 | 2021-04-09 | 2021-04-09 | No |  | Risk of delay (amber) | Yvonne to set up the meeting with Vendor this week | Vidit | Srikanth/Rajesh | UKRTHSMAPDVW01; | UKRTHSMAPDVW01 |  | RE-HOST | RAQA | RAQA | EMEA | 4 | 10 | 10 - Full Throttle EMEA Application - Batch 2 | Apr | MG2 | No | Yes | Easy Migration | High | Moderate migration | Germany | Windows Server 2012 R2 Standard (6.2.9200) for Prod both App and DB & Windows Server 2012 R2 Standard (6.3.9600) for Test/Dev | Vendor Developed Application | MS SQL Server 2012 | Test/Dev/Prod | 4 | NA | Windows Server 2012 R2 for both .NET FW 4.5.2 App and MS SQL 2012 DB. 9. External Integration to BAS AS 400 System. Interface to BAS in every 5 mins. | New module CAQ will be implemented during 2020. Number of transactions is not known yet. This can trigger increment in traffic and may require additional capacity.Latency Issues b/w Terminals & Server. Performance issue with the line connectivity between terminals and server post azure migration. This needs to be tested, working closely with the vendor during Migration Phase. Latency with BAS AS400 to be validated. External Systems BAS AS400 This needs to be validated, if application migration wont impact any connections with BAS system. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
64 | Hydra (Tuttlingen) | PROD | Aileen Diola | Sri Tupil |  | W4-MG2 | 2021-04-23 | 2021-04-23 | No |  | Risk of delay (amber) | Yvonne to set up the meeting with Vendor this week | Vidit | Srikanth/Rajesh | UKRTHSMAPPVW01 | UKRTHSMDBPVW04 |  | RE-HOST | RAQA | RAQA | EMEA | 4 | 10 | 10 - Full Throttle EMEA Application - Batch 2 | Apr | MG2 | No | Yes | Easy Migration | High | Moderate migration | Germany | Windows Server 2012 R2 Standard (6.2.9200) for Prod both App and DB & Windows Server 2012 R2 Standard (6.3.9600) for Test/Dev | Vendor Developed Application | MS SQL Server 2012 | Test/Dev/Prod | 4 | NA | Windows Server 2012 R2 for both .NET FW 4.5.2 App and MS SQL 2012 DB. 9. External Integration to BAS AS 400 System. Interface to BAS in every 5 mins. | New module CAQ will be implemented during 2020. Number of transactions is not known yet. This can trigger increment in traffic and may require additional capacity.Latency Issues b/w Terminals & Server. Performance issue with the line connectivity between terminals and server post azure migration. This needs to be tested, working closely with the vendor during Migration Phase. Latency with BAS AS400 to be validated. External Systems BAS AS400 This needs to be validated, if application migration wont impact any connections with BAS system. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
36 | ID Prove | PROD | Yvonne Braun | Massimo Trambaioli | X | W5-MG1 | 2021-05-07 | 2021-05-07 | No |  | Not started (grey) | Propose to move to April 23rd |  |  | DETUTSMAPPW02 | DETUTSMAPPW02 | EUAZRSMDBPVW01, EUAZRSMDBPVW02 | RE-HOST(App)/RE-PLATFORM(DB) | Supply Chain | Supply Chain | EMEA | 2 | 5 | 05 - Simple/Medium Apps | Feb | MG1 | No | No | Medium | Medium | Low | Tuttlingen, Germany | Windows Server 2012 R2 Standard | COTS | Sql Server 2012 R2 | Prod | 1 | None | None | IP Address changes |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
29 | InfinityQS ProFicient (SPC software) | PROD | Aileen Diola | Sri Tupil |  |  | 2021-02-28 | 2021-02-28 | Yes | Both servers are scheduled for Decom as per SDM by end of this year. | Out of scope (dark grey) | [7 empty] | RAQA | RAQA | US, EMEA | 2 | 5 | 05 - Simple/Medium Apps | Feb | MG1 | No | No | Simple | Medium | Simple | Memphis, US | Windows Server 2016 Standard | COTS | Sql Server 2012 Express | PROD | 2 | None | NA | Compatibility of MS Access 32bit |  | No |  |  | Yes |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Yes |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
92 | Informatica (Wound Data Intergration) | PROD | Sathiamurthy Samidurai | Stuart Robinson |  | W3-MG2 | 2021-03-19 | 2021-03-05 | No |  | On track (green) |  | Venkat/Isha | Srikanth Venkatasen | NLAMSSMAPPVW21 | UKRTH-SMDBPVW32 |  | RE-HOST | Data & Analytics | Data & Analytics, ETA Tool | US | 1 | 3 | 03 - SNI Developed + Co-Hosted Apps | Mar | MG2 | No | No | Complex Migration | High | Simple | US, EUC | Windows Server 2012 R2 | COTS | Sql Server 2012 | PROD, DEV | 4 | Informatica (SoNAR Data Intergration), Cognos BI (Complaints Analytics), AWM Data Warehouse, GSC Data Warehouse Admin Tool, Global Data Warehouse, Enterprise Business Objects Reporting | Integration with P360 and will be with C360. Co-hosted application on the server(s). Data shared between IDQ and GBIP application. | Risks identified for Year End reporting ,Co-host dependent application. |  | Yes | 2020-01-25 | 2021-01-28 | No | 2020-02-08 |  | No |  |  | No |  |  | No |  |  | No |  |  | No | 2021-02-10 |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
92 | Informatica (Wound Data Intergration) | DEV | Sathiamurthy Samidurai | Stuart Robinson |  | W1-MG2 | 2021-01-22 | 2021-01-22 | No |  | Finished (blue) |  |  |  | NLAMSSMAPPVW21 | USMAN-SMAPPVW54 |  | RE-HOST | Data & Analytics | Data & Analytics, ETA Tool | US | 1 | 3 | 03 - SNI Developed + Co-Hosted Apps | Jan | MG2 | No | No | Complex Migration | High | Simple | US, EUC | Windows Server 2012 R2 | COTS | Sql Server 2012 | PROD, DEV | 4 | Informatica (SoNAR Data Intergration), Cognos BI (Complaints Analytics), AWM Data Warehouse, GSC Data Warehouse Admin Tool, Global Data Warehouse, Enterprise Business Objects Reporting | Integration with P360 and will be with C360. Co-hosted application on the server(s). Data shared between IDQ and GBIP application. | Risks identified for Year End reporting ,Co-host dependent application. |  | Done | 2020-12-11 | 2021-01-22 | Yes | 2020-12-30 | 2021-01-22 | No | 2021-01-13 | 2021-01-13 | Yes | 2021-01-04 | 2021-01-04 | Yes | 2021-01-11 | 2021-01-11 | Yes | 2021-01-15 | 2021-01-15 | Yes | 2021-01-08 | 2021-01-08 | Yes | 2021-01-13 | 2021-01-13 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-22 | 2021-01-22 | Yes | 2021-01-24 | 2021-01-24 | Yes | 2021-01-24 | 2021-01-24 | Done, no evidence provided | N/A | N/A | Done, no evidence provided | Done, no evidence provided | N/A | N/A | N/A | N/A | N/A | No | 2021-02-19 |  | Yes | 2021-02-19 | 2021-02-08 | No | 2021-02-19 |  | No | 2021-02-19 |  | No | 2021-02-19
93 | Informatica MDM Data Quality | DEV | Sathiamurthy Samidurai | Stuart Robinson |  | W4-MG1 | 2021-04-09 | 2021-01-30 | No |  | Risk of delay (amber) | On Prem upgrade expereinced issues | Venkat/Isha/Shirisha | Praveen | USMEMSMAPDVL13 | USMEM-SMDBDVL10 |  | RE-PLATFORM | Data & Analytics | Data & Analytics, Quality Tool | US | 1 | 4 | 4 - Complex Application Group | Jan | MG2 | No | No | Complex Migration | High | Complex Migration | SNI Internal Globally | Linux Red Hat 6.10/6.7 Enterprise | COTS | Oracle 12.1c | PROD, DEV, TEST, QA & EVL | 5 | Informatica P360 Informatica MDM Data Quality Cognos BI (Complaints Analytics) Informatica (SoNAR Data Intergration) | Integration with P360 and will be with C360. Co-hosted application on the server(s). Data shared between IDQ and GBIP application. | DB data shared with other Informatica Apps. , Co-host dependent application ,Oracle DB is old version and it is shared with other Informatica Apps. |  | Yes | 2020-12-23 | 2020-12-23 | Yes | 2021-01-29 | 2021-01-29 | No |  |  | Yes |  | 2021-01-18 | Yes |  | 2021-01-25 | Yes |  | 2021-01-29 | Yes | 2021-01-29 | 2021-01-29 | Yes | 2021-02-03 | 2021-02-03 | No | 2021-02-19 | 2021-02-19 | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
93 | Informatica MDM Data Quality | TEST | Sathiamurthy Samidurai | Stuart Robinson |  | W4-MG1 | 2021-04-09 | 2021-01-30 | No |  | Risk of delay (amber) | On Prem upgrade expereinced issues | Venkat/Isha/Shirisha | Praveen | USMEMSMAPTVL15 | USMEMSMAPTVL15 |  | RE-PLATFORM | Data & Analytics | Data & Analytics, Quality Tool | US | 1 | 4 | 4 - Complex Application Group | Jan | MG2 | No | No | Complex Migration | High | Complex Migration | SNI Internal Globally | Linux Red Hat 6.10/6.7 Enterprise | COTS | Oracle 12.1c | PROD, DEV, TEST, QA & EVL | 5 | Informatica P360 Informatica MDM Data Quality Cognos BI (Complaints Analytics) Informatica (SoNAR Data Intergration) | Integration with P360 and will be with C360. Co-hosted application on the server(s). Data shared between IDQ and GBIP application. | DB data shared with other Informatica Apps. , Co-host dependent application ,Oracle DB is old version and it is shared with other Informatica Apps. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  | 2021-01-21 | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
93 | Informatica MDM Data Quality | QA | Sathiamurthy Samidurai | Stuart Robinson |  | W4-MG1 | 2021-04-09 | 2021-01-30 | No |  | Risk of delay (amber) | On Prem upgrade expereinced issues | Venkat/Isha/Shirisha | Praveen | USATLSMAPQPL04 | USATLSMAPQPL04 |  | RE-PLATFORM | Data & Analytics | Data & Analytics, Quality Tool | US | 1 | 4 | 4 - Complex Application Group | Jan | MG2 | No | No | Complex Migration | High | Complex Migration | SNI Internal Globally | Linux Red Hat 6.10/6.7 Enterprise | COTS | Oracle 12.1c | PROD, DEV, TEST, QA & EVL | 5 | Informatica P360 Informatica MDM Data Quality Cognos BI (Complaints Analytics) Informatica (SoNAR Data Intergration) | Integration with P360 and will be with C360. Co-hosted application on the server(s). Data shared between IDQ and GBIP application. | DB data shared with other Informatica Apps. , Co-host dependent application ,Oracle DB is old version and it is shared with other Informatica Apps. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
93 | Informatica MDM Data Quality | EVL | Sathiamurthy Samidurai | Stuart Robinson |  |  | 2021-04-09 | 2021-01-30 | Yes | EVL out of scope | Out of scope (dark grey) |  |  |  | USMEMSMAPEVL16 | USMEMSMAPEVL16 |  | RE-PLATFORM | Data & Analytics | Data & Analytics, Quality Tool | US | 1 | 4 | 4 - Complex Application Group | Jan | MG2 | No | No | Complex Migration | High | Complex Migration | SNI Internal Globally | Linux Red Hat 6.10/6.7 Enterprise | COTS | Oracle 12.1c | PROD, DEV, TEST, QA & EVL | 5 | Informatica P360 Informatica MDM Data Quality Cognos BI (Complaints Analytics) Informatica (SoNAR Data Intergration) | Integration with P360 and will be with C360. Co-hosted application on the server(s). Data shared between IDQ and GBIP application. | DB data shared with other Informatica Apps. , Co-host dependent application ,Oracle DB is old version and it is shared with other Informatica Apps. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
93 | Informatica MDM Data Quality | PROD | Sathiamurthy Samidurai | Stuart Robinson |  | W5-MG2 | 2021-05-21 | 2021-01-30 | No |  | Not started (grey) |  |  |  | USATLSMAPPPL04 | USATLSMAPPPL04 |  | RE-PLATFORM | Data & Analytics | Data & Analytics, Quality Tool | US | 1 | 4 | 4 - Complex Application Group | Jan | MG2 | No | No | Complex Migration | High | Complex Migration | SNI Internal Globally | Linux Red Hat 6.10/6.7 Enterprise | COTS | Oracle 12.1c | PROD, DEV, TEST, QA & EVL | 5 | Informatica P360 Informatica MDM Data Quality Cognos BI (Complaints Analytics) Informatica (SoNAR Data Intergration) | Integration with P360 and will be with C360. Co-hosted application on the server(s). Data shared between IDQ and GBIP application. | DB data shared with other Informatica Apps. , Co-host dependent application ,Oracle DB is old version and it is shared with other Informatica Apps. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
88 | Informatica P360 | DEV | Sathiamurthy Samidurai | Stuart Robinson |  | W4-MG1 | 2021-04-09 | 2021-01-30 | No |  | Risk of delay (amber) | On Prem upgrade expereinced issues | Venkat/Isha/Shirisha | Praveen | USMEMSMAPDVL13 | USMEM-SMDBDVL10 |  | RE-PLATFORM | Data & Analytics | Data Exchange | US | 1 | 4 | 4 - Complex Application Group | Jan | MG2 | No | Yes | Complex Migration | High | Complex Migration | Globally SNI Internal | Linux 6.10 & Linux 6.7 | COTS | Oracle 12c | 2 PROD Server: USATLSMAPPPL04 USATL-SMDBPUL02 2 QA Server: USATLSMAPQPL04, USATL-SMDBQUL02 2 TEST Server: USMEMSMAPTVL15, USMEM-SMDBTVL12, 2 DEV Server: USMEM-SMAPPDVL1, USMEM-SMDBDVL10 2 EVL Server: USMEMSMAPEVL16, USMEM-SMDBEVL13 | 10 | - Integration with GHX & Logility (Indirect integration with SAP PR1). SAP PR1 > Logility DI > P360 > GHX - Co-hosted application on the server(s).- Data shared between IDQ and GBIP application. | MDM, Logility, SAP, GHX | COTS version upgrade |  | Yes | 2020-12-23 | 2020-12-23 | Yes | 2021-01-29 | 2021-01-29 | No |  |  | Yes |  | 2021-01-18 | Yes |  | 2021-01-25 | Yes |  | 2021-01-29 | Yes | 2021-01-29 | 2021-01-29 | Yes | 2021-02-03 | 2021-02-03 | No | 2021-02-19 | 2021-02-19 | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
88 | Informatica P360 | TEST | Sathiamurthy Samidurai | Stuart Robinson |  | W4-MG1 | 2021-04-09 | 2021-01-30 | No |  | Risk of delay (amber) | On Prem upgrade expereinced issues | Venkat/Isha/Shirisha | Praveen | USMEMSMAPTVL15 | USMEM-SMDBTVL12 |  | RE-PLATFORM | Data & Analytics | Data Exchange | US | 1 | 4 | 4 - Complex Application Group | Jan | MG2 | No | Yes | Complex Migration | High | Complex Migration | Globally SNI Internal | Linux 6.10 & Linux 6.7 | COTS | Oracle 12c | 2 PROD Server: USATLSMAPPPL04 USATL-SMDBPUL02 2 QA Server: USATLSMAPQPL04, USATL-SMDBQUL02 2 TEST Server: USMEMSMAPTVL15, USMEM-SMDBTVL12, 2 DEV Server: USMEM-SMAPPDVL1, USMEM-SMDBDVL10 2 EVL Server: USMEMSMAPEVL16, USMEM-SMDBEVL13 | 10 | - Integration with GHX & Logility (Indirect integration with SAP PR1). SAP PR1 > Logility DI > P360 > GHX - Co-hosted application on the server(s).- Data shared between IDQ and GBIP application. | MDM, Logility, SAP, GHX | COTS version upgrade |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  | 2021-01-21 | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
88 | Informatica P360 | QA | Sathiamurthy Samidurai | Stuart Robinson |  | W4-MG1 | 2021-04-09 | 2021-01-30 | No |  | Risk of delay (amber) | On Prem upgrade expereinced issues | Venkat/Isha/Shirisha | Praveen | USATLSMAPQPL04 | USATL-SMDBQUL02 |  | RE-PLATFORM | Data & Analytics | Data Exchange | US | 1 | 4 | 4 - Complex Application Group | Jan | MG2 | No | Yes | Complex Migration | High | Complex Migration | Globally SNI Internal | Linux 6.10 & Linux 6.7 | COTS | Oracle 12c | 2 PROD Server: USATLSMAPPPL04 USATL-SMDBPUL02 2 QA Server: USATLSMAPQPL04, USATL-SMDBQUL02 2 TEST Server: USMEMSMAPTVL15, USMEM-SMDBTVL12, 2 DEV Server: USMEM-SMAPPDVL1, USMEM-SMDBDVL10 2 EVL Server: USMEMSMAPEVL16, USMEM-SMDBEVL13 | 10 | - Integration with GHX & Logility (Indirect integration with SAP PR1). SAP PR1 > Logility DI > P360 > GHX - Co-hosted application on the server(s).- Data shared between IDQ and GBIP application. | MDM, Logility, SAP, GHX | COTS version upgrade |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  | 2021-01-21 | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
88 | Informatica P360 | EVL | Sathiamurthy Samidurai | Stuart Robinson |  |  | 2021-04-09 | 2021-01-30 | Yes | EVL out of scope | Out of scope (dark grey) |  |  |  | USMEMSMAPEVL16 | USMEM-SMDBEVL13 |  | RE-PLATFORM | Data & Analytics | Data Exchange | US | 1 | 4 | 4 - Complex Application Group | Jan | MG2 | No | Yes | Complex Migration | High | Complex Migration | Globally SNI Internal | Linux 6.10 & Linux 6.7 | COTS | Oracle 12c | 2 PROD Server: USATLSMAPPPL04 USATL-SMDBPUL02 2 QA Server: USATLSMAPQPL04, USATL-SMDBQUL02 2 TEST Server: USMEMSMAPTVL15, USMEM-SMDBTVL12, 2 DEV Server: USMEM-SMAPPDVL1, USMEM-SMDBDVL10 2 EVL Server: USMEMSMAPEVL16, USMEM-SMDBEVL13 | 10 | - Integration with GHX & Logility (Indirect integration with SAP PR1). SAP PR1 > Logility DI > P360 > GHX - Co-hosted application on the server(s).- Data shared between IDQ and GBIP application. | MDM, Logility, SAP, GHX | COTS version upgrade |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  | 2021-01-21 | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
88 | Informatica P360 | PROD | Sathiamurthy Samidurai | Stuart Robinson |  | W5-MG2 | 2021-05-21 | 2021-01-30 | No |  | Not started (grey) |  |  |  | USATLSMAPPPL04 | USATL-SMDBPUL02 |  | RE-PLATFORM | Data & Analytics | Data Exchange | US | 1 | 4 | 4 - Complex Application Group | Jan | MG2 | No | Yes | Complex Migration | High | Complex Migration | Globally SNI Internal | Linux 6.10 & Linux 6.7 | COTS | Oracle 12c | 2 PROD Server: USATLSMAPPPL04 USATL-SMDBPUL02 2 QA Server: USATLSMAPQPL04, USATL-SMDBQUL02 2 TEST Server: USMEMSMAPTVL15, USMEM-SMDBTVL12, 2 DEV Server: USMEM-SMAPPDVL1, USMEM-SMDBDVL10 2 EVL Server: USMEMSMAPEVL16, USMEM-SMDBEVL13 | 10 | - Integration with GHX & Logility (Indirect integration with SAP PR1). SAP PR1 > Logility DI > P360 > GHX - Co-hosted application on the server(s).- Data shared between IDQ and GBIP application. | MDM, Logility, SAP, GHX | COTS version upgrade |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  | 2021-01-21 | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
90 | Inventures (SCAMPI) Web App | PROD | Ian Bennett | Sri Tupil |  | W3-MG1 | 2021-03-05 | 2021-06-30 | No |  | Imminent Delay (red) | Network and Security Changes are pending to enable access to App from Internet and Intranet. | Deepak Sathya Babu | Rahul Sarin | USMEMSMAPPVW23;USMAN-SMWSPVW12(Reimbursement Admin); | USMAN-SMDBPVW12 | USAZRSMDBPVW04, USAZRSMDBPVW05 | RE-HOST(App)/RE-PLATFORM(DB) | R&D | R&D, Custom implant manufacturing | US | 6 | 18 | 18 - Complex Application Group | Jun | MG1 | No | Yes | Complex Migration | Medium | Complex Migration | US | Windows Server 2016 Standard | Vendor Developed | Sql Server 2016 | PROD, DEV | 4 | Express Implants, Express Visionaire, Opentext ECM | Integration with Matrix (reading information of UDI data) and sending information to Prisym and SAP. Co-Hosted with Express Implants application. | Both Express Instruments & Inventures (SCAMPI) Web App applications as we learnt during the SME sessions are one and the same. These are duplicate entries in the CMDB. |  | Yes | 2020-01-25 | 2021-01-29 | Yes | 2020-02-08 | 2020-02-10 | Yes | 2021-02-08 | 2020-02-10 | Yes |  |  | Yes |  |  | Yes |  |  | Yes | 2021-02-10 | 2021-02-11 | Yes | 2021-02-17 | 2021-02-17 | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
90 | Inventures (SCAMPI) Web App | DEV | Ian Bennett | Sri Tupil |  | W1-MG2 | 2021-01-22 | 2021-01-22 | No |  | Finished (blue) |  |  |  | USMEMSMAPDVW18(User Facing Module); USMAN-SMWSDVW07(Admin Module); | USMAN-SMDPDVW16 | USAZRSMDBDVW03 | RE-HOST(App)/RE-PLATFORM(DB) | R&D | R&D, Custom implant manufacturing | US | 6 | 18 | 18 - Complex Application Group | Jun | MG1 | No | Yes | Complex Migration | Medium | Complex Migration | US | Windows Server 2016 Standard | Vendor Developed | Sql Server 2016 | PROD, DEV | 4 | Express Implants, Express Visionaire, Opentext ECM | Integration with Matrix (reading information of UDI data) and sending information to Prisym and SAP. Co-Hosted with Express Implants application. | Both Express Instruments & Inventures (SCAMPI) Web App applications as we learnt during the SME sessions are one and the same. These are duplicate entries in the CMDB. |  | Done | 2020-12-11 | 2021-01-22 | Yes | 2020-12-30 | 2021-01-22 | No | 2021-01-13 | 2021-01-13 | Yes | 2021-01-04 | 2021-01-11 | Yes | 2021-01-11 | 2021-01-15 | Yes | 2021-01-15 | 2021-01-18 | Yes | 2021-01-08 | 2021-01-08 | Yes | 2021-01-13 | 2021-01-13 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-21 | 2021-01-22 | Yes | 2021-01-22 | 2021-01-22 | Yes | 2021-01-24 | 2021-01-24 | Yes | 2021-01-24 | 2021-03-02 | Done, no evidence provided | N/A | N/A | Done, no evidence provided | Done, no evidence provided | N/A | N/A | N/A | N/A | N/A | No | 2021-02-19 |  | Yes | 2021-02-19 | 2021-02-08 | No | 2021-02-19 |  | No | 2021-02-19 |  | Yes | 2021-02-19 | 2021-02-22
90 | Inventures (SCAMPI) Web App | QA | Ian Bennett | Sri Tupil |  | W1-MG2 | 2021-01-22 | 2021-01-22 | No |  | Finished (blue) |  |  |  | USMAN-SMWSQVW05(Admin Module) | USMAN-SMDPDVW16 | USAZRSMDBQVW02 | RE-HOST(App)/RE-PLATFORM(DB) | R&D | R&D, Custom implant manufacturing | US | 6 | 18 | 18 - Complex Application Group | Jun | MG1 | No | Yes | Complex Migration | Medium | Complex Migration | US | Windows Server 2016 Standard | Vendor Developed | Sql Server 2016 | PROD, DEV | 4 | Express Implants, Express Visionaire, Opentext ECM | Integration with Matrix (reading information of UDI data) and sending information to Prisym and SAP. Co-Hosted with Express Implants application. | Both Express Instruments & Inventures (SCAMPI) Web App applications as we learnt during the SME sessions are one and the same. These are duplicate entries in the CMDB. |  | Done | 2020-12-11 | 2021-01-22 | Yes | 2020-12-30 | 2021-01-22 | No | 2021-01-13 | 2021-01-13 | Yes | 2021-01-04 | 2021-01-11 | Yes | 2021-01-11 | 2021-01-15 | Yes | 2021-01-15 | 2021-01-18 | Yes | 2021-01-08 | 2021-01-08 | Yes | 2021-01-13 | 2021-01-13 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-21 | 2021-01-22 | Yes | 2021-01-22 | 2021-01-22 | Yes | 2021-01-24 | 2021-01-24 | Yes | 2021-01-24 | 2021-03-02 | Done, no evidence provided | N/A | N/A | Done, no evidence provided | Done, no evidence provided | N/A | N/A | N/A | N/A | N/A | No | 2021-02-19 |  | Yes | 2021-02-19 | 2021-02-08 | No | 2021-02-19 |  | No | 2021-02-19 |  | Yes | 2021-02-19 | 2021-02-22
65 | IQ-Soft (Aarau) | PROD | Aileen Diola | Sri Tupil |  |  | 2021-04-09 | 2021-04-30 | Yes | AVS scope. Ken's appoval to follow. | Out of scope (dark grey) |  |  |  | CHAARSMAPPW14 | CHAARSMAPPW14 |  | RE-HOST | RAQA | RAQA | EMEA | 4 | 10 | 10 - Full Throttle EMEA Application - Batch 2 | Apr | MG2 | No | Yes | Moderate Migration | Low | I am migrating this to SAAS by Q2 of 2022, so the answer will depend on how much is the overall cloud migration cost vs keeping it in the DC? | EUROPE | Windows Server 2008 R2 Standard | COTS | SQL Server 2008 | Prod | 1 | NA | There is plan to implement a Global Calibration Management systems and this should replace one out of the two functions of IQ-Soft (Tuttlingen) software by 2022. We need to get more information from the business if there is any plan/changes in this application and the platform. Should we migrate this to the cloud, there will be software upgrade and license change cost that the vendor will charge SNI Calibration Management will be replaced by Hydra during 2020. | There is plan to implement a Global Calibration Management systems and this should replace one out of the two functions of IQ-Soft (Tuttlingen) software by 2022. We need to get more information from the business if there is any plan/changes in this application and the platform. Should we migrate this to the cloud, there will be software upgrade and license change cost that the vendor will charge SNI. Calibration Management will be replaced by Hydra during 2020. ->As per SDM there may be documents available in the server but AG (vendor) specific documents IT Technical support document is not available Solution architecture diagram is not available and it is in German.Before the migration need to discuss with the business like should we migrate this to cloud ,there will be software upgrade and license cost that the vendor will chare SNI. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
66 | IRAMEA-LATAM Data Warehouse (South Africa) | PROD | Mark Elliott | Stuart Robinson |  | W4-MG2 | 2021-04-23 | 2021-04-30 | No |  | Imminent Delay (red) | Potential Latency issue. Mark Elliot is proposing a different solution, Mat Pie to confirm | Isha/Venkat | Srikanth/Rajesh |  | ZAORCLEM |  | RE-HOST | Data & Analytics | Data & Analytics | EMEA | 4 | 10 | 10 - Full Throttle EMEA Application - Batch 2 | Apr | MG2 | No | No | Moderate Migration | Medium | Moderate migration | South Africa | Windows Server 2012 R2 Standard | SNI custom built in house | Oracle 12C | Prod | 1 | NA | Connectivity to other systems like - Reporting system, data file feed would be a concern which needs to be validated during the azure migration. DNS is configured. To be verified. Mark to check with GBS. No other applications sharing the VM. | IP Address Change – Hardcoding, Application dependencies & DNS Configuration Migration to Azure AS IS won’t be any issue. Connectivity to other systems like - Reporting system, data file feed would be a concern which needs to be validated during the azure migration. DNS is configured. To be verified. Mark to check with GBS Dependency on integration systems Data feed coming in from ERP systems and flowing out as reports via reporting tool. | Need to check if in Azure it will allow additional processes for Oracle DB. Need to check with the testing schedule | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
30 | iStability | PROD | Aileen Diola | Sri Tupil |  | W2-MG1 | 2021-02-05 | 2021-02-05 | No |  | Finished (blue) |  |  |  | USASHSMDBDVW03 | USASHSMDBDVW03 |  | RE-HOST | RAQA | RAQA, Business Application | US | 2 | 5 | 05 - Simple/Medium Apps | Feb | MG1 | No | Yes | Moderate Migration | Low | Moderate Migration | Ft. Worth, Texas | Windows Server 2012 R2 | COTS | MS Sql Server 2012 | PROD | 1 | Another Apps DB running "Commercial Contract Management" | NA | Hardcoded IP Address Changes, Replatform to Windows Server 2019 |  | Yes | 2020-12-23 | 2020-12-23 | Yes | 2021-01-18 | 2021-01-15 | Yes | 2021-01-14 | 2021-01-19 | Yes | 2021-01-18 | 2021-01-18 | Yes | 2021-01-25 | 2021-01-25 | Yes | 2021-01-29 | 2021-01-29 | Yes | 2021-01-15 | 2021-01-15 | Yes | 2021-01-20 | 2021-01-20 | Yes | 2021-02-05 | 2021-02-05 | Yes | 2021-02-04 | 2021-02-04 | Yes | 2021-02-05 | 2021-02-05 | Yes | 2021-02-07 | 2021-02-07 | Yes | 2021-02-07 | 2021-08-02 | Done, no evidence provided | N/A | N/A | Done, no evidence provided | Done, no evidence provided | N/A | N/A | N/A | N/A | N/A | Yes | 2021-03-05 |  | No | 2021-03-05 |  | No | 2021-03-05 |  | No | 2021-03-05 |  | No | 2021-03-05
86 | jaki | PROD | Chika Ishii | Firas Almahamid | X | W5-MG2 | 2021-05-21 | 2021-05-30 | No |  | Not started (grey) | Propose to move to April 23rd |  |  | JPTOKSMAPPW06 |  |  | RE-HOST | Data & Analytics | Data & Analytics | APAC | 5 | 18 | 18 - Complex Application Group | May | MG2 | No | No | Moderate Migration | Simple | Moderate Migration | APAC | Window Server 2008 R2 | COTS | In Built DB | Prod | 1 | None | BPCS, SAP ERP, Dr.Sum & Connect Plus (Co-Hosted) | Risk 1 - Vendor support Mitigation 1 - SNI enable vendor support during migration Risk 2 - OS compatibility Mitigation 2 - Currently it is in windows server 2008 R2, need to check during migration which server is in place as they are planning to migrate to new version windows server 2012 by Sept’20. Risk 3 - Hostname is used in some batch jobs. Mitigation 3 - SDM/Vendor are planning to change them, ETA: Unknown as of documenting, hence, while migrating to Azure, hostname of the server may have to be retained. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
115 | Kaba Elostar | PROD | Paul Davison | Chris Cook | X | W7-MG2 | 2021-07-23 | 2021-07-30 | No |  | Not started (grey) | Propose to move to April 23rd |  |  | CHAARSMAPPW19 |  |  | RE-HOST | Group Functions | Group Functions | EMEA | 7 | 21 | 21 - Final EMEA/APAC application | Jul | MG2 | No | No | Medium | Low | Moderate migration |  | Windows 2012 R2 Standard | COTS | Kaba Eloster | Prod | 1 | None | 1. Support and assistance required from Werner Fischer and the supplier. Since no Documentation and no test cases available. 2. Connectivity to door access, keys to be validated in Aarau facility during Azure migration. 3. No other application sharing the VM. But SDM opinion of migration is “cannot be migrated”. SDM to check with the supplier, why? | IP Address Change – Hardcoding SDM opinion |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
127 | KepServerEx (Amsterdam) | PROD | Carla Morris |  |  | PW-MG4 | 2020-12-04 | 2020-12-04 | No |  | Finished (blue) |  |  |  | UKHULSMDBPVW04 |  |  | RE-HOST | Manufacturing | Manufacturing | EMEA | Pilot | Pilot | 00 - Pilot | Dec | MG2 | No | No | UnSure | Low | Easy Migration | Amsterdam USA | Windows Server 2012 R2 | COTS | SQL Server 2012 | Prod | 2 | No |  | Latency - SDM/SME to prepare and create Metrics to measure the expected latency between all the devices of this application (Desktop client, Kepware Server, PI system, Manufacturing floor devices). |  | Done | 2020-10-05 | 2020-10-05 | Yes | 2020-11-17 | 2020-11-17 | Yes | 2020-11-17 | 2020-11-17 | Yes | 2020-11-17 | 2020-11-17 | Yes | 2020-11-24 | 2020-11-24 | Yes | 2020-11-28 | 2020-11-28 | Yes | 2020-11-21 | 2020-11-21 | Yes | 2020-11-24 | 2020-11-24 | Yes | 2020-12-04 | 2020-12-04 | Yes | 2020-12-04 | 2020-12-04 | Yes | 2020-12-05 | 2020-12-05 | Yes | 2020-12-07 | 2020-12-07 | Yes | 2020-12-07 | 2020-12-08 | Done, no evidence provided | N/A | N/A | Done, no evidence provided | Done, no evidence provided | N/A | N/A | N/A | N/A | N/A | Yes | 2021-01-02 | 2021-01-02 | Yes | 2021-01-02 | 2021-02-08 | No | 2021-01-02 |  | No | 2021-01-02 |  | Yes | 2021-01-02 | 2021-01-20
67 | Lasernet / Nemhandel | PROD | Sebastian Pasch |  | X | W4-MG2 | 2021-04-23 | 2021-04-30 | No |  | On track (green) | Infra and DB team to share cutover steps | Vidit | Rahul/Saurabh | NRS03 |  | EUAZRSMDBPVW01, EUAZRSMDBPVW02 | RE-HOST(App)/RE-PLATFORM(DB) | ERP | ERP | EMEA | 4 | 10 | 10 - Full Throttle EMEA Application - Batch 2 | Apr | MG2 | No | No | Easy Migration | Medium | Upgrade required | EUROPE | Window Server 2008 R2 Standard | COTS | SQL Server Compact 4.0 | Prod | 1 | Shared Server with print server Certificates for Nemhandel app SAP batch job | IP Address Change – Hardcoding Resolve with hostname/domain name. If not, validate IP change and reconfigure integration systems. | Shared Server This server is also serving as a print server Hybrid Strategy Implement hybrid strategy before migration Application Upgrade and vendor support SNI ensure availability of vendor to install latest stable application version that meet business requirements. Please check known issue with latest version. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
128 | LDAPUpdate | PROD | Andres Bernard | Firas Almahamid |  | PW-MG3 | 2020-11-20 | 2020-11-20 | No |  | Finished (blue) |  |  |  |  | USMAN-SMDBPVW12 |  | RE-PLATFORM | Commercial | Commercial | US | Pilot | Pilot | 00 - Pilot | Nov | MG1 | No | No | Simple | Low | Simple | USA | Windows Server 2012 Standard | SNI Dev | Sql Server 2012 R2 | Prod,Dev | 2 | With LDAPUpdate few other applications are co-hosted in the same server. -> Contracts -> ECAP -> Endo Loans -> Inventures (SCAMPI) Web App -> Kitting -> LeadTracker -> Reimbursement -> Salient | Dependency with co-hosted applications, which are sharing the same VM | With LDAPUpdate few other applications are co-hosted in the same server. -> Contracts -> ECAP -> Endo Loans -> Inventures (SCAMPI) Web App -> Kitting -> LeadTracker -> Reimbursement -> Salient During the cloud migration need to move all the applications in one group |  | Done | 2020-10-05 | 2020-10-05 | Yes | 2020-11-03 | 2020-11-03 | Yes | 2020-11-03 | 2020-11-03 | Yes | 2020-11-03 | 2020-11-03 | Yes | 2020-11-10 | 2020-11-10 | Yes | 2020-11-14 | 2020-11-14 | Yes | 2020-11-07 | 2020-11-07 | Yes | 2020-11-10 | 2020-11-10 | Yes | 2020-11-20 | 2020-11-20 | Yes | 2020-11-20 | 2020-11-20 | Yes | 2020-11-21 | 2020-11-21 | Yes | 2020-11-23 | 2020-11-23 | Yes | 2020-11-23 | 2020-11-23 | Done, no evidence provided | N/A | N/A | Done, no evidence provided | Done, no evidence provided | N/A | N/A | N/A | N/A | N/A | Yes | 2020-12-19 | 2021-01-02 | Yes | 2020-12-19 | 2021-02-08 | No | 2020-12-19 |  | No | 2020-12-19 |  | Yes | 2020-12-19 | 2021-02-22
128 | LDAPUpdate | TEST | Andres Bernard | Firas Almahamid |  | PW-MG2 | 2020-11-12 | 2020-11-12 | No |  | Finished (blue) |  |  |  |  | USMAN-SMDPDVW16 |  | RE-PLATFORM | Commercial | Commercial | US | Pilot | Pilot | 00 - Pilot | Nov | MG1 | No | No | Simple | Low | Simple | USA | Windows Server 2012 Standard | SNI Dev | Sql Server 2012 R2 | Prod,Dev | 2 | With LDAPUpdate few other applications are co-hosted in the same server. -> Contracts -> ECAP -> Endo Loans -> Inventures (SCAMPI) Web App -> Kitting -> LeadTracker -> Reimbursement -> Salient | Dependency with co-hosted applications, which are sharing the same VM | With LDAPUpdate few other applications are co-hosted in the same server. -> Contracts -> ECAP -> Endo Loans -> Inventures (SCAMPI) Web App -> Kitting -> LeadTracker -> Reimbursement -> Salient During the cloud migration need to move all the applications in one group |  | Done | 2020-10-05 | 2020-10-05 | Yes | 2020-10-26 | 2020-10-26 | Yes | 2020-10-26 | 2020-10-26 | Yes | 2020-10-26 | 2020-11-17 | Yes | 2020-11-02 | 2020-11-02 | Yes | 2020-11-06 | 2020-11-06 | Yes | 2020-10-30 | 2020-10-30 | Yes | 2020-11-02 | 2020-11-02 | Yes | 2020-11-12 | 2020-11-12 | Yes | 2020-11-12 | 2020-11-12 | Yes | 2020-11-13 | 2020-11-13 | Yes | 2020-11-15 | 2020-11-15 | Yes | 2020-11-15 | 2020-11-15 | Done, no evidence provided | N/A | N/A | Done, no evidence provided | Done, no evidence provided | N/A | N/A | N/A | N/A | N/A | Yes | 2020-12-11 | 2021-01-02 | Yes | 2020-12-11 | 2021-02-08 | No | 2020-12-11 |  | No | 2020-12-11 |  | Yes | 2020-12-11 | 2021-02-22
26 | Lutron | PROD | Paul Davison | Chris Cook |  |  | 2021-02-28 | 2021-02-28 | Yes | Latency issue | Out of scope (dark grey) |  |  |  | LUT-2035764-001 | LUT-2035764-001 |  | RE-HOST | Group Functions | Building Automation in Costa Rica | US | 2 | 5 | 05 - Simple/Medium Apps | Feb | MG1 | No | No | Moderate Migration | Medium | Moderate Migration | USA,Costa Rica | Windows Server 2008 R2 | COTS | SQL Server 2012 | Prod | 1 | NA | NA | NA |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
77 | Mainsaver CMMS (UK) | QA | Carla Morris | Derek Spillane |  | W5-MG1 | 2021-05-07 | 2021-05-30 | No |  | Not started (grey) |  |  |  | NLAMSSMDBQVW01; | NLAMSSMDBQVW01 |  | RE-HOST | Manufacturing | Manufacturing | US | 5 | 14 | 14 - Data Warehouse Application | May | MG2 | No | Yes | Moderate Migration | Low | Moderate Migration | Europe | Windows Server 2012 R2 | COTS | MS Sql Server 2012 | PROD, QA | 2 | Report taken on Monday has slow performance issue in current env. | Monday Reports runs an hour ,Speed on system to access and generate report | Infomaker file server drive |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
77 | Mainsaver CMMS (UK) | PROD | Carla Morris | Derek Spillane |  | W5-MG2 | 2021-05-21 | 2021-05-30 | No |  | Not started (grey) |  |  |  | NLAMSSMDBPVW07 | NLAMSSMDBPVW07 |  | RE-HOST | Manufacturing | Manufacturing | US | 5 | 14 | 14 - Data Warehouse Application | May | MG2 | No | Yes | Moderate Migration | Low | Moderate Migration | Europe | Windows Server 2012 R2 | COTS | MS Sql Server 2012 | PROD, QA | 2 | Report taken on Monday has slow performance issue in current env. | Monday Reports runs an hour ,Speed on system to access and generate report | Infomaker file server drive |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
3 | MATLAB | PROD | Requalann Pereira | Sri Tupil |  | W6-MG1 | 2021-06-04 | 2021-01-30 | No |  | Not started (grey) |  |  |  | BBTAPP01 |  |  | RE-HOST | R&D | Manufacturing - CNC Programming | US | 1 | 1 | 01 - Network License Server - Batch 1 | Jan | MG1 | No | No | Moderate Migration | Medium | Moderate Migration | USA | Windows 2012 | COTS | NA | Prod | 1 | Myriad, FlexLM,SolidWorks, Unigraphics | License MAC bind | Shared License Server - BBTAPP01 |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  | 2021-01-21 | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
49 | Mcosomos | PROD | Aileen Diola |  |  |  |  | 2021-03-30 | Yes | Out of scope - Desktop application. There is no app server. | Out of scope (dark grey) |  |  |  | CHAARSMFSPW03 |  |  | RE-HOST | Manufacturing | Manufacturing | EMEA | 3 | 8 | 08 - Full Throttle EMEA Application - Batch 1 | Mar | MG2 | No | No | Moderate Migration | Medium | Moderate migration | Aarau Switzerland | Windows Server 2012 R2 Standard | COTS | NA | Fileserver | 1 | File Server VM shared with other applications. The File Server is used by other applications like – Visionaire and VEI Label along with MCOSMOS | IP Address Hardcoding IP address reference to these application need to be reconfigured during Azure migration. | File Server VM shared with other applications. The File Server is used by other applications like – Visionaire and VEI Label along with MCOSMOS |  | Yes | 2020-01-25 | 2021-01-28 | No | 2020-02-08 |  | No |  |  | No |  |  | No |  |  | No |  |  | No | 2021-02-24 |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
56 | Metasys | PROD | Paul Davison | Chris Cook |  | W4-MG2 | 2021-04-23 | 2021-04-30 | No |  | On track (green) | Infra and DB team to share cutover steps | Raju | Srikanth/Rajesh | USASHSMDBPVW22 | USASHSMDBPVW22 | USAZRSMDBPVW02, USAZRSMDBPVW03 | RE-HOST(App)/RE-PLATFORM(DB) | Group Functions | Manufacturing | US | 4 | 11 | 11 - US Medium/Complex Application | Apr | MG1 | No | Yes | Moderate Migration | Medium | Moderate Migration | USA | Winows 2016 | COTS | MS SQL 2016 | Prod | 1 | NA | Network Connectivites with controllers and machines on Shop Floor. | IP Address Hardcoding between - Central Controller and App Server. Shop Floor Manufacturing Unit. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
10 | MIMICS | PROD | Requalann Pereira | Sri Tupil |  | W5-MG1 | 2021-05-07 | 2021-01-30 | No |  | Not started (grey) |  |  |  | MEMSRV434; |  |  | RE-PLATFORM | R&D | R&D | US | 1 | 2 | 02 - Network License Server - Batch 2 | Jan | MG1 | No | Yes | Simple | Low | Simple | US | Windows Server 2008 Enterprise | COTS | NA | PROD | 1 | Co-host application Unigraphics, Flex LM, Simulia Abaqus (Solidworks is ruled out) |  | Manual License file generation ,Server location in Memphis makes worldwide SNI Engineer face license acquiring slow (Latency) |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  | 2021-01-21 | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
33 | Minitab | PROD | Aileen Diola | Sri Tupil |  | W1-MG2 | 2021-01-22 | 2021-01-22 | No |  | Finished (blue) |  |  |  | UKRTHSMDBPVW29 |  |  | RE-HOST | RAQA | RAQA | EMEA | 1 | 5 | 05 - Simple/Medium Apps | Jan | MG1 | No | Yes | Simple | Low | SDM: OEE application (not related to MiniTab) MS SQL server is co-hosted on the Minitab Server. Minitab dependencies on the server is only restricted as "Network License Server". | All SNI Internal | Windows 2012 R2 Standard | COTS | None | Prod | 1 | OEE | Cohost apps | Mac address are validated for each desktop clients with license server. |  | Done | 2020-12-11 | 2020-12-11 | Yes | 2020-12-30 | 2021-01-22 | Yes | 2021-01-13 | 2021-01-13 | Yes | 2021-01-04 | 2020-12-17 | Yes | 2021-01-11 | 2021-01-15 | Yes | 2021-01-15 | 2021-01-18 | Yes | 2021-01-08 | 2021-01-08 | Yes | 2021-01-13 | 2021-01-13 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-21 | 2021-01-22 | Yes | 2021-01-22 | 2021-01-22 | Yes | 2021-01-24 | 2021-01-24 | Yes | 2021-01-24 | 2021-01-25 | Done, no evidence provided | N/A | N/A | Done, no evidence provided | Done, no evidence provided | N/A | N/A | N/A | N/A | N/A | Yes | 2021-02-19 | 2021-02-03 | Yes | 2021-02-19 | 2021-02-08 | No | 2021-02-19 |  | No | 2021-02-19 |  | No | 2021-02-19
44 | Mobile Inventory Management System | TEST | Andres Bernard | Firas Almahamid |  | W7-MG1 | 2021-07-09 | 2021-03-30 | No |  | Imminent Delay (red) | Out of Wave 3. Reschedule to July. |  |  | EQVSWB01 | AUVSDB00 |  | RE-HOST | Commercial | Commercial | US | 3 | 7 | 07 - Simple/Medium Apps - Moving to EMEA | Mar | MG1 | Yes | Yes | Moderate migration | Medium | Moderate migration | USA | Windows Server 2008 Standard | SNI Dev | Sql Server 2008 | Dev,Archive,Prod | 6 | No | Code Freeze cannot be done on Month-End’s | DB Connection Issue(On going Issue) and this should be resolved before moving into azure |  | Yes | 2020-01-25 | 2021-01-28 | No | 2020-02-08 |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
44 | Mobile Inventory Management System | Archive-Prod | Andres Bernard | Firas Almahamid |  | W7-MG1 | 2021-07-09 | 2021-03-30 | No |  | Imminent Delay (red) | Out of Wave 3. Reschedule to July. |  |  | USMANSMWSPVW15 | EQVSDB00 |  | RE-HOST | Commercial | Commercial | US | 3 | 7 | 07 - Simple/Medium Apps - Moving to EMEA | Mar | MG1 | Yes | Yes | Moderate migration | Medium | Moderate migration | USA | Windows Server 2008 Standard | SNI Dev | Sql Server 2008 | Dev,Archive,Prod | 6 | No | Code Freeze cannot be done on Month-End’s | DB Connection Issue(On going Issue) and this should be resolved before moving into azure |  | Yes | 2020-01-25 | 2021-01-28 | No | 2020-02-08 |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
44 | Mobile Inventory Management System | PROD | Andres Bernard | Firas Almahamid |  | W7-MG2 | 2021-07-23 | 2021-03-30 | No |  | Imminent Delay (red) | Out of Wave 3. Reschedule to July. |  |  | USMANSMWSPVW15 | USMANSMDBPW14; USMANSMDBPW15; |  | RE-HOST | Commercial | Commercial | US | 3 | 7 | 07 - Simple/Medium Apps - Moving to EMEA | Mar | MG1 | Yes | Yes | Moderate migration | Medium | Moderate migration | USA | Windows Server 2008 Standard | SNI Dev | Sql Server 2008 | Dev,Archive,Prod | 6 | No | Code Freeze cannot be done on Month-End’s | DB Connection Issue(On going Issue) and this should be resolved before moving into azure |  | Yes | 2020-01-25 | 2021-01-28 | No | 2020-02-08 |  | No |  |  | No |  |  | No |  |  | No |  |  | No | 2021-02-24 |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
44 | Mobile Inventory Management System | DR | Andres Bernard | Firas Almahamid |  | W7-MG2 | 2021-07-23 | 2021-03-30 | No |  | Imminent Delay (red) | Out of Wave 3. Reschedule to July. |  |  | UKRTHSMWSQVW15; | UKRTHSMDBQPW14 |  | RE-HOST | Commercial | Commercial | US | 3 | 7 | 07 - Simple/Medium Apps - Moving to EMEA | Mar | MG1 | Yes | Yes | Moderate migration | Medium | Moderate migration | USA | Windows Server 2008 Standard | SNI Dev | Sql Server 2008 | Dev,Archive,Prod | 6 | No | Code Freeze cannot be done on Month-End’s | DB Connection Issue(On going Issue) and this should be resolved before moving into azure |  | Yes | 2020-01-25 | 2021-01-28 | No | 2020-02-08 |  | No |  |  | No |  |  | No |  |  | No |  |  | No | 2021-02-24 |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
87 | Motion Board | PROD | Chika Ishii | Firas Almahamid | X |  | 2021-05-30 | 2021-05-30 | Yes | To be decomissioned end of the year. To be confirmed it will be fully retired EOY (Mat P) | Out of scope (dark grey) |  |  |  | JPTOKSMAPPW06 |  |  | RE-HOST | Data & Analytics | Data & Analytics | APAC | 5 | 16 | 16 - Complex Application Group | May | MG2 | No | No | Moderate Migration | Simple | Moderate Migration | APAC | Window Server 2008 R2 | COTS | In Built DB | Prod | 7 | None | BPCS, SAP ERP, Dr.Sum & Connect Plus (Co-Hosted) | Risk 1 - Vendor support Mitigation 1 - SNI enable vendor support during migration Risk 2 - OS compatibility Mitigation 2 - Currently it is in windows server 2008 R2, need to check during migration which server is in place as they are planning to migrate to new version windows server 2012 by Sept’20. Risk 3 - Hostname is used in some batch jobs. Mitigation 3 - SDM/Vendor are planning to change them, ETA: Unknown as of documenting, hence, while migrating to Azure, hostname of the server may have to be retained. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
4 | Myriad | PROD | Requalann Pereira | Sri Tupil |  | W5-MG1 | 2021-05-07 | 2021-01-30 | No |  | Not started (grey) |  |  |  | MEMSRV403 |  |  | RE-PLATFORM | R&D | R&D | US | 1 | 2 | 02 - Network License Server - Batch 2 | Jan | MG1 | No | No | Simple | Low | Vendor Support Not Available | SNI Internal | Windows Server 2008 | COTS | NA | Prod | 1 | FlexLM, MATLAB,SolidWorks, Unigraphics | NA | IP Address Change – Hardcoding, No Test Env Available | DNA - need to check if we can incorporate some US apps in Jan | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  | 2021-01-21 | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
6 | Nomino Security | PROD | Andres Bernard | Firas Almahamid |  | W3-MG1 | 2021-03-05 | 2021-03-05 | No |  | On track (green) |  | Vidit Kumar | Rahul Sarin | USMAN-SMWSPVW12 | SMRTHSQL2 (Cluster); UKRTHSMDBPW03; UKRTHSMDBPW04; | USAZRSMDBPVW02, USAZRSMDBPVW03 | RE-HOST(App)/RE-PLATFORM(DB) | Commercial | Commercial | US | 1 | 3 | 03 - SNI Developed + Co-Hosted Apps | Jan | MG2 | No | No | Simple | Low | Easy Migration | Globally SNI Internal | Windows Server 2012 | SNI Dev'ed | Sql Server 2008/12 | Dev, Test, Prod | 6 | SNID Archived shipping documents ECAP ENCORE HR Notification Global Return Disposition Tool GSC Datawarehouse Admin Tool Inventures Web App EndoLoans QA Change Control Recon LaunchPad(SSO) Reimbursement Sales Request Forms Non-Employee Database | This application required to set access to users for wound apps (SNID, ENCORE, GSC Datawarehouse, QA Change Control) | App and DB servers are shared across other applications in SNI, IP Address Change – Hardcoding |  | Yes | 2020-01-25 | 2021-01-28 | Yes | 2020-02-08 | 2020-02-10 | Yes | 2021-02-08 | 2020-02-10 | No |  |  | No |  |  | No |  |  | Yes | 2021-02-10 | 2021-02-11 | Yes | 2021-02-17 | 2021-02-17 | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
6 | Nomino Security | DEV | Andres Bernard | Firas Almahamid |  | W1-MG2 | 2021-01-22 | 2021-01-22 | No |  | Finished (blue) |  |  |  | USMAN-SMWSDVW07 | SMRTHSQL3 (Cluster); UKRTHSMDBPW06; UKRTHSMDBPW05; | USAZRSMDBDVW02 | RE-HOST(App)/RE-PLATFORM(DB) | Commercial | Commercial | US | 1 | 3 | 03 - SNI Developed + Co-Hosted Apps | Jan | MG2 | No | No | Simple | Low | Easy Migration | Globally SNI Internal | Windows Server 2012 | SNI Dev'ed | Sql Server 2008/12 | Dev, Test, Prod | 6 | SNID Archived shipping documents ECAP ENCORE HR Notification Global Return Disposition Tool GSC Datawarehouse Admin Tool Inventures Web App EndoLoans QA Change Control Recon LaunchPad(SSO) Reimbursement Sales Request Forms Non-Employee Database | This application required to set access to users for wound apps (SNID, ENCORE, GSC Datawarehouse, QA Change Control) | App and DB servers are shared across other applications in SNI, IP Address Change – Hardcoding |  | Done | 2020-12-11 | 2020-12-11 | Yes | 2020-12-30 | 2021-01-22 | No | 2021-01-13 | 2021-01-13 | Yes | 2021-01-04 | 2021-01-04 | Yes | 2021-01-11 | 2021-01-11 | Yes | 2021-01-15 | 2021-01-15 | Yes | 2021-01-08 | 2021-01-08 | Yes | 2021-01-13 | 2021-01-13 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-22 | 2021-01-22 | Yes | 2021-01-24 | 2021-01-24 | Yes | 2021-01-24 | 2021-01-24 | Done, no evidence provided | N/A | N/A | Done, no evidence provided | Done, no evidence provided | N/A | N/A | N/A | N/A | N/A | No | 2021-02-19 |  | Yes | 2021-02-19 | 2021-02-08 | No | 2021-02-19 |  | No | 2021-02-19 |  | No | 2021-02-19
6 | Nomino Security | QA | Andres Bernard | Firas Almahamid |  | W1-MG2 | 2021-01-22 | 2021-01-22 | No |  | Finished (blue) |  |  |  | USMAN-SMWSQVW05 | SMRTHSQL3 (Cluster); UKRTHSMDBPW06; UKRTHSMDBPW05; | USAZRSMDBQVW01 | RE-HOST(App)/RE-PLATFORM(DB) | Commercial | Commercial | US | 1 | 3 | 03 - SNI Developed + Co-Hosted Apps | Jan | MG2 | No | No | Simple | Low | Easy Migration | Globally SNI Internal | Windows Server 2012 | SNI Dev'ed | Sql Server 2008/12 | Dev, Test, Prod | 6 | SNID Archived shipping documents ECAP ENCORE HR Notification Global Return Disposition Tool GSC Datawarehouse Admin Tool Inventures Web App EndoLoans QA Change Control Recon LaunchPad(SSO) Reimbursement Sales Request Forms Non-Employee Database | This application required to set access to users for wound apps (SNID, ENCORE, GSC Datawarehouse, QA Change Control) | App and DB servers are shared across other applications in SNI, IP Address Change – Hardcoding |  | Done | 2020-12-11 | 2020-12-11 | Yes | 2020-12-30 | 2021-01-22 | No | 2021-01-13 | 2021-01-13 | Yes | 2021-01-04 | 2021-01-04 | Yes | 2021-01-11 | 2021-01-11 | Yes | 2021-01-15 | 2021-01-15 | Yes | 2021-01-08 | 2021-01-08 | Yes | 2021-01-13 | 2021-01-13 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-22 | 2021-01-22 | Yes | 2021-01-24 | 2021-01-24 | Yes | 2021-01-24 | 2021-01-24 | Done, no evidence provided | N/A | N/A | Done, no evidence provided | Done, no evidence provided | N/A | N/A | N/A | N/A | N/A | No | 2021-02-19 |  | Yes | 2021-02-19 | 2021-02-08 | No | 2021-02-19 |  | No | 2021-02-19 |  | No | 2021-02-19
7 | Non-Employee Database | DEV | Paul Davison | Chris Cook |  | W1-MG2 | 2021-01-22 | 2021-01-22 | No |  | Finished (blue) |  |  |  | USMAN-SMWSDVW07 | USMANSMDBDUW01 | USAZRSMDBDVW02 | RE-HOST(App)/RE-PLATFORM(DB) | Group Functions | Group Functions | US | 1 | 3 | 03 - SNI Developed + Co-Hosted Apps | Jan | MG2 | No | No | Simple | Low | Easy Migration | Globally SNI Internal | Windows Server 2012 | SNI Dev'ed | Sql Server 2012 | Dev, Test, Prod | 6 | SNID Archived shipping documents ECAP ENCORE HR Notification Global Return Disposition Tool GSC Datawarehouse Admin Tool Inventures Web App Nomino Security QA Change Control Recon LaunchPad(SSO) Reimbursement Sales Request Forms EndoLoans | NA | App and DB servers are shared across other applications in SNI, IP Address Change – Hardcoding |  | Done | 2020-12-11 | 2020-12-11 | Yes | 2020-12-30 | 2021-01-22 | No | 2021-01-13 | 2021-01-13 | Yes | 2021-01-04 | 2021-01-04 | Yes | 2021-01-11 | 2021-01-11 | Yes | 2021-01-15 | 2021-01-15 | Yes | 2021-01-08 | 2021-01-08 | Yes | 2021-01-13 | 2021-01-13 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-22 | 2021-01-22 | Yes | 2021-01-24 | 2021-01-24 | Yes | 2021-01-24 | 2021-01-24 | Done, no evidence provided | N/A | N/A | Done, no evidence provided | Done, no evidence provided | N/A | N/A | N/A | N/A | N/A | No | 2021-02-19 |  | Yes | 2021-02-19 | 2021-02-08 | No | 2021-02-19 |  | No | 2021-02-19 |  | Yes | 2021-02-19 | 2021-02-03
7 | Non-Employee Database | QA | Paul Davison | Chris Cook |  | W1-MG2 | 2021-01-22 | 2021-01-22 | No |  | Finished (blue) |  |  |  | USMAN-SMWSQVW05 | USMANSMDBQUW01 | USAZRSMDBQVW01 | RE-HOST(App)/RE-PLATFORM(DB) | Group Functions | Group Functions | US | 1 | 3 | 03 - SNI Developed + Co-Hosted Apps | Jan | MG2 | No | No | Simple | Low | Easy Migration | Globally SNI Internal | Windows Server 2012 | SNI Dev'ed | Sql Server 2012 | Dev, Test, Prod | 6 | SNID Archived shipping documents ECAP ENCORE HR Notification Global Return Disposition Tool GSC Datawarehouse Admin Tool Inventures Web App Nomino Security QA Change Control Recon LaunchPad(SSO) Reimbursement Sales Request Forms EndoLoans | NA | App and DB servers are shared across other applications in SNI, IP Address Change – Hardcoding |  | Done | 2020-12-11 | 2020-12-11 | Yes | 2020-12-30 | 2021-01-22 | No | 2021-01-13 | 2021-01-13 | Yes | 2021-01-04 | 2021-01-04 | Yes | 2021-01-11 | 2021-01-11 | Yes | 2021-01-15 | 2021-01-15 | Yes | 2021-01-08 | 2021-01-08 | Yes | 2021-01-13 | 2021-01-13 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-22 | 2021-01-22 | Yes | 2021-01-24 | 2021-01-24 | Yes | 2021-01-24 | 2021-01-24 | Done, no evidence provided | N/A | N/A | Done, no evidence provided | Done, no evidence provided | N/A | N/A | N/A | N/A | N/A | No | 2021-02-19 |  | Yes | 2021-02-19 | 2021-02-08 | No | 2021-02-19 |  | No | 2021-02-19 |  | Yes | 2021-02-19 | 2021-02-03
7 | Non-Employee Database | PROD | Paul Davison | Chris Cook |  | W3-MG1 | 2021-03-05 | 2021-03-05 | No |  | On track (green) |  | Venkat/Isha/Shirisha | Srikanth Venkatasen | USMAN-SMWSPVW12 | USMAN-SMDBPVW12 | USAZRSMDBPVW02, USAZRSMDBPVW03 | RE-HOST(App)/RE-PLATFORM(DB) | Group Functions | Group Functions | US | 1 | 3 | 03 - SNI Developed + Co-Hosted Apps | Jan | MG2 | No | No | Simple | Low | Easy Migration | Globally SNI Internal | Windows Server 2012 | SNI Dev'ed | Sql Server 2012 | Dev, Test, Prod | 6 | SNID Archived shipping documents ECAP ENCORE HR Notification Global Return Disposition Tool GSC Datawarehouse Admin Tool Inventures Web App Nomino Security QA Change Control Recon LaunchPad(SSO) Reimbursement Sales Request Forms EndoLoans | NA | App and DB servers are shared across other applications in SNI, IP Address Change – Hardcoding |  | Yes | 2020-01-25 | 2021-01-28 | Yes | 2020-02-08 | 2020-02-10 | Yes | 2021-02-08 | 2020-02-10 | No |  |  | No |  |  | No |  |  | Yes | 2021-02-10 | 2021-02-11 | Yes | 2021-02-17 | 2021-02-17 | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
34 | OEE | PROD | Carla Morris | Derek Spillane |  | W1-MG2 | 2021-01-22 | 2021-01-22 | No |  | Finished (blue) |  |  |  | UKRTHSMDBPVW29 | UKRTHSMDBPVW29 |  | RE-HOST | Manufacturing | Manufacturing | EMEA | 1 | 5 | 05 - Simple/Medium Apps | Jan | MG1 | No | No | Simple Migration | Low | Easy Migration | UK | Windows Server 2012 R2 Standard | COTS | Sql Server 2012 R2 | Prod | 1 | Minitab | Minitab | OEE is not currently supported on Azure PAAS SQL. SQL Server Version & Azure SQL/Cloud VM Hosting |  | Done | 2020-12-11 | 2021-01-22 | Yes | 2020-12-30 | 2021-01-22 | Yes | 2021-01-13 | 2021-01-13 | Yes | 2021-01-04 | 2021-01-05 | Yes | 2021-01-11 | 2021-01-15 | Yes | 2021-01-15 | 2021-01-18 | Yes | 2021-01-08 | 2021-01-08 | Yes | 2021-01-13 | 2021-01-13 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-21 | 2021-01-22 | Yes | 2021-01-22 | 2021-01-22 | Yes | 2021-01-24 | 2021-01-24 | Yes | 2021-01-24 | 2021-01-25 | Done, no evidence provided | N/A | N/A | Done, no evidence provided | Done, no evidence provided | N/A | N/A | N/A | N/A | N/A | Yes | 2021-02-19 | 2021-02-03 | Yes | 2021-02-19 | 2021-02-08 | No | 2021-02-19 |  | No | 2021-02-19 |  | No | 2021-02-19
94 | Offline Counting | PROD | Amit Shokeen | Massimo Trambaioli |  | W6-MG2 | 2021-06-18 | 2021-06-30 | No |  | Not started (grey) |  |  |  | USMAN-SMSIPVW30 |  |  | RE-PLATFORM | Supply Chain | Supply Chain | US | 6 | 18 | 18 - Complex Application Group | Jun | MG1 | Yes | No | Moderate Migration | Low | Migrate | USA | Window Server 2008 R2 Std | COTS | SQL Express 11.0.7001.0 | Prod | 1 | None | Dependency on SAP batch jobs, so hybrid strategy need to adopt | Vendor support Ensure SNI IT and business team support during migration Customization/Configuration Identify configuration changes ahead of migration IP Dependency – hardcoding Resolve with hostname, if not details need to provide Hybrid Strategy Plan /implement hybrid strategy before migration |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
68 | OLMEC - UDI Printing | PROD | Requalann Pereira | Sri Tupil |  | W4-MG1 | 2021-04-09 | 2021-04-30 | No |  | On track (green) |  | Kishore | Srikanth/Rajesh | NLAMSSMDBPVW06; SGSINSMAPPVW20 |  |  | RE-HOST | R&D | R&D | EMEA/APAC | 4 | 10 | 10 - Full Throttle EMEA Application - Batch 2 | Apr | MG2 | No | Yes | Moderate Migration | Medium | Latency requirement & Network License Server info unknown to SDM.Server specific to APAC will be moved and not Europe servers | Europe & APAC | Windows Server 2016 Standard | COTS | MS SQL Server 2016 | Prod | 2 | None | None | Risk 1 - License information not available Mitigation 1 - During SME session and follow up with users at manufacturing floor, we were not able to determine how license are maintained, the same needs to be clarified before actual migration starts. Risk 2 - Integration to SNI apps, Infra Services info not available Mitigation 2 - During SME session and follow up with users, we were not able to determine if the application relies on any SNI application to input serialization or aggregation data for UDI printing, and also how the Printing device are setup and configured on the Desktop. Any integration aspects shared by SME needs to made available before actual migration starts. Risk 3 - Latency Mitigation 3 - SDM/SME to share the current Latency Metrics before detail migration plans is drafted. Test Case to be documented and made available to test all the end point of Desktop application, Application Server & DB. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
122 | Oracle Enterprise Manager | PROD | Sathiamurthy Samidurai | Stuart Robinson |  | PW-MG4 | 2020-12-04 | 2020-12-04 | No |  | Finished (blue) |  |  |  | USATL-SMAPPUL02 | USATL-SMDBPUL02; USATL-SMDBPUL04; |  | RE-PLATFORM | Data & Analytics | Central Monitoring System | US | Pilot | Pilot | 00 - Pilot | Nov | MG2 | No | No | Moderate Migration | Medium | Moderate Migration | USA | Linux 6.10 & Linux 6.7 | COTS - Oracle OEM 13c | Oracle 12c | 5 Environments, 2 Prod (App+DB), 2 Test (App+DB), 1 Production DR | 5 | Dependency on other applications databases sharing the TEST server. Test Target Application Databases Sharing the Test Servers. Informatica P360 Oracle Enterprise Manager Cognos BI (Complaints Analytics) Global Business Information Platform Informatica MDM Data Quality | Connectivity to 60 ERP Databases on-prem | Test Sever VMs are shared with other apps |  | Done | 2020-10-05 | 2020-10-05 | Yes | 2020-11-17 | 2020-11-17 | Yes | 2020-11-17 | 2020-11-17 | Yes | 2020-11-17 | 2020-11-17 | Yes | 2020-11-24 | 2020-11-24 | Yes | 2020-11-28 | 2020-11-28 | Yes | 2020-11-21 | 2020-11-21 | Yes | 2020-11-24 | 2020-11-24 | Yes | 2020-12-04 | 2020-12-04 | Yes | 2020-12-04 | 2020-12-04 | Yes | 2020-12-05 | 2020-12-05 | Yes | 2020-12-07 | 2020-12-07 | Yes | 2020-12-07 | 2020-12-07 | Done, no evidence provided | N/A | N/A | Not done | Not done | N/A | N/A | N/A | N/A | N/A | Yes | 2021-01-02 | 2021-01-02 | Yes | 2021-01-02 | 2021-02-08 | No | 2021-01-02 |  | No | 2021-01-02 |  | No | 2021-01-02
122 | Oracle Enterprise Manager | DR | Sathiamurthy Samidurai | Stuart Robinson |  | PW-MG4 | 2020-12-04 | 2020-12-04 | No |  | Finished (blue) |  |  |  |  | USMEM-SMDBPUL06 |  | RE-PLATFORM | Data & Analytics | Central Monitoring System | US | Pilot | Pilot | 00 - Pilot | Nov | MG2 | No | No | Moderate Migration | Medium | Moderate Migration | USA | Linux 6.10 & Linux 6.7 | COTS - Oracle OEM 13c | Oracle 12c | 5 Environments, 2 Prod (App+DB), 2 Test (App+DB), 1 Production DR | 5 | Dependency on other applications databases sharing the TEST server. Test Target Application Databases Sharing the Test Servers. Informatica P360 Oracle Enterprise Manager Cognos BI (Complaints Analytics) Global Business Information Platform Informatica MDM Data Quality | Connectivity to 60 ERP Databases on-prem | Test Sever VMs are shared with other apps |  | Done | 2020-10-05 | 2020-10-05 | Yes | 2020-11-17 | 2020-11-17 | Yes | 2020-11-17 | 2020-11-17 | Yes | 2020-11-17 | 2020-11-17 | Yes | 2020-11-24 | 2020-11-24 | Yes | 2020-11-28 | 2020-11-28 | Yes | 2020-11-21 | 2020-11-21 | Yes | 2020-11-24 | 2020-11-24 | Yes | 2020-12-04 | 2020-12-04 | Yes | 2020-12-04 | 2020-12-04 | Yes | 2020-12-05 | 2020-12-05 | Yes | 2020-12-07 | 2020-12-07 | Yes | 2020-12-07 | 2020-12-07 | Done, no evidence provided | N/A | N/A | Not done | Not done | N/A | N/A | N/A | N/A | N/A | Yes | 2021-01-02 | 2021-01-02 | Yes | 2021-01-02 | 2021-02-08 | No | 2021-01-02 |  | No | 2021-01-02 |  | No | 2021-01-02
122 | Oracle Enterprise Manager | QA | Sathiamurthy Samidurai | 2 |  | PW-MG2 | 2020-11-12 | 2020-11-12 | No |  | Finished (blue) |  |  |  | USMEM-SMAPTVL13 | USMEM-SMDBTVL12 |  | RE-PLATFORM | Data & Analytics | Central Monitoring System | US | Pilot | Pilot | 00 - Pilot | Nov | MG2 | No | No | Moderate Migration | Medium | Moderate Migration | USA | Linux 6.10 & Linux 6.7 | COTS - Oracle OEM 13c | Oracle 12c | 5 Environments, 2 Prod (App+DB), 2 Test (App+DB), 1 Production DR | 5 | Dependency on other applications databases sharing the TEST server. Test Target Application Databases Sharing the Test Servers. Informatica P360 Oracle Enterprise Manager Cognos BI (Complaints Analytics) Global Business Information Platform Informatica MDM Data Quality | Connectivity to 60 ERP Databases on-prem | Test Sever VMs are shared with other apps |  | Done | 2020-10-05 | 2020-10-05 | Yes | 2020-10-26 | 2020-10-26 | Yes | 2020-10-26 | 2020-10-26 | Yes | 2020-10-26 | 2020-10-26 | Yes | 2020-11-02 | 2020-11-02 | Yes | 2020-11-06 | 2020-11-06 | Yes | 2020-10-30 | 2020-10-30 | Yes | 2020-11-02 | 2020-11-02 | Yes | 2020-11-12 | 2020-11-12 | Yes | 2020-11-12 | 2020-11-12 | Yes | 2020-11-13 | 2020-11-19 | Yes | 2020-11-15 | 2020-11-20 | Yes | 2020-11-15 | 2020-11-15 | Done, no evidence provided | N/A | N/A | Not done | Not done | N/A | N/A | N/A | N/A | N/A | Yes | 2020-12-11 | 2021-01-02 | Yes | 2020-12-11 | 2021-02-08 | No | 2020-12-11 |  | No | 2020-12-11 |  | No | 2020-12-11
113 | Oracle Hyperion | PROD | Paul Davison | Chris Cook |  | W7-MG1 | 2021-07-09 | 2021-07-30 | No |  | Not started (grey) |  |  |  | DFWSHY00; DFWSHY01; DFWSHY02 |  |  | RE-HOST | Group Functions | Group Functions | US | 7 | 23 | 23 - High Critical Application | Jul | MG1 | No | No | Moderate Migration | Low | Moderate Migration | USA | Windows Server 2008 R2 SP1, | COTS | Oracle Essbase 11.x | Dev, Test, Prod, DR | 3 | None | FTP Server, Window Jobs and SAP | Retiring year in year 2021 Replacing with new platform (Cognos TM1) is under process, tentative by 2021 Limited Vendor support, lack of documentation and testing details Ensure vendor/SME support during migration Excel Plug-in dependency Validate plug-in use for security and others concern Tightly coupled window jobs Make sure jobs are running with proper credentials |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
53 | OSISoft PI System | PROD | Requalann Pereira | Sri Tupil |  | W5-MG1 | 2021-05-07 | 2021-03-30 | No |  | Imminent Delay (red) | Need clarity on legal position |  |  | SUZS06PI; SUZS07OPC; | UKHULSMDBPVW02 |  | RE-PLATFORM | Manufacturing | Manufacturing | EMEA | 3 | 8 | 08 - Full Throttle EMEA Application - Batch 1 | Mar | MG2 | No | No | Complex Migration | Low | RE-PLATFORM case. Complex Migration (Cannot be Migrated AS-IS). No Vendor support. User base seems to UK, server location in Souzou (China). | EUROPE | Windows 2003 Standard Windows 2012 R2 Standard | COTS | MS SQL Server 2012 | Prod | 3 | NA | RE-PLATFORM | OS is legacy (2003) • SUZS06PI • SUZS07OPC Matt: To ‘RE-PLATFORM’ with latest OS/Application version, post the following groundwork... 1. Need vendor confirmation if the application can be deployed on latest server (OS 2019), MSQ SQL DB 2016. 2. Need to know user base (# of actual user) to decide on the criticality. Latency requirements Also since we are RE-PLATFORMing the application, the current latency metrics is a MUST to have. As this is an PI system which may have data (time series) stored in SQL Server in real time, so the latency between the Lab equipment to Server (if any) or between desktop PC to Application server/DB, latency metrics will also be needed to have handy before migration. |  | Yes | 2020-01-25 | 2021-01-28 | No | 2020-02-08 |  | No |  |  | No |  |  | No |  |  | No |  |  | No | 2021-02-24 |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
2 | Partmaker | PROD | Carla Morris | Derek Spillane |  |  | 2021-06-30 | 2021-01-30 | Yes | License server to be decomissioned | Out of scope (dark grey) |  |  |  | BBTAPP01 |  |  | RE-HOST | Manufacturing | Manufacturing -CAM System | US | 1 | 2 | 02 - Network License Server - Batch 2 | Jan | MG1 | No | Yes | Moderate Migration | Medium | Moderate Migration | Memphis, Mansfield, China | Windows 2012 | COTS | NA | Prod | 7 | 11. The Production environment has 1 License Server which is shared across with other AutoCAD applications within SNI. BBTAPP01 APPS: AutoCAD PowerMill PowerShape FeatureCAM Ultimate (PartMaker) CAMWorks Vericut Solidworks (North America) Altium MATLAB | License Server - BBTAPP01 | Shared License Servers |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  | 2021-01-21 | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
123 | Paymetric | PROD | Pablo Iradier |  |  | PW-MG3 | 2020-11-20 | 2020-11-20 | No |  | Finished (blue) |  |  |  | USMANSMPMPVW01 |  |  | RE-HOST | Manufacturing | Payment | US | Pilot | Pilot | 00 - Pilot | Nov | MG1 | No | No | Complex Migration | High | Complex Migration | GBS Team in Costa Rica | Windows 2008 R2 | COTS | NA | 2, 1 Prod, 1 Quality. | 2 | NA | SAP ERP | IP Address |  | Done | 2020-10-05 | 2020-10-05 | Yes | 2020-11-03 | 2020-11-03 | Yes | 2020-11-03 | 2020-11-03 | Yes | 2020-11-03 | 2020-11-03 | Yes | 2020-11-10 | 2020-11-10 | Yes | 2020-11-14 | 2020-11-14 | Yes | 2020-11-07 | 2020-11-07 | Yes | 2020-11-10 | 2020-11-10 | Yes | 2020-11-20 | 2020-11-20 | Yes | 2020-11-20 | 2020-11-20 | Yes | 2020-11-21 | 2020-11-21 | Yes | 2020-11-23 | 2020-11-23 | Yes | 2020-11-23 | 2020-11-23 | Done, no evidence provided | N/A | N/A | Done, no evidence provided | Done, no evidence provided | N/A | N/A | Done with evidence provided | N/A | N/A | Yes | 2020-12-19 | 2021-01-02 | Yes | 2020-12-19 | 2021-02-08 | No | 2020-12-19 |  | No | 2020-12-19 |  | Yes | 2020-12-19 | 2021-01-13
123 | Paymetric | QA | Pablo Iradier |  |  | PW-MG1 | 2020-11-06 | 2020-11-06 | No |  | Finished (blue) |  |  |  | USMANSMPMDVW01 |  |  | RE-HOST | Manufacturing | Payment | US | Pilot | Pilot | 00 - Pilot | Nov | MG1 | No | No | Complex Migration | High | Complex Migration | GBS Team in Costa Rica | Windows 2008 R2 | COTS | NA | 2, 1 Prod, 1 Quality. | 2 | NA | SAP ERP | IP Address |  | Done | 2020-10-05 | 2020-10-05 | Yes | 2020-10-20 | 2020-10-20 | Yes | 2020-10-20 | 2020-10-20 | Yes | 2020-10-20 | 2020-10-20 | Yes | 2020-10-27 | 2020-10-27 | Yes | 2020-10-31 | 2020-10-31 | Yes | 2020-10-24 | 2020-10-24 | Yes | 2020-10-27 | 2020-10-27 | Yes | 2020-11-06 | 2020-11-06 | Yes | 2020-11-06 | 2020-11-06 | Yes | 2020-11-07 | 2020-11-07 | Yes | 2020-11-09 | 2020-11-09 | Yes | 2020-11-09 | 2020-11-09 | Done, no evidence provided | N/A | N/A | Done, no evidence provided | Done, no evidence provided | N/A | N/A | Done with evidence provided | N/A | N/A | Yes | 2020-12-05 | 2021-01-02 | Yes | 2020-12-05 | 2021-02-08 | No | 2020-12-05 |  | No | 2020-12-05 |  | Yes | 2020-12-05 | 2021-01-13
31 | PMPA | DEV | Sathiamurthy Samidurai | Stuart Robinson |  | W5-MG1 | 2021-05-07 | 2021-05-30 | No |  | Not started (grey) |  |  |  | USASHSMAPDVL01; USASHSMAPDVL02 |  |  | RE-HOST | Data & Analytics | Data & Analytics | US | 5 | 13 | 13 - Simple/Medium Apps | May | MG2 | No | Yes | Moderate Migration | Medium | Low to Medium | USA | Red hat Enterprise Linux OS 7.4 | Vendor Developed | MarkLogic Server 9 with VHF | Dev, Test, QA, Prod, DR | 19 | QA server USMEM-SMAPQVW01 shared with TM1 apps | DNS entries, URLs and GBIP datahub connection | Upgrading to ReactJS Need confirmation on release date Vendor Support Change over plan Known issue – Hardware Failure Follow Up gathering IP Change Dependency |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
31 | PMPA | QA | Sathiamurthy Samidurai | Stuart Robinson |  | W5-MG1 | 2021-05-07 | 2021-05-30 | No |  | Not started (grey) |  |  |  | USASHSMWSQVL01; USASHSMAPQVL01; USASHSMAPQVL02; USASHSMWSTVL01; USASHSMAPTVL01; USASHSMAPTVL02 | USASHSMDBQVL01; USASHSMDBTVL01 |  | RE-HOST | Data & Analytics | Data & Analytics | US | 5 | 13 | 13 - Simple/Medium Apps | May | MG2 | No | Yes | Moderate Migration | Medium | Low to Medium | USA | Red hat Enterprise Linux OS 7.4 | Vendor Developed | MarkLogic Server 9 with VHF | Dev, Test, QA, Prod, DR | 19 | QA server USMEM-SMAPQVW01 shared with TM1 apps | DNS entries, URLs and GBIP datahub connection | Upgrading to ReactJS Need confirmation on release date Vendor Support Change over plan Known issue – Hardware Failure Follow Up gathering IP Change Dependency |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
31 | PMPA | PROD | Sathiamurthy Samidurai | Stuart Robinson |  | W5-MG2 | 2021-05-21 | 2021-05-30 | No |  | Not started (grey) |  |  |  | USASHSMWSPVL01; USASHSMWSPVL02; USASHSMAPPVL01; USASHSMAPPVL02 | USASHSMDBPVL01; USASHSMDBPVL02; USASHSMDBPVL03 |  | RE-HOST | Data & Analytics | Data & Analytics | US | 5 | 13 | 13 - Simple/Medium Apps | May | MG2 | No | Yes | Moderate Migration | Medium | Low to Medium | USA | Red hat Enterprise Linux OS 7.4 | Vendor Developed | MarkLogic Server 9 with VHF | Dev, Test, QA, Prod, DR | 19 | QA server USMEM-SMAPQVW01 shared with TM1 apps | DNS entries, URLs and GBIP datahub connection | Upgrading to ReactJS Need confirmation on release date Vendor Support Change over plan Known issue – Hardware Failure Follow Up gathering IP Change Dependency |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
99 | Power BI (China) | QA | Jinble Li | Firas Almahamid |  | W6-MG1 | 2021-06-04 | 2021-06-30 | No |  | Not started (grey) |  |  |  | CNSHAQVQA01; | CNSHAQVQA01 | China servers TBD | RE-HOST(App)/RE-PLATFORM(DB) | Data & Analytics | Data & Analytics | APAC | 6 | 19 | 19 - APAC Complex Group | Jun | MG2 | No | Yes | Complex Migration | Simple | GxP complaint, High Customization. Heavy ETL Data/scripts runs daily. | APAC | Windows Server 2016 & 2012 R2 Std | COTS | SQL Server 2017, 2012 | QA , Prod | 2 | None | None | Risk 1 - As per SDM there is no dependencies of other application, however as per IT architecture it does have integration with SNI application Mitigation 1 - SDM and their development/Operation team needs to list out all the dependencies to this application. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
99 | Power BI (China) | PROD | Jinble Li | Firas Almahamid |  | W6-MG2 | 2021-06-18 | 2021-06-30 | No |  | Not started (grey) |  |  |  | CNSHAPOWERBI01 | CNSHAPOWERBI01 | China servers TBD | RE-HOST(App)/RE-PLATFORM(DB) | Data & Analytics | Data & Analytics | APAC | 6 | 19 | 19 - APAC Complex Group | Jun | MG2 | No | Yes | Complex Migration | Simple | GxP complaint, High Customization. Heavy ETL Data/scripts runs daily. | APAC | Windows Server 2016 & 2012 R2 Std | COTS | SQL Server 2017, 2012 | QA , Prod | 2 | None | None | Risk 1 - As per SDM there is no dependencies of other application, however as per IT architecture it does have integration with SNI application Mitigation 1 - SDM and their development/Operation team needs to list out all the dependencies to this application. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
85 | PricingTool | PROD | Andres Bernard | Firas Almahamid |  | W5-MG2 | 2021-05-21 | 2021-05-30 | No |  | Not started (grey) |  |  |  | ESBARSMWEBPW01 | ESBARSMWEBPW01 | EUAZRSMDBPVW01, EUAZRSMDBPVW02 | RE-HOST(App)/RE-PLATFORM(DB) | Commercial | Commercial | EMEA | 5 | 15 | 15 - EMEA Medium Application REHOST Only Group | May | MG2 | No | No | Moderate Migration | Medium | Moderate | Europe | Windows 2012 R2 | SNI developed | SQLServer 2008 R2 | Prod,Dev | 2 | None | The application is communicating with Cognos and SAP for data retrieval. Communication with Cognos via http o Cognos is by the host name: usatl-smappuw03 o SAP uses winshuttle and it is by the host name: http://winshuttle.smith-nephew.com/QueryFiles/ | No supporting and testcase documents Configuration place holders for the IP address Need SDM/SME support for technical support during migration SAP, Cognos Integration points to be validated in Azure Cloud. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
82 | Primion | PROD | Paul Davison | Chris Cook |  | W4-MG2 | 2021-04-23 | 2021-05-30 | No |  | On track (green) | Infra and DB team to share cutover steps | Kishore | Srikanth | UKRTHSMAPPVW23 | UKRTHSMDBPW04; UKRTHSMDBPW03 | EUAZRSMDBPVW01, EUAZRSMDBPVW02 | RE-HOST(App)/RE-PLATFORM(DB) | Group Functions | Group Functions | EMEA | 5 | 15 | 15 - EMEA Medium Application REHOST Only Group | May | MG2 | No | No | Moderate Migration | Low | Moderate migration | Germany | App - Windows Server 2012 Standard – Dedicated VM, DB - Windows Server 2008 R2 Enterprise – Physical Servers | COTS | MS Cluster SQL Database 2005 – PWS on SMRTHSQL2 Server | Prod | 3 | 1. QA Change Control 2. Nomino SecurityFlex LM | 1. Client and all terminal devices, door access, alarm solution all needs to be referred to new IP. 2. Other applications are also using these servers. Need to sort out dependency and plan it effectively. Both VMs are shared by others apps as mentioned below: UKRTHSMDBPW04 UKRTHSMDBPW03 QA Change Control Nomino Security | Cluster SQL Database is shared across with other applications in SNI Other applications are also using these servers. Need to sort out dependency and plan it effectively. 1. QA Change Control 2. Nomino SecurityFlex LM IP Address Change – Hardcoding Client and all terminal devices, door access, alarm solution all needs to be referred to new IP. Customer is expecting an upgrade As per SME, Upgrade is recommended, based on the experience with Hydra which was tried and tested in AWS cloud and brought back to On-prem. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
19 | PTC Creo | PROD | Requalann Pereira | Sri Tupil |  | W6-MG1 | 2021-06-04 | 2021-01-30 | No |  | Not started (grey) |  |  |  | BBTAPP01 |  |  | RE-HOST | R&D | R&D | US | 1 | 1 | 01 - Network License Server - Batch 1 | Jan | MG1 | No | No | Moderate migration | Low | Moderate migration | USA | Windows Server 2012 R2 Standard | COTS | NA | Prod | 1 | The server BBTAPP01 is co-hosted with Network License Server by other few applications . Vericut, Altium Designer, MATLAB & Solidworks (Standalone Edition). | 1) Server BBTAPP01 also host Network License Manager for Vericut, Altium Designer, MATLAB & Solidworks (Standalone Edition). 2) The files are stored in server BBTFIEL01 server and the user will be accessing the file from the app server, it has been classified as ‘Infrastructure Servers - AMER - Non-Qualified’ in SNI Inventory.K8 | 1) The server BBTAPP01 is co-hosted with Network License Server by other few applications.Move group to be created to move this server post consultation with SDM of the following application… Vericut, Altium Designer, MATLAB & Solidworks (Standalone Edition). 2) File server BBTFIEL01 used for file storage.Migration to enable IP/port. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  | 2021-01-21 | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
130 | QA Change Control | DEV | Aileen Diola | Sri Tupil |  | W1-MG2 | 2021-01-22 | 2021-01-22 | No |  | Finished (blue) |  |  |  | USMAN-SMWSDVW07 | SMRTHSQL3 (Cluster); UKRTHSMDBPW06; UKRTHSMDBPW05; | USAZRSMDBDVW02 | RE-HOST(App)/RE-PLATFORM(DB) |  | RAQA | US | 1 |  |  |  |  | No | [14 empty] | Done | 2020-12-11 | 2020-12-11 | Yes | 2020-12-30 | 2021-01-22 | No | 2021-01-13 | 2021-01-14 | Yes | 2021-01-04 | 2021-01-08 | Yes | 2021-01-11 | 2021-01-15 | Yes | 2021-01-15 | 2021-01-18 | Yes | 2021-01-15 | 2021-01-15 | Yes | 2021-01-18 | 2021-01-18 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-21 | 2021-01-22 | Yes | 2021-01-22 | 2021-01-22 | Yes | 2021-01-24 | 2021-01-24 | Yes | 2021-01-24 | 2021-01-25 | Done, no evidence provided | N/A | N/A | Done, no evidence provided | Done, no evidence provided | N/A | N/A | N/A | N/A | N/A | No | 2021-02-19 |  | Yes | 2021-02-19 | 2021-02-08 | No | 2021-02-19 |  | No | 2021-02-19 |  | No | 2021-02-19
130 | QA Change Control | QA | Aileen Diola | Sri Tupil |  | W1-MG2 | 2021-01-22 | 2021-01-22 | No |  | Finished (blue) |  |  |  | USMAN-SMWSQVW05 | SMRTHSQL3 (Cluster); UKRTHSMDBPW06; UKRTHSMDBPW05; | USAZRSMDBQVW01 | RE-HOST(App)/RE-PLATFORM(DB) |  | RAQA | US | 1 |  |  |  |  | No | [14 empty] | Done | 2020-12-11 | 2020-12-11 | Yes | 2020-12-30 | 2021-01-22 | No | 2021-01-13 | 2021-01-14 | Yes | 2021-01-04 | 2021-01-08 | Yes | 2021-01-11 | 2021-01-15 | Yes | 2021-01-15 | 2021-01-18 | Yes | 2021-01-15 | 2021-01-15 | Yes | 2021-01-18 | 2021-01-18 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-21 | 2021-01-22 | Yes | 2021-01-22 | 2021-01-22 | Yes | 2021-01-24 | 2021-01-24 | Yes | 2021-01-24 | 2021-01-25 | Done, no evidence provided | N/A | N/A | Done, no evidence provided | Done, no evidence provided | N/A | N/A | N/A | N/A | N/A | No | 2021-02-19 |  | Yes | 2021-02-19 | 2021-02-08 | No | 2021-02-19 |  | No | 2021-02-19 |  | No | 2021-02-19
130 | QA Change Control | PROD | Aileen Diola | Sri Tupil |  | W3-MG1 | 2021-03-05 | 2021-03-05 | No |  | On track (green) |  | Vidit Kumar | Rahul Sarin | USMAN-SMWSPVW12 | SMRTHSQL2(SQL Cluster); UKRTHSMDBPW03; UKRTHSMDBPW04 | USAZRSMDBPVW02, USAZRSMDBPVW03 | RE-HOST(App)/RE-PLATFORM(DB) |  | RAQA | US | 1 |  |  |  |  | No | [14 empty] | Yes | 2020-01-25 | 2021-01-28 | Yes | 2020-02-08 | 2020-02-10 | Yes | 2021-02-08 | 2020-02-10 | Yes |  |  | Yes |  |  | Yes |  |  | Yes | 2021-02-10 | 2021-02-11 | Yes | 2021-02-17 | 2021-02-17 | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
72 | QAD ERP | DEV | Carla Morris | Chris Cook |  | W5-MG1 | 2021-05-07 | 2021-05-30 | No |  | Not started (grey) |  |  |  | QAD01 |  |  | RE-HOST | Manufacturing | Manufacturing - Inventory | US | 5 | 14 | 14 - Shop Floor Medium/Complex Application | May | MG1 | No | Yes | Complex Migration | Medium | Complex Migration | US-MD/Columbia | Linux 6.9 | COTS | Progress Database | 4 Environments, Prod, Test, Dev, Val – Total 4 Instances on same VM - QAD01 - VM | 4 | Eagle RF express.Both QAD ERP & Eagle RF Express applications will be covered in one application migration. | SAP, Eagle RF Express Guns. | QAD ERP - This is tightly coupled with the Eagle RF Express application. The migration for QAP ERP will also suffice the migration requirement for Eagle RF Express. **************************************************************** Printer Configuration, Third Party Drivers. COTS version compatibility | Moved to a different server in DC | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
72 | QAD ERP | TEST | Carla Morris | Chris Cook |  | W5-MG1 | 2021-05-07 | 2021-05-30 | No |  | Not started (grey) |  |  |  | QAD01 |  |  | RE-HOST | Manufacturing | Manufacturing - Inventory | US | 5 | 14 | 14 - Shop Floor Medium/Complex Application | May | MG1 | No | Yes | Complex Migration | Medium | Complex Migration | US-MD/Columbia | Linux 6.9 | COTS | Progress Database | 4 Environments, Prod, Test, Dev, Val – Total 4 Instances on same VM - QAD01 - VM | 4 | Eagle RF express.Both QAD ERP & Eagle RF Express applications will be covered in one application migration. | SAP, Eagle RF Express Guns. | QAD ERP - This is tightly coupled with the Eagle RF Express application. The migration for QAP ERP will also suffice the migration requirement for Eagle RF Express. **************************************************************** Printer Configuration, Third Party Drivers. COTS version compatibility | Moved to a different server in DC | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
72 | QAD ERP | VAL | Carla Morris | Chris Cook |  | W5-MG1 | 2021-05-07 | 2021-05-30 | No |  | Not started (grey) |  |  |  | QAD01 |  |  | RE-HOST | Manufacturing | Manufacturing - Inventory | US | 5 | 14 | 14 - Shop Floor Medium/Complex Application | May | MG1 | No | Yes | Complex Migration | Medium | Complex Migration | US-MD/Columbia | Linux 6.9 | COTS | Progress Database | 4 Environments, Prod, Test, Dev, Val – Total 4 Instances on same VM - QAD01 - VM | 4 | Eagle RF express.Both QAD ERP & Eagle RF Express applications will be covered in one application migration. | SAP, Eagle RF Express Guns. | QAD ERP - This is tightly coupled with the Eagle RF Express application. The migration for QAP ERP will also suffice the migration requirement for Eagle RF Express. **************************************************************** Printer Configuration, Third Party Drivers. COTS version compatibility | Moved to a different server in DC | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
72 | QAD ERP | PROD | Carla Morris | Chris Cook |  | W5-MG1 | 2021-05-07 | 2021-05-30 | No |  | Not started (grey) |  |  |  | QAD01 |  |  | RE-HOST | Manufacturing | Manufacturing - Inventory | US | 5 | 14 | 14 - Shop Floor Medium/Complex Application | May | MG1 | No | Yes | Complex Migration | Medium | Complex Migration | US-MD/Columbia | Linux 6.9 | COTS | Progress Database | 4 Environments, Prod, Test, Dev, Val – Total 4 Instances on same VM - QAD01 - VM | 4 | Eagle RF express.Both QAD ERP & Eagle RF Express applications will be covered in one application migration. | SAP, Eagle RF Express Guns. | QAD ERP - This is tightly coupled with the Eagle RF Express application. The migration for QAP ERP will also suffice the migration requirement for Eagle RF Express. **************************************************************** Printer Configuration, Third Party Drivers. COTS version compatibility | Moved to a different server in DC | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
100 | RADB | QA | Aileen Diola | Sri Tupil |  | W6-MG1 | 2021-06-04 | 2021-06-30 | No |  | Not started (grey) |  |  |  | CNSHARADB01 | CNSHABIDEV01 |  | RE-HOST | RAQA | RAQA | APAC | 6 | 19 | 19 - APAC Complex Group | Jun | MG2 | No | No | Complex Migration | Medium | Complex Migration | APAC | Window 2008 R2 Std | Vendor | Window 2012 R2 Std + SQL Server 2012 |  | 5 | None | DNS entries, URLs, Bartender, Power-AX DR server is shared with other apps | Risk 1 - IP Address Change – Hardcoding Mitigation 1 - Resolve with hostname/domain name. If not, validate IP change and reconfigure integration systems. Risk 2 - SME Availability Mitigation 2 - Ensure SME / Vendor support for migration Risk 3 - Application integration and external connect Mitigation 3 - Identify integration points before migration |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
100 | RADB | PROD | Aileen Diola | Sri Tupil |  | W6-MG2 | 2021-06-18 | 2021-06-30 | No |  | Not started (grey) |  |  |  | CNSHALABELING01 | CNSHACLSDB01 |  | RE-HOST | RAQA | RAQA | APAC | 6 | 19 | 19 - APAC Complex Group | Jun | MG2 | No | No | Complex Migration | Medium | Complex Migration | APAC | Window 2008 R2 Std | Vendor | Window 2012 R2 Std + SQL Server 2012 |  | 5 | None | DNS entries, URLs, Bartender, Power-AX DR server is shared with other apps | Risk 1 - IP Address Change – Hardcoding Mitigation 1 - Resolve with hostname/domain name. If not, validate IP change and reconfigure integration systems. Risk 2 - SME Availability Mitigation 2 - Ensure SME / Vendor support for migration Risk 3 - Application integration and external connect Mitigation 3 - Identify integration points before migration |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
100 | RADB | DR | Aileen Diola | Sri Tupil |  | W6-MG2 | 2021-06-18 | 2021-06-30 | No |  | Not started (grey) |  |  |  |  | CNSHADRDB02 |  | RE-HOST | RAQA | RAQA | APAC | 6 | 19 | 19 - APAC Complex Group | Jun | MG2 | No | No | Complex Migration | Medium | Complex Migration | APAC | Window 2008 R2 Std | Vendor | Window 2012 R2 Std + SQL Server 2012 |  | 5 | None | DNS entries, URLs, Bartender, Power-AX DR server is shared with other apps | Risk 1 - IP Address Change – Hardcoding Mitigation 1 - Resolve with hostname/domain name. If not, validate IP change and reconfigure integration systems. Risk 2 - SME Availability Mitigation 2 - Ensure SME / Vendor support for migration Risk 3 - Application integration and external connect Mitigation 3 - Identify integration points before migration |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
101 | RAMS (China) | QA | Aileen Diola | Sri Tupil |  | W6-MG1 | 2021-06-04 | 2021-06-30 | No |  | Not started (grey) |  |  |  | CNSHABPMQADB01 | CNSHABPMQADB01 | China servers TBD | RE-HOST(App)/RE-PLATFORM(DB) | RAQA | RAQA | APAC | 6 | 19 | 19 - APAC Complex Group | Jun | MG2 | No | No | Complex Migration | High | RAMS process is part of Eflow | APAC | Windows 2012 R2 Standard Windows 2008 R2 Enterprise | COTS | MS SQL Server 2012 | Prod,QA,DR | 6 | Both E-Flow & RAMS(China) applications will be covered in one application migration. | Data warehouse (Hospital data, Distributor TSA, Report), POWeR AX2012(MMDM,VMDM), Salesforce(DRM,DMDM), Biz talk(DMDM), WeChat, SFDC. | As learnt during the SME sessions, RAMS(China) is a process under the E-FLOW application. ******************************************************************************** Risk 1 - DMZ server Mitigation 1 - Public facing url to be tested when move of DMZ server is made. Risk 2 - Hardcoded IP in source code Mitigation 2 - Some web page is using the hardcoded IP address in the application. SDM/SME need confirm with the vendor before migration to either change it and test in lower Env., before the same is replicated to PROD. Risk 3 - SDM project team expecting HA & LB to be implemented on new cloud environment. Mitigation 3 - SDM needs to talk to their VP/Ken/Chris to initiate the talk, and work on the plan & cost of the same. Note: To be cognizant that these may not be part of this migration budget. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
101 | RAMS (China) | PROD | Aileen Diola | Sri Tupil |  | W6-MG2 | 2021-06-18 | 2021-06-30 | No |  | Not started (grey) |  |  |  | CNSHABPM02; CNSHABPMQA01; CNSHABPM01; | CNSHABPMDB01 | China servers TBD | RE-HOST(App)/RE-PLATFORM(DB) | RAQA | RAQA | APAC | 6 | 19 | 19 - APAC Complex Group | Jun | MG2 | No | No | Complex Migration | High | RAMS process is part of Eflow | APAC | Windows 2012 R2 Standard Windows 2008 R2 Enterprise | COTS | MS SQL Server 2012 | Prod,QA,DR | 6 | Both E-Flow & RAMS(China) applications will be covered in one application migration. | Data warehouse (Hospital data, Distributor TSA, Report), POWeR AX2012(MMDM,VMDM), Salesforce(DRM,DMDM), Biz talk(DMDM), WeChat, SFDC. | As learnt during the SME sessions, RAMS(China) is a process under the E-FLOW application. ******************************************************************************** Risk 1 - DMZ server Mitigation 1 - Public facing url to be tested when move of DMZ server is made. Risk 2 - Hardcoded IP in source code Mitigation 2 - Some web page is using the hardcoded IP address in the application. SDM/SME need confirm with the vendor before migration to either change it and test in lower Env., before the same is replicated to PROD. Risk 3 - SDM project team expecting HA & LB to be implemented on new cloud environment. Mitigation 3 - SDM needs to talk to their VP/Ken/Chris to initiate the talk, and work on the plan & cost of the same. Note: To be cognizant that these may not be part of this migration budget. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
101 | RAMS (China) | DR | Aileen Diola | Sri Tupil |  | W6-MG2 | 2021-06-18 | 2021-06-30 | No |  | Not started (grey) |  |  |  | CNSHADRDB03 | CNSHADRDB04 | China servers TBD | RE-HOST(App)/RE-PLATFORM(DB) | RAQA | RAQA | APAC | 6 | 19 | 19 - APAC Complex Group | Jun | MG2 | No | No | Complex Migration | High | RAMS process is part of Eflow | APAC | Windows 2012 R2 Standard Windows 2008 R2 Enterprise | COTS | MS SQL Server 2012 | Prod,QA,DR | 6 | Both E-Flow & RAMS(China) applications will be covered in one application migration. | Data warehouse (Hospital data, Distributor TSA, Report), POWeR AX2012(MMDM,VMDM), Salesforce(DRM,DMDM), Biz talk(DMDM), WeChat, SFDC. | As learnt during the SME sessions, RAMS(China) is a process under the E-FLOW application. ******************************************************************************** Risk 1 - DMZ server Mitigation 1 - Public facing url to be tested when move of DMZ server is made. Risk 2 - Hardcoded IP in source code Mitigation 2 - Some web page is using the hardcoded IP address in the application. SDM/SME need confirm with the vendor before migration to either change it and test in lower Env., before the same is replicated to PROD. Risk 3 - SDM project team expecting HA & LB to be implemented on new cloud environment. Mitigation 3 - SDM needs to talk to their VP/Ken/Chris to initiate the talk, and work on the plan & cost of the same. Note: To be cognizant that these may not be part of this migration budget. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
20 | Recon LaunchPad (SSO) | DEV | Andres Bernard | Firas Almahamid |  | W1-MG2 | 2021-01-22 | 2021-01-22 | No |  | Finished (blue) |  |  |  | USMAN-SMWSDVW07 |  |  | RE-HOST | Commercial | Commercial | US | 1 | 3 | 03 - SNI Developed + Co-Hosted Apps | Jan | MG2 | No | No | Complex Migration | Medium | Complex Migration | USA | Windows Server 2012 R2 | SNI Dev | NA | Dev,QA,Prod | 3 | SNID Archived shipping documents ECAP ENCORE EndoLoans HR Notification Global Returns Disposition Tool Inventures Web App Nomino Security QA Change Control GSC DataWareHouse Reimbursement Sales Request Forms Non-Employee Database | Below are the List of all the SNI Application/Domains/websites, that Recon LaunchPad serves to facilitate SSO authentication. Express Instruments Express Implants Express Visionaire | 1) Shared server with following apps a. SNID Archived Shipping Documents b. ECAP c. ENCORE d. Endo Loans e. Global Returns Disposition Tool f. GSC Data Warehouse Admin Tool g. HR Notification h. Inventures (SCAMPI) Web App i. Non-Employee Database j. Nomino Security k. QA Change Control l. Reimbursement m. Sales Request Forms When migrating into azure need to plan all the app in same move group. 2) No Test cases and Documents.Need support from SDM/SME/Support team during migration. |  | Done | 2020-12-11 | 2020-12-11 | Yes | 2020-12-30 | 2021-01-22 | No | 2021-01-13 | 2021-01-13 | Yes | 2021-01-04 | 2021-01-04 | Yes | 2021-01-11 | 2021-01-11 | Yes | 2021-01-15 | 2021-01-15 | Yes | 2021-01-08 | 2021-01-08 | Yes | 2021-01-13 | 2021-01-13 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-22 | 2021-01-22 | Yes | 2021-01-24 | 2021-01-24 | Yes | 2021-01-24 | 2021-01-24 | Done, no evidence provided | N/A | N/A | Done, no evidence provided | Done, no evidence provided | N/A | N/A | N/A | N/A | N/A | No | 2021-02-19 |  | Yes | 2021-02-19 | 2021-02-08 | No | 2021-02-19 |  | No | 2021-02-19 |  | No | 2021-02-19
20 | Recon LaunchPad (SSO) | QA | Andres Bernard | Firas Almahamid |  |  |  | 2021-01-30 | Yes | According to cutover planning there is no QA environment for this App. | Out of scope (dark grey) |  |  |  | USMAN-SMWSQVW05 |  |  | RE-HOST | Commercial | Commercial | US | 1 | 3 | 03 - SNI Developed + Co-Hosted Apps | Jan | MG2 | No | No | Complex Migration | Medium | Complex Migration | USA | Windows Server 2012 R2 | SNI Dev | NA | Dev,QA,Prod | 3 | SNID Archived shipping documents ECAP ENCORE EndoLoans HR Notification Global Returns Disposition Tool Inventures Web App Nomino Security QA Change Control GSC DataWareHouse Reimbursement Sales Request Forms Non-Employee Database | Below are the List of all the SNI Application/Domains/websites, that Recon LaunchPad serves to facilitate SSO authentication. Express Instruments Express Implants Express Visionaire | 1) Shared server with following apps a. SNID Archived Shipping Documents b. ECAP c. ENCORE d. Endo Loans e. Global Returns Disposition Tool f. GSC Data Warehouse Admin Tool g. HR Notification h. Inventures (SCAMPI) Web App i. Non-Employee Database j. Nomino Security k. QA Change Control l. Reimbursement m. Sales Request Forms When migrating into azure need to plan all the app in same move group. 2) No Test cases and Documents.Need support from SDM/SME/Support team during migration. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  | 2021-01-21 | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
20 | Recon LaunchPad (SSO) | PROD | Andres Bernard | Firas Almahamid |  | W3-MG1 | 2021-03-05 | 2021-03-05 | No |  | On track (green) |  | Deepak Sathya Babu | Rahul Sarin | USMAN-SMWSPVW12 |  |  | RE-HOST | Commercial | Commercial | US | 1 | 3 | 03 - SNI Developed + Co-Hosted Apps | Jan | MG2 | No | No | Complex Migration | Medium | Complex Migration | USA | Windows Server 2012 R2 | SNI Dev | NA | Dev,QA,Prod | 3 | SNID Archived shipping documents ECAP ENCORE EndoLoans HR Notification Global Returns Disposition Tool Inventures Web App Nomino Security QA Change Control GSC DataWareHouse Reimbursement Sales Request Forms Non-Employee Database | Below are the List of all the SNI Application/Domains/websites, that Recon LaunchPad serves to facilitate SSO authentication. Express Instruments Express Implants Express Visionaire | 1) Shared server with following apps a. SNID Archived Shipping Documents b. ECAP c. ENCORE d. Endo Loans e. Global Returns Disposition Tool f. GSC Data Warehouse Admin Tool g. HR Notification h. Inventures (SCAMPI) Web App i. Non-Employee Database j. Nomino Security k. QA Change Control l. Reimbursement m. Sales Request Forms When migrating into azure need to plan all the app in same move group. 2) No Test cases and Documents.Need support from SDM/SME/Support team during migration. |  | Yes | 2020-01-25 | 2021-01-28 | Yes | 2020-02-08 | 2020-02-10 | Yes | 2021-02-08 | 2020-02-10 | No |  |  | No |  |  | No |  |  | Yes | 2021-02-10 | 2021-02-11 | Yes | 2021-02-17 | 2021-02-17 | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
15 | Reimbursement | DEV | Andres Bernard | Firas Almahamid |  | W1-MG2 | 2021-01-22 | 2021-01-22 | No |  | Finished (blue) |  |  |  | USMEMSMAPDVW18(User Facing Module); USMAN-SMWSDVW07(Reimbursement Admin); | USMAN-SMDPDVW16 | USAZRSMDBDVW02 | RE-HOST(App)/RE-PLATFORM(DB) | Commercial | Commercial | US | 1 | 3 | 03 - SNI Developed + Co-Hosted Apps | Jan | MG2 | No | No | Simple Migration | Low | I am migrating it to SaaS | USA | Window Server 2012 R2 | SNI developed | SQL Server 2012 R2 | DEV, QA, Prod | 5 | None | Nothing | Uses legacy technology SDM Opinion Version issue Missing Info Classic Asp.net I’m migrating it to SaaS Legacy asp version DB Version, OS Version, Dependency |  | Done | 2020-12-11 | 2020-12-11 | Yes | 2020-12-30 | 2021-01-22 | No | 2021-01-13 | 2021-01-13 | Yes | 2021-01-04 | 2021-01-04 | Yes | 2021-01-11 | 2021-01-11 | Yes | 2021-01-15 | 2021-01-15 | Yes | 2021-01-08 | 2021-01-08 | Yes | 2021-01-13 | 2021-01-13 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-22 | 2021-01-22 | Yes | 2021-01-24 | 2021-01-24 | Yes | 2021-01-24 | 2021-01-24 | Done, no evidence provided | N/A | N/A | Done, no evidence provided | Done, no evidence provided | N/A | N/A | N/A | N/A | N/A | No | 2021-02-19 |  | Yes | 2021-02-19 | 2021-02-08 | No | 2021-02-19 |  | No | 2021-02-19 |  | No | 2021-02-19
15 | Reimbursement | QA | Andres Bernard | Firas Almahamid |  | W1-MG2 | 2021-01-22 | 2021-01-22 | No |  | Finished (blue) |  |  |  | USMAN-SMWSQVW05(Reimbursement Admin) | USMAN-SMDPDVW16 | USAZRSMDBQVW01 | RE-HOST(App)/RE-PLATFORM(DB) | Commercial | Commercial | US | 1 | 3 | 03 - SNI Developed + Co-Hosted Apps | Jan | MG2 | No | No | Simple Migration | Low | I am migrating it to SaaS | USA | Window Server 2012 R2 | SNI developed | SQL Server 2012 R2 | DEV, QA, Prod | 5 | None | Nothing | Uses legacy technology SDM Opinion Version issue Missing Info Classic Asp.net I’m migrating it to SaaS Legacy asp version DB Version, OS Version, Dependency |  | Done | 2020-12-11 | 2020-12-11 | Yes | 2020-12-30 | 2021-01-22 | No | 2021-01-13 | 2021-01-13 | Yes | 2021-01-04 | 2021-01-04 | Yes | 2021-01-11 | 2021-01-11 | Yes | 2021-01-15 | 2021-01-15 | Yes | 2021-01-08 | 2021-01-08 | Yes | 2021-01-13 | 2021-01-13 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-22 | 2021-01-22 | Yes | 2021-01-24 | 2021-01-24 | Yes | 2021-01-24 | 2021-01-24 | Done, no evidence provided | N/A | N/A | Done, no evidence provided | Done, no evidence provided | N/A | N/A | N/A | N/A | N/A | No | 2021-02-19 |  | Yes | 2021-02-19 | 2021-02-08 | No | 2021-02-19 |  | No | 2021-02-19 |  | No | 2021-02-19
15 | Reimbursement | PROD | Andres Bernard | Firas Almahamid |  | W3-MG1 | 2021-03-05 | 2021-03-05 | No |  | Imminent Delay (red) | Network and Security Changes are pending to enable access to App from Internet and Intranet. | Deepak Sathya Babu | Rahul Sarin | USMEMSMAPPVW23; USMAN-SMWSPVW12(Reimbursement Admin); | USMAN-SMDBPVW12 | USAZRSMDBPVW02, USAZRSMDBPVW03 | RE-HOST(App)/RE-PLATFORM(DB) | Commercial | Commercial | US | 1 | 3 | 03 - SNI Developed + Co-Hosted Apps | Jan | MG2 | No | No | Simple Migration | Low | I am migrating it to SaaS | USA | Window Server 2012 R2 | SNI developed | SQL Server 2012 R2 | DEV, QA, Prod | 5 | None | Nothing | Uses legacy technology SDM Opinion Version issue Missing Info Classic Asp.net I’m migrating it to SaaS Legacy asp version DB Version, OS Version, Dependency |  | Yes | 2020-01-25 | 2021-01-28 | Yes | 2020-02-08 | 2020-02-10 | Yes | 2021-02-08 | 2020-02-10 | No |  |  | No |  |  | No |  |  | Yes | 2021-02-10 | 2021-02-11 | Yes | 2021-02-17 | 2021-02-17 | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
21 | Sales Request Forms | DEV | Andres Bernard | Firas Almahamid |  | W1-MG2 | 2021-01-22 | 2021-01-22 | No |  | Finished (blue) |  |  |  | USMAN-SMWSDVW07 | USMAN-SMDPDVW16 | USAZRSMDBDVW02 | RE-HOST(App)/RE-PLATFORM(DB) | Commercial | Commercial | US | 1 | 3 | 03 - SNI Developed + Co-Hosted Apps | Jan | MG2 | No | No | Simple | Medium | Simple | USA | Windows Server 2012 R2 | SNI Dev | Sql Server 2012 R2 | Dev,QA,Prod | 4 | SNID Archived shipping documents ECAP ENCORE EndoLoans HR Notification Global Returns Disposition Tool Inventures Web App Nomino Security QA Change Control GSC DataWareHouse Reimbursement Recon LaunchPad Non-Employee Database | We are getting oracle data from DataHUB .In the DataHUB side we have a SONAR batch job to pull the data from the oracle and load it into the Sales Request Form DB. From Cloud point since the oracle is not in cloud we will be having a latency after migration. | The same server is shared by many other application/database.To migrate the applications in this server to azure in one group. |  | Done | 2020-12-11 | 2020-12-11 | Yes | 2020-12-30 | 2021-01-22 | No | 2021-01-13 | 2021-01-13 | Yes | 2021-01-04 | 2021-01-04 | Yes | 2021-01-11 | 2021-01-11 | Yes | 2021-01-15 | 2021-01-15 | Yes | 2021-01-08 | 2021-01-08 | Yes | 2021-01-13 | 2021-01-13 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-22 | 2021-01-22 | Yes | 2021-01-24 | 2021-01-24 | Yes | 2021-01-24 | 2021-01-24 | Done, no evidence provided | N/A | N/A | Done, no evidence provided | Done, no evidence provided | N/A | N/A | N/A | N/A | N/A | No | 2021-02-19 |  | Yes | 2021-02-19 | 2021-02-08 | No | 2021-02-19 |  | No | 2021-02-19 |  | No | 2021-02-19
21 | Sales Request Forms | QA | Andres Bernard | Firas Almahamid |  | W1-MG2 | 2021-01-22 | 2021-01-22 | No |  | Finished (blue) |  |  |  | USMAN-SMWSQVW05 | USMAN-SMDPDVW16 | USAZRSMDBQVW01 | RE-HOST(App)/RE-PLATFORM(DB) | Commercial | Commercial | US | 1 | 3 | 03 - SNI Developed + Co-Hosted Apps | Jan | MG2 | No | No | Simple | Medium | Simple | USA | Windows Server 2012 R2 | SNI Dev | Sql Server 2012 R2 | Dev,QA,Prod | 4 | SNID Archived shipping documents ECAP ENCORE EndoLoans HR Notification Global Returns Disposition Tool Inventures Web App Nomino Security QA Change Control GSC DataWareHouse Reimbursement Recon LaunchPad Non-Employee Database | We are getting oracle data from DataHUB .In the DataHUB side we have a SONAR batch job to pull the data from the oracle and load it into the Sales Request Form DB. From Cloud point since the oracle is not in cloud we will be having a latency after migration. | The same server is shared by many other application/database.To migrate the applications in this server to azure in one group. |  | Done | 2020-12-11 | 2020-12-11 | Yes | 2020-12-30 | 2021-01-22 | No | 2021-01-13 | 2021-01-13 | Yes | 2021-01-04 | 2021-01-04 | Yes | 2021-01-11 | 2021-01-11 | Yes | 2021-01-15 | 2021-01-15 | Yes | 2021-01-08 | 2021-01-08 | Yes | 2021-01-13 | 2021-01-13 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-22 | 2021-01-22 | Yes | 2021-01-24 | 2021-01-24 | Yes | 2021-01-24 | 2021-01-24 | Done, no evidence provided | N/A | N/A | Done, no evidence provided | Done, no evidence provided | N/A | N/A | N/A | N/A | N/A | No | 2021-02-19 |  | Yes | 2021-02-19 | 2021-02-08 | No | 2021-02-19 |  | No | 2021-02-19 |  | No | 2021-02-19
21 | Sales Request Forms | PROD | Andres Bernard | Firas Almahamid |  | W3-MG1 | 2021-03-05 | 2021-03-05 | No |  | On track (green) |  | Deepak Sathya Babu | Rahul Sarin | USMAN-SMWSPVW12 | USMAN-SMDBPVW12 | USAZRSMDBPVW02, USAZRSMDBPVW03 | RE-HOST(App)/RE-PLATFORM(DB) | Commercial | Commercial | US | 1 | 3 | 03 - SNI Developed + Co-Hosted Apps | Jan | MG2 | No | No | Simple | Medium | Simple | USA | Windows Server 2012 R2 | SNI Dev | Sql Server 2012 R2 | Dev,QA,Prod | 4 | SNID Archived shipping documents ECAP ENCORE EndoLoans HR Notification Global Returns Disposition Tool Inventures Web App Nomino Security QA Change Control GSC DataWareHouse Reimbursement Recon LaunchPad Non-Employee Database | We are getting oracle data from DataHUB .In the DataHUB side we have a SONAR batch job to pull the data from the oracle and load it into the Sales Request Form DB. From Cloud point since the oracle is not in cloud we will be having a latency after migration. | The same server is shared by many other application/database.To migrate the applications in this server to azure in one group. |  | Yes | 2020-01-25 | 2021-01-28 | Yes | 2020-02-08 | 2020-02-10 | Yes | 2021-02-08 | 2020-02-10 | No |  |  | No |  |  | No |  |  | Yes | 2021-02-10 | 2021-02-11 | Yes | 2021-02-17 | 2021-02-17 | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
51 | SEAL Application | PROD | Krzysztof Gaik | Massimo Trambaioli |  | W4-MG1 | 2021-04-09 | 2021-03-30 | No |  | On track (green) | Infra team to share cutover steps | Saurabh | Praveen | UKHUL-SMAPPVW10 | NA |  | RE-PLATFORM | ERP | ERP | EMEA | 3 | 8 | 08 - Full Throttle EMEA Application - Batch 1 | Mar | MG2 | No | Yes | Moderate Migration | Medium | High / Complex | Europe and Asia | Windows Server 2008 Standard | COTS | NA | Prod | 1 | NA | SAP connectivity | SAP connectivity Ensure hybrid strategy is implemented, may be during landing zone or subsequent phase. IP dependency - hardcoding SNI provides IP change details ahead of migration |  | Yes | 2020-01-25 | 2021-01-28 | No | 2020-02-08 |  | No |  |  | No |  |  | No |  |  | No |  |  | No | 2021-02-24 |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
119 | Smart EHL | DEV | Paul Davison | Chris Cook |  | W7-MG1 | 2021-07-09 | 2021-07-30 | No |  | Not started (grey) |  |  |  | UKRTH-SMAPPVW30 | UKRTH-SMDBPVW30 |  | RE-HOST | Group Functions | Group Functions | EMEA | 7 | 21 | 21 - Final EMEA/APAC application | Jul | MG2 | No | No | Moderate Migration | Low | Moderate | Hull AWM | Window Server 2008 R2 | COTS | SQL Server 2008 R2 | Dev,Prod | 4 | None | IP Hardcoding Biostar Server communication | Vendor support SNI enable vendor support during migration IP Dependency Do changes in Biostar devices / server |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
119 | Smart EHL | PROD | Paul Davison | Chris Cook |  | W7-MG1 | 2021-07-09 | 2021-07-30 | No |  | Not started (grey) |  |  |  | UKRTH-SMAPPVW30 | UKRTH-SMDBPVW30 |  | RE-HOST | Group Functions | Group Functions | EMEA | 7 | 21 | 21 - Final EMEA/APAC application | Jul | MG2 | No | No | Moderate Migration | Low | Moderate | Hull AWM | Window Server 2008 R2 | COTS | SQL Server 2008 R2 | Dev,Prod | 4 | None | IP Hardcoding Biostar Server communication | Vendor support SNI enable vendor support during migration IP Dependency Do changes in Biostar devices / server |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
16 | SNID Archived Shipping Documents | DEV | Amit Shokeen | Massimo Trambaioli |  | W1-MG2 | 2021-01-22 | 2021-01-22 | No |  | Finished (blue) |  |  |  | USMAN-SMWSDVW07 |  |  | RE-HOST | Supply Chain | Supply Chain | US | 1 | Pilot | 03 - SNI Developed + Co-Hosted Apps | Nov | MG2 | No | No | Moderate Migration | Low | Moderate Migration | USA | Window Server 2012 Standard | SNI developed | NA | DEV, QA, Prod | 3 | HR Notification ECAP ENCORE EndoLoans Global Return Disposition Tool GSC Datawarehouse Admin Tool Inventures Web App Nomino Security QA Change Control Recon LaunchPad(SSO) Reimbursement Sales Request Forms Non-Employee Database | 5. Has dependency on Nomino Security application and database for user authorization.Sharing production server with almost 12 apps | No Vendor support Ensure SNI IT and business team availability for migration Server sharing with other apps Plan application migration in same move group |  | Done | 2020-11-30 | 2020-12-11 | Yes | 2020-12-30 | 2021-01-22 | No | 2021-01-13 | 2021-01-13 | Yes | 2021-01-04 | 2021-01-04 | Yes | 2021-01-11 | 2021-01-11 | Yes | 2021-01-15 | 2021-01-15 | Yes | 2021-01-08 | 2021-01-08 | Yes | 2021-01-13 | 2021-01-13 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-22 | 2021-01-22 | Yes | 2021-01-24 | 2021-01-24 | Yes | 2021-01-24 | 2021-01-24 | Done, no evidence provided | N/A | N/A | Done, no evidence provided | Done, no evidence provided | N/A | N/A | N/A | N/A | N/A | No | 2021-02-19 |  | Yes | 2021-02-19 | 2021-02-08 | No | 2021-02-19 |  | No | 2021-02-19 |  | Yes | 2021-02-19 | 2021-02-16
16 | SNID Archived Shipping Documents | QA | Amit Shokeen | Massimo Trambaioli |  | W1-MG2 | 2021-01-22 | 2021-01-22 | No |  | Finished (blue) |  |  |  | USMAN-SMWSQVW05 |  |  | RE-HOST | Supply Chain | Supply Chain | US | 1 | Pilot | 03 - SNI Developed + Co-Hosted Apps | Nov | MG2 | No | No | Moderate Migration | Low | Moderate Migration | USA | Window Server 2012 Standard | SNI developed | NA | DEV, QA, Prod | 3 | HR Notification ECAP ENCORE EndoLoans Global Return Disposition Tool GSC Datawarehouse Admin Tool Inventures Web App Nomino Security QA Change Control Recon LaunchPad(SSO) Reimbursement Sales Request Forms Non-Employee Database | 5. Has dependency on Nomino Security application and database for user authorization.Sharing production server with almost 12 apps | No Vendor support Ensure SNI IT and business team availability for migration Server sharing with other apps Plan application migration in same move group |  | Done | 2020-11-30 | 2020-12-11 | Yes | 2020-12-30 | 2021-01-22 | No | 2021-01-13 | 2021-01-13 | Yes | 2021-01-04 | 2021-01-04 | Yes | 2021-01-11 | 2021-01-11 | Yes | 2021-01-15 | 2021-01-15 | Yes | 2021-01-08 | 2021-01-08 | Yes | 2021-01-13 | 2021-01-13 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-21 | 2021-01-21 | Yes | 2021-01-22 | 2021-01-22 | Yes | 2021-01-24 | 2021-01-24 | Yes | 2021-01-24 | 2021-01-24 | Done, no evidence provided | N/A | N/A | Done, no evidence provided | Done, no evidence provided | N/A | N/A | N/A | N/A | N/A | No | 2021-02-19 |  | Yes | 2021-02-19 | 2021-02-08 | No | 2021-02-19 |  | No | 2021-02-19 |  | Yes | 2021-02-19 | 2021-02-16
16 | SNID Archived Shipping Documents | PROD | Amit Shokeen | Massimo Trambaioli |  | W3-MG1 | 2021-03-05 | 2021-03-05 | No |  | On track (green) |  | Deepak Sathya Babu | Rahul Sarin | USMAN-SMWSPVW12 |  |  | RE-HOST | Supply Chain | Supply Chain | US | 1 | Pilot | 03 - SNI Developed + Co-Hosted Apps | Nov | MG2 | No | No | Moderate Migration | Low | Moderate Migration | USA | Window Server 2012 Standard | SNI developed | NA | DEV, QA, Prod | 3 | HR Notification ECAP ENCORE EndoLoans Global Return Disposition Tool GSC Datawarehouse Admin Tool Inventures Web App Nomino Security QA Change Control Recon LaunchPad(SSO) Reimbursement Sales Request Forms Non-Employee Database | 5. Has dependency on Nomino Security application and database for user authorization.Sharing production server with almost 12 apps | No Vendor support Ensure SNI IT and business team availability for migration Server sharing with other apps Plan application migration in same move group |  | Yes | 2020-01-25 | 2021-01-28 | Yes | 2020-02-08 | 2020-02-10 | Yes | 2021-02-08 | 2020-02-10 | No |  |  | No |  |  | No |  |  | Yes | 2021-02-10 | 2021-02-11 | Yes | 2021-02-17 | 2021-02-17 | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
133 | SNMAG_DWH | PROD | Antoine d'Overschie | Massimo Trambaioli |  |  |  | 2021-05-30 | No |  | Not started (grey) | [7 empty] | Supply Chain | Supply Chain | EMEA | [5 empty] | No | No |  |  |  | Aarau Switzerland | [9 empty] | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
11 | Solidworks | PROD | Requalann Pereira | Sri Tupil |  | W6-MG1 | 2021-06-04 | 2021-01-30 | No |  | Not started (grey) |  |  |  | BBTAPP01; USASHSMAPPVW21; |  |  | RE-HOST | R&D | R&D | US | 1 | 2 | 02 - Network License Server - Batch 2 | Jan | MG1 | No | No | Simple | Low | Simple | Memphis, US | Windows Server 2012 R2 | COTS | NA | PROD | 1 | Myriad, MATLAB, FlexLM, Unigraphics | NA | Server also host license manager for the Solidworks PDM Workgroup, Vericut, Altium Designer, MATLAB, PTC Creo & Solidworks |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  | 2021-01-21 | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
111 | Solidworks PDM Professional | DEV | Requalann Pereira | Sri Tupil |  | W4-MG1 | 2021-04-09 | 2021-07-30 | No |  | Risk of delay (amber) | SME needs time to respond to queries raised by Shweta | Shweta | Srikanth/Rajesh | USMEMSMDBDVW11 | USMEMSMDBDVW11 |  | RE-HOST | R&D | R&D | US | 7 | 23 | 23 - High Critical Application | Jul | MG1 | No | No | Complex Migration | High | Complex Migration | US & Europe | Windows Server 2016 Standard | COTS | Sql Server 2016 | PROD, TEST | 6 | None | SAP system check-out of file to convert to PDF from the vault repository | As per SDM host name of server needs to be retained Latency is cause of concern. There are users that are geographically disperse so the latency could be an issue for the teams. The geography of the reseller will matter in the support contracts. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
111 | Solidworks PDM Professional | PROD | Requalann Pereira | Sri Tupil |  | W6-MG1 | 2021-06-04 | 2021-07-30 | No |  | Not started (grey) |  |  |  | USASHSMAPPVW21; | USASHSMAPPVW27; USASHSMDBPVW16; NLAMSSMDBPVW08; NLAMSSMDBPVW09 |  | RE-HOST | R&D | R&D | US | 7 | 23 | 23 - High Critical Application | Jul | MG1 | No | No | Complex Migration | High | Complex Migration | US & Europe | Windows Server 2016 Standard | COTS | Sql Server 2016 | PROD, TEST | 6 | None | SAP system check-out of file to convert to PDF from the vault repository | As per SDM host name of server needs to be retained Latency is cause of concern. There are users that are geographically disperse so the latency could be an issue for the teams. The geography of the reseller will matter in the support contracts. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
112 | Solidworks PDM Workgroup | PROD | Requalann Pereira | Sri Tupil |  | W7-MG2 | 2021-07-23 | 2021-07-30 | No |  | Not started (grey) |  |  |  |  | R3 |  | RE-HOST | R&D | R&D | US | 7 | 23 | 23 - High Critical Application | Jul | MG1 | No | Yes | Simple | Low | Simple | US | Windows Server 2008 R2 | COTS | Sql Server 2008 | PROD | 1 | None | NA | NA |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
55 | SOTI | PROD | Amit Shokeen | Massimo Trambaioli |  | W4-MG1 | 2021-04-09 | 2021-04-30 | No |  | On track (green) |  | Raju | Srikanth/Rajesh | USMEM-SMAPPVW35 | USMEM-SMAPPVW35 |  | RE-HOST | Manufacturing | Manufacturing -Warehouse | US | 4 | 11 | 11 - US Medium/Complex Application | Apr | MG1 | No | No | Moderate Migration | Medium | Moderate Migration | USA | Windows 2012 | COTS | MS SQL 2014 | Prod | 1 | Connectivity to SAP System & RF Guns | SAP | Latency issues when migrated to Cloud |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
38 | Spectrum 10 | PROD | Aileen Diola | Sri Tupil | X | W7-MG2 | 2021-07-23 | 2021-07-30 | No |  | Not started (grey) |  |  |  |  | NLAMSSMDBPVW03 | EUAZRSMDBPVW01, EUAZRSMDBPVW02 | RE-HOST(App)/RE-PLATFORM(DB) | RAQA | RAQA | EMEA | 7 | 21 | 21 - Final EMEA/APAC application | Jul | MG2 | No | Yes | Easy Migration | Medium | Userbase is in USA but the server base is in Netherland | USA | Windows 2012 R2 Standard | COTS | MS SQL Server 2012 | Prod | 1 | NA | NA | Spectrum is an GXP validated application - Spectrum 10 server move will need to rely on GXP process validation/approval. Latency requirements - Though the lab instruments is passing the Data to desktop application, and not to the SQL Server. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
116 | Syngistix | PROD | Aileen Diola | Sri Tupil |  | W7-MG2 | 2021-07-23 | 2021-07-30 | No |  | Not started (grey) |  |  |  | NLAMSSMAPPVW28 |  |  | RE-HOST | RAQA | RAQA | EMEA | 7 | 21 | 21 - Final EMEA/APAC application | Jul | MG2 | No | Yes | Moderate Migration | Medium | To remove the dependency on TIAMO GxP & SOX complaince, SDM suggestng to poin the File Server Role to different *New* server and test the file server dependency. | USA | Windows Server 2012 R2 Standard | COTS | NA | Prod | 1 | Trios Guardian and TIAMO | NA | TIAMO is an GxP % SOX validated application co-hosted on the same server - Syngistix server move will need to rely on TIAMO GxP & SOX process approval. - Since the only SNI infrastructure asset this application is connected to is used as a file server, we can try to replicate the exact server/file server setting and get a test PC where Syngistix is installed and perform a test connection from the local PC to the new file server in the cloud. | Syngistix, TIAMO and Trios share the file server with Spectrum 10 | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
54 | Tableau Bridge | DEV | Sathiamurthy Samidurai | Stuart Robinson |  | W4-MG1 | 2021-04-09 | 2021-04-30 | No |  | On track (green) | waiting for Chaitanya's response. No cutover steps needed as this is a new server build request from Sathia. Request To be raised by Sathia via GBS with Matt Kolenda's Team | Isha/Venkat/Sirisha | Rahul/Saurabh | USMEMSMAPDVW21 | USMEMSMAPDVW21 |  | RE-HOST | Supply Chain | Data Analytics | US | 4 | 11 | 11 - US Medium/Complex Application | Apr | MG1 | No | No | Moderate Migration | Medium | Moderate Migration | USA | Windows 2016 | COTS | MS SQL 2017 | 3 Environments, 1 Prod VM for APP & 1 for Database, 1 Dev VM for APP | 3 | Alteryx | GBIP SONAR, P360, Logility | IP Address | SDM to decide on overall Roadmap and planning | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
54 | Tableau Bridge | PROD | Sathiamurthy Samidurai | Stuart Robinson |  | W4-MG2 | 2021-04-23 | 2021-04-30 | No |  | On track (green) | To be moved to May as per Sathia's proposal | Isha/Venkat/Sirisha | Rahul/Saurabh | USMEMSMAPPVW34 | USMEMSMAPPVW35 |  | RE-HOST | Supply Chain | Data Analytics | US | 4 | 11 | 11 - US Medium/Complex Application | Apr | MG1 | No | No | Moderate Migration | Medium | Moderate Migration | USA | Windows 2016 | COTS | MS SQL 2017 | 3 Environments, 1 Prod VM for APP & 1 for Database, 1 Dev VM for APP | 3 | Alteryx | GBIP SONAR, P360, Logility | IP Address | SDM to decide on overall Roadmap and planning | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
83 | Tarife | PROD | Yvonne Braun | Massimo Trambaioli | X | W5-MG1 | 2021-05-07 | 2021-05-30 | No |  | Not started (grey) | Propose to move to April 23rd |  |  | DETUTSMAPPW02 |  |  | RE-HOST | Supply Chain | Supply Chain | EMEA | 5 | 15 | 15 - EMEA Medium Application REHOST Only Group | May | MG2 | No | No | Easy Migration | Low | Easy Migration | Europe | Windows Server 2012 R2 Standard | COTS | dbf-files | Prod | 1 | Yes, Integrated with ASSIST4. Both needs to be moved together, hosted on same Platform. | NA | Shared VMs between ASSIST4 and Tarife The Production VM is shared between ASSIST4 and Tarife application. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
117 | TIAMO | PROD | Aileen Diola | Sri Tupil | X | W7-MG2 | 2021-07-23 | 2021-07-30 | No |  | Not started (grey) | Propose to move to April 23rd |  |  | NLAMSSMAPPVW28 |  |  | RE-HOST | Manufacturing | Manufacturing | EMEA | 7 | 21 | 21 - Final EMEA/APAC application | Jul | MG2 | Yes | Yes | Easy Migration | Low | Long process to migrate s it is GxP & SOX compliance application. (FDA 21 CFR Part 11 compliant.) | Europe | Windows 2012 R2 Standard | COTS | NA | Prod | 1 | With Application ‘Trios Guardian’ & ‘Syngistix’ | With Application ‘Trios Guardian’ & ‘Syngistix’ | HUS16 (Hull WM Labs TIAMO Server, on windows 2000) mapped to TIAMO application. However, during SME session validation, infra team observed, Server looks not to be SNI network During actual migration detailed investigation will be carried out. If this server needs to be migrated then it has to be ‘RE-PLATFROM’ to windows 2012 or higher (SDM needs to confirm the same, and also check with Vendor min OS recommendation prior to the Migration) |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
107 | TM1 Cognos Configuration | DEV | Sathiamurthy Samidurai | Stuart Robinson |  | W3-MG2 | 2021-03-19 | 2021-03-30 | No |  | On track (green) |  | Venkat/Isha/Shirisha | karuppanan, Rajeshkannan | USMEM-SMAPEVW35 | NA |  | RE-HOST | Data & Analytics | TM1 | US | 3 | 9 | 09 - High Critical Application | Mar | MG2 | Yes | No | Moderate Migration | High | Moderate Migration | Globally SNI Internal | Windows 2016 | COTS | TM1 Cubes | 1 for Prod, 1 for QA, 1 for Dev | 3 | 1. All 5 TM1 applications are sharing these servers, Migration needs to be planned accordingly. | Platform for all TM1 apps | All 4 TM1 apps are built on this Platform. |  | Yes | 2020-01-25 | 2021-01-28 | No | 2020-02-08 |  | No |  |  | No |  |  | No |  |  | No |  |  | No | 2021-02-24 |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
107 | TM1 Cognos Configuration | QA | Sathiamurthy Samidurai | Stuart Robinson |  | W4-MG2 | 2021-04-23 | 2021-03-30 | No |  | On track (green) | ticket for docker to remain open. Need to wait for W3-MG2 cutover | Venkat/Isha/Shirisha | Srikanth/Rajesh | USATL-SMAPQUW05 |  |  | RE-HOST | Data & Analytics | TM1 | US | 3 | 9 | 09 - High Critical Application | Mar | MG2 | Yes | No | Moderate Migration | High | Moderate Migration | Globally SNI Internal | Windows 2016 | COTS | TM1 Cubes | 1 for Prod, 1 for QA, 1 for Dev | 3 | 1. All 5 TM1 applications are sharing these servers, Migration needs to be planned accordingly. | Platform for all TM1 apps | All 4 TM1 apps are built on this Platform. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
107 | TM1 Cognos Configuration | PROD | Sathiamurthy Samidurai | Stuart Robinson |  | W5-MG2 | 2021-05-21 | 2021-03-30 | No |  | Not started (grey) |  |  |  | USATLSMAPPPW07 |  |  | RE-HOST | Data & Analytics | TM1 | US | 3 | 9 | 09 - High Critical Application | Mar | MG2 | Yes | No | Moderate Migration | High | Moderate Migration | Globally SNI Internal | Windows 2016 | COTS | TM1 Cubes | 1 for Prod, 1 for QA, 1 for Dev | 3 | 1. All 5 TM1 applications are sharing these servers, Migration needs to be planned accordingly. | Platform for all TM1 apps | All 4 TM1 apps are built on this Platform. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
105 | TM1(Global Cost Visibility) | DEV | Sathiamurthy Samidurai | Stuart Robinson |  | W3-MG2 | 2021-03-19 | 2021-03-30 | No |  | On track (green) |  | Venkat/Isha/Shirisha | karuppanan, Rajeshkannan | USMEM-SMAPEVW35 | NA |  | RE-HOST | Data & Analytics | TM1 | US | 3 | 9 | 09 - High Critical Application | Mar | MG2 | Yes | No | Moderate Migration | High | Moderate Migration | Globally SNI Internal | Windows 2016 | SNI Dev'ed | TM1 Cubes | 1 for Prod, 1 for QA, 1 for Dev | 3 | 1. All 5 TM1 applications are sharing these servers, Migration needs to be planned accordingly. | GBIP - Datahub, Non SAP Sources | IP Address, Enhancements going on. Finance Team involvement. |  | Yes | 2020-01-25 | 2021-01-28 | No | 2020-02-08 |  | No |  |  | No |  |  | No |  |  | No |  |  | No | 2021-02-24 |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
105 | TM1(Global Cost Visibility) | QA | Sathiamurthy Samidurai | Stuart Robinson |  | W4-MG2 | 2021-04-23 | 2021-03-30 | No |  | On track (green) | ticket for docker to remain open. Need to wait for W3-MG2 cutover | Venkat/Isha/Shirisha | Srikanth/Rajesh | USATL-SMAPQUW05 |  |  | RE-HOST | Data & Analytics | TM1 | US | 3 | 9 | 09 - High Critical Application | Mar | MG2 | Yes | No | Moderate Migration | High | Moderate Migration | Globally SNI Internal | Windows 2016 | SNI Dev'ed | TM1 Cubes | 1 for Prod, 1 for QA, 1 for Dev | 3 | 1. All 5 TM1 applications are sharing these servers, Migration needs to be planned accordingly. | GBIP - Datahub, Non SAP Sources | IP Address, Enhancements going on. Finance Team involvement. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
105 | TM1(Global Cost Visibility) | PROD | Sathiamurthy Samidurai |  |  | W5-MG2 | 2021-05-21 | 2021-03-30 | No |  | Not started (grey) |  |  |  | USATLSMAPPPW07 |  |  | RE-HOST | Data & Analytics | TM1 | US | 3 | 9 | 09 - High Critical Application | Mar | MG2 | Yes | No | Moderate Migration | High | Moderate Migration | Globally SNI Internal | Windows 2016 | SNI Dev'ed | TM1 Cubes | 1 for Prod, 1 for QA, 1 for Dev | 3 | 1. All 5 TM1 applications are sharing these servers, Migration needs to be planned accordingly. | GBIP - Datahub, Non SAP Sources | IP Address, Enhancements going on. Finance Team involvement. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
106 | TM1(Transfer Pricing) | DEV | Sathiamurthy Samidurai | Stuart Robinson |  | W3-MG2 | 2021-03-19 | 2021-03-30 | No |  | On track (green) |  | Venkat/Isha/Shirisha | karuppanan, Rajeshkannan | USMEM-SMAPEVW35 | NA |  | RE-HOST | Data & Analytics | TM1 | US | 3 | 9 | 09 - High Critical Application | Mar | MG2 | Yes | No | Moderate Migration | High | Moderate Migration | Globally SNI Internal | Windows 2016 | SNI Dev'ed | TM1 Cubes | 1 for Prod, 1 for QA, 1 for Dev | 3 | 1. All 5 TM1 applications are sharing these servers, Migration needs to be planned accordingly. | GBIP - Datahub, Non SAP Sources | IP Address, Enhancements going on. Finance Team involvement. |  | Yes | 2020-01-25 | 2021-01-28 | No | 2020-02-08 |  | No |  |  | No |  |  | No |  |  | No |  |  | No | 2021-02-24 |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
106 | TM1(Transfer Pricing) | QA | Sathiamurthy Samidurai | Stuart Robinson |  | W4-MG2 | 2021-04-23 | 2021-03-30 | No |  | On track (green) | ticket for docker to remain open. Need to wait for W3-MG2 cutover | Venkat/Isha/Shirisha | Srikanth/Rajesh | USATL-SMAPQUW05 |  |  | RE-HOST | Data & Analytics | TM1 | US | 3 | 9 | 09 - High Critical Application | Mar | MG2 | Yes | No | Moderate Migration | High | Moderate Migration | Globally SNI Internal | Windows 2016 | SNI Dev'ed | TM1 Cubes | 1 for Prod, 1 for QA, 1 for Dev | 3 | 1. All 5 TM1 applications are sharing these servers, Migration needs to be planned accordingly. | GBIP - Datahub, Non SAP Sources | IP Address, Enhancements going on. Finance Team involvement. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
106 | TM1(Transfer Pricing) | PROD | Sathiamurthy Samidurai |  |  | W5-MG2 | 2021-05-21 | 2021-03-30 | No |  | Not started (grey) |  |  |  | USATLSMAPPPW07 |  |  | RE-HOST | Data & Analytics | TM1 | US | 3 | 9 | 09 - High Critical Application | Mar | MG2 | Yes | No | Moderate Migration | High | Moderate Migration | Globally SNI Internal | Windows 2016 | SNI Dev'ed | TM1 Cubes | 1 for Prod, 1 for QA, 1 for Dev | 3 | 1. All 5 TM1 applications are sharing these servers, Migration needs to be planned accordingly. | GBIP - Datahub, Non SAP Sources | IP Address, Enhancements going on. Finance Team involvement. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
124 | Tops Pro | PROD | Requalann Pereira | Sri Tupil |  | PW-MG3 | 2020-11-20 | 2020-11-20 | No |  | Finished (blue) |  |  |  | USAUS-SMLIPVW02 |  |  | RE-HOST | R&D | R&D,is a packaging design and pallet layout software | US | Pilot | Pilot | 00 - Pilot | Nov | MG1 | No | No | Simple Migration | Low | Easy Migration | USA,SNI Internal | Windows 2012 R2 Standard | COTS | NA | Prod | 1 | NA | Nothing. | Nothing Found |  | Done | 2020-10-05 | 2020-10-05 | Yes | 2020-11-03 | 2020-11-03 | Yes | 2020-11-03 | 2020-11-03 | Yes | 2020-11-03 | 2020-11-03 | Yes | 2020-11-10 | 2020-11-10 | Yes | 2020-11-14 | 2020-11-14 | Yes | 2020-11-07 | 2020-11-07 | Yes | 2020-11-10 | 2020-11-10 | Yes | 2020-11-20 | 2020-11-20 | Yes | 2020-11-20 | 2020-11-20 | Yes | 2020-11-21 | 2020-11-21 | Yes | 2020-11-23 | 2020-11-23 | Yes | 2020-11-23 | 2020-11-24 | Done, no evidence provided | N/A | N/A | Done, no evidence provided | Done, no evidence provided | N/A | N/A | N/A | N/A | N/A | Yes | 2020-12-19 | 2021-01-02 | Yes | 2020-12-19 | 2021-02-08 | No | 2020-12-19 |  | No | 2020-12-19 |  | Yes | 2020-12-19 | 2021-01-12
39 | TOTVS | PROD | Eduardo Lima | Firas Almahamid |  | W5-MG2 | 2021-05-21 | 2021-03-30 | No |  | Risk of delay (amber) | Latency risk for users from Brazil |  |  | SEN-PROD01; SEN-PROD02; SEN-PROD03; SEN-PROD04 | SEN-PROD02 |  | RE-HOST | ERP | ERP Platform for Brazil | US | 3 | 7 | 07 - Simple/Medium Apps - Moving to EMEA | Mar | MG1 | No | Yes | Complex migration | High | Complex migration | USA,Brazil | Windows Server 10 64-Bit in Azure | COTS | MS Cluster SQL Database 2016 – 64 Bit | (4 Prod, 2 QA). | 8 | NA | 1. Migration will be Azure to Azure and to be planned with proper business approval during the non-business hrs. 2. All Integrated systems connectivity needs to be validated during migration. | Complex migration, with high probability of impacts for the business Migration will be Azure to Azure and to be planned with proper business approval during the non-business hrs. Integration Systems All Integrated systems connectivity needs to be validated during migration. Latency Issues The application is used in Brazil only and the production servers are in local Azure Zone, hence there is no latency issues observed from the client end. But for lower environments the servers are in USA Zone, where the comparatively high latency is observed. Need to see validate this during migration from Vendor Azure to SNI Azure | Need to plan the Test/Dev env in an earlier month and Prod in a later Month | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
39 | TOTVS | DEV | Eduardo Lima | Firas Almahamid |  | W3-MG2 | 2021-03-19 | 2021-03-30 | No |  | Risk of delay (amber) | RDS Licensing requirement | Shweta Goel /Kishore Balimidi | Rahul Sarin | SEN-HOMOL01; SEN-HOMOL02 | SEN-HOMOL02 |  | RE-HOST | ERP | ERP Platform for Brazil | US | 3 | 7 | 07 - Simple/Medium Apps - Moving to EMEA | Mar | MG1 | No | Yes | Complex migration | High | Complex migration | USA,Brazil | Windows Server 10 64-Bit in Azure | COTS | MS Cluster SQL Database 2016 – 64 Bit | (4 Prod, 2 QA). | 8 | NA | 1. Migration will be Azure to Azure and to be planned with proper business approval during the non-business hrs. 2. All Integrated systems connectivity needs to be validated during migration. | Complex migration, with high probability of impacts for the business Migration will be Azure to Azure and to be planned with proper business approval during the non-business hrs. Integration Systems All Integrated systems connectivity needs to be validated during migration. Latency Issues The application is used in Brazil only and the production servers are in local Azure Zone, hence there is no latency issues observed from the client end. But for lower environments the servers are in USA Zone, where the comparatively high latency is observed. Need to see validate this during migration from Vendor Azure to SNI Azure | Need to plan the Test/Dev env in an earlier month and Prod in a later Month | Yes | 2020-01-25 | 2021-01-28 | No | 2020-02-08 |  | No |  |  | No |  |  | No |  |  | No |  |  | No | 2021-02-10 |  |  |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
52 | Trackwise (EU) | DEV | Aileen Diola | Sri Tupil |  | W3-MG1 | 2021-03-05 | 2021-03-30 | Yes | To be moved to AVS because of SQL 2005 and no upgrade possible. Ken approval to follow. | Out of scope (dark grey) |  |  |  | CHAARSMAPPW03 | CHAARSMAPPW03 |  | RE-HOST | RAQA | RAQA | EMEA | 3 | 8 | 08 - Full Throttle EMEA Application - Batch 1 | Mar | MG2 | No | No | Easy Migration | Medium | Complex migration | Europe | Windows Server 2008 R2 Standard Service Pack 1 | Vendor developed application | MS SQL 2005 | 1 Prod, 1 Validation, 1 Development, 1 Database | 4 | Trackwise is running on the Dedicated VM’s, its not sharing the VMs with other application. | 14. Archiving System doesn’t have any direct integration with Trackwise. Manually the documents are being placed there in - OS7. | Only Repair & Production process module to be continued to use. Rest modules are planned to be migrated separately to smartSolve QMS system. To be replaced before 2021. SDM to check, if they want to migrate only few modules to Cloud or they want to migrate all modules to Azure Cloud. |  | Yes | 2020-01-25 | 2021-01-28 | No | 2020-02-08 |  | No |  |  | No |  |  | No |  |  | No |  |  | No | 2021-02-10 |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
52 | Trackwise (EU) | VAL | Aileen Diola | Sri Tupil |  | W3-MG1 | 2021-03-05 | 2021-03-30 | Yes | To be moved to AVS because of SQL 2005 and no upgrade possible. Ken approval to follow. | Out of scope (dark grey) |  |  |  | CHAARSMAPPW04 | CHAARSMAPPW04 |  | RE-HOST | RAQA | RAQA | EMEA | 3 | 8 | 08 - Full Throttle EMEA Application - Batch 1 | Mar | MG2 | No | No | Easy Migration | Medium | Complex migration | Europe | Windows Server 2008 R2 Standard Service Pack 1 | Vendor developed application | MS SQL 2005 | 1 Prod, 1 Validation, 1 Development, 1 Database | 4 | Trackwise is running on the Dedicated VM’s, its not sharing the VMs with other application. | 14. Archiving System doesn’t have any direct integration with Trackwise. Manually the documents are being placed there in - OS7. | Only Repair & Production process module to be continued to use. Rest modules are planned to be migrated separately to smartSolve QMS system. To be replaced before 2021. SDM to check, if they want to migrate only few modules to Cloud or they want to migrate all modules to Azure Cloud. |  | Yes | 2020-01-25 | 2021-01-28 | No | 2020-02-08 |  | No |  |  | No |  |  | No |  |  | No |  |  | No | 2021-02-10 |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
52 | Trackwise (EU) | PROD | Aileen Diola | Sri Tupil |  | W3-MG2 | 2021-03-19 | 2021-03-30 | Yes | To be moved to AVS because of SQL 2005 and no upgrade possible. Ken approval to follow. | Out of scope (dark grey) |  |  |  | CHAARSMAPPW05 | CHAARSMDBPW02 |  | RE-HOST | RAQA | RAQA | EMEA | 3 | 8 | 08 - Full Throttle EMEA Application - Batch 1 | Mar | MG2 | No | No | Easy Migration | Medium | Complex migration | Europe | Windows Server 2008 R2 Standard Service Pack 1 | Vendor developed application | MS SQL 2005 | 1 Prod, 1 Validation, 1 Development, 1 Database | 4 | Trackwise is running on the Dedicated VM’s, its not sharing the VMs with other application. | 14. Archiving System doesn’t have any direct integration with Trackwise. Manually the documents are being placed there in - OS7. | Only Repair & Production process module to be continued to use. Rest modules are planned to be migrated separately to smartSolve QMS system. To be replaced before 2021. SDM to check, if they want to migrate only few modules to Cloud or they want to migrate all modules to Azure Cloud. |  | Yes | 2020-01-25 | 2021-01-28 | No | 2020-02-08 |  | No |  |  | No |  |  | No |  |  | No |  |  | No | 2021-02-24 |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
118 | Trios Guardian | PROD | Aileen Diola | Sri Tupil | X | W7-MG2 | 2021-07-23 | 2021-07-30 | No |  | Not started (grey) | Propose to move to April 23rd |  |  | NLAMSSMAPPVW28 |  |  | RE-HOST | RAQA | RAQA | EMEA | 7 | 21 | 21 - Final EMEA/APAC application | Jul | MG2 | No | No | Easy Migration | Low | Server is GxP & SOX validated system (dependency on TIAMO). | Europe | ndows Server 2012 R2 Standard | COTS | NA – File Server | Prod | 1 | dependency on TIAMO | NA | IP addresses and hostnames are hardcoded in the client application and the terminals to save file - SDM/Ops Support team to make IP change to be during Azure Migration for file server location. - Migration team need to retain the file server host name. TIAMO is an GxP % SOX validated application - Hence Trios Guardian server move will need to rely on TIAMO GxP & SOX process approval. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
25 | Unified Functional Testing | QA | Sathiamurthy Samidurai | Stuart Robinson |  | W5-MG1 | 2021-05-07 | 2021-05-30 | No |  | Not started (grey) |  |  |  | USMEM-SMAPQVW01 |  |  | RE-PLATFORM | Data & Analytics | Data & Analytics,UFT provides regression testing functionality for application testers | US | 5 | 13 | 13 - Simple/Medium Apps | May | MG2 | No | No | Moderate Migration | Low | Moderate migration | USA,SNI Internal | Windows 2012 R2 Standard | COTS | NA | QA | 1 | NA | Separate VM for this application. So planning to RE-PLATFORM. | RE-PLATFORM. |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
1 | Unigraphics | PROD | Requalann Pereira | Sri Tupil |  | W5-MG1 | 2021-05-07 | 2021-01-30 | No |  | Not started (grey) |  |  |  | MEMSRV403; MEMSRV434; |  |  | RE-PLATFORM | R&D | Manufacturing - CAD Modelling | US | 1 | 1 | 01 - Network License Server - Batch 1 | Jan | MG1 | No | No | Moderate Migration | Medium | Moderate Migration | USA & Global | Windows 2008 Enterprise | COTS | NA | Prod | 3 | Has 2 License Servers shared across with other applications within SNI. MSMSERV403 & MSMSERV434 APPS: Solidworks Flex LM MIMICS Simulia Abaqus Flex LM MATLAB Myriad | License Servers - MEMSERV403, 434 | Shared License Servers | Matt | Yes | 2020-12-20 |  | Yes | 2021-01-13 |  | Yes | 2021-01-13 |  | Yes | 2021-01-13 |  | Yes | 2021-01-20 |  | Yes | 2021-01-24 |  | Yes | 2021-01-17 |  | Yes | 2021-01-20 |  | Yes | 2021-01-30 | 2021-01-21 | Yes | 2021-01-30 |  | Yes | 2021-01-31 |  | Yes | 2021-02-02 | 2021-02-02 | Yes | 2021-02-02 |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Yes | 2021-02-28 |  | Yes | 2021-02-28 |  | Yes | 2021-02-28 |  | Yes | 2021-02-28 |  | Yes | 2021-02-28
75 | VEI Label Verification | QA | Carla Morris | Derek Spillane |  | W5-MG1 | 2021-05-07 | 2021-05-30 | No |  | Not started (grey) |  |  |  |  | USMEMSMDBQVW01; USMEMSMDBQVW02 |  | RE-HOST | Manufacturing | Manufacturing | US | 5 | 14 | 14 - Shop Floor Medium/Complex Application | May | MG1 | No | Yes | Moderate migration | High | Moderate migration | Memphis facility, US | Windows Server 2016(APP), Windows Server 2012(DB) | COTS | Sql Server 2016 | Test, Prod | 4 | NA | SAP | IP Address Change – Hardcoding |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
75 | VEI Label Verification | PROD | Carla Morris | Derek Spillane |  | W5-MG2 | 2021-05-21 | 2021-05-30 | No |  | Not started (grey) |  |  |  |  | USASHSMDBPVW08; USASHSMDBPVW09 |  | RE-HOST | Manufacturing | Manufacturing | US | 5 | 14 | 14 - Shop Floor Medium/Complex Application | May | MG1 | No | Yes | Moderate migration | High | Moderate migration | Memphis facility, US | Windows Server 2016(APP), Windows Server 2012(DB) | COTS | Sql Server 2016 | Test, Prod | 4 | NA | SAP | IP Address Change – Hardcoding |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
17 | Vericut | PROD | Carla Morris | Derek Spillane | MAC | W6-MG1 | 2021-06-04 | 2021-01-30 | No |  | Not started (grey) |  |  |  | BBTAPP01 |  |  | RE-HOST | Manufacturing | Manufacturing | US | 1 | 1 | 01 - Network License Server - Batch 1 | Jan | MG1 | No | No | Simple Migration | Low | Easy Migration | USA | Windows Server 20012 R2 Standard | COTS | NA | Prod | 1 | Prod Server BBTAPP01 shared with Solidworks PDM Workgroup Vericut Altium Designer MATLAB PTC Creo Solidworks | IP / MAC binding with license file | Latency consideration 2kb sec bandwidth Plan latency before migration and execute test cases to validate latency. Mac address dependency Change license file or other information accordingly Dependency on License Server – FlexLM Plan to migrate in same move group |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  | 2021-01-21 | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
43 | Visionaire Case Processing of Images | QA | Requalann Pereira | Sri Tupil |  |  | 2021-06-30 | 2021-03-30 | Yes | To be moved to AWS in April | Out of scope (dark grey) |  |  |  | USMAN-SMWSQVW02 |  |  | RE-PLATFORM | R&D | R&D, central storage for patient case files | US, EMEA, APAC | 3 | 7 | 07 - Simple/Medium Apps - Moving to EMEA | Mar | MG1 | No | Yes | Complex Migration | High | High risk dependency on VCM migration. | US, Europe and APAC | Windows Server 2008 R2/ 2008 Enterprise | COTS | NA | LB, PROD, DEV, QA | 17 | None | Remote/Initialize, HiRes, Segway, Aspera, Sync, P2P, VCM, ISILON, SAP (PRD, PR1), | Latency between ISILON and remote sites (address the network performance with the size of file with the teams in Sydney. Noida, and Aarau). PROD server (NOISRV001, NOISRV002 & NOISRV002) hosting other Vendor network. VCM moving by another vendor Q4 2020. Dependencies Co-Hosted application in LB server ‘Remove/Initialize’ application has license |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
43 | Visionaire Case Processing of Images | LB | Requalann Pereira | Sri Tupil |  |  | 2021-06-30 | 2021-03-30 | Yes | To be moved to AWS in April | Out of scope (dark grey) |  |  |  | USMEM-SMAPPVW22 |  |  | RE-PLATFORM | R&D | R&D, central storage for patient case files | US, EMEA, APAC | 3 | 7 | 07 - Simple/Medium Apps - Moving to EMEA | Mar | MG1 | No | Yes | Complex Migration | High | High risk dependency on VCM migration. | US, Europe and APAC | Windows Server 2008 R2/ 2008 Enterprise | COTS | NA | LB, PROD, DEV, QA | 17 | None | Remote/Initialize, HiRes, Segway, Aspera, Sync, P2P, VCM, ISILON, SAP (PRD, PR1), | Latency between ISILON and remote sites (address the network performance with the size of file with the teams in Sydney. Noida, and Aarau). PROD server (NOISRV001, NOISRV002 & NOISRV002) hosting other Vendor network. VCM moving by another vendor Q4 2020. Dependencies Co-Hosted application in LB server ‘Remove/Initialize’ application has license |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
43 | Visionaire Case Processing of Images | PROD | Requalann Pereira | Sri Tupil |  |  | 2021-06-30 | 2021-03-30 | Yes | To be moved to AWS in April | Out of scope (dark grey) |  |  |  | USMEMSMAPPVW08; USMEM-SMAPPVW21; USMEM-SMAPPVW23; CHAARSMAPPW08; CHAARSMFSPW02; AUSYDSMAPPW01; AUSYDSMFSPW02; NOISRV001; NOISRV002; NOISRV003; | USMAN-SMWSDVW04; USMANSMAPDVW30; USMEM-SMAPDVW29; AUSYDSMAPDW01; |  | RE-PLATFORM | R&D | R&D, central storage for patient case files | US, EMEA, APAC | 3 | 7 | 07 - Simple/Medium Apps - Moving to EMEA | Mar | MG1 | No | Yes | Complex Migration | High | High risk dependency on VCM migration. | US, Europe and APAC | Windows Server 2008 R2/ 2008 Enterprise | COTS | NA | LB, PROD, DEV, QA | 17 | None | Remote/Initialize, HiRes, Segway, Aspera, Sync, P2P, VCM, ISILON, SAP (PRD, PR1), | Latency between ISILON and remote sites (address the network performance with the size of file with the teams in Sydney. Noida, and Aarau). PROD server (NOISRV001, NOISRV002 & NOISRV002) hosting other Vendor network. VCM moving by another vendor Q4 2020. Dependencies Co-Hosted application in LB server ‘Remove/Initialize’ application has license |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
45 | Visual SVN | PROD | Requalann Pereira | Sri Tupil |  |  | 2021-03-30 | 2021-03-30 | Yes | Req to provide the retirement date | Out of scope (dark grey) |  |  |  | EQVSRD00 |  |  | RE-HOST | R&D | R&D | US | 3 | 7 | 07 - Simple/Medium Apps - Moving to EMEA | Mar | MG1 | No | No | Moderate migration | Low | Moderate migration | USA | Windows Server 2008 R2 | COTS | NA | Prod | 1 | MIMS also uses this as QA server for SqlServer DB | MIMS also uses this as QA server for SqlServer DB | JIRA , Crucible , Subversion and some database in MySql MIMS also uses this as QA server for SqlServer DB |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
37 | Winflex | PROD | Yvonne Braun | Massimo Trambaioli | X | W4-MG2 | 2021-04-23 | 2021-04-23 | Yes | Out of Scope because of Fileserver dependency | Not started (grey) |  |  |  | DETUTSMFSPW02 |  |  | RE-HOST | Manufacturing | Manufacturing | EMEA | 2 | 5 | 05 - Simple/Medium Apps | Feb | MG1 | No | No | Easy Migration | Low | Easy migration, only files on the fileserver have to be migrated, the application runs on a single PC. | Europe | Windows Server 2012 R2 | COTS | NA | Prod | 1 | NA | NA | 1) Other application like Fedex Ship manager and Prisym Medica BAS Trans are sharing the file server 2) Applications like “Firmenhandbuch” aren’t mentioned in the CMDB 3) Also there are the print server and file server 1) Need to check whether these applications are migration candidates and move them in one group 2) Need to find the applications whichever is not in CMDB but sharing the file server |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
57 | Winshuttle | DEV | Mahmood Mohammed | Stuart Robinson |  | W4-MG1 | 2021-04-09 | 2021-04-30 | No |  | On track (green) |  | Deepak | Srikanth/Rajesh | USASHSMAPDVW05 | USASHSMDBDVW05 |  | RE-HOST | ERP | ERP | US | 4 | 11 | 11 - US Medium/Complex Application | Apr | MG1 | Yes | Yes | Moderate migration | High | Moderate migration | Globally SNI Internal | Windows Server 2012 | COTS | Sql Server 2012 | Dev, Test, Prod | 10 | NA | SAP, Third Party APIs | IP Address Change – Hardcoding |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
57 | Winshuttle | QA | Mahmood Mohammed | Stuart Robinson |  | W4-MG1 | 2021-04-09 | 2021-04-30 | No |  | On track (green) |  | Deepak | Srikanth/Rajesh | USASHSMAPQVW05; USASHSMWSQVW05; | USASHSMDBQVW05 |  | RE-HOST | ERP | ERP | US | 4 | 11 | 11 - US Medium/Complex Application | Apr | MG1 | Yes | Yes | Moderate migration | High | Moderate migration | Globally SNI Internal | Windows Server 2012 | COTS | Sql Server 2012 | Dev, Test, Prod | 10 | NA | SAP, Third Party APIs | IP Address Change – Hardcoding |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
57 | Winshuttle | PROD | Mahmood Mohammed | Stuart Robinson |  | W4-MG2 | 2021-04-23 | 2021-04-30 | No |  | On track (green) |  | Deepak | Srikanth/Rajesh | USASHSMAPPVW12; USASHSMAPPVW11; USASHSMWSPVW06; USASHSMWSPVW05 | USASHSMDBPVW05 |  | RE-HOST | ERP | ERP | US | 4 | 11 | 11 - US Medium/Complex Application | Apr | MG1 | Yes | Yes | Moderate migration | High | Moderate migration | Globally SNI Internal | Windows Server 2012 | COTS | Sql Server 2012 | Dev, Test, Prod | 10 | NA | SAP, Third Party APIs | IP Address Change – Hardcoding |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | Not done | No |  |  | No |  |  | No |  |  | No |  |  | No
`
Formulas:
BOAC-Planned Date = IF(Table1[[#This Row],[CC-Planned Date]]="","",Table1[[#This Row],[CC-Planned Date]]+Definitions!$D5)
UDPTN planned date = IF(Table1[[#This Row],[CC-Planned Date]]="","",Table1[[#This Row],[CC-Planned Date]]+Definitions!$D6)
UDPPR-Planned Date = IF(Table1[[#This Row],[CC-Planned Date]]="","",Table1[[#This Row],[CC-Planned Date]]+Definitions!$D7)
UDPPRD-Planned Date = IF(Table1[[#This Row],[CC-Planned Date]]="","",Table1[[#This Row],[CC-Planned Date]]+Definitions!$D8)
CS-Planned Date = IF(Table1[[#This Row],[CC-Planned Date]]="","",Table1[[#This Row],[CC-Planned Date]]+Definitions!$D9)
CA--Planned Date = IF(Table1[[#This Row],[CC-Planned Date]]="","",Table1[[#This Row],[CC-Planned Date]]+Definitions!$D10)
PIC-Planned Date = IF(Table1[[#This Row],[CC-Planned Date]]="","",Table1[[#This Row],[CC-Planned Date]]+Definitions!$D11)
SNI OPTC-Planned Date = IF(Table1[[#This Row],[CC-Planned Date]]="","",Table1[[#This Row],[CC-Planned Date]]+Definitions!$D12)
CC-Planned Date = IF(Table1[[#This Row],[MS-Planned Date]]="","",Table1[[#This Row],[MS-Planned Date]])
HATC-Planned Date = IF(Table1[[#This Row],[CC-Planned Date]]="","",Table1[[#This Row],[CC-Planned Date]]+Definitions!$D14)
HATC-Actual Date = IF(Table1[[#This Row],[CC-Planned Date]]="","",Table1[[#This Row],[CC-Planned Date]]+Definitions!$D14)
SATC-Planned Date = IF(Table1[[#This Row],[CC-Planned Date]]="","",Table1[[#This Row],[CC-Planned Date]]+Definitions!$D14)
ASDC-Planned Date = IF(Table1[[#This Row],[CC-Planned Date]]="","",Table1[[#This Row],[CC-Planned Date]]+Definitions!$D17)
CUC-Planned Date = IF(Table1[[#This Row],[CC-Planned Date]]="","",Table1[[#This Row],[CC-Planned Date]]+Definitions!$D18)
OPDC-Planned Date = IF(Table1[[#This Row],[CC-Planned Date]]="","",Table1[[#This Row],[CC-Planned Date]]+Definitions!$D19)
HS Planned Date = IF(Table1[[#This Row],[CC-Planned Date]]="","",Table1[[#This Row],[CC-Planned Date]]+Definitions!$D20)
MSO-Planned Date = IF(Table1[[#This Row],[CC-Planned Date]]="","",Table1[[#This Row],[CC-Planned Date]]+Definitions!$D21)
CPC-Planned Date = IF(Table1[[#This Row],[MS-Planned Date]]="","",Table1[[#This Row],[MS-Planned Date]]+14)
CPC-Planned Date = IF(Table1[[#This Row],[CC-Planned Date]]="","",Table1[[#This Row],[CC-Planned Date]]+Definitions!$D4)
MS-Planned Date = IF(Table1[[#This Row],[CC-Planned Date]]="","",Table1[[#This Row],[CC-Planned Date]]+Definitions!$D3)
MS-Actual Date = IF(Table1[[#This Row],[CC-Planned Date]]="","",Table1[[#This Row],[CC-Planned Date]]+Definitions!$D3)
UDPTN actual date = IF(Table1[[#This Row],[CC-Planned Date]]="","",Table1[[#This Row],[CC-Planned Date]]+Definitions!$D6)

## Definitions
Up to medium complex migration
Migration Status Code | Description | Weeks before cutover | Days before cutover
Migration Scheduled | The Application environment has been added to the Application Migration Roster for its Wave and a cutover window has been assigned and confirmed | -6 | -42
Cutover Planning Complete | All the application specific detailed information has been captured and discussed with the SDMs and the detailed step by step cutover plan is ready for the application | -2.5 | -18
Business Owner Approval Complete | Application Business owner has approved the downtime window for the application. | -2.5 | -18
UAT, Data, Performance testers nominated |  | -2.5 | -18
UAT, Data, Performance Plan Ready | All the UAT, Data and Performance testing plans have been finalized with the App SDMs and stored in Azure DevOps. | -1.5 | -11
UAT, Data, Performance tests ready in DevOps and approved |  | -1 | -7
CR Submitted | The Change Request for the cutover of the application has been submitted for approvals in ServiceNow | -2 | -14
CR Approved | The Change Request for the cutover of the application has been approved by CAB in ServiceNow | -1.5 | -11
Precutover Implementation Complete | Server setup on Azure , initial data sync, and all other precutover/predowntime preparation tasks have been completed | 0 | -1
On Prem Testing Completed | All the test case scenarios have been tested at On Prem before the application is migrated to Azure. | 0 | -1
Cutover Completed | The application has been cutover to Azure successfully and the Applications downtime window has closed. | 0 | 2
Azure Testing Completed | The cutover to Azure has been completed and all the post cutover tests(Connectivity, Smoke Test, UAT , Performance, Data) have been completed successfully and the results stored in Azure DevOps | 0 | 2
Handover from DXC | For DXC supported applications
Handover to HCL OPS |  | 1 | 7
Application Summary Document completed | The applications summary document has been created/updated with all Azure information and is submitted to SNI SDM for Sign Off | 4 | 28
CMDB Update Completed | The CMDB has been updated with all the Azure information incorporated in the CIs | 4 | 28
On Prem Decom Completed | The On Prem environment has been appropriately decommisioned post the applications migration to Azure is complete | 4 | 28
Hypercare signed off | Hypercare signed off | 4 | 28
Migration Signed Off | The SDM has signed off the migration to Azure as completed. | 4 | 28

## StatusColList
Migration Scheduled
MS-Planned Date
MS-Actual Date
Cutover Planning Complete
CPC-Planned Date
CPC-Actual Date
Business Owner Approval Complete
BOAC-Planned Date
BOAC-Actual Date
UAT, Data, Performance Plan Ready
UDPPR-Planned Date
UDPPR-Actual Date
CR Submitted
CS-Planned Date
CS--Actual Date
CR Approved
CA--Planned Date
CA--Actual Date
Precutover Implementation Complete
PIC-Planned Date
PIC-Actual Date
On Prem Testing Completed
OPTC-Planned Date
OPTC-Actual Date
Cutover Completed
CC-Planned Date
CC-Actual Date
Azure Testing Completed
ATC-Planned Date
ATC-Actual Date
Application Summary Document completed
ASDC-Planned Date
ASDC-Actual Date
CMDB Update Completed
CUC-Planned Date
CUC-Actual Date
On Prem Decom Completed
OPDC-Planned Date
OPDC-Actual Date
Migration Signed Off
MSO-Planned Date
MSO-Actual Date

## Change Control
Change ID | Change Type | Application Name | Change | Updated By | Approved BY | Date
1 | Migration Strategy Change | SNID Archived Shipping Documents | Moved Treatment to Rehost and Wave to Wave 1 | Debojit | Amit S | 2020-12-09
2 | Scope Change | Dubai Axapta | Out of scope | Mateusz P | Ken | 2020-12-11
3 | Migration Strategy Change | Informatica MDM Data Quality | Changed Treatment Plan to REPLATFORM as per SNI SDM request (Sathia) & discussion with SNI leadership on 10th Dec | Debojit | Ken/Adrian | 2020-12-10
4 | Scope Change | QA Change Control | Added QA Change Control application to migration scope to mitigate comingling situation and Rehosting to Azure. | Debojit | Ken | 2020-12-14
5 | Scope Change | Recon LaunchPad (SSO) - QA Environment | According to cutover planning there is no QA environment for this App. Markes Out of Scope. | Debojit |  | 2021-01-11
6 | Scope Change | Inventures (SCAMPI) Web App - DEV Environment | Added the DEV environment also, which was not part of the initial assessment which had QA and PROD only. | Debojit |  | 2021-01-11
7 | Scope Change | Reimbursement - DEV Environment | Added the DEV environment also, which was not part of the initial assessment which had QA and PROD only. | Debojit |  | 2021-01-11
8 | Schedule Change | Bugzilla | Moved out of Wave 2 | Jyotsna | Matt Pie | 2021-01-15
9 | Schedule Change | CVS | Moved out of Wave 2 | Jyotsna | Matt Pie | 2021-01-15
10 | Schedule Change | Cockpit | Moved to Wave 8 | Jyotsna | Matt Pie | 2021-01-15
11 | Schedule Change | ID Prove | Moved to Wave 5 | Jyotsna | Yvonne | 2021-01-15
12 | Schedule Change | Winflex | Moved out of Wave 2 to Wave 4 because it has dependencies associated with Hydra & Assist4 which is scheduled for Wave 4 | Jyotsna | Yvonne/Matt Pie | 2021-01-15
13 | Schedule Change | Lutron | Moved out of W2-MG1 | Jyotsna |  | 2021-01-15
14 | Scope Change | InfinityQS ProFicient (SPC software) | Out of scope because this application is planned to be phased out before end of this year. | Jyotsna | Ken / Aileen | 2021-01-20
15 | Scope Change | FileZilla | Retired application now, moved out of scope. | Mateusz P | Ken | 2021-02-01
16 | Scope Change | Cockpit | Review because it is already in Azure as part of new build | Mateusz P | Ken | 2021-02-01
17 | Scope Change | Axapta (all) | Out of scope | Mateusz P | Ken | 2021-02-01
18 | Migration Strategy Change | Electronic Instructions for Use (Dev &QA) | Changed Treatment Plan to REPLATFORM as part of DB consolidation | Jyotsna | Matt Pie / Carla | 2021-02-03
19 | Scope Change | Mobile Inventory Management System (Dev & QA) | Added the DEV and QA environments for this Application to the list which was not part of the list initially | Debojit |  | 2021-02-03
20 | Other | Target DB Servers for SQL 2019 consolidation | Column N includes target DB servers for SQL 2019 consolidation. | Mateusz P | Mateusz P | 2021-02-04
21 | Scope Change | Lutron | Out of scope because of the latency requirements - to be verified again | Mateusz P | Ken | 2021-02-04
22 | Scope Change | Mcosomos | Out of scope - Desktop application. There is no app server. | Mateusz P |  | 2021-02-04
23 | Scope Change | Motion Board | To be decomissioned end of the year. To be confirmed it will be fully retired EOY (Mat P) | Mateusz P |  | 2021-02-04
24 | Scope Change | Trackwise (EU) | To be moved to AVS because of SQL 2005 and no upgrade possible. Ken approval to follow. Retirement date to follow. | Mateusz P |  | 2021-02-04
25 | Scope Change | Expres Visionaire | To be retired. | Mateusz P | Adrian | 2021-02-08
26 | Scope Change | Partmaker | License server to be decomissioned, hence app out of scope | Mateusz P | Adrian | 2021-02-08
27 | Schedule Change | Informatica (Wound Data Intergration) - PROD | Moved to W3-MG2 19th Mar cutover per request from Sathia | Debojit | Sathia / Ken | 2021-02-08
28 | Schedule Change | AWM Data Warehouse - PROD | Moved to W3-MG2 19th Mar cutover per request from Sathia | Debojit | Sathia / Ken | 2021-02-08
29 | Migration Strategy Change | Flex LM - PROD | Changed to REPLATFORM. Per SNI guidelines Windows 2008 Enterprise & Standard is not supported in SNi Azure Cloud | Debojit |  | 2021-02-09
30 | Migration Strategy Change | MIMICS - PROD | Changed to REPLATFORM. Per SNI guidelines Windows 2008 Enterprise & Standard is not supported in SNi Azure Cloud | Debojit |  | 2021-02-09
31 | Migration Strategy Change | Myriad - PROD | Changed to REPLATFORM. Per SNI guidelines Windows 2008 Enterprise & Standard is not supported in SNi Azure Cloud | Debojit |  | 2021-02-09
32 | Migration Strategy Change | SEAL Application - PROD | Changed to REPLATFORM. Per SNI guidelines Windows 2008 Enterprise & Standard is not supported in SNi Azure Cloud | Debojit |  | 2021-02-09
33 | Migration Strategy Change | Unigraphics - PROD | Changed to REPLATFORM. Per SNI guidelines Windows 2008 Enterprise & Standard is not supported in SNi Azure Cloud | Debojit |  | 2021-02-09
34 | Migration Strategy Change | Visionaire Case Processing of Images - QA, LB, PROD | Changed to REPLATFORM. Per SNI guidelines Windows 2008 Enterprise & Standard is not supported in SNi Azure Cloud | Debojit |  | 2021-02-09
35 | Schedule Change | Visionaire Case Processing of Images - QA, LB, PROD | Moved to June Wave 6 as the Application migration project has to be aligned with AWS migration of Visionaire | Lukasz P | Requalann | 2021-02-16
36 | Schedule Change | Informatica MDM Data Quality | Moved to W4-MG1 as per Adrian | Mateusz P | Adrian | 2021-02-16
37 | Schedule Change | Informatica P360 | Moved to W4-MG1 as per Adrian | Mateusz P | Adrian | 2021-02-16
38 | Scope Change | IQ-Soft (Aarau) | AVS scope. Ken's appoval to follow. | Mateusz P |  | 2021-02-16
39 | Scope Change | Visionaire Case Processing of Images | To be moved to AWS in April | Mateusz P | Adrian | 2021-02-16
40 | Schedule Change | Tarife | Has to go with Assist4. Moved to W5-MG1 | Mateusz P | Adrian | 2021-02-16
41 | Scope Change | Informatica MDM Data Quality | EVL env out of scope | Mateusz P | Adrian | 2021-02-16
42 | Scope Change | Informatica P360 | EVL env out of scope | Mateusz P | Adrian | 2021-02-16
43 | Scope Change | Global Labeling System (PRISYM) | Addition to the scope | Mateusz P | Ken | 2021-02-16
44 | Scope Change | SNMAG_DWH | Addition to the scope | Mateusz P | Ken | 2021-02-16
45 | Other | Inventures (SCAMPI) Web App | SDM - Ian Bennett | Mateusz P | Ken | 2021-02-16
46 | Other | Electronic Instructions for Use | SDM - Carla Morris | Mateusz P | Ken | 2021-02-16
47 | Schedule Change | FLEx LM - PROD | Moved to 30th May 2021 to include with Co-Mingled Apps. | Arun S |  | 2021-02-18
48 | Other | CIMCO Mansfield | Updated server names for CIMCO Mansfield DEV and PROD based on inputs from App SME Greg T | Debojit M |  | 2021-02-20
49 | Schedule Change | CIMCO Memphis | Aligned CIMCO Memphis to Wave 6 with CIMCO China since server is being shared with CIMCO China | Debojit M |  | 2021-02-20
50 | Schedule Change | dataSTOR | Moved to April cutover due to delays in planning from vendor. | Debojit M | Adrian C | 2021-02-23
51 | Schedule Change | OSISoft PI System | Rescheduled to Wave 5 MG1 to accomodate decision around China regulatory requirements. | Debojit M | Adrian C | 2021-02-23
52 | Schedule Change | SEAL Application | Rescheduled to Wave 4 MG1 to accomodate vendor dependency and engagement. | Debojit M | Mateusz P | 2021-02-23
53 | Schedule Change | TOTVS - DEV | Assigned to W3-MG2 instead of W3-MG1 to accomodate additional time to build firewall rules for DMZ & terminal server licensing. | Debojit M | Mateusz P | 2021-02-23
54 | Schedule Change | Mobile Inventory Management System | Moved to July per discussion with ITLT. May be included with additional apps as a REHOST. | Debojit M | Adrian C | 2021-02-24
55 | Scope Change | Winflex | Moved to Out Of Scope per discussion with Yvonee because of the File Server dependency. | Debojit M | Ken | 2021-02-24
56 | Migration Strategy Change | Winshuttle, PricingTool, AWD Tracker, Metasys, Lasernet / Nemhandel, ID Prove, Spectrum 10 | DB Re-platform - SQL 2019 consolidation | Mateusz P |  | 2021-02-24
57 | Schedule Change | eRoom | Removed from scope as the application is retired. | Jyotsna K | Ken | 2021-03-02
58 | Migration Strategy Change | Winshuttle | Changed to re-host | Mateusz P |  | 2021-03-05
59
60
61
62
63
64
65
66
67
68
69
70
71

## CMDB_data
Name | Alias | Application Disposition | Description | Business Domain | IT Application Owner | Service Delivery Manager | Hardware | OS | Web Services | Middleware | DB | Application | Other | IT Support | Desktop | OS Version | DB Version | IIs Version | App Type | EOL | Production Date | TIME | Cloud Migration model | Email | ITLT
Abel X3 |  | Retired | ERP France-Ortho. 11/3/15 - Linda states she does not support this application. Delivery Manager was set to Linda as part of the original EAP setup in 2012. |  | Imtiaz Iqbal | Paul Davison | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | paul.davison@smith-nephew.com
Al Abbas, Solutions ME, CAD Gulf, VIN Systems - Citrix & Oracle 10G |  | Retired | Remote Access / Oracle reporting / HR Payroll |  | Imtiaz Iqbal | Requalann Pereira | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Requalann.Pereira@smith-nephew.com
Archie |  | Retired | Information repository for sales people - retired with EPO golive |  | Firas Almahamid | Alison Conlon | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Alison.Conlon@smith-nephew.com
Articulate |  | Retired | Training Team AWMANZ Video Editing Tools |  | Imtiaz Iqbal | Marianne Morton | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Marianne.Morton@smith-nephew.com
Avery Wizard |  | Retired | Label Printing |  | Imtiaz Iqbal | Marianne Morton | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Marianne.Morton@smith-nephew.com
Bitcom |  | Retired | Instrument programming sorftware used in Exogen manufacturing process. 01/20/16 - Per Al, this is retired. "The below app is no longer applicable for ASD and I see no associated serer to decom. This is my request to delete or deactivate. Bitcom - Instrument programming software used in Exogen manufacturing process." |  | Christopher Rowley | Alvin Whitney | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Al.Whitney@smith-nephew.com
BSFactura |  | Retired | electronic invoicing |  | Firas Almahamid | Alison Conlon | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Alison.Conlon@smith-nephew.com
Cashbook |  | Retired | Electronic Banking and Financial Software. Interfaces to BPCS. Used by Italy and Sweden. |  | Firas Almahamid | Alison Conlon | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Alison.Conlon@smith-nephew.com
Citibank Check image viewer |  | Retired | Check viewer. |  | Tjebbes Feenstra | Paul Davison | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | paul.davison@smith-nephew.com
Cognos Business Intelligence |  | Retired | Datawarehouse Reporting Tool |  | Imtiaz Iqbal | Marianne Morton | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Marianne.Morton@smith-nephew.com
Cognos Enterprise Planning Suite |  | Retired | Financial Planning tool |  | Imtiaz Iqbal | Marianne Morton | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Marianne.Morton@smith-nephew.com
COGNOS METRIC MANAGER |  | Retired | Named user/intranet/division specific |  | Imtiaz Iqbal | Marianne Morton | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Marianne.Morton@smith-nephew.com
Coheris Conso+ |  | Retired | Collections and finance |  | Firas Almahamid | Alison Conlon | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Alison.Conlon@smith-nephew.com
Contaplus |  | Retired | Accounting software for the BSN business |  | Firas Almahamid | Alison Conlon | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Alison.Conlon@smith-nephew.com
COVERIS |  | Retired | Accounting software for collections |  | Firas Almahamid | Alison Conlon | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Alison.Conlon@smith-nephew.com
Crystal reports client |  | Retired | Legacy Reporting -OEM for Adonix (not a BI App, EPR Trans Reporting). 01/11/16 - Chris Cook took ownership of this. "Obsolete but we can't turn it off (yet) due to data retention issues – one to add to our growing system retirement problem – I will pick this up.". Removing Linda as the Delivery Manager as assigned to Richard to until research complete. |  | Firas Almahamid | Richard Hepwood | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Richard.Hepwood@smith-nephew.com
CTIOS |  | Retired | CTI integration software |  | Imtiaz Iqbal | Michael Schatten | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Michael.Schatten@smith-nephew.com
Demand Solutions |  | Retired | Forecasting |  | Imtiaz Iqbal | Marianne Morton | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Marianne.Morton@smith-nephew.com
Discovery |  | Retired | Training Team Software |  | Imtiaz Iqbal | Marianne Morton | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Marianne.Morton@smith-nephew.com
Dmax (for marketing/sales tenders in AWM/ANZ) |  | Retired | Tenders |  | Imtiaz Iqbal | Marianne Morton | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Marianne.Morton@smith-nephew.com
Docuware (Marl) |  | Retired | Document Management. 02/04/16 - Update from Sebastian: "Docuware does no longer exist in 2 instances – over the past year we have successfully combined both instances (Tuttlingen and Marl) into one instance hosted in Tuttlingen. There is no server that would be affected as part of the Datacenter move." Setting disposition of this application to RETIRED. |  | Firas Almahamid | Alison Conlon | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Alison.Conlon@smith-nephew.com
E-Commerce: GHX/Sedico (Don't know what this is) |  | Retired | E-Commerce: GHX/Sedico. 03/22/16 - Retiring from inventory. Per Al Whitney, this no longer used. |  | Chris Cook | Alvin Whitney | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Al.Whitney@smith-nephew.com
E-Finance Suite (E-cash/E-tresury) |  | Retired | Cash/treasury application - retired with EPO golive |  | Firas Almahamid | Alison Conlon | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Alison.Conlon@smith-nephew.com
EuroCollect |  | Retired | Debt management system - interfaced with Hub BPCS ACR module - retired with EPO golive |  | Firas Almahamid | Alison Conlon | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Alison.Conlon@smith-nephew.com
Euronetting |  | Retired | Web based - used for Group netting |  | Tjebbes Feenstra | Paul Davison | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | paul.davison@smith-nephew.com
Extensis |  | Retired | Digital asset management software |  | Chris Cook | David Gamble | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | David.Gamble@smith-nephew.com
Fiery Command Workstation |  | Retired | Print integration software spain,portugal and austria |  | Alison Conlon | Hugo Vizella | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Hugo.Vizella@smith-nephew.com
Forecast |  | Retired | local demand planning |  | Firas Almahamid | Alison Conlon | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Alison.Conlon@smith-nephew.com
Forefinance |  | Retired | Fixet assets and collections for Italy - Retired with EPO |  | Firas Almahamid | Alison Conlon | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Alison.Conlon@smith-nephew.com
FTP/SSL |  | Retired | Local secured ftp server |  | Imtiaz Iqbal | Michael Schatten | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Michael.Schatten@smith-nephew.com
Getronics - Call Manager 4.0 |  | Retired | IP Telephony |  | Imtiaz Iqbal | Michael Schatten | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Michael.Schatten@smith-nephew.com
Gypsilon |  | Retired | Asset management application. 01/26/16 - Per Yvonne B: Gypsilon user left company in Jan 2014, local install was deleted |  | Christopher Rowley | Alvin Whitney | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Al.Whitney@smith-nephew.com
Hoja de gastos |  | Retired | Custom application for travel expenses |  | Firas Almahamid | Alison Conlon | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Alison.Conlon@smith-nephew.com
Hyperion -MRS |  | Retired | reporting software |  | Firas Almahamid | Alison Conlon | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Alison.Conlon@smith-nephew.com
ICG Machine Centre Europe |  | Retired | Could be patient monitoring kit rather than software |  | Imtiaz Iqbal | Paul Davison | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | paul.davison@smith-nephew.com
ILEARN INTERACTIVE |  | Retired | iLearn Interactive is training software - possibly used in manufacturing Retired Per Paul Davison 30 OCT 17 |  | Firas Almahamid | Gernot Moeller | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Gernot.Moeller@smith-nephew.com
ILEARN VIBRATION |  | Retired | iLearn Vibration Client Retired Per Paul Davison 30 OCT 17 |  | Firas Almahamid | Gernot Moeller | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Gernot.Moeller@smith-nephew.com
IMS Loader (teams Cagedim) |  | Retired | Interface between BO and Teams |  | Firas Almahamid | Alison Conlon | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Alison.Conlon@smith-nephew.com
INSOURCE |  | Retired | InSource Domestic Income Tax & Provisions. Replaced by CORPTAX. Instruction sent to Mark Beal to decommission this application (on server MEMSRV064) on 25 June 2015. |  | Tjebbes Feenstra | Paul Davison | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | paul.davison@smith-nephew.com
Internet Banking (Isabel/ING) |  | Retired | Banking softawre used by Finance |  | Firas Almahamid | Alison Conlon | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Alison.Conlon@smith-nephew.com
iScala (Finland) |  | Retired | Sales, GL Accounting, Personnel, Sales, Inventory, PL, SO, PO Stock Statistics / S/C, PUR, Fixed Assets, Cash Paul D: was decommissioned 2 years ago. |  | Imtiaz Iqbal | Paul Davison | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | paul.davison@smith-nephew.com
Japan Ortho BI tool |  | Retired | Reporting for Japan ASD division. 07/27/16 - Email from Firas stating this is no longer in use. CMDB team confirming. |  | Imtiaz Iqbal | Tsutomu Hirooka | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Tsutomu.Hirooka@smith-nephew.com
KOFAX ocr |  | Retired | Scanning for shipping documents |  | Firas Almahamid | [8 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned
Label Print - Labelling PC's Warehouse Baar |  | Retired | Labeling tool - all label printing has been replaced by the SAP generated labels since EPO golive, therefore changing state to retired (Seb) |  | Firas Almahamid | Massimo Trambaioli | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Massimo.Trambaioli@smith-nephew.com
Local intranet (CH) |  | Retired | Local intranet application decommed in 2016 (Seb) |  | Chris Cook | [8 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned
Lotus InterNotes |  | Retired | Believed to be used in conjunction with Boomerang (Canada Lotus Notes) for publishing onto Web for expenses. |  | Tjebbes Feenstra | Paul Davison | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | paul.davison@smith-nephew.com
Lotus SmartSuite |  | Retired | lotus notes |  | Christopher Rowley | Paul Davison | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | paul.davison@smith-nephew.com
Microsoft Small Business Accounting |  | Retired | Accounting packaage |  | Tjebbes Feenstra | Paul Davison | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | paul.davison@smith-nephew.com
NAVI INTRA |  | Retired | Business Intelligence sw Tool for Japan |  | Imtiaz Iqbal | Tsutomu Hirooka | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Tsutomu.Hirooka@smith-nephew.com
OCOGS (Other Cost of Goods Sold) |  | Retired | OCOGS is a .Net application that was developed as part of the See Through Profitability Project |  | Tjebbes Feenstra | Paul Davison | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | paul.davison@smith-nephew.com
Optus Aircard 3G Watcher |  | Retired | Wireless Internet |  | Imtiaz Iqbal | Marianne Morton | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Marianne.Morton@smith-nephew.com
Oracle UPK Tool (Switzerland) |  | Retired | Oracle database documentation. 02/09/16 - Per Matt Stephens, after much research and reviewing the server environment, this is not a valid application entry. Setting disposition to Retired. |  | Mark Towne | Ramesh Balabhadruni | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Ramesh.Balabhadruni@smith-nephew.com
ORG PLUS PRO |  | Retired | Human Concept's Org Plus Professional. SaaS integrated with SAP |  | Tjebbes Feenstra | Paul Davison | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | paul.davison@smith-nephew.com
Politikkens ordbog (DEN-ENG dictionary) |  | Retired | Installed on all computers |  | Imtiaz Iqbal | Paul Davison | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | paul.davison@smith-nephew.com
Q-Master (local PABX voicemail and Queue Mgt in AWMANZ) |  | Retired | Local PABX Client Software |  | Imtiaz Iqbal | Marianne Morton | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Marianne.Morton@smith-nephew.com
Qualicare End note |  | Retired | Quality |  | Firas Almahamid | Alison Conlon | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Alison.Conlon@smith-nephew.com
QUARK XPRESS |  | Retired | Macromedia - Quark XPress |  | Imtiaz Iqbal | Marianne Morton | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Marianne.Morton@smith-nephew.com
Quicktax |  | Retired | Tax calculation software ***Set to Retired per Paul Davidson on 7-JAN-16:ALPHAM |  | Tjebbes Feenstra | Paul Davison | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | paul.davison@smith-nephew.com
Sales Rep application wound |  | Retired | Sales reporting tool |  | Firas Almahamid | Alison Conlon | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Alison.Conlon@smith-nephew.com
Sales Rep Reporting System (Go Pharmacy) |  | Retired | Sales reporting tool France |  | Firas Almahamid | Alison Conlon | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Alison.Conlon@smith-nephew.com
SAP BPS |  | Retired | Forecasting and Budgeting in SAP. 1/19/16 - Retired per Steve Horgan, Paul Wilson. |  | Tjebbes Feenstra | [8 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned
SCR-VISOR |  | Retired | custom application for field sales reports |  | Firas Almahamid | Alison Conlon | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Alison.Conlon@smith-nephew.com
SEN ERP Client |  | Retired | ERP for Greece |  | Imtiaz Iqbal | Santhosh Nair | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Santhosh.Nair@smith-nephew.com
SGA Kits |  | Retired | Inventory counting |  | Firas Almahamid | Alison Conlon | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Alison.Conlon@smith-nephew.com
SIP |  | Retired | Polish mini ERP system - invoicing for Poland. 1/11/16 - Per Chris C, this should be obsolete, no longer in use, researching. Changing Delivery Manager from Linda to Richard. |  | Chris Cook | Richard Hepwood | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Richard.Hepwood@smith-nephew.com
Smith Finance |  | Retired | Application to enter automatically bank transfers and payments |  | Firas Almahamid | Alison Conlon | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Alison.Conlon@smith-nephew.com
SNBelgium |  | Retired | Holiday request and customer complaint follow up application. 03/22/16 - Removing from inventory. Per Al Whitney, this is a really old app and is retired. |  | Christopher Rowley | Alvin Whitney | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Al.Whitney@smith-nephew.com
SQL Database for Labels |  | Retired | PO Label Database Application |  | Imtiaz Iqbal | Paul Davison | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | paul.davison@smith-nephew.com
SWING Sales Rep Reporting System (Local development) |  | Retired | Reporting tool for the Sales network in Endo France - being discontinued |  | Firas Almahamid | Alison Conlon | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Alison.Conlon@smith-nephew.com
Telefon Software (Aastra ASC Client) |  | Retired | VoIP client |  | Imtiaz Iqbal | Michael Schatten | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Michael.Schatten@smith-nephew.com
Third Party Sellers Compliance Toolkit Extranet Share Point site |  | Retired | Web site for third party sellers compliance. Unknown application. |  | Tjebbes Feenstra | Paul Davison | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | paul.davison@smith-nephew.com
Tobit Faxware |  | Retired | Fax client. Very similar to Kofax. |  | Imtiaz Iqbal | Michael Schatten | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned
Trumark - laser marking |  | Retired | Marks serial numbers etc on product. 01/25/16 - Updated ITLT Owner, Delivery Manager per Imtiaz request. 01/26/16 - Per Yvonne B. Laser marking machine was retired. |  | Christopher Rowley | Alvin Whitney | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Al.Whitney@smith-nephew.com
Upside (contract f/service) and Upside Power user |  | Retired | Surgeon Contracts - Ortho. Now Decommissioned. |  | Tjebbes Feenstra | Paul Davison | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | paul.davison@smith-nephew.com
VIRTUAL DUB |  | Retired | Video capture and editing software Movie Viewer for Vendor Graphics. 01/26/16 - Per Yvonne B: Virtual DUB user left company in Apr 2013, local install was deleted |  | Firas Almahamid | Alvin Whitney | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Al.Whitney@smith-nephew.com
Vital'Acess |  | Retired | Purchasing. 1/11/16 - Neither Firas nor Chris C know anything about this app. Removing Linda as the Delivery Manager. |  | Imtiaz Iqbal | Michael Schatten | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Michael.Schatten@smith-nephew.com
Vodafone statistics loader |  | Retired | Loads phone expenses details for reporting |  | Firas Almahamid | Alison Conlon | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Alison.Conlon@smith-nephew.com
Wanao |  | Retired | Tenders application |  | Firas Almahamid | Alison Conlon | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Alison.Conlon@smith-nephew.com
Worldship |  | Retired | UPS Shipping software. 03/22/16 - Update from Al Whitney, no longer using this product. Replaced by ConnectShip. |  | Christopher Rowley | Alvin Whitney | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Al.Whitney@smith-nephew.com
ArboNet |  | Retired | This application is running through an internet site so can be opened from home by the HR manager in case of a disaster. |  | Firas Almahamid | Alison Conlon | [7 empty] | Limited | [5 empty] | Unknown | 38352.375 | Unassigned |  | Alison.Conlon@smith-nephew.com
Badge Doors |  | Retired | Doors and entry software |  | Firas Almahamid | Alison Conlon | [7 empty] | Limited | [5 empty] | Unknown | 38352.375 | Unassigned |  | Alison.Conlon@smith-nephew.com
Dunn & Bradstreet |  | Retired | Credit information and credit reports |  | Tjebbes Feenstra | Paul Davison | [7 empty] | External | [5 empty] | Unknown | 38352.375 | Unassigned |  | paul.davison@smith-nephew.com
Edok srl |  | Retired | Invoices / Archive Optical |  | Imtiaz Iqbal | Paul Davison | [7 empty] | Limited | [5 empty] | Unknown | 38352.375 | Unassigned |  | paul.davison@smith-nephew.com
FIRST WINDOW 2000 |  | Retired | FirstWindow 2000. ACH and wires |  | Tjebbes Feenstra | Paul Davison | [7 empty] | External | [5 empty] | Unknown | 38352.375 | Unassigned |  | paul.davison@smith-nephew.com
Hyperion Wired |  | Retired | Endoscopy Data Warehouse(EDWODS) feeds Hyperio WIRED. Sales reporting tool for sales managers. This application is retired (server ANDSRV38). |  | Tjebbes Feenstra | Paul Davison | [7 empty] | External | [5 empty] | Unknown | 38352.375 | Unassigned |  | paul.davison@smith-nephew.com
ING Bank |  | Retired | Banking software - Third party Payments and arhcive for account stmt extracts. 01/12/16 - Per Linda and Bart Claes: "ING Bank app I an application that was used for communication with the bank (account statements, payments, …) This has been replaced with online solutions, and accounting confirmed me they no longer use the application nor do they need it for archives or anything. So the application is obsolete." |  | Firas Almahamid | Linda Ivy-Rosser | [7 empty] | External | [5 empty] | Unknown | 38352.375 | Unassigned |  | Linda.Rosser@smith-nephew.com
Ipass |  | Retired | Remote dial up software |  | Firas Almahamid | Alison Conlon | [7 empty] | Limited | [5 empty] | Unknown | 38352.375 | Unassigned |  | Alison.Conlon@smith-nephew.com
Majesty |  | Retired | customs tool |  | Firas Almahamid | Gernot Moeller | [7 empty] | None | [5 empty] | Unknown | 38352.375 | Unassigned |  | Gernot.Moeller@smith-nephew.com
Mercury |  | Retired | ESX Virtual - Mercury. 03/22/16 - Removing from inventory. Per Al Whitney, this is no longer in place. |  | Christopher Rowley | Alvin Whitney | [7 empty] | None | [5 empty] | Unknown | 38352.375 | Unassigned |  | Al.Whitney@smith-nephew.com
Microsoft Business Solution (Navison) |  | Retired | Marl - already retired since SAP golive in 2008/2009 but 10 years availability needs to be ensured |  | Alison Conlon | Sebastian Pasch | [7 empty] | Limited | [5 empty] | Unknown | 38352.375 | Unassigned |  | Sebastian.Pasch@smith-nephew.com
Microsoft Dynamics CRM 2011 (ANZ) |  | Retired | -KEEPING FOR HISTORICAL REFERENCE- CRM application used by AWM ANZ, 10/20/15 - Per Roger Heffington, GxP assessment = true (complete). |  | Firas Almahamid | Jerry Li | [7 empty] | None | [5 empty] | Unknown | 38352.375 | Unassigned |  | Jerry.Li@smith-nephew.com
Powerkey |  | Retired | End user demo tool now retired since conversion to sales life online |  | Firas Almahamid | Gernot Moeller | [7 empty] | None | [5 empty] | Unknown | 38352.375 | Unassigned |  | Gernot.Moeller@smith-nephew.com
RAET |  | Retired | HR Software |  | Firas Almahamid | Alison Conlon | [7 empty] | Limited | [5 empty] | Unknown | 38352.375 | Unassigned |  | Alison.Conlon@smith-nephew.com
RedOxygen Office SMS |  | Retired | Office SMS, Bulk SMS |  | Imtiaz Iqbal | Marianne Morton | [7 empty] | None | [5 empty] | Unknown | 38352.375 | Unassigned |  | Marianne.Morton@smith-nephew.com
Reference Manager |  | Retired | We do not maintain but we do support Retired Per Paul Davison 30 OCT 17 |  | Firas Almahamid | Gernot Moeller | [7 empty] | None | [5 empty] | Unknown | 38352.375 | Unassigned |  | Gernot.Moeller@smith-nephew.com
Access 2003 (CRM Informix) |  | Retired | CRM application used in Marl Retired Per Paul Davison 30 OCT 17 Setting to Archived as an UNKNOWN server was found with this information running on it. 30-JAN-18 | ASD (Advanced Surgical Devices) | Firas Almahamid | Paul Davison | [7 empty] | Limited | [5 empty] | Unknown | 38352.375 | Unassigned |  | paul.davison@smith-nephew.com
Activesync - Server |  | Retired | Exchange Server component that allows Mobile Devices to connect to Exchange servers for Mail, Calendar, Contacts. 02/09/16 - Updated disposition to Retired after speaking with Julie. | IT | Alison Conlon | David Margossian | [7 empty] | External | [5 empty] | Unknown | 38352.375 | Unassigned |  | David.Margossian@smith-nephew.com
Adobe Creative suite |  | Retired | PDF edit/creation/photoshop etc | Commercial | Anna Falbogowska | Hugo Vizella | [7 empty] | Partial | [5 empty] | No | 38352.375 | Unassigned |  | Hugo.Vizella@smith-nephew.com
Alchemy |  | Retired | Alchemy. 07/27/16 - Email from Firas stating this is no longer in use. CMDB team confirming. | Group Functions | Firas Almahamid | Mark Elliott | [7 empty] | None | [5 empty] | Unknown | 38352.375 | Unassigned |  | Mark.Elliott@smith-nephew.com
Amadeus Selling Platform Amadeus vista |  | Retired | retailing application for travel professionals | ASD (Advanced Surgical Devices) | Firas Almahamid | Gernot Moeller | [7 empty] | None | [5 empty] | Unknown | 38352.375 | Unassigned |  | Gernot.Moeller@smith-nephew.com
Amtech 2004 |  | Retired | Product design software | R&D | Imtiaz Iqbal | Ian Bennett | [7 empty] | None | [5 empty] | Unknown | 38352.375 | Unassigned |  | ian.bennett@smith-nephew.com
BACS |  | Retired | Web-based software - used to transfer money between accounts. Files are extracted from SAP and then put on mapped shared drives which are then picked up from within the web-based BACS system. | Group Functions | Imtiaz Iqbal | Paul Davison | [7 empty] | None | [5 empty] | Unknown | 38352.375 | Unassigned |  | paul.davison@smith-nephew.com
Bank of America -WORKS PayMGR |  | Retired | Program used to process P cards; E-Payables and T&E cards. Replaced by Concur T&E. | ASD-US | Tjebbes Feenstra | Paul Davison | [7 empty] | Limited | [5 empty] | Unknown | 38352.375 | Unassigned |  | paul.davison@smith-nephew.com
Bank of Ireland |  | Retired | Web based - used for IRISH co payment | Group Functions | Imtiaz Iqbal | Steve Horgan | [13 empty] | Unknown | 38352.375 | Unassigned |  | Stephen.Horgan@smith-nephew.com
Blackberry Enterprise Server |  | Retired | Middleware service; redirects emails and synchronizes contacts and calendaring information between servers, desktop workstations, and mobile devices | IT | Alison Conlon | Alison Conlon | [7 empty] | External | [5 empty] | Unknown | 38352.375 | Unassigned |  | Alison.Conlon@smith-nephew.com
Ceridian Payroll |  | Retired | Historic only. Server HUS56 was scheduled for decommission in June 2015. | Human Resources | Tjebbes Feenstra | Paul Davison | [7 empty] | External | [5 empty] | Unknown | 38352.375 | Unassigned |  | paul.davison@smith-nephew.com
Chase BankOne |  | Retired | Paper Checks; Wires; ACH | Group Functions | Imtiaz Iqbal | Steve Horgan | [13 empty] | Unknown | 38352.375 | Unassigned |  | Stephen.Horgan@smith-nephew.com
CX-Programmer |  | Retired | Provides a common platform for developing programs for all types of Omron PLC controllers. 01/25/16 - Updated Delivery Manager per request from Chris R. and Imtiaz. | Manufacturing | Imtiaz Iqbal | Ian Bennett | [7 empty] | None | [5 empty] | Unknown | 38352.375 | Unassigned |  | ian.bennett@smith-nephew.com
DYMO LABELWRITER SW |  | Retired | Software for Dymo Labelwriters | Manufacturing | Imtiaz Iqbal | Amit Shokeen | [7 empty] | Limited | [5 empty] | Unknown | 38352.375 | Unassigned |  | Amit.Shokeen@smith-nephew.com
Extol |  | Retired | EDI Software for US Wound | AWM (Advanced Wounded M...) | Imtiaz Iqbal | Santhosh Nair | [7 empty] | None | [5 empty] | Unknown | 38352.375 | Unassigned |  | Santhosh.Nair@smith-nephew.com
GLOBAL LBL - PKG DEV APP |  | Retired | Package Development Application Global Labeling. 01/21/16 - Update from Al. This is running on a desktop today and will be retired within 90-120 days. | Manufacturing, Operations and Supply Cha | Imtiaz Iqbal | Amit Shokeen | [7 empty] | None | [5 empty] | Unknown | 38352.375 | Unassigned |  | Amit.Shokeen@smith-nephew.com
GMC - GREEN MOUNTAIN |  | Retired | Provides Carrier Invoice tracking, service levels, match to internal accounts. Hosted web app with some client software on selected PC's | Manufacturing, Operations and Supply Cha | Christopher Rowley | David Gamble | [7 empty] | External | [5 empty] | Unknown | 38352.375 | Unassigned |  | David.Gamble@smith-nephew.com
IXOS |  | Retired | Document Archiving system. Replaced by Opentext in Q1 2011. Now maintained for historical purposes only. 05/17/16 - This application's disposition was set to 'Retired' but appears to still be operational for "historical purposes". Server still in place. Setting disposition to 'Archive'. | ASD (Advanced Surgical Devices) | Tjebbes Feenstra | Paul Davison | [7 empty] | Limited | [5 empty] | Unknown | 38352.375 | Unassigned |  | paul.davison@smith-nephew.com
Learn Japanese |  | Retired | elearning application for japanese | Both ASD and AWM | Firas Almahamid | Massimo Trambaioli | [7 empty] | None | [5 empty] | Unknown | 38352.375 | Unassigned |  | Massimo.Trambaioli@smith-nephew.com
PHC |  | Archive | ERP for Portugal. 06/22/16 - Per Dave Metcalfe, this is no longer a production system, in place for reference only. Changing Criticality to Important and Disposition to Archive. | ASD/AWM | Chris Cook | Hugo Vizella | [7 empty] | Partial | [5 empty] | Unknown | 38352.375 | Unassigned |  | Hugo.Vizella@smith-nephew.com
Quark |  | Retired | Design Software Retired Per Paul Davison 30 OCT 17 | ASD (Advanced Surgical Devices) | Firas Almahamid | Gernot Moeller | [7 empty] | None | [5 empty] | Unknown | 38352.375 | Unassigned |  | Gernot.Moeller@smith-nephew.com
RBS |  | Retired | Web based - used for Hedging | Group Functions | Imtiaz Iqbal | Steve Horgan | [13 empty] | Unknown | 38352.375 | Unassigned |  | Stephen.Horgan@smith-nephew.com
Spreadsheet Server |  | Retired | Allows transfer of data from BPCS to Excel. Was used with Hull BPCS (MANLIVE). Now decommissioned. | AWM (Advanced Wounded M...) | Tjebbes Feenstra | Paul Davison | [7 empty] | Limited | [5 empty] | Unknown | 38352.375 | Unassigned |  | paul.davison@smith-nephew.com
TNT Express Manager |  | Retired | Shipment Manager for Loan Pool | Supply Chain | Alison Conlon | Sebastian Pasch | [7 empty] | External | [5 empty] | Unknown | 38352.375 | Unassigned |  | Sebastian.Pasch@smith-nephew.com
UPS Client |  | Retired | Lager - Marl | Supply Chain | Firas Almahamid | Massimo Trambaioli | [7 empty] | None | [5 empty] | Unknown | 38352.375 | Unassigned |  | Massimo.Trambaioli@smith-nephew.com
ZMOD Exchange - AS400 Communications |  | Retired | EDI and Messaging Communications tool for US Wound RESETTING APP TO ACTIVE - SERVERS ARE STILL related to this apps environment; this needs to be corrected prior to setting applications to retired in all cases. | AWM (Advanced Wounded M...) | Imtiaz Iqbal | Santhosh Nair | [7 empty] | None | [5 empty] | Unknown | 38352.375 | Unassigned |  | Santhosh.Nair@smith-nephew.com
Adobe Professional |  | Retired | Creating Pdf | Group Functions | Dave Cranny | Hugo Vizella | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Hugo.Vizella@smith-nephew.com
Adobe Purchase Requisition Workflow |  | Retired | US only - Adobe Purchase Requisition forms routed electronically for approval based on SAP HR Cost Center owners. | Supply Chain | Manas Singha | Amit Shokeen | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Amit.Shokeen@smith-nephew.com
Adonix X3 |  | Retired | ERP France-Ortho. 10/25/12 - Per Adrien Le Strat and Thomas Groiss, no longer in use, business moved to HUB BPCS - in place for historical queries only. 1/19/16 - The option to specify 'Historical' as an Application Disposition status has not been moved to PROD yet. Leaving as 'Declining' for now. resetting to retired after infrastructure was identified as incorrectly mapped | Local Europe | Chris Cook | Hugo Vizella | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Hugo.Vizella@smith-nephew.com
ARTICULATE PRESENTER PRO |  | Retired | Articulate --Learn.com Course creation. Add-on for PowerPoint for Training | Group Functions | Imtiaz Iqbal | Andres Bernard | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Andres.Bernard@smith-nephew.com
AssetPro |  | Retired | Finance, managing Assets | Group Functions | Imtiaz Iqbal | Jerry Li | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Jerry.Li@smith-nephew.com
Authentication Service (MyCareer SSO) |  | Retired | Performance management - SaaS .Net Application used to bypass login screen. Decommissioned 7 Jan after confirmation from Nikki West and Jerry Poreca. | ASD (Advanced Surgical Devices) | Tjebbes Feenstra | Paul Davison | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | paul.davison@smith-nephew.com
Bar1 |  | Retired | Bar code scanning | Both ASD and AWM | Firas Almahamid | Mark Elliott | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Mark.Elliott@smith-nephew.com
Bartender |  | Retired | Product labeling. This is being replaced by the Enlabel product{Mark L.C - Not responsible for Maintenance} Server is in China. | RAQA | Imtiaz Iqbal | Amit Shokeen | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Amit.Shokeen@smith-nephew.com
CAMTASIA STUDIO |  | Retired | TechSmith's Camtasia MultiMedia Presesntation Sw | Corporate | Imtiaz Iqbal | Andres Bernard | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Andres.Bernard@smith-nephew.com
CAPTIVATE |  | Retired | Adobe Captivate - Screen capture. Learn.com course creation; Feb. 6, 2018: Although Captivate is also an old authoring tool that has been decommissioned. It's no longer used to generate new content but we do have historic content that needs to be brought over from Captivate to Articulate. | Enterprise | Imtiaz Iqbal | Andres Bernard | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Andres.Bernard@smith-nephew.com
Chromatography System Empower (To be decomissioned per owner) |  | Retired | Lab equipment. 03/22/16 - Update from Al Whitney, this has been retired. | ASD (Advanced Surgical Devices) | Christopher Rowley | Alvin Whitney | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Al.Whitney@smith-nephew.com
Cisco Aironet |  | Retired | Phone software | IT | Imtiaz Iqbal | Mark Beal | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Mark.Beal@smith-nephew.com
Cisco IP Communicator Client |  | Retired | Phone software | Global | Anna Falbogowska | Hugo Vizella | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Hugo.Vizella@smith-nephew.com
Cisco VPN Client |  | Retired | Client to connect to the global network from remote locations | IT | Alison Conlon | Alison Conlon | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Alison.Conlon@smith-nephew.com
Codesoft |  | Retired | Product labeling software | Manufacturing, Operations and Supply Cha | Imtiaz Iqbal | Amit Shokeen | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Amit.Shokeen@smith-nephew.com
Color RIP |  | Retired | Raster Image Processor | R&D | Imtiaz Iqbal | Ian Bennett | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | ian.bennett@smith-nephew.com
Compliance Intranet |  | Retired | Internal Web site used by Compliance | Both ASD and AWM | Tjebbes Feenstra | David Gamble | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | David.Gamble@smith-nephew.com
Contracts |  | Retired | Site used by Finance to manage all the Surgeon contracts | ASD (Advanced Surgical Devices) | Chris Cook | Paul Davison | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | paul.davison@smith-nephew.com
Cronacle |  | Retired | Scheduling Package supporting Manugistics | Supply Chain | Imtiaz Iqbal | Amit Shokeen | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Amit.Shokeen@smith-nephew.com
DBU Softron |  | Retired | Data Base Utility | IT | Firas Almahamid | Mark Elliott | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Mark.Elliott@smith-nephew.com
Decco 2000 |  | Retired | Used in shop B for obtaining DNC data when milling screws and nails. | Manufacturing | Imtiaz Iqbal | Ian Bennett | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | ian.bennett@smith-nephew.com
Dimensions |  | Retired | PLM Printer Software | R&D | Imtiaz Iqbal | Ian Bennett | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | ian.bennett@smith-nephew.com
DPD Client |  | Retired | all warehouse outbound delivery | ASD (Advanced Surgical Devices) | Firas Almahamid | Gernot Moeller | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Gernot.Moeller@smith-nephew.com
DPD Tracking |  | Retired | Webservice that loads all status data from DPD to provide an overview if all outbound deliveries have reached the receiver in-time | ASD (Advanced Surgical Devices) | Firas Almahamid | Gernot Moeller | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Gernot.Moeller@smith-nephew.com
e-Newsletter |  | Retired | China Newsletter | Local | Imtiaz Iqbal | Guoliang Wu | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | guoliang.wu@smith-nephew.com
EDITLOGIC |  | Retired | printLogic is a server-based ENOVIA MatrixOne web integration that allows users to batch print documents directly from their MatrixOne databases. editLogic allows you to open, edit and save Program Code directly to Matrix without ever opening the Business | Both ASD and AWM | Imtiaz Iqbal | Ian Bennett | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | ian.bennett@smith-nephew.com
Employee database |  | Retired | Employee database | Both ASD and AWM | Firas Almahamid | Massimo Trambaioli | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Massimo.Trambaioli@smith-nephew.com
EPLAN View |  | Retired | CAD/CAE software | R&D | Imtiaz Iqbal | Ian Bennett | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | ian.bennett@smith-nephew.com
Esprit 2008 |  | Retired | CAM software | Manufacturing | Imtiaz Iqbal | Ian Bennett | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | ian.bennett@smith-nephew.com
Goldmine |  | Retired | CRM and Sales Leads. 03/22/16 - Update from Al Whitney, this is a SaaS service, not sure if it is still used. | IT | Imtiaz Iqbal | Amit Shokeen | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Amit.Shokeen@smith-nephew.com
IBM Client Access |  | Retired | PC Access to AS/400 (iSeries) for any location with BPCS but also BAS in Tuttlingen and other AS400 based systems in S&N | ERP | Dave Cranny | Sebastian Pasch | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Sebastian.Pasch@smith-nephew.com
ILLUSTRATOR CS |  | Retired | Adobe Illustrator CS | Group Functions | Hugo Vizella | Hugo Vizella | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Hugo.Vizella@smith-nephew.com
IMANY |  | Retired | Contract Management Software - hosted site used to get Medicaid/Medicare rates. 03/22/16 - Update from Al Whitney, this is a SaaS service, not sure if it is still used. | Group Functions | Imtiaz Iqbal | Amit Shokeen | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Amit.Shokeen@smith-nephew.com
Industry News |  | Retired | Site to post news clips that are relative to the SN business | ASD (Advanced Surgical Devices) | Tjebbes Feenstra | Paul Davison | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | paul.davison@smith-nephew.com
Interforms/ Interfax |  | Retired | Faxing & emailing from AS400 | IT | Firas Almahamid | Mark Elliott | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Mark.Elliott@smith-nephew.com
Jcharge Credit Card |  | Retired | Credit card approval software on the AS400 | AWM (Advanced Wounded M...) | Imtiaz Iqbal | Paul Davison | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | paul.davison@smith-nephew.com
KIX32 Login scripts |  | Retired | Logon script | IT | Imtiaz Iqbal | Tsutomu Hirooka | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Tsutomu.Hirooka@smith-nephew.com
Kodak IAS (for AS400) |  | Retired | DHR Imaging Software runs on AS400 | RAQA | Ian Bennett | Matthew Stephens | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Matthew.Stephens@smith-nephew.com
Kronos Workforce Central and Kronos Connect - Memphis |  | Retired | Time and Attendance System Changed DEL MGR from Steve to Richard Stinson Per Steve's approval - 22-sep-16 MCA | Group Functions | Philip Sedgwick | Paul Davison | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | paul.davison@smith-nephew.com
LANSA |  | Retired | Loanset and consignment monitoring -Product Vendor support - unsupported -Delivery Manager CERT: 9-JUN-17 | Commercial | Firas Almahamid | Mark Elliott | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Mark.Elliott@smith-nephew.com
LAWTRAC |  | Retired | Web app for scheduling and tracking legal matters. Attachments are stored on app server, tracked in DB server. Uses ColdFusion, SQL Server 2005. Confirmation that legal extracted all data to TyMetrix. Access was removed to Lawtrac as of Dec 1, 2015. Shared servers (web and SQL) so servers cannot be decommissioned. | ASD (Advanced Surgical Devices) | Tjebbes Feenstra | Paul Davison | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | paul.davison@smith-nephew.com
LOT-Verfolgung |  | Retired | Tracking batches shipped (S&N Germany before SAP golive) | ASD (Advanced Surgical Devices) | Firas Almahamid | Gernot Moeller | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Gernot.Moeller@smith-nephew.com
MAC/MEK Server |  | Retired | SAP - Movex Interface license server global Setting to retired: this is a component within MOVEX per Amit S. & Antoine D'O | Manufacturing, Operations and Supply Cha | Imtiaz Iqbal | Amit Shokeen | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Amit.Shokeen@smith-nephew.com
Mathcad |  | Retired | Cad software | Both ASD and AWM | Firas Almahamid | Massimo Trambaioli | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Massimo.Trambaioli@smith-nephew.com
Mitutoyo Cosmos |  | Retired | Production/Quality measurement | ASD (Advanced Surgical Devices) | Imtiaz Iqbal | Ramesh Balabhadruni | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Ramesh.Balabhadruni@smith-nephew.com
MS System Center Ops Manager |  | Retired | BizTalk Application/Server monitoring | Both ASD and AWM | Firas Almahamid | Massimo Trambaioli | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Massimo.Trambaioli@smith-nephew.com
My trust marketing |  | Retired | May be externally administered. 03/22/16 - Update from Al Whitney, this is a SaaS service, not sure if it is still used. | Commercial | Imtiaz Iqbal | Amit Shokeen | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Amit.Shokeen@smith-nephew.com
Object Studio |  | Retired | PLM Printer Software | R&D | Imtiaz Iqbal | Ian Bennett | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | ian.bennett@smith-nephew.com
Objet Printer |  | Retired | PLM Printer Software | R&D | Imtiaz Iqbal | Ian Bennett | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | ian.bennett@smith-nephew.com
Okino Computer Graphics |  | Retired | Cad software | R&D | Ian Bennett | Matthew Stephens | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Matthew.Stephens@smith-nephew.com
OLX Client |  | Retired | automated email signature based on information from AD and templates | IT | Dave Cranny | Sebastian Pasch | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Sebastian.Pasch@smith-nephew.com
PCM (Complaint Management) |  | Retired | Web interface to capture Customer Compaints - Compliant Mgmt software. 1/11/16 - Neither Firas nor Chris are familiar with this. Linda does not support. Removing owner and manager for now. This is Germany AWM Complaint Management. Chris Cook as ITLT, Gernot Moeller as Delivery Manager | RAQA | Firas Almahamid | Andres Bernard | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Andres.Bernard@smith-nephew.com
Print on Demand |  | Retired | Literature orders for field. Historic data will be supported by Vanick group until May 2013 Setting to retired per Amit S. 30JAN18 | Both ASD and AWM | Chris Cook | Amit Shokeen | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Amit.Shokeen@smith-nephew.com
Print Remote |  | Retired | Printing cost control Ramesh B. and Hugo V. confirmed this app has been retired. | ASD (Advanced Surgical Devices) | Firas Almahamid | Gernot Moeller | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Gernot.Moeller@smith-nephew.com
Proscript |  | Retired | PLM softtware | R&D | Derek Spillane | Ian Bennett | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | ian.bennett@smith-nephew.com
Rheometer STARe software |  | Retired | Thermal analysis software (desktop software only, uses server for file storage). | Manufacturing | Imtiaz Iqbal | Amit Shokeen | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Amit.Shokeen@smith-nephew.com
RS Bizware (RSView, RSLinx, RSLogix) |  | Retired | Plant management tool. 03/22/16 - Per Al Whitney, PC based tools. He inherited from Paul Wilson. | Manufacturing | Imtiaz Iqbal | Amit Shokeen | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Amit.Shokeen@smith-nephew.com
Sharepoint |  | Retired | sharepoint portal in Germany | AWM (Advanced Wounded M...) | Firas Almahamid | Gernot Moeller | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Gernot.Moeller@smith-nephew.com
SN Template/Fonts |  | Retired | Local user support with application issues | IT | Imtiaz Iqbal | Paul Davison | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | paul.davison@smith-nephew.com
SPACEWARE SOFTWARE |  | Retired | Unigraphics - Spaceball Software | R&D | Ian Bennett | Matthew Stephens | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Matthew.Stephens@smith-nephew.com
Sunet |  | Retired | SUVA healthcare application - Swiss accident insurer | Both ASD and AWM | Firas Almahamid | Massimo Trambaioli | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Massimo.Trambaioli@smith-nephew.com
Tandberg Video conferencing system |  | Retired | Tandberg video conferencing Retired Per Paul Davison 30 OCT 17 | ASD (Advanced Surgical Devices) | Firas Almahamid | Gernot Moeller | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Gernot.Moeller@smith-nephew.com
TB-DECO |  | Retired | Software to program Tornos Machines | Manufacturing | Imtiaz Iqbal | Ian Bennett | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | ian.bennett@smith-nephew.com
Unique |  | Retired | Payroll. 07/27/16 - Email from Firas stating this is no longer in use. CMDB team confirming. | Group Functions | Firas Almahamid | Mark Elliott | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Mark.Elliott@smith-nephew.com
Unlimited Data Manager |  | Retired | Data Connection with the Laptop over UMTS | ASD (Advanced Surgical Devices) | Firas Almahamid | Gernot Moeller | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Gernot.Moeller@smith-nephew.com
Varicent |  | Retired | Sales Incentive Compensation Management | Commercial | Imtiaz Iqbal | Andres Bernard | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Andres.Bernard@smith-nephew.com
Worksite |  | Retired | UK Legal document and email management application (Legal may reactivate software and start new vendor support agreement) Dana confirmed application no longer used. | ASD (Advanced Surgical Devices) | Tjebbes Feenstra | Paul Davison | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | paul.davison@smith-nephew.com
WSUS |  | Retired | MS Patch updates for servers and workstations | Global | Alison Conlon | Hugo Vizella | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Hugo.Vizella@smith-nephew.com
East5 |  | Retired | Clinical Trial Planning application | Product/Clinical | Sri Tupil | Matthew Stephens | [7 empty] | Full | [5 empty] | No | 38352.375 | Tolerate |  | Matthew.Stephens@smith-nephew.com
Create Print, Email, Fax (Forms for BPCS printing) in AWMANZ |  | Retired | BPCS Form printing | ERP | Jerry Li | Jerry Li | EOL | EOL | EOL | EOL | EOL | EOL | EOL | Full |  |  |  | No IIs | SNI dev'ed | Yes | 38352.375 | Eliminate |  | Jerry.Li@smith-nephew.com
BPCS - AWM (ANZ) |  | Archive | ERP System. 07/01/16 - Update from Dave Metcalfe: "Checked with Paul Haylett – this is historical only now after ANZPO so not critical" |  | Firas Almahamid | Marianne Morton | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Marianne.Morton@smith-nephew.com | Firas Almahamid
EDIWIN 4 |  | Active | Edicom Contract- Applicattion was hosted outsite S&N Edicom Online. SaaS application. SLA contract for DR situation in place. ITLT Cert: 26-MAY-17 Product Vendor Support: Supported Delivery Manager Certified: 7-JUN-17 | RAQA | Jacek Karas | Ian Bennett | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | ian.bennett@smith-nephew.com | Sri Tupil
Reflections (AS400 emulator for AWMANZ BPCS) |  | Active | BPCS/AS400 Emulator | IT | Jerry Li | Jerry Li | EOL | EOL | EOL | EOL | EOL | EOL | EOL | Full |  |  |  | No IIs | SNI dev'ed | Yes | 38352.375 | Eliminate |  | Jerry.Li@smith-nephew.com | Firas Almahamid
TotalHR |  | Archive | Legacy HR & Payroll Application. 1/12/16 - Per Paul Davison, this application is used in archive mode only. Once new application disposition is added to track these ("Historic Only"), this will be updated. | ASD (Advanced Surgical Devices) | Tjebbes Feenstra | Steve Horgan | [7 empty] | Limited | [5 empty] | Unknown | 38352.375 | Unassigned |  | Stephen.Horgan@smith-nephew.com | Firas Almahamid
Business Objects (IRAMEA) |  | Active | Sales Figures | Data & Analytics | Stuart Robinson | Mark Elliott | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2012 | SQL 2012 | No IIs | SNI dev'ed | No | 38352.375 | Tolerate |  | Mark.Elliott@smith-nephew.com | Stuart Robinson
Cisco System Unity VM and unified messaging |  | Active | Phone software | IT | Roman Wojtasik | Roman Wojtasik | EOL | EOL | Not EOL | Not EOL | Not EOL | EOL | Not EOL | Full | Not EOL | Non windows | No DB | No IIs | COTS | Yes | 38352.375 | Unassigned |  | Roman.Wojtasik@smith-nephew.com | Anna Falbogowska
COGNOS Powerplay |  | Active | Sales Figures Data Classification set to Company Private per email to CMDB from Luke Oldfield | Data & Analytics | Stuart Robinson | Sathiamurthy Samidurai | EOL | EOL | EOL | EOL | EOL | EOL | EOL |  |  | Unknown | Unknown | No IIs | SNI dev'ed | Yes | 38352.375 | Migrate |  | Sathiamurthy.Samidurai@smith-nephew.com | Stuart Robinson
E-Adept |  | Active | CRM interfaces Tenders, repairs, prices used by Spain only. Supported by: Albert Jiménez. Adept System Management - Telf. 934808682 // 639304095 www.adept.es // ajimenez@adept.es e-Adept is the tool used for tracking and Service & Repair in Spain for Sports Medicine products only. It tracks the returns of medical devices to Tuttlingen (Germany) for service or repair. It holds critical data such as batch numbers for traceability of medical devices. E-Adept is responsible for generating all the documentation required for the repair centre, customer and warehouse. There is no complaint data held in the tool. It does NOT interface with any other Application, it is completely stand-alone. It works well and there are no requirements for system changes at present. Any plan to remove e-Adept would require a full archive of the data to retain the batch history data. There is currently no active migration plan for this solution. | Commercial | Firas Almahamid | Andres Bernard | EOL | EOL | EOL | EOL | EOL | EOL | EOL | Limited | EOL | Windows 2008 | SQL 2008 | No IIs | SNI dev'ed | Yes | 38352.375 | Tolerate |  | Andres.Bernard@smith-nephew.com | Firas Almahamid
END NOTE (ANZ) |  | Active | Commercial reference management software for managing bibliographies and references | R&D | Jerry Li | Jerry Li | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL |  | None | EOL | Non windows | No DB | No IIs | COTS | No | 38352.375 | Eliminate |  | Jerry.Li@smith-nephew.com | Firas Almahamid
Epats |  | Active | NPWT - monitor & manage patients requirement | Data & Analytics | Stuart Robinson | Mark Elliott | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2012 | Other DB | No IIs | SNI dev'ed | No | 38352.375 | Tolerate |  | Mark.Elliott@smith-nephew.com | Stuart Robinson
HR Notification |  | Active | Web based application that notifies key departments of a new hire via e-mail. In House Application. URL: http://orthonet.smith-nephew.com/NonEmpNotification/default.aspx | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial | Not EOL | Windows 2012 | SQL 2012 | 8.0 (2012) | SNI dev'ed | No | 38352.375 | Tolerate |  | paul.davison@smith-nephew.com | Chris Cook
InfinityQS ProFicient (SPC software) |  | Active | InfinityQS Proficient is an SPC Software that is used for Statistical Process Control. Its current functionalities are: - Data collection & integration - Real-time monitoring & analysis - Workflow management - Reporting | RAQA | Sri Tupil | Aileen Diola | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2016 | SQL 2016 |  | COTS | Unknown | 38352.375 | Tolerate |  | Aileen.Diola@smith-nephew.com | Sri Tupil
iScala (Hong Kong) |  | Active | ERP Product Vendor Support= UNSUPPORTED Delivery Manager Cert:22JUN17 | ERP | Massimo Trambaioli | Magnus Chen | EOL | EOL |  |  |  | EOL | EOL | Limited | EOL | Windows 2003 | No DB | 6.0 (2003) | Vendor Developed | Unknown | 38352.375 | Unassigned |  | Magnus.Chen@smith-nephew.com | Massimo Trambaioli
Jobrouter |  | Active | Workflow tool for document management system - deals with approvals etc | ERP | Dave Cranny | Sebastian Pasch | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2008R2 | SQL 2008R2 | No IIs | COTS | No | 38352.375 | Unassigned |  | Sebastian.Pasch@smith-nephew.com
Microsoft Dynamics CRM 2016 (ANZ) |  | Active | CRM System for ANZ Copied from Microsoft Dynamics CRM 2011 (ANZ) per Troy 30-JAN-17. Dec. 2020 "We do not connect to other apps for now . CRM manual shared has reports details . " | Commercial | Rohit Gupta | Rohit Gupta | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2016 | SQL 2016 | Unknown | COTS | No | 38352.375 | Unassigned |  | Rohit.Gupta@smith-nephew.com | Firas Almahamid
TIAMO |  | Active | control and database software for titrators, dosing devices and sample changers that allows complete laboratory automation | RAQA | Sri Tupil | Aileen Diola | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Limited | Not EOL | Windows 2012 | Windows 2012 | 8.0 (2012) | COTS | No | 38352.375 | Tolerate |  | Aileen.Diola@smith-nephew.com | Sri Tupil
TotalChrom |  | Active | A COTS application that is use for chromatography data handling by the quality business unit. | RAQA | Sri Tupil | Aileen Diola | EOL | EOL | EOL | EOL | EOL | EOL | EOL | Limited | EOL | Windows 2003 | No DB | Unknown | COTS | Yes | 38352.375 | Eliminate |  | Aileen.Diola@smith-nephew.com | Sri Tupil
Adams |  | Active | Ortho Research and Product Development. 12/3/13 - Updated name from "LifeMod and Adams" to "Adams" per Randall Reavis. | R&D | Ian Bennett | Matthew Stephens | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2012 | No DB | No IIs | COTS | No | 38352.375 | Tolerate | Cannot go cloud | Matthew.Stephens@smith-nephew.com | Sri Tupil
Alphacam 2010 |  | Active | CAM server is only a license server Potential instructions for license.. being checked.. https://www.alphacam.com/faqs/?accordionsectionid=B0B1F888_A43A_D8A2_FC912CA24BB48E67 | Manufacturing | Derek Spillane | Carla Morris | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | EOL | Not EOL | Full |  | Windows 2012 | No DB | No IIs | COTS | Yes | 38352.375 | Tolerate | Replatform | Carla.Morris@smith-nephew.com | Derek Spillane
Auftragsverwaltung (Loaner Pool) |  | Active | Loaner application | Supply Chain | Manas Singha | Amit Shokeen | EOL | EOL | EOL | EOL | Unknown | Not EOL | Not EOL | Partial |  | Windows 2003 | SQL 2008 | 6.0 (2003) | SNI dev'ed | No | 38352.375 | Tolerate | Cannot go cloud | Amit.Shokeen@smith-nephew.com | Massimo Trambaioli
AutoVue |  | Active | Enables Collaboration of 2D and 3D file formats from all major applications. Converts Documents to Viewable Images Preouction Print Process View Document Images (Drawings, Specifications, Procedures) Used for Matrix One compatability / process. Must replace with the next PLM set of tools and capabilities. | R&D | Ian Bennett | Matthew Stephens | Not EOL | Not EOL | EOL | EOL | Not EOL | EOL | Not EOL | Full |  | Windows 2012 | Other DB | No IIs | COTS | Yes | 38352.375 | Migrate | Cannot go cloud | Matthew.Stephens@smith-nephew.com | Sri Tupil
Axapta 2009 (China) |  | Active | China, Malaysia, Thailand, Singapore. Finance / SCM; 06/24/2014 - Update from Shaban - iScala (Malaysia) and iScala (Thailand) retired, functionality moved to this application. Product Vendor Support=Supported Delivery Manager Cert=22JUN17 | ERP | Massimo Trambaioli | Emily Yu | EOL | EOL | EOL | Not EOL | EOL | Not EOL | Not EOL | Full |  | Windows 2008R2 | SQL 2008R2 | 7.5 (2008R2) | SNI dev'ed | No | 38352.375 | Migrate | Unknown | Emily.Yu@smith-nephew.com | Massimo Trambaioli
Axway |  | Active | GHX EDI Sales Orders | ERP | Jacek Karas | Pawel Pietrzyk |  | Not EOL |  |  | Unknown |  |  | Full |  | Windows 2012 | No DB | 8.0 (2012) |  | Unknown | 38352.375 | Tolerate | Unknown | Pawel.Pietrzyk@smith-nephew.com | Massimo Trambaioli
CAPA Content Server |  | Active | Corrective and Preventive action document managegment system that is integrated to SAP system | RAQA | Sri Tupil | Aileen Diola | EOL | Not EOL | EOL | EOL | EOL | Not EOL | EOL | Full |  | Windows 2008 | SQL 2008 | 7.0 (2008) | Vendor Dev'ed | Yes | 38352.375 | Migrate | To SaaS | Aileen.Diola@smith-nephew.com | Sri Tupil
CorpTax |  | Active | Corporate Domestic tax returns compliance application. Since 2007, Corptax is hosted externally, on the Corptax website. See attached. Each year has its own websiite. Data and application is not on our servers anymore. | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Non windows | Other DB | No IIs | SaaS | No | 38352.375 | Tolerate | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
DKS (Germany) |  | Active | Finance Debit, Credit, General Ledger. 01/20/16 - RTO - Updated from email request from Yvonne. | Group Functions | Philip Sedgwick | Paul Davison | EOL | EOL | Not EOL | Not EOL | EOL | EOL | EOL | Partial | Not EOL | Non windows | Other DB | No IIs | COTS | Yes | 38352.375 | Tolerate | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
DNC5000 |  | Active | Procution CNC sofware | Manufacturing | Derek Spillane | Antoine d'Overschie | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2012 | SQL 2012 | No IIs | Vendor Dev'ed | Unknown | 38352.375 | Tolerate | Unknown | Antoine.doverschie@smith-nephew.com | Massimo Trambaioli
Docuware |  | Active | Document Management. | RAQA | Sri Tupil | Aileen Diola | EOL | EOL | EOL | EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2008R2 |  | 7.5 (2008R2) | COTS | Yes | 38352.375 | Migrate | To SaaS | Aileen.Diola@smith-nephew.com | Sri Tupil
eDiscovery |  | Active | Provide capability to perfrom more efficient eDiscovery - forensic technology software | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2012 | SQL 2005 | No IIs | COTS | Yes | 38352.375 | Migrate | Rehost (L&S) | paul.davison@smith-nephew.com | Chris Cook
END NOTE |  | Active | Commercial reference management software for managing bibliographies and references | R&D | Ian Bennett | Matthew Stephens | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2016 | No DB | No IIs | COTS | No | 38352.375 | Tolerate | Repurchase | Matthew.Stephens@smith-nephew.com | Sri Tupil
EOS RP Tools |  | Active | Application to post process for the plastic and metal sintering machines - Required for 3D printing of products such as Visionaire on EOS 3D printers | Manufacturing | Derek Spillane | Carla Morris | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Unknown | Partial |  | Windows 2012 | No DB | No IIs | COTS | Unknown | 38352.375 | Tolerate | Cannot go cloud | Carla.Morris@smith-nephew.com | Derek Spillane
EOSINT M2x0 PSW3.5 |  | Active | Application to post process for the plastic and metal sintering machines - Required for 3D printing of products such as Visionaire on EOS 3D printers | Manufacturing | Derek Spillane | Carla Morris | EOL | EOL | Not EOL | Not EOL | Not EOL | Not EOL | Unknown | Full |  | Pre Windows 2003 | No DB | No IIs | COTS | Unknown | 38352.375 | Tolerate | Cannot go cloud | Carla.Morris@smith-nephew.com | Derek Spillane
EOSINT M3xx PSW3.3 |  | Active | Application to post process for the plastic and metal sintering machines - Required for 3D printing of products such as Visionaire on EOS 3D printers | Manufacturing | Derek Spillane | Carla Morris | EOL | EOL | Not EOL | Not EOL | Not EOL | Not EOL | Unknown | Full |  | Pre Windows 2003 | No DB | No IIs | COTS | Unknown | 38352.375 | Tolerate | Cannot go cloud | Carla.Morris@smith-nephew.com | Derek Spillane
EpiSys (Hull) |  | Active | Product and Pallet Shipper Labels for outbound shipping to customers and/or sterilization.. File Share for Shuzhu It appears that they are still using \\suzs04\dept\hu_label for Hull it is \\ukhulsmfspw01\dept\hu_label Per Yvonne Braun Feb 25,2020 - Episys: ongoing project, test PC is installed, currently stuck as the business needs to define resources to check all label designs in Hull and Suzhou. | Manufacturing | Derek Spillane | Carla Morris | Unknown | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Unknown | Partial |  |  |  |  | COTS | Unknown | 38352.375 | Migrate | Cannot go cloud | Carla.Morris@smith-nephew.com | Derek Spillane
Eurydice |  | Active | Customer Tenders and Pricing. Business Owner is Jeremy Hurand. Now hosted with Eurydice: https://eurydiceweb.fr/EUW. Jeremy stated data on the old server (LMSVM04) is required until end of 2021. | Commercial | Manish Sahay | Andres Bernard | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None |  | Non windows | No DB | No IIs | SaaS | No | 38352.375 | Tolerate | Cannot go cloud | Andres.Bernard@smith-nephew.com | Firas Almahamid
Geomagic |  | Active | 3-D design and engineering technology that streamlines a wide range of inspection and manufacturing processes | R&D | Ian Bennett | Matthew Stephens | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | EOL | Not EOL | Full |  | Windows 2008R2 | No DB | No IIs | COTS | Yes | 38352.375 | Tolerate | Replatform | Matthew.Stephens@smith-nephew.com | Sri Tupil
GMB (Cost and Fixed assets) |  | Active | Cost Accounting, Fixed Assets used in Tuttlingen. 01/20/16 - RTO, DR Plan - Updated from email request from Yvonne. Replaced in Jan 2018 by Schilling cost accounting and fixed assets. Still used for information retirieval purposes until fiscal year end (2019). | Group Functions | Philip Sedgwick | Paul Davison | EOL | Not EOL | Not EOL | EOL | EOL | EOL | Not EOL | Partial | Not EOL | Non windows | Other DB | No IIs | Vendor Dev'ed | Yes | 38352.375 | Eliminate | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
HAAS Multigrind |  | Active | Application for broach machine and Knee femoral machine Per Lynn Phillips - - Sortware sits on a specific machine to controll machines, alos copy of software on laptop to allow for running simulations. -As of 07/15/2020 the hardware and software has been sold and software will no longer be used/needed. - only hanging on to the software on the laptop until the buyer gets the machine up and running to help with any questions. - No need for any archiving/support | Manufacturing | Derek Spillane | Carla Morris | EOL | Not EOL | Not EOL | Not EOL | Not EOL | EOL | Not EOL | Full | Not EOL |  |  |  | COTS | Yes | 38352.375 | Tolerate | Cannot go cloud | Carla.Morris@smith-nephew.com | Derek Spillane
HAAS SW |  | Active | Application for broach machine and Knee femoral machine Per Lynn Phillips - - Sortware sits on a specific machine to controll machines, alos copy of software on laptop to allow for running simulations. -As of 07/15/2020 the hardware and software has been sold and software will no longer be used/needed. - only hanging on to the software on the laptop until the buyer gets the machine up and running to help with any questions. - No need for any archiving/support | Manufacturing | Derek Spillane | Carla Morris | EOL | EOL | Not EOL | Not EOL | Not EOL | EOL | Not EOL | Full | EOL |  |  |  | COTS | Yes | 38352.375 | Tolerate | Cannot go cloud | Carla.Morris@smith-nephew.com | Derek Spillane
ID Prove |  | Active | Sanctions list checking softawre. 01/20/16 - RTO, DR Plan - Updated from email request from Yvonne. | Supply Chain | Manas Singha | Yvonne Braun | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2012 | SQL 2012 | 8.0 (2012) | COTS | No | 38352.375 | Unassigned | Unknown | Yvonne.Braun@smith-nephew.com | Massimo Trambaioli
Image Access |  | Retired | document archiving | RAQA | Ian Bennett | Matthew Stephens | Unknown | Not EOL | Not EOL | Not EOL | Not EOL | EOL | Unknown | None |  | Non windows | No DB | No IIs | COTS | No | 38352.375 | Tolerate | Cannot go cloud | Matthew.Stephens@smith-nephew.com
Image Pro Plus |  | Retired | Powerful 2D and 3D image processing, enhancement, and analysis software with extensive measurement and customization features | R&D | Ian Bennett | Matthew Stephens | Unknown | Not EOL | Not EOL | Not EOL | Not EOL | EOL | Unknown | Full | [5 empty] | Yes | 38352.375 | Tolerate | Cannot go cloud | Matthew.Stephens@smith-nephew.com
IQ-Soft (Aarau) |  | Active | This is a COTS application utilized by Aarau site. This software have two modules; 1. Calibration Management used by Quality Management 2. Operating Equipment Management used by Downstream Engineering | RAQA | Sri Tupil | Aileen Diola | EOL | EOL | EOL | EOL | EOL | EOL | EOL | Full |  | Windows 2008R2 |  | 7.5 (2008R2) | COTS | Yes | 38352.375 | Migrate | To SaaS | Aileen.Diola@smith-nephew.com | Sri Tupil
Kaba Elostar |  | Active | Software that manages key entry. Used at Aarau. | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Windows 2012 | SQL 2012 | No IIs | Vendor Dev'ed | No | 38352.375 | Tolerate | Unknown | paul.davison@smith-nephew.com | Chris Cook
Kayang Payroll |  | Active | China Payroll Product Vendor Support=Supported Delivery Manager Cert: 22JUN17 | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | EOL | Not EOL | Partial | Not EOL | Windows 2012 | SQL 2012 | 8.0 (2012) | Vendor Dev'ed | Yes | 38352.375 | Eliminate | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
KBM |  | Active | ERP Financials/Sales/Logistics -Mark Elliott is Primary Support unable to update -Product Vendor Support level-Unsopported Delivery Manager Cert: 9-JUN-17 | ERP | Massimo Trambaioli | Amit Shokeen | EOL | EOL | EOL | EOL | EOL | EOL | EOL | Full |  | Windows 2008R2 | Other DB | 7.5 (2008R2) | COTS | Unknown | 38352.375 | Eliminate | Unknown | Amit.Shokeen@smith-nephew.com | Massimo Trambaioli
LIFEMOD BIOMECHANICS SYS |  | Active | Engineering software for biomechanics which quickly creates accurate, dynamic human models which can be analyzed for contacts, displacements, velocity, acceleration, muscle and joint forces, muscle timings, control functions and energetics. | R&D | Ian Bennett | Matthew Stephens | Unknown | Unknown | Not EOL | Not EOL | Not EOL | EOL | Unknown | Full |  | Non windows | No DB | No IIs | COTS | Yes | 38352.375 | Tolerate | Cannot go cloud | Matthew.Stephens@smith-nephew.com | Sri Tupil
M-Plot |  | Retired | Printing and converting application used with Unigraphics | R&D | Ian Bennett | Matthew Stephens | Unknown | Not EOL | Not EOL | Not EOL | Not EOL | EOL | Unknown | Full | [5 empty] | Yes | 38352.375 | Tolerate | Cannot go cloud | Matthew.Stephens@smith-nephew.com
Magic X |  | Active | Real time design rule checking software. Application for the plastic and metal sintering machines | R&D | Ian Bennett | Matthew Stephens | Unknown | Not EOL | Not EOL | Not EOL | Not EOL | EOL | Unknown | Full |  | Non windows | No DB | No IIs | COTS | Yes | 38352.375 | Tolerate | Replatform | Matthew.Stephens@smith-nephew.com | Sri Tupil
Mainsaver (US) |  | Active | Manufacturing Maintenance and Repair management software | Manufacturing | Derek Spillane | Carla Morris | Not EOL | EOL | Not EOL | Not EOL | EOL | EOL | Not EOL | Full |  | Windows 2008R2 |  |  | SaaS | Unknown | 38352.375 | Tolerate | To SaaS | Carla.Morris@smith-nephew.com | Derek Spillane
MASK |  | Active | Used by engineers to measure patient x rays and compare to patients MRI's. Used by Visionaire designers to manipulate MRI's. Creates 3d pictures of paitents bones | R&D | Ian Bennett | Matthew Stephens | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial |  | Non windows | No DB | No IIs | SNI dev'ed | No | 38352.375 | Migrate | Cannot go cloud | Matthew.Stephens@smith-nephew.com | Sri Tupil
MATLAB |  | Active | Serves as the foundation for all MathWorksª products. It includes a programming language and tools for algorithm development, data analysis, data visualization, and numeric computation. Local install only | R&D | Ian Bennett | Matthew Stephens | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2012 | Other DB | No IIs | COTS | No | 38352.375 | Tolerate | Replatform | Matthew.Stephens@smith-nephew.com | Sri Tupil
Memotech |  | Active | Application for storing and tracking legal docs such as patents and litigation. Memotech was moved to SaaS solution with CPA Global (Amazon AWS) on June 19, 2018. Link is: https://us.memotech.cpaglobal.com/sm17hn/#/dashboard | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Non windows | Other DB | No IIs | SaaS | No | 38352.375 | Invest | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
Microsoft CRM |  | Retired | CRM software Entire Organization / Sales /Cust Serv | Commercial | Santhosh Nair | Andres Bernard | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2016 | SQL 2016 |  | COTS | No | 38352.375 | Migrate | To SaaS | Andres.Bernard@smith-nephew.com
MIMICS |  | Active | Segmentation tools to convert your scanner data to a range of output formats, or perform a variety of design and engineering operations directly on your 3D model | R&D | Ian Bennett | Matthew Stephens | Unknown | EOL | Not EOL | Not EOL | Not EOL | EOL | Unknown | Full |  | Windows 2008 | No DB | No IIs | COTS | Yes | 38352.375 | Tolerate | Replatform | Matthew.Stephens@smith-nephew.com | Sri Tupil
Myriad |  | Active | Viewing software used for AutoCAD drawings | R&D | Ian Bennett | Matthew Stephens | Unknown | EOL | Not EOL | Not EOL | Not EOL | EOL | Unknown | Full |  | Windows 2008 | No DB | No IIs | COTS | Yes | 38352.375 | Migrate | Cannot go cloud | Matthew.Stephens@smith-nephew.com | Sri Tupil
Normenviewer |  | Retired | Document viewer app that works with multple file types provides information on Standards like ISO | R&D | Ian Bennett | Matthew Stephens | Unknown | Unknown | Not EOL | Not EOL | Not EOL | Unknown | Unknown | Full | [5 empty] | Unknown | 38352.375 | Tolerate | Cannot go cloud | Matthew.Stephens@smith-nephew.com
P+I, LOGA/400 - Germany (Tuttlingen) Ortho |  | Active | Personnel Management Software | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | EOL | EOL | EOL | EOL | EOL | EOL | Full | Not EOL | Non windows | Other DB | No IIs | COTS | Yes | 38352.375 | Eliminate | Go to DataCenter as a Service | paul.davison@smith-nephew.com | Chris Cook
P11D Organiser |  | Active | Application used in Hull to manage some tax reporting for employees. Creates P11D tax statements which are sent out to employees annually. Now a SaaS application. Link: https://www.myp11d.com/P11D Not SSO. | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Non windows | Other DB | No IIs | COTS | No | 38352.375 | Tolerate | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
PanelBuilder |  | Active | Used to develop machine HMI configuration (Hull) | Manufacturing | Derek Spillane | Carla Morris | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Non windows | No DB | No IIs | COTS | Unknown | 38352.375 | Tolerate | Cannot go cloud | Carla.Morris@smith-nephew.com | Derek Spillane
PCM (procurement) |  | Active | Procurement software | Procurement | Manas Singha | Antoine d'Overschie | EOL | EOL | EOL | Not EOL | EOL | EOL | EOL | Partial |  | Windows 2003 | SQL 2000 | No IIs | Vendor Dev'ed | Unknown | 38352.375 | Migrate | Unknown | Antoine.doverschie@smith-nephew.com | Massimo Trambaioli
Popsy |  | Active | Accounting Software - Luxemburg & Dutch holding co & Dutch wound mgmt business. Now hosted on cloud - https://connect.cloudbizz.com/vpn/index.html. Popsy was on BENTFS3. | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Non windows | Other DB | No IIs | SaaS | No | 38352.375 | Tolerate | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
Proquis Software |  | Active | Quality Management systems in Warwick that is use for Non Conformance, CAPA Management, Audit Management, Records and Doc Management, Supplier Quality Management, Batch Record Management, Calibration Management | RAQA | Sri Tupil | Aileen Diola | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2012 | SQL 2012 | 8.0 (2012) | Vendor Dev'ed | No | 38352.375 | Tolerate | To SaaS | Aileen.Diola@smith-nephew.com | Sri Tupil
Pure |  | Retired | Used for service request workflow for expense and travel; Purchase Orders. 1/11/16 - Per Chris Cook, this should be TJ or Chris Rowley. | Group Functions | Philip Sedgwick | Paul Davison | EOL | EOL | EOL | EOL | EOL | EOL | EOL | Full | Not EOL | Windows 2003 | SQL 2005 | 6.0 (2003) | COTS | Yes | 38352.375 | Eliminate | Unknown | paul.davison@smith-nephew.com
SAS |  | Active | Statistical analysis of clinical trials. Supports statistical analysis of clinical trial results for product developments Components and # licenses are: Base SAS x9 SAS/ACCESS with ODBC x1 SAS/FSP x4 SAS/GRAPH x5 SAS/IML x1 SAS/QC x1 SAS/STAT x5 | Supply Chain | Manas Singha | Amit Shokeen | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2016 | No DB | No IIs | SaaS | No | 38352.375 | Invest | Cannot go cloud | Amit.Shokeen@smith-nephew.com | Massimo Trambaioli
Set Eval |  | Active | Trauma Eval Service Agreement ITLT Cert: 26-MAY-17 | Supply Chain | Manas Singha | Amit Shokeen | Not EOL | Not EOL | Not EOL | EOL | EOL | EOL | Not EOL | None |  | Windows 2012 | SQL 2008 | 8.0 (2012) | Vendor Dev'ed | No | 38352.375 | Invest | Rehost (L&S) | Amit.Shokeen@smith-nephew.com | Massimo Trambaioli
SNH Performance Knee |  | Retired | Desktop app; user/owner cannot be located: XtraNet Server Sw - SNH Perf Knee w/ColdFusion | Commercial | Santhosh Nair | Andres Bernard | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  |  |  |  | SNI dev'ed | No | 38352.375 | Tolerate | Cannot go cloud | Andres.Bernard@smith-nephew.com
SSO LearnCenter |  | Active | .Net Application used to bypass login screen | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2012 | No DB | 8.0 (2012) | SNI dev'ed | No | 38352.375 | Migrate | Rehost (L&S) | paul.davison@smith-nephew.com | Chris Cook
Streamserve |  | Active | Movex output management | ERP | Manas Singha | Antoine d'Overschie | EOL | EOL | EOL | EOL | Unknown | Unknown | Unknown | Full |  | Windows 2003 | No DB | 6.0 (2003) | Vendor Dev'ed | Unknown | 38352.375 | Tolerate | Cannot go cloud | Antoine.doverschie@smith-nephew.com | Massimo Trambaioli
Tarife |  | Active | Customs Tariff No. Administration | Supply Chain | Manas Singha | Yvonne Braun | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2012 | No DB | 8.0 (2012) | COTS | No | 38352.375 | Unassigned | To SaaS | Yvonne.Braun@smith-nephew.com | Massimo Trambaioli
TECHEDIT- TECHVIEW |  | Retired | Software for edit image files from Matrix. Local Install only | R&D | Ian Bennett | Matthew Stephens | Unknown | Not EOL | Not EOL | Not EOL | Not EOL | Unknown | Unknown | Full | [5 empty] | Yes | 38352.375 | Tolerate | Cannot go cloud | Matthew.Stephens@smith-nephew.com
TEST STAR II |  | Retired | Software to run simulation machines in FEA. Local install only | R&D | Ian Bennett | Matthew Stephens | Unknown | Not EOL | Not EOL | Not EOL | Not EOL | Unknown | Unknown | Full |  | Non windows | No DB | No IIs | COTS | No | 38352.375 | Tolerate | Cannot go cloud | Matthew.Stephens@smith-nephew.com
Tethered Scanners - GDC |  | Active | SR30, SR60, SR61 configurations for GDC | Supply Chain | Manas Singha | Amit Shokeen | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2016 | No DB | No IIs | COTS | No | 38352.375 | Tolerate | Cannot go cloud | Amit.Shokeen@smith-nephew.com | Massimo Trambaioli
WR |  | Active | CNC programming and data transfer to machines. 01/20/16 - Email from Yvonne, this application is GxP. Per Yvonne Braun Feb 25, 2020 (Win7) WR: can be upgraded, ongoing project under the lead of Uwe Schelbert, Manager Production Support. The database will change from MS Access to SQL and the application will be Win10 compatible. One PC is already upgraded. Upgrade needs to be performed by the vendor. | Manufacturing | Derek Spillane | Carla Morris | Not EOL | Not EOL | Not EOL | Not EOL | Unknown | Not EOL | Unknown | Full |  | Windows 2012 | No DB | 8.0 (2012) | COTS | Unknown | 38352.375 | Migrate | Cannot go cloud | Carla.Morris@smith-nephew.com | Derek Spillane
Compleo |  | Retired | Output control application for AS 400 | IT | Massimo Trambaioli | Amit Shokeen | Not EOL | EOL | EOL | EOL | EOL | EOL | EOL | None |  | Windows 2008 | Other DB | 7.0 (2008) | COTS | No | 38351.375 | Eliminate | Unknown | Amit.Shokeen@smith-nephew.com
Euro log |  | Active | Logistics Loaners software | Supply Chain | Manas Singha | Amit Shokeen | Not EOL | Not EOL | EOL | EOL | Unknown | Not EOL | Not EOL | Full |  | Windows 2012 | Other DB | 8.0 (2012) | SNI dev'ed | Unknown | 37621.375 | Tolerate | Rehost (L&S) | Amit.Shokeen@smith-nephew.com | Massimo Trambaioli
Express Implants |  | Active | Used to gather custom implant information and schedule/track custom implant manufacturing for surgeons | R&D | Ian Bennett | Matthew Stephens | EOL | EOL | Not EOL | Unknown | Unknown | Not EOL | Unknown | Partial |  | Windows 2008R2 | SQL 2008 | 7.5 (2008R2) | Vendor Dev'ed |  | 37256.375 | Migrate | Rehost (L&S) | Matthew.Stephens@smith-nephew.com | Sri Tupil
Express Instruments |  | Active | Used to gather custom implant information and schedule/track custom implant manufacturing for surgeons | R&D | Ian Bennett | Matthew Stephens | EOL | EOL | Not EOL | Unknown | EOL | Not EOL | Unknown | Full |  | Windows 2008R2 | SQL 2005 | 7.5 (2008R2) | Vendor Dev'ed | Unknown | 37256.375 | Migrate | Unknown | Matthew.Stephens@smith-nephew.com | Sri Tupil
FedEx Ship Manager (Server) |  | Active | Shipping software - supported by Fedex Two servers for failover are provisioned by FedEx. | Supply Chain | Manas Singha | Amit Shokeen | Not EOL | EOL | EOL | Unknown | Not EOL | EOL | Unknown | Full |  | Windows 2008R2 | Other DB | No IIs | Vendor Dev'ed | Unknown | 32873.375 | Tolerate | Unknown | Amit.Shokeen@smith-nephew.com | Massimo Trambaioli
P2000 Security Management System |  | Active | SN north Amerioca corporate security badging and access control. Replaces the following: Secure Perfect, DSX, Andover Continuum | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | EOL | EOL | EOL | EOL | Not EOL | Not EOL | Partial | Not EOL | Windows 2008R2 | SQL 2008 | 7.5 (2008R2) | COTS | Yes | 41448.375 | Tolerate | Go to DataCenter as a Service | paul.davison@smith-nephew.com | Chris Cook
Payroll - Uno (Colombia) |  | Active | Payroll Calculations, Deductions, Payments. Linux based system. 02/18/16 - ARB Review of a system to replace this called Softland. | Group Functions | Philip Sedgwick | Paul Davison | EOL | EOL | EOL | EOL | EOL | EOL | EOL | None | Not EOL | Non windows | Other DB | No IIs | COTS | Yes | 42418.375 | Migrate | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
SmartSystems |  | Retired | SmartSystems - RF Guns(Opal Intermec CK71) inventory, licensing, remote control Baar | Supply Chain | Manas Singha | Amit Shokeen | Not EOL | EOL | EOL | EOL | EOL | Not EOL | Not EOL | Partial |  | Windows 2008 | SQL 2008R2 | 7.0 (2008) | COTS | Unknown | 42186.375 | Eliminate | Go to DataCenter as a Service | Amit.Shokeen@smith-nephew.com
Allevyn |  | Active | Game targeted at nurses product knowledge. Community nurse lunches have been undertaken for many years by many different companies and have become stagnant and this is a way in which we can reinvigorate these essential lunchtime meetings. The Allevyn iDetail activity is an iPad application which has been designed to give territory managers in field an opportunity to engage with nurses during lunch meetings in a fun way which encourages learning and knowledge around our Allevyn product range. | Commercial | Manish Sahay | Andres Bernard | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None |  | Non windows | Other DB | No IIs | SNI dev'ed | No | 42005.375 | Tolerate | To SaaS | Andres.Bernard@smith-nephew.com | Firas Almahamid
Alteryx |  | Active | Alteryx is a Vendor developed application using Alteryx platform and used at global location by Operations team. The application provides ETL analytics for loading and manipulating data sets without the need for coding and the output of this tool can go to a server, Excel, Power BI, or Tableau. | Data & Analytics | Stuart Robinson | Sathiamurthy Samidurai | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2016 | SQL 2012 | No IIs | Vendor Dev'ed | No | 43482.375 | Tolerate | Rehost (L&S) | Sathiamurthy.Samidurai@smith-nephew.com | Stuart Robinson
Altium Designer |  | Active | Bluebelt An electrical CAD package for electrical design schematics capture and printed circuit boards layout. | R&D | Ian Bennett | Matthew Stephens | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial | Not EOL | Windows 2012 | No DB | No IIs | COTS | No | 41640.375 | Invest | Replatform | Matthew.Stephens@smith-nephew.com | Sri Tupil
Appitude |  | Active | Andres Bernard (IT) Jameschris.stewart - requestor - "There is no software. All we're getting is access to their web portal so we can get visibility to sales that are running through their members (both S&N and competitors). There is no confidential information being shared. This is like a monthly sales report that our internal sales analytics team runs for us except that Aptitude is creating this sales report for their members and allowing us access. " $25K for 21 users. | Commercial | Manish Sahay | Andres Bernard | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None |  | Non windows | Other DB | No IIs | Vendor Dev'ed | No | 42979.375 | Tolerate | To SaaS | Andres.Bernard@smith-nephew.com | Firas Almahamid
ASD Pedidos |  | Retired | Dan Foster - IPad app for loan orders - app had been rolled out in Spain - contains list of configurations and hospitals, insurance companies, and doctor information. IPad mail client is used to send to customer service team to generate an order one of our IT (Mickale Ila) personnel is now the manager of the company (Winfor) - conflict ? IOS app project needs to be formalized - in order to roll this out to other georgraphies IT Support = NONE NAME UPDATED PER INC0377222 | Commercial | Santhosh Nair | Andres Bernard | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None |  | Non windows | Other DB | No IIs | SNI dev'ed | No | 42962.375 | Tolerate | To SaaS | Andres.Bernard@smith-nephew.com
BackupExec(OSIRIS) |  | Active | Windows Backup | IT | Roman Wojtasik | Patryk Bromirski | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2016 | No DB | No IIs | COTS | Unknown | 43466.375 | Migrate | Cannot go cloud | Patryk.Bromirski@smith-nephew.com | Anna Falbogowska
BAS |  | Active | Order management, Sales, MRP. Original Name: "OMS, BAS". Per Yvonne, OMS was the vendor name. However, vendor is no longer in business. 01/20/16 - Yvonne sent email indicating this is GxP. | ERP | Massimo Trambaioli | Yvonne Braun | Not EOL | Not EOL | Unknown | Not EOL | Not EOL | EOL | Not EOL | Full |  | Non windows | Other DB | No IIs | SNI dev'ed | No | 38351.375 | Unassigned | Cannot go cloud | Yvonne.Braun@smith-nephew.com | Massimo Trambaioli
Brightcove |  | Active | SaaS provider of online video services for publishing/distributing corporate video on the web (and mobile devices). ITLT Cert: 26-MAY-17 Product Vendor Support=Supported Delivery Manager Cert= 22JUN17 | Commercial | Manish Sahay | Andres Bernard | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial |  |  |  |  | SaaS | No | 41213.3333 | Tolerate | To SaaS | Andres.Bernard@smith-nephew.com | Firas Almahamid
Bugzilla |  | Active | Bluebelt "Maintains records related to product and design history file investigations and actions on performance issues identified on Robotics products. Used for Navio Product Development" | R&D | Ian Bennett | Matthew Stephens | Not EOL | EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial | Not EOL | Non windows | No DB | No IIs | COTS | No | 41640.375 | Migrate | Rearchitect | Matthew.Stephens@smith-nephew.com | Sri Tupil
CA Clarity |  | Active | Portfolio management tool | Group Functions | Lois Spencer | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Non windows | Other DB | No IIs | SaaS | No | 40124.375 | Tolerate | To SaaS | paul.davison@smith-nephew.com | Chris Cook
CadapultFM |  | Active | Facility Management solution. http://www.cadapultfm.com/ | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Non windows | No DB | No IIs | SaaS | No | 40553.375 | Tolerate | To SaaS | paul.davison@smith-nephew.com | Chris Cook
Castlight |  | Active | Provides cost comparisons based on your chosen health plan. Tool will know your view search history - UHC/Caremark/Dental - NDA for data sharing. Can add single sign on in enrollment window. Goal to provide data to better utilize health plan. UHC - claims data - S&N eligibility file (demographic information) - integrate with WORKDAY feeds go out weekly to vendor from Workday (same as UHC, Fidelity, etc.). Not IT supported. Per Laura Doyle: We are sun setting the Castlight system as of 1/11/2021. | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Non windows | Other DB | No IIs | SaaS | No | 42979.375 | Eliminate | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
cCleaner |  | Active | Monitoring Software for Atracsys - List all softwares available on the SNI computers used by Atracsys | Enterprise Technology | Kevin Ponce | Kevin Ponce | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Unknown | No DB | No IIs | COTS | No | 43914.3333 | Tolerate | Cannot go cloud | Kevin.Ponce@smith-nephew.com
Cimplicity |  | Retired | Monitors, Control and Record Cleanroom, HVAC and Lab equipment. Product Vendor: Applied Control Engineering, Inc.Version: Proficy HMI/SCADA - CIMPLICITY v8.20 Build 20326. SCADA system from GE. Control, monitor & record cleanroom, HVAC and lab equipment temperature, humidity, pressure and other parameters & alarms Tevor La Bast is Primary Support, not able to add | Manufacturing | Derek Spillane | Carla Morris | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Unknown | Full | Not EOL | Windows 2012 | SQL 2017 | 8.0 (2012) | COTS | No | 40378.375 | Tolerate | Cannot go cloud | Carla.Morris@smith-nephew.com | Derek Spillane
Cockpit |  | Active | Bluebelt Web-application that manages product requirement specifications, test plans, risk assessments, summary test reports and requirement-to-test report traces. Used for Navio Product Development to record and maintain design history file documents. | R&D | Ian Bennett | Matthew Stephens | Not EOL | EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial | Not EOL | Windows 2008R2 | Other DB | 8.0 (2012) | COTS | Yes | 41640.375 | Migrate | Replatform | Matthew.Stephens@smith-nephew.com | Sri Tupil
Cognos BI (SoNAR Sales Dashboards & Standard Reporting) |  | Active | Cognos instances for Enterprise Data Warehouse (GBIP) environment. ITLT Cert:26-JUN-17 | Data & Analytics | Stuart Robinson | Sathiamurthy Samidurai | Not EOL | EOL | Not EOL | Not EOL | EOL | Not EOL | Not EOL | Full |  | Windows 2012 | Other DB | No IIs | SNI dev'ed | Yes | 42968.375 | Tolerate | Rehost (L&S) | Sathiamurthy.Samidurai@smith-nephew.com | Stuart Robinson
Cognos Demand Planning |  | Active | Used for demand planning of the former Plus products. Update from Lucie: "Manu produces a plan for the Plus parts that is passed to SAP PRD. Those forecasts are then netted to create the production plan. The result is then passed to Cognos for further forecast intelligence and the final result is passed to Movex." Demand Planning: "All countries use the web interface with Cognos to enter their forecast changes. Always have. These forecasts go directly into the Cognos system the demand planners use in Baar Switzerland. THose forecasts in Cognos pass into Movex - the Aarau manufcturing system. " | Supply Chain | Manas Singha | Antoine d'Overschie | EOL | EOL | EOL | Not EOL | EOL | EOL | EOL | Partial |  | Windows 2003 | SQL 2005 | No IIs | Vendor Dev'ed | Unknown | 40247.375 | Tolerate | Unknown | Antoine.doverschie@smith-nephew.com | Massimo Trambaioli
Concur |  | Active | Travel & Expense | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Non windows | Other DB | No IIs | SaaS | No | 42273.375 | Invest | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
Connect Ship (UPS/DHL) |  | Active | Shipping System for UPS/DHL. 01/21/16 - Update from Al. Non-FedEx Shipping software for XPS Ship in SAP Licensed through Catalyst - Licensed for Connectship and 2 carriers - UPS, DHL. Removing DHL Connect and Progistics to combine into this one entry. | Supply Chain | Manas Singha | Amit Shokeen | Not EOL | Not EOL | Not EOL | Not EOL | EOL | Not EOL | Not EOL | Full |  | Windows 2012 | SQL 2008R2 | 8.0 (2012) | COTS |  | 39691.375 | Tolerate | Rehost (L&S) | Amit.Shokeen@smith-nephew.com | Massimo Trambaioli
Corporate TaxPrep |  | Retired | Canada Income tax returns prepared by GHO US Tax /Memphis | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial |  |  |  |  | COTS | Unknown | 39447.375 | Tolerate | To SaaS | paul.davison@smith-nephew.com
CVENT |  | Active | June 9, 2020 - Strategic Meeting Mgmt platform to support the planning, organisation and conducts of our MedEd courses and commercial events and meetings - The solution to also support aggregate spend reporting and compliance to our meetings management policy. =============================== Event Management Software & Hospitality Solutions; Used to schedule surgeon training events as well as internal/.external and HCP events | Commercial | Firas Almahamid | Andres Bernard | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  |  |  |  | SaaS | No | 40948.375 | Invest | To SaaS | Andres.Bernard@smith-nephew.com | Firas Almahamid
Data Fax |  | Active | Data Fax application is SaaS and Clinical group only has access with a Login. | RAQA | Sri Tupil | Aileen Diola | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2016 | No DB | No IIs | SaaS | No | 40178.375 | Migrate | To SaaS | Aileen.Diola@smith-nephew.com | Sri Tupil
EpiSys (Suzhou) |  | Active | Product and Pallet Shipper Labels for outbound shipping to customers and/or sterilization Per Yvonne Braun Feb 25,2020 - Episys: ongoing project, test PC is installed, currently stuck as the business needs to define resources to check all label designs in Hull and Suzhou. | Manufacturing | Derek Spillane | Carla Morris | Unknown | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Unknown | Partial |  |  |  |  | COTS | Unknown | 42098.375 | Migrate | Cannot go cloud | Carla.Morris@smith-nephew.com | Derek Spillane
eRoom |  | Retired | Retire in Dec. 2020; 1-6-16: Delivery Manager was Steve McNeill. Changed to Robert Jones; being Archived and then retired in Q1 2020 | Commercial | Santhosh Nair | Andres Bernard | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | EOL | Not EOL | Partial |  |  |  |  | COTS | Yes | 40214.375 | Eliminate | Cannot go cloud | Andres.Bernard@smith-nephew.com
Evisense |  | Active | Refrigeration monitoring for lab environments. | R&D | Ian Bennett | Matthew Stephens | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Windows 2012 | No DB | 8.0 (2012) | COTS | No | 41821.375 | Tolerate | Unknown | Matthew.Stephens@smith-nephew.com | Sri Tupil
Exactus Payroll Application (Costa Rica) |  | Active | Payroll Calculations, Deductions, Payments. 01/27/16 - Application registered by Mark Cheney. | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Windows 2016 | SQL 2016 | No IIs | COTS | No | 39814.375 | Migrate | Rehost (L&S) | paul.davison@smith-nephew.com | Chris Cook
Express Visionaire |  | Active | 04/10/14 - Reported as an application missing from EAP by Randall Reavis team during WARP. Visionaire case flow website. | R&D | Ian Bennett | Matthew Stephens | Not EOL | Not EOL | Unknown | Not EOL | EOL | Not EOL | Not EOL | Full |  | Windows 2008R2 | SQL 2005 | 7.5 (2008R2) | Vendor Dev'ed | Yes | 39447.375 | Tolerate | Rehost (L&S) | Matthew.Stephens@smith-nephew.com | Sri Tupil
FAS 500 -Sage |  | Active | Fixed Assets. 6 users in the U.S. (3 Florida; 3 Memphis). This application is accessed via a remote desktop connection and not from the users pc - via RDP server USMAN-SMTSPW01. This has the client Sage software installed. USMAN-SMAPPVW52 is the Windows 2012 server which has the server (and client) Sage software installed and holds the data. | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial | Not EOL | Windows 2012 | No DB | No IIs | COTS | No | 37621.375 | Tolerate | Rehost (L&S) | paul.davison@smith-nephew.com | Chris Cook
Fed X Café System |  | Active | International shipping. Medium volume domestic shipping. Non-order shipping (connectship) - Desktop only | Supply Chain | Manas Singha | Amit Shokeen | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2016 | No DB | No IIs | SaaS | No | 40184.375 | Tolerate | Cannot go cloud | Amit.Shokeen@smith-nephew.com | Massimo Trambaioli
file |  | Active | Calibration Management software used by Quality Management | RAQA | Sri Tupil | Aileen Diola | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2016 | SQL 2016 |  | COTS | No | 40179.375 | Invest | To SaaS | Aileen.Diola@smith-nephew.com | Sri Tupil
FileMaker |  | Active | Software to support Professional Education Training Equipment process and team in EUCAN. | Commercial | Manish Sahay | Andres Bernard | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None |  | Windows 2012 | No DB | No IIs | COTS | No | 42873.375 | Tolerate | Rehost (L&S) | Andres.Bernard@smith-nephew.com | Firas Almahamid
Flex LM |  | Active | FlexLM3 (CPS Data Collector Only) | R&D | Ian Bennett | Matthew Stephens | Not EOL | EOL | Not EOL | Not EOL | Unknown | Not EOL | Unknown | Full |  | Windows 2008 | No DB | No IIs | COTS | Yes | 38717.375 | Tolerate | Replatform | Matthew.Stephens@smith-nephew.com | Sri Tupil
Forte ADS [Automation Director Services] |  | Active | Multi-server system for control of conveyor system at GDC. Hard Servers in Memphis-GDC. Not in AD. Supported by Vendor. Co-op plan (swappable distributed apps) has not been fully implemented. | Supply Chain | Manas Singha | Amit Shokeen | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2012 | SQL 2012 | 8.0 (2012) | COTS |  | 39447.375 | Tolerate | Cannot go cloud | Amit.Shokeen@smith-nephew.com | Massimo Trambaioli
GBIS Data Staging Process |  | Active | Global Business Information System for Sales, Cost, and Inventory. Local Market data consolidation | Data & Analytics | Stuart Robinson | Sathiamurthy Samidurai | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | EOL | Not EOL | Partial |  | Windows 2012 | Other DB | No IIs | SNI dev'ed | Yes | 40178.375 | Eliminate | Cannot go cloud | Sathiamurthy.Samidurai@smith-nephew.com | Stuart Robinson
Global Returns Disposition Tool |  | Active | Approval or rejection of Sports Med and Ortho goods requested for return to the global distribution center. | Commercial | Manish Sahay | Andres Bernard | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2012 | SQL 2012 | 8.0 (2012) | SNI dev'ed | No | 43484.375 | Tolerate | Rehost (L&S) | Andres.Bernard@smith-nephew.com | Firas Almahamid
Informatica (Wound Data Intergration) |  | Active | ETA tool. Mainly used to load data between BPCS, ERP, WMD Data Warehouse and MLE planning system Name Formally Informatica (Hull) Changed per SRR0082319 to reflect current name | Data & Analytics | Stuart Robinson | Sathiamurthy Samidurai | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2012 | Other DB | No IIs | SNI dev'ed | No | 40178.375 | Invest | Rehost (L&S) | Sathiamurthy.Samidurai@smith-nephew.com | Stuart Robinson
Interform/400 |  | Active | Printout Design. 01/20/16 - RTO, DR Plan - Updated from email request from Yvonne. | ERP | Massimo Trambaioli | Yvonne Braun | Not EOL | Not EOL | Unknown | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Non windows | Other DB | No IIs | COTS | No | 38351.375 | Unassigned | Cannot go cloud | Yvonne.Braun@smith-nephew.com | Massimo Trambaioli
ISIS Data Staging Process |  | Active | International Sales Information System - Provides global sales values and volumes bu SKU and period | Data & Analytics | Stuart Robinson | Sathiamurthy Samidurai | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | EOL | Not EOL | Partial |  | Windows 2012 | Other DB | No IIs | SNI dev'ed | Yes | 40178.375 | Eliminate | Unknown | Sathiamurthy.Samidurai@smith-nephew.com | Stuart Robinson
KepServerEx (UK - Hull) |  | Active | KEPServerEX enables users to connect, manage, monitor, and control diverse automation devices and software applications through a single-server interface. ' Used in UK - Hull only. John Hodgson owner.. ***Note - There is another application also referred to as "Kepserver" related to Hermes/Tulip which is already cloud - Dan Meyers SME | Manufacturing | Derek Spillane | Carla Morris | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial |  | Windows 2012 | SQL 2012 | 8.0 (2012) | COTS | No | 40066.375 | Tolerate | Rehost (L&S) | Carla.Morris@smith-nephew.com | Derek Spillane
Labview |  | Active | Graphical programming has revolutionized the development of test, measurement, and control applications. Regardless of experience, engineers and scientists can rapidly and cost-effectively interface with measurement and control hardware, analyze data, sha | R&D | Ian Bennett | Matthew Stephens | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Non windows | No DB | No IIs | COTS | No | 41275.375 | Tolerate | Cannot go cloud | Matthew.Stephens@smith-nephew.com | Sri Tupil
LDAPUpdate |  | Active | .Net Application that runs daily to update the LDAP database on USMAN-SMDBPVW12 | Commercial | Manish Sahay | Andres Bernard | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2012 | SQL 2012 | 8.0 (2012) | SNI dev'ed | No | 38717.375 | Tolerate | Rehost (L&S) | Andres.Bernard@smith-nephew.com | Firas Almahamid
Learn Center |  | Active | Learning Management. SaaS | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Non windows | Other DB | No IIs | SaaS | No | 39082.375 | Migrate | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
Lotus Notes - Hull AWM |  | Active | Workflow Application. Used to record Deviations, Corrective Actions, RA Correspondence etc. | RAQA | Sri Tupil | Aileen Diola | EOL | EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2003 | SQL 2000 | 6.0 (2003) | Vendor Dev'ed | Yes | 36525.375 | Migrate | To SaaS | Aileen.Diola@smith-nephew.com | Sri Tupil
MeConnect |  | Retired | Daniel Foster and Daniella Rustenburg (local administrator Holland) Peter Maarschelk (reports to Alison Conlon) event booking in production for 5 years - supported by desktop IT. Want to use it across Europe regions (Holland) Demo of the solution professional education training - doctor information - pdf of HPC passport uploaded to solution. Just now implement HTTPS encrypted. third party company developed supported by ex-employee (part time). He uses sub-contractors. No contract, no SLA. 50 reps, 10 users and doctors. Hosted on Amazon - uses Russian sub-contractors | Commercial | Santhosh Nair | Andres Bernard | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None |  | Non windows | Other DB | No IIs | SaaS | No | 39655.375 | Migrate | Cannot go cloud | Andres.Bernard@smith-nephew.com
Nomino Security |  | Active | Sets access for legacy Nomino applications (eg. Shipping docs, Encore); | Commercial | Manish Sahay | Andres Bernard | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL |  |  |  |  | No | 37622.375 | Tolerate | Cannot go cloud | Andres.Bernard@smith-nephew.com | Firas Almahamid
OSISoft PI System |  | Active | OSIsoft software is used to capture, process, analyze, and store data. It is used as lab software and is not GxP. | Manufacturing | Ian Bennett | Matthew Stephens | Unknown | Unknown | Not EOL | Not EOL | Not EOL | Unknown | Unknown | Partial |  | Non windows | No DB | No IIs | COTS | Unknown | 43152.375 | Tolerate | Cannot go cloud | Matthew.Stephens@smith-nephew.com | Sri Tupil
Palo Alto DNS Filtering |  | Active | Used to whitelist/blacklist URLs in the Palo Alto DNS filter protection component. | Infosec | Lawrence Zorio | Paul Funk | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Non windows | Other DB | No IIs | COTS | No | 43646.375 | Invest | Unknown | paul.funk@smith-nephew.com | Lawrence Zorio
Power BI (China) |  | Active | Run all relevant PowerBI reports for business department | Data & Analytics | Jerry Li | Jinble Li | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2012 | SQL 2012 | No IIs | SNI dev'ed | No |  | Invest | Rehost (L&S) | Jinble.Li@smith-nephew.com | Firas Almahamid
QA Change Control |  | Active | The QA Change Control system is a web application utilizing a SQL database. The system is a Change Log with the primary purpose to general Change Control numbers against changes made to systems, processes and products at Hull or other S&N sites and 3rd party manufacturers. The database is used to search and retrieve all related changes to particular products and/or equipment. All change control data is printed, approved and stored in paprt folders archived on site. This is a GxP and Validated application. DEV and QA uses SMRTHSQL3 DB cluster (UKRTHSMDBPW05 and UKRTHSMDBPW06). PROD uses SMRTHSQL2 DB cluster (UKRTHSMDBPW05 and UKRTHSMDBPW06) | RAQA | Sri Tupil | Aileen Diola | Not EOL | Not EOL | Not EOL | Not EOL | EOL | Not EOL | Not EOL | Full |  | Windows 2012 | SQL 2008R2 | 8.0 (2012) | Vendor Dev'ed | Yes | 36788.375 | Migrate | To SaaS | Aileen.Diola@smith-nephew.com | Sri Tupil
QRF (Question Resolution Form) |  | Retired | It is designed to manage the communication between the sales force and the Ops team as well as to manage the creation and completion of requests to transfer customer accounts or resolve sales discrepancies within a territory. Read/writes to external systems, complex. | Commercial | Santhosh Nair | Andres Bernard | EOL | EOL | Not EOL | Not EOL | EOL | Not EOL | Not EOL | Full |  | Windows 2008R2 | SQL 2008 | 7.5 (2008R2) | SNI dev'ed | Yes | 41275.375 | Eliminate | To SaaS | Andres.Bernard@smith-nephew.com
Reimbursement |  | Active | Web based application - Informational. Per Doug C, Internet exposed b/c accessed by sales reps AND office admins for doctors that use our products. In production since 2006. "There is an internal web application called ReimbursementAdmin which is on mmpsrv046 and being moved this weekend to USMAN-SMWSPVW12. This application is used by Michelle Lowe to update the Content on the Public Facing web application, Reimbursement, on mmpsrv023." | Commercial | Manish Sahay | Andres Bernard | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2012 | SQL 2012 | 8.0 (2012) | SNI dev'ed | No | 38717.375 | Migrate | To SaaS | Andres.Bernard@smith-nephew.com | Firas Almahamid
Sage Symfonia |  | Active | old Finance system from Poland "Sage Symfonia" – previous to the SAP migration. Business owner: Anna Lach this system is still sporadically used and required for audits | Group Functions | Philip Sedgwick | Paul Davison | EOL | EOL | EOL | Not EOL | EOL | EOL | Not EOL | None | EOL | Non windows | Other DB | No IIs | COTS | Yes | 38718.375 | Eliminate | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
Sales Request Forms |  | Active | Sales Request Forms | Commercial | Manish Sahay | Andres Bernard | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial |  | Windows 2012 | SQL 2012 | 8.0 (2012) | SNI dev'ed | No | 41307.375 | Migrate | To SaaS | Andres.Bernard@smith-nephew.com | Firas Almahamid
Scanfile |  | Retired | Used to scan documents for electronic storgage | Group Functions | Philip Sedgwick | Paul Davison | EOL | EOL | EOL | Not EOL | EOL | EOL | Not EOL | None |  | Non windows | Other DB | No IIs | COTS | Yes | 36525.375 | Eliminate | Cannot go cloud | paul.davison@smith-nephew.com | Sri Tupil
SEN ERP |  | Retired | ERP for Greece. Vendor is Singularlogic S.A. | ERP | Philip Sedgwick | Paul Davison | EOL | EOL | EOL | Not EOL | EOL | EOL | Not EOL | None |  | Non windows | Other DB | No IIs | COTS | Yes | 41330.375 | Eliminate | Cannot go cloud | paul.davison@smith-nephew.com
SmartGit |  | Active | Bluebelt ""SmartGit" is an interface to "Git". SmartGit is an alternative GUI client that is friendlier than the command-line Git client. Used for Navio Product Development " | R&D | Ian Bennett | Matthew Stephens | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial | Not EOL | Non windows | Other DB | No IIs | COTS | No | 40909.375 | Tolerate | Rearchitect | Matthew.Stephens@smith-nephew.com | Sri Tupil
SNID Archived Shipping Documents |  | Active | Repository of archived shipping documententation for orders shipped from the Movianto and UDG 3PLs. Developed internally. | Supply Chain | Manas Singha | Amit Shokeen | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2012 | SQL 2012 | 8.0 (2012) | SNI dev'ed | No | 37987.375 | Tolerate | Rehost (L&S) | Amit.Shokeen@smith-nephew.com | Massimo Trambaioli
Solidworks PDM Professional |  | Active | Product Data Management Software. Secures Solidworks files and metadata. | R&D | Ian Bennett | Matthew Stephens | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2016 | SQL 2016 | No IIs | COTS | No | 42917.375 | Migrate | Cannot go cloud | Matthew.Stephens@smith-nephew.com | Sri Tupil
Solidworks PDM Workgroup |  | Active | Solidworks PDM Workgroup stores CAD models in a secure vault. | R&D | Ian Bennett | Matthew Stephens | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Windows 2012 | Other DB | No IIs | COTS | No | 43099.375 | Migrate | Cannot go cloud | Matthew.Stephens@smith-nephew.com | Sri Tupil
Symon Jumpstart |  | Active | 03/16/16 - According to the directory, Russell Dodd is part of MedEd. Chris C suggested TJ/Sam would be the owners - TJ asked Sam to work with business to identify IT contact. Symon Jumpstart is a utility that scans sub nets for the ip addresses of the SDA's. It is not a critical application and should not interfere with the operation of the digital sign system. Symon as a whole is a digital sign system that controls the content of the LED signs that are used at Smith and Nephew facilities in the Memphis area. Also, Nicolas Bussey (desktop) has RDP access to this system. | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | EOL | Not EOL | Not EOL | EOL | Not EOL | Not EOL | Partial | Not EOL | Windows 2008R2 | SQL 2008 | No IIs | COTS | Yes | 42389.375 | Tolerate | Rehost (L&S) | paul.davison@smith-nephew.com | Chris Cook
Taxback |  | Active | Tracking VAT and Tax obligations fro expenses run through Concur. | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Non windows | Other DB | No IIs | SaaS | No | 42950.375 | Tolerate | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
TM1 Cognos Configuration |  | Active | Cognos EPO Ax aplication retired in 2018. The old EPO Ax cognos servers repurposed for TM1 Cognos configuration and TM1 development. | Data & Analytics | Stuart Robinson | Sathiamurthy Samidurai | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial |  | Windows 2016 | No DB | No IIs | SNI dev'ed | No | 41913.375 | Invest | Replatform | Sathiamurthy.Samidurai@smith-nephew.com | Stuart Robinson
US Professional Website |  | Active | Product site for US HCPs. Some content requires credentials setup for end user to access. | Commercial | Manish Sahay | Andres Bernard | EOL | EOL | EOL | Not EOL | EOL | EOL | EOL | Full |  | Windows 2008 | SQL 2008 | 7.0 (2008) | COTS | Yes | 40179.375 | Migrate | To SaaS | Andres.Bernard@smith-nephew.com | Firas Almahamid
Vericut |  | Active | CNC Program Optimizer License server only | Manufacturing | Derek Spillane | Carla Morris | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2012 | No DB | 8.0 (2012) | COTS | Unknown | 42951.375 | Tolerate | Rehost (L&S) | Carla.Morris@smith-nephew.com | Derek Spillane
Visionaire Case Management (Legacy) |  | Active | Visionaire case flow website | R&D | Ian Bennett | Matthew Stephens | Unknown | EOL | Not EOL | Not EOL | Not EOL | EOL | Unknown | Full |  | Windows 2008 | SQL 2005 | 7.5 (2008R2) | Vendor Dev'ed | Yes | 39447.375 | Eliminate | To SaaS | Matthew.Stephens@smith-nephew.com | Sri Tupil
Visionaire Case Management (VCM) |  | Active | Patient matched solutions. ASD-Recon custom cutting block specification tool | R&D | Ian Bennett | Matthew Stephens | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2012 | SQL 2016 | 8.0 (2012) | Vendor Dev'ed | No | 39447.375 | Invest | Cannot go cloud | Matthew.Stephens@smith-nephew.com | Sri Tupil
Visual Cron |  | Active | for Web-EDI and automated Job/Task Controller | IT | Manas Singha | Tsutomu Hirooka | Not EOL | EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2008R2 | No DB | 7.5 (2008R2) | Vendor Dev'ed | Unknown | 43125.375 | Tolerate | Cannot go cloud | Tsutomu.Hirooka@smith-nephew.com | Firas Almahamid
Visual SVN |  | Active | Apache Subversion service | R&D | Ian Bennett | Matthew Stephens | Not EOL | EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial | Not EOL | Non windows | Other DB | No IIs | COTS | Yes | 40179.375 | Migrate | Rearchitect | Matthew.Stephens@smith-nephew.com | Sri Tupil
ZDOC |  | Active | Was used for document archiving pre introduction of HP finance. Not used anymore but business would like to keep until 2020. | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Windows 2012 | SQL 2008R2 | No IIs | COTS | No | 38718.375 | Eliminate | Rehost (L&S) | paul.davison@smith-nephew.com | Chris Cook
ANZPowerBI |  | Active | Reporting tool that accesses SAP PR1, SoNar and End User Data Sources | Data & Analytics | Jerry Li | Jerry Li | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2012 | SQL 2016 | No IIs | SNI dev'ed | No | 43289.375 | Invest |  | Jerry.Li@smith-nephew.com | Firas Almahamid
CardAccess 3000 |  | Active | Building Card Access System used in Costa Rica. 05/31/16 - Adding per request from Mark Beal. | Group Functions | Philip Sedgwick | Paul Davison | EOL | EOL | Not EOL | Not EOL | EOL | Not EOL | Not EOL |  | Not EOL | Windows 2008R2 | SQL 2008R2 | No IIs | COTS | Yes | 42521.375 | Tolerate |  | paul.davison@smith-nephew.com | Chris Cook
Easytrack Complaints system (Historic only - now replaced) |  | Active | Customer Compaints - superceded by SmartComplaints (Pilgrim) - History only | RAQA | Sri Tupil | Aileen Diola | EOL | EOL | EOL | Not EOL | Not EOL | EOL | Unknown | Partial |  | Windows 2003 | Other DB | 6.0 (2003) | Vendor Dev'ed | Unknown | 36891.375 | Eliminate |  | Aileen.Diola@smith-nephew.com | Sri Tupil
Evolve Study Manager CTMS |  | Active | Web based Clinical Trials Management Software Evolve Study Manager CTMS is a COTS application utilized by ASD Global Clinical Operations in Hull UK for tracking summary information and key documents necessary in the management of clinical studies. | RAQA | Sri Tupil | Aileen Diola | EOL | EOL | EOL | EOL | EOL | EOL | EOL | Limited | EOL | Windows 2008 | SQL 2008 | 7.0 (2008) | COTS | Yes | 40739.375 | Eliminate |  | Aileen.Diola@smith-nephew.com | Sri Tupil
Filezilla FTP Server |  | Retired | Transfering files into Business Objects server in South Africa. Not vendor supported. | Data & Analytics | Stuart Robinson | Mark Elliott | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2012 | SQL 2012 | No IIs | Vendor Dev'ed | No | 41640.375 | Tolerate |  | Mark.Elliott@smith-nephew.com
iScala (Singapore) |  | Retired | Legacy ERP system. 04/14/16 - This application was flagged as fully retired in previous EAP site but was added back into application portfolio when it was discovered that the system was still in place. Out of vendor support. | Both ASD and AWM | Firas Almahamid | Mulyanto Ng |  |  | Unknown | Unknown | EOL | EOL | Unknown | Limited | Unknown | Windows 2003 | Other DB | 6.0 (2003) | COTS | Unknown | 39568.375 | Eliminate |  | Mulyanto.Ng@smith-nephew.com
IXI UMS Fax Server |  | Active | Fax Server solution for inbound fax services, integrated in our CISCO VOIP/IPT | IT | Roman Wojtasik | Tomasz Kwiatkowski | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2016 | No DB | No IIs | COTS | No | 42552.375 | Unassigned |  | Tomasz.Kwiatkowski@smith-nephew.com | Anna Falbogowska
Lutron |  | Active | Building Automation in Costa Rica | Group Functions | Philip Sedgwick | Paul Davison | EOL | EOL | EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2008R2 | SQL 2012 | 7.5 (2008R2) | COTS | Yes | 42567.375 | Tolerate |  | paul.davison@smith-nephew.com | Chris Cook
Primion |  | Active | PRIMION is time capture system used in Germany commercial business. We have time capture terminals in both Marl and Hamburg. Also this is the former vacation planning system. Also this system manages the access to the building in Marl and is coupled with the Alarm system. The user-interface is a Website: http://ukrthsmappvw23/primeweb/index.jsp NOTES from Sebastian: This was introduced in July 2014. Business Owner is Udo Jensen (HR Director Germany). This is vendor supported application. The server is running a local SQL Express database. It does run IE11 native and no web-plugins/add-ons required. There is also a full client software to program key-cards, to my knowledge. | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | EOL | Not EOL | Not EOL | None | Not EOL | Windows 2012 | SQL 2005 | No IIs | COTS | Yes | 41821.375 | Tolerate |  | paul.davison@smith-nephew.com | Chris Cook
SEAL Application |  | Active | SEAL application manages printed content for the AWM DMS System - Applying watermarking and other information based on document status. Used in Europe and Asia. | ERP | Jacek Karas | Krzysztof Gaik | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL |  | Not EOL | Windows 2008 | No DB | Unknown | COTS | No | 39082.375 | Invest |  | Krzysztof.Gaik@smith-nephew.com | Massimo Trambaioli
Sharegate |  | Active | Tool will support data migration from personal file shares to OneDrive. Will be installed on dedicated vm machine only for migrartion activities. No Access for end users. | Enterprise Technology | Anna Falbogowska | Ludwik Hreczycho | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Unknown | Unknown | No IIs | SaaS | No |  | Unassigned |  | Ludwik.Hreczycho@smith-nephew.com | Anna Falbogowska
Solarwinds |  | Active | Network Performance monitor | IT | Roman Wojtasik | Patryk Bromirski | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2019 | SQL 2017 | 8.0 (2012) | COTS | No | 44140.375 | Unassigned |  | Patryk.Bromirski@smith-nephew.com | Anna Falbogowska
SVN Tortoise |  | Active | Atracsys document repository, documentation revision controlling software | IT | Kevin Ponce | Kevin Ponce | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Unknown | No DB | No IIs | COTS | No | 43769.3333 | Unassigned |  | Kevin.Ponce@smith-nephew.com
TransPerfect AI Portal for Language Translation (QRA) |  | Active | TransPerfect AI Portal for language translation service for QRA users. A Web platform that enables S+N QRA users to submit various document types for machine translation utilizing stand-alone enterprise machine translation server. | RAQA | Sri Tupil | Aileen Diola | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2019 | No DB | No IIs | SaaS | No | 43872.375 | Invest |  | Aileen.Diola@smith-nephew.com | Sri Tupil
WebFOCUS |  | Archive | Business Intelligence Reporting Suite for Noridcs region based on BPCS (HUB) and iScala. It covers sale statistics, some financial reports, prices, L&C, warehouse... | Data & Analytics | Stuart Robinson | Sathiamurthy Samidurai | EOL | EOL | EOL | EOL | EOL | EOL | EOL | Full |  | Windows 2012 | No DB | No IIs | Vendor Dev'ed | Yes | 37621.375 | Migrate |  | Sathiamurthy.Samidurai@smith-nephew.com | Stuart Robinson
XPS Ship |  | Active | Packing and Shipping in SAP | ERP | Jacek Karas | Pawel Pietrzyk |  | EOL |  |  | Unknown |  |  | Full |  | Windows 2008R2 | No DB | 7.5 (2008R2) |  | Unknown | 39447.375 | Tolerate |  | Pawel.Pietrzyk@smith-nephew.com | Massimo Trambaioli
Axapta 2009 (Malaysia & Thailand) |  | Active | Operations for Malaysia & Thailand | ERP | Massimo Trambaioli | Mulyanto Ng | [7 empty] | Full | [5 empty] | Unknown | 41426.375 | Unassigned |  | Mulyanto.Ng@smith-nephew.com | Massimo Trambaioli
Cimco (Malaysia) |  | Planned | Stores, send\recieves and audits CNC\CMM programs for manufacturing. |  | Francisco Marconcini | Carla Morris | [7 empty] | Full | [5 empty] | No |  | Unassigned |  | Carla.Morris@smith-nephew.com | Derek Spillane
CIMCO (Warwick) |  | Active | Distributed Numeric Control | Manufacturing | Derek Spillane | Carla Morris | [7 empty] | Full | [5 empty] | No |  | Unassigned |  | Carla.Morris@smith-nephew.com | Derek Spillane
EverBridge |  | Planned | Send notification to SNI employee/contractor in case of disatser |  | Massimo Trambaioli | Amit Shokeen | [7 empty] | Full | [5 empty] | Unknown |  | Unassigned |  | Amit.Shokeen@smith-nephew.com | Massimo Trambaioli
GBS Reporting |  | Planned | KPI Reporting for GBS team. Application is utilising Power BI, Redshift and Glue. | Commercial | Stuart Robinson | Sathiamurthy Samidurai | [7 empty] | Full | [5 empty] | No | 44101.375 | Unassigned |  | Sathiamurthy.Samidurai@smith-nephew.com | Stuart Robinson
Inventures (SCAMPI) Web App |  | Active | Site used by R&D and Marketing to track new prodcut ideas. Update from Doug C.: "The main application (Scampi) is used by the Inventures team to manage new product ideas. This is an internal application and is on mmpsrv046 and is scheduled to move to USMAN-SMWSPVW12 the weekend of Feb. 13th. There is a public facing application (this is a one page form) for Inventures called New Ideas and is public facing and hosted on mmpsrv023. This application is used by doctors, nurses, Sales Reps, … to submit new product ideas." | R&D | Sri Tupil | Ian Bennett | [7 empty] | Full | [5 empty] | Unknown | 39813.375 | Unassigned |  | ian.bennett@smith-nephew.com | Sri Tupil
Loaners/OSC |  | Active | Schedule Surgical Cases by Procedure and Loaner Orders by Procedure/Catalog/Kit - Order, Pick, Pack, Ship, Receive, Inspect, Replenish. June 2, 2020: Being replaced by Movemedical next year. That's phase two. ============================= Being Replaced by SAP. 03/09/16 - Per Dave M, this is now in scope for SOX. ITLT Cert:26-JUN-17 USASHSMDBQVW01 is the TEST OSC server for Visionaire | Commercial | Manish Sahay | Andres Bernard | EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | EOL | Full |  |  |  |  | SNI dev'ed | Yes | 36891.375 | Migrate |  | Andres.Bernard@smith-nephew.com | Firas Almahamid
Maestro Control |  | Active | The Lyophilizer system is used to freeze dry Collagenase Powder NP after the Dialyzation phase. The VirTis Maestro Lyophilizer control system is designed to be utilized with VirTis-brand Lyophilizer units for optimal functionality. The Maestro control system provides freeze-drying control capability with up to 12 thermal treatment steps and 16 primary drying steps; alarm monitoring; historical data collection. | Manufacturing | Sri Tupil | Aileen Diola | [7 empty] | None | [5 empty] | Unknown |  | Unassigned |  | Aileen.Diola@smith-nephew.com | Sri Tupil
Movex |  | Active | ERP software | ERP | Massimo Trambaioli | Antoine d'Overschie | [7 empty] | Full | [5 empty] | Unknown | 38351.375 | Unassigned |  | Antoine.doverschie@smith-nephew.com | Massimo Trambaioli
Orbit |  | Archive | Orthopedic RFID Loaner. 07/01/16 - Update from Dave Metcalfe: "Orbit since ANZPO is now historical data retrieval only, last DR was in 2014 – should be downgraded from Critical." -Support MGR updated per CMDB Mailbox |  | Chris Cook | Jerry Li | [7 empty] | Full | [5 empty] | Unknown | 38472.375 | Unassigned |  | Jerry.Li@smith-nephew.com | Firas Almahamid
Reimbursement CRM - Wound |  | Active | Reimbursement CRM - Wound Dynamics 365 | Commercial | Manish Sahay | Andres Bernard | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | [5 empty] | SaaS | No | 43541.3333 | Tolerate |  | Andres.Bernard@smith-nephew.com | Firas Almahamid
SAP Cloud Connector |  | Active | SAP Cloud Connector for integration of Ariba with SAP Systems (S4H & ERP Systems) | ERP | Jacek Karas | Pawel Pietrzyk | [7 empty] | Partial | [5 empty] | No |  | Unassigned |  | Pawel.Pietrzyk@smith-nephew.com | Massimo Trambaioli
Scanfile |  | Active | Used to scan documents for electronic storage. - Training records. (file format: PDF) - Calibration and preventive maintenance records (Work Orders). (file format: PDF and specific application database) - Laboratory test records. (file format: PDF and specific equipment database) - Batch records report of the Manufacturing. (file format: PDF) - Equipment's Qualification records. (file format: PDF) | Manufacturing |  | Aileen Diola | [13 empty] | Yes |  | Unassigned |  | Aileen.Diola@smith-nephew.com | Sri Tupil
ERP (China - Kingdee - HISTORICAL REFERENCE) |  | Archive | Kingdee V11. old ERP before AX, need keep it for Finance audit | Commercial | Firas Almahamid | Massimo Trambaioli | [7 empty] | Partial | [5 empty] | Unknown |  |  |  | Massimo.Trambaioli@smith-nephew.com
SAP EHP (HR) |  | Retired | SAP EHP (HR) | Group Functions | Firas Almahamid | [8 empty] | Full | [5 empty] | No | 38717.375 | Unassigned
Access Control Form |  | Retired | User Provisioning into S&N for former ArthroCare employees. | ASD (Advanced Surgical Devices) | Alison Conlon | David Gamble | [7 empty] | Full | [5 empty] | Unknown |  | Unassigned |  | David.Gamble@smith-nephew.com
Agile Cache (CRNTIFS0) |  | Retired | Quality System Documentation (ARTC Procedures). 01/25/16 - Updated Delivery Manager per request from Chris R. and Imtiaz. Setting to retired per Ramesh B. 01FEB18 | Both ASD and AWM | Imtiaz Iqbal | Ramesh Balabhadruni | [7 empty] | [Unknown] | [5 empty] | Unknown |  | Unassigned |  | Ramesh.Balabhadruni@smith-nephew.com
ArcServe Backup & Replication |  | Retired | Network Back Ups |  | Imtiaz Iqbal | Marianne Morton | [7 empty] | Full | [5 empty] | Unknown | 38472.375 | Unassigned |  | Marianne.Morton@smith-nephew.com
AT&T Connect |  | Retired | Web/audio/video collaboration service. 02/09/16 - Removed Julie Lothrop from Primary Support. She states she provides no support for this services. | IT | Dave Cranny | Patrick Prudhon | [7 empty] | Full | [5 empty] | Unknown | 41060.375 | Unassigned |  | Patrick.Prudhon@smith-nephew.com
AWM Product Websites |  | Retired | AWM Product Websites for North America and Canada. Includes: Santyl website; santyl.com; applysantyl.com;l Oasis website; oasiswoundmatrix.com; oasisecm.com; oasisultra.com; Regranex website; regranex.com; regranex360.com; Proshield Website; proshield.com; proshield.ca; santyl.ca Apache/Tomcat/MySQL. | Commercial | Firas Almahamid | Andres Bernard | [7 empty] | Full | [5 empty] | Unknown | 38353.375 | Unassigned |  | Andres.Bernard@smith-nephew.com
Bartender (Extruded Films) |  | Retired | 07/18/16 - Discovered this instance. Per Paul D: "There is however another instance of Bartender which is currently used for Extruded Films (Gilberdyke) in the UK and runs on the server GINTFS1. Label requests are generated from BPCS (MANLIVE) and sent via FTP to GINTFS1 which are then picked up by the Bartender application, processed and printed. The Hull desktop team (usually Stef Szafran) usually troubleshoots issues with it, whether it be rebooting the attached printing devices, the printers or arranging for a reboot of the server – which is also used a general file share/print. I think it would be useful to have this created as a new application to avoid the conflict and confusion between the two applications. " Application retired. GINTFS1 was decommissioned. |  | Francisco Marconcini | Paul Davison | [13 empty] | Unknown |  | Unassigned |  | paul.davison@smith-nephew.com
Biztalk |  | Retired | Business process management (BPM) software Ramesh asked to have this retired/ duplicate of the other Biztalk app | ASD (Advanced Surgical Devices) | Firas Almahamid | Ramesh Balabhadruni | [7 empty] | Full | [5 empty] | Unknown | 34699.375 | Unassigned |  | Ramesh.Balabhadruni@smith-nephew.com
Blue Coat |  | Retired | 05/31/16 - Adding per request from Mark Beal. Joey Zhao is the contact for remaining required information. | Commercial | Jerry Li | [14 empty] | Unknown | 42478.375 | Unassigned
Boomerang |  | Retired | Process Employee Business Expenses. Expense reports have been extracted from Boomerang by Donna Lavallee and uploaded into OpenText. Waiting on business to do testing and confirm Boomerang (MOW2K07) can be decommissioned. | 0 | Imtiaz Iqbal | Paul Davison | [7 empty] | Full | [5 empty] | Unknown | 33603.375 | Unassigned |  | paul.davison@smith-nephew.com
Business Objects (Italy) |  | Retired | Data Warehouse Reporting tool. 02/27 - Added per request from Miguel Illa. RESETTING APP TO ACTIVE - SERVERS ARE STILL related to this apps environment; this needs to be corrected prior to setting applications to retired in all cases. | Local Europe | Mark Towne | Tomasz Fijalkowski | [7 empty] | None | [5 empty] | Unknown | 37987.375 | Unassigned |  | Tomasz.Fijalkowski@smith-nephew.com
Cognos (Adaytum) |  | Retired | Financial Planning tool. Sometimes referred to as 'Adaytum'. Used in Finance and used for Commisions. | 0 | Imtiaz Iqbal | Paul Davison | [7 empty] | Limited | [5 empty] | Unknown | 37621.375 | Unassigned |  | paul.davison@smith-nephew.com
Collaborate |  | Retired | Supply Chain: Forecasting & Demand Management | Supply Chain | Imtiaz Iqbal | Amit Shokeen | [7 empty] | Full | [5 empty] | Unknown | 37256.375 | Unassigned |  | Amit.Shokeen@smith-nephew.com
Contract Management - Montreal |  | Retired | Contract Price with Hospital & Group Purchasing | Commercial | Imtiaz Iqbal | Paul Davison | [7 empty] | Full | [5 empty] | Unknown | 35430.375 | Unassigned |  | paul.davison@smith-nephew.com
Cross Reference |  | Retired | https://sales.smithnephew.net/CrossRef Used by Sales operations | Commercial | Firas Almahamid | Andres Bernard | [7 empty] | Full | [5 empty] | Unknown | 39813.375 | Unassigned |  | Andres.Bernard@smith-nephew.com
CS Contact Centre |  | Retired | CS Contact Centre - Wallboard Display Web Server | IT | Imtiaz Iqbal | Michael Schatten | [13 empty] | Unknown | 43126.375 | Unassigned |  | Michael.Schatten@smith-nephew.com
Dmax Tender |  | Retired | Tender Submissions |  | Imtiaz Iqbal | Marianne Morton | [7 empty] | Full | [5 empty] | Unknown | 38472.375 | Unassigned |  | Marianne.Morton@smith-nephew.com
Documentum /EZSubs |  | Retired | Electronic Document Submission. As part of the Global Regulatory Submissions project (Enovia), this system was confirmed decommissioned as of 15/02/2016. Servers were WMHU2K14/15/16, WMHU2K10 and 11 (Citrix) and WMHU2K20 (Citrix DB). set to retired - 14-may-18 | AWM (Advanced Wounded M...) | Mark Towne | Paul Davison | [7 empty] | Full | [5 empty] | Unknown | 37256.375 | Unassigned |  | paul.davison@smith-nephew.com
DOF/Web DOF |  | Retired | Site used by sales reps to enter orders for self delivered products | ASD (Advanced Surgical Devices) | Chris Cook | Paul Davison | [7 empty] | Full | [5 empty] | Unknown | 36525.375 | Unassigned |  | paul.davison@smith-nephew.com
DSSOCKET OCX |  | Retired | Part of OSC - being replaced by SAP. dsSocket TCP/IP OCX - simplifies Socket calls from OpscCenter VB to FedEx Server | ASD (Advanced Surgical Devices) | Imtiaz Iqbal | Amit Shokeen | [7 empty] | Full | [5 empty] | Unknown | 37621.375 | Unassigned |  | Amit.Shokeen@smith-nephew.com
Dynatrace |  | Retired | Application Performance Monitoring (APM) tool used currently to monitor just Prisym (Global Labeling System) | Manufacturing | Bob Watkins | Amit Shokeen | [7 empty] | Full | [5 empty] | Unknown | 42614.375 | Unassigned |  | Amit.Shokeen@smith-nephew.com
E-Nable |  | Retired | Sales tax exemption certificate database. Confirmed by business user (Deborah Gangi) that it is no longer used and can be discontinued. |  | Tjebbes Feenstra | Paul Davison | [7 empty] | Limited | [5 empty] | Unknown | 39447.375 | Unassigned |  | paul.davison@smith-nephew.com
Easycom for Windev |  | Retired | Needed to connect to European HUB BPCS to retrieve data for Eurodata. Now retired as moved onto SAP. | AWM (Advanced Wounded M...) | Christopher Rowley | Paul Davison | [7 empty] | Full | [5 empty] | Unknown | 36525.375 | Unassigned |  | paul.davison@smith-nephew.com
EasyPay Enterprise |  | Retired | Payroll system. Used in Singapore, Thailand, Malaysia Per - Linda Rosser. This application had been decommisionsed | Both ASD and AWM | Imtiaz Iqbal | [8 empty] | Limited | [5 empty] | Unknown | 42370.375 | Unassigned
Enventive |  | Retired | Application is used for early mechanical / positioning simulation. *Delivery Manager changed due to error on EAP document | R&D | Imtiaz Iqbal | Ian Bennett | [7 empty] | Limited | [5 empty] | Unknown | 42642.375 | Unassigned |  | ian.bennett@smith-nephew.com
EPO Analytics Warehouse |  | Retired | Data warehouse environment for Cognos Analytics (SQL SSIS environment) | Data & Analytics | Imtiaz Iqbal | Tomasz Fijalkowski | [7 empty] | Full | [5 empty] | Unknown | 41936.375 | Unassigned |  | Tomasz.Fijalkowski@smith-nephew.com
EventsPro |  | Retired | Events Management |  | Imtiaz Iqbal | Marianne Morton | [7 empty] | Full | [5 empty] | Unknown | 38472.375 | Unassigned |  | Marianne.Morton@smith-nephew.com
Feeling the Squeeze |  | Retired | Visualization of Allevyn and DURAFIBER UKI 70/30 proposition | Commercial | Imtiaz Iqbal | Andres Bernard | [7 empty] | Limited | [5 empty] | Unknown | 42163.375 | Unassigned |  | Andres.Bernard@smith-nephew.com
Fixed Asset Loans System (AS400) |  | Retired | Instrument Fixed Assets |  | Imtiaz Iqbal | Tsutomu Hirooka | [7 empty] | Full | [5 empty] | Unknown | 38472.375 | Unassigned |  | Tsutomu.Hirooka@smith-nephew.com
FRU (Field Roster Update) |  | Retired | The FRU System is used by sales force management to notify the necessary home office teams of the following conditions in the sales force; new hires, promotions, territory transfers, personal information changes, etc…. | Commercial | Firas Almahamid | Andres Bernard | [7 empty] | Full | [5 empty] | Unknown | 41275.375 | Unassigned |  | Andres.Bernard@smith-nephew.com
Gentran EDI |  | Retired | This system is Retired. There shouldn't be compliance any longer EDI for Biotherapeutics PER Robert Jones, still active responsible for 90% AWB sales; Planning retirement when global EDI solution is built | ERP | Imtiaz Iqbal | Robert Jones | [7 empty] | Full | [5 empty] | Unknown | 40214.375 | Unassigned |  | Robert.Jones@smith-nephew.com
Get Paid |  | Retired | Receivables / Order to Cash Management | Group Functions | Imtiaz Iqbal | Paul Davison | [7 empty] | Limited | [5 empty] | Unknown | 37621.375 | Unassigned |  | paul.davison@smith-nephew.com
Global Loaners (Mymediset) |  | Retired | 07/07/16 - Per Alison Molloy, this is an older, retired version of MyMediset. Retiring this entry and creating new. GLP Project OP09017. Medical Loanset - Interfaces with Endo ECC, will interface with RFID, Global Mobile system, Ortho SAP | Both ASD and AWM | Tjebbes Feenstra | Paul Wilson | [7 empty] | Full | [5 empty] | Unknown | 36891.375 | Unassigned |  | Paul.Wilson@smith-nephew.com
GLPI Application |  | Retired | Inventory Server | [10 empty] | None | [5 empty] | Unknown |  | Unassigned
Healthpoint University |  | Retired | 1-6-16: Delivery Manager was Steve McNeill. Changed to Robert Jones. 9/13/17 - Per Robert Jones, this was retired in favor of an iPad application developed and implemented by the business. | AWM-US | Chris Cook | Robert Jones | [7 empty] | None | [5 empty] | Unknown | 40878.375 | Unassigned |  | Robert.Jones@smith-nephew.com
HP iDMS |  | Retired | HP finance tool; Steve Horgan and Tony Pockney. Integrated with SecureAuth. | Group Functions | Tjebbes Feenstra | Paul Davison | [7 empty] | Full | [5 empty] | Unknown | 42395.375 | Unassigned |  | paul.davison@smith-nephew.com
HR Interview Guide |  | Retired | Allows manager to prepare HR Interview Guides for use during interviews. In house application | Group Functions | Imtiaz Iqbal | Andres Bernard | [7 empty] | Full | [5 empty] | Unknown | 40178.375 | Unassigned |  | Andres.Bernard@smith-nephew.com
Hyperion - GRS (HISTORICAL REFERENCE) |  | Retired | Old Hyperion application with historical data. | Both ASD and AWM | Tjebbes Feenstra | Paul Davison | [7 empty] | None | [5 empty] | Unknown | 34700.375 | Unassigned |  | paul.davison@smith-nephew.com
Informatica (Legacy Apps Data Intergration) |  | Retired | ETA tool. Mainly used to load data between BPCS, ERP, WMD Data Warehouse and MLE planning system */Updated name from having Manassas in name to have Ashburn per SRR0073231 at the request of CAB to prevent confusion Name Formally Informatica (Ashburn) Changed per SRR0082319 to reflect current name | Data & Analytics | Chris Cook | Tomasz Fijalkowski | [7 empty] | External | [5 empty] | Unknown | 41557.375 | Unassigned |  | Tomasz.Fijalkowski@smith-nephew.com
Infrastrcure MFG DEMO Service |  | Retired | *** THIS IS FOR DEMO PURPOSES ONLY*** ***NOT FOR PRODUCTION ENVIRONMENTS***. | Manufacturing | Derek Spillane | Carla Morris | [7 empty] | Full | [5 empty] | Unknown | 43252.375 | Unassigned |  | Carla.Morris@smith-nephew.com
InSeal |  | Retired | 05/31/16 - Adding as a placeholder for now per request from Mark Beal. 07/06/17. Application to manage Cafeteria |  | Alison Conlon | David Hernández | [7 empty] | Limited | [5 empty] | Unknown |  | Unassigned |  | David.Hernandez@smith-nephew.com
Invoices Archiving |  | Retired | Gumbo Server | [10 empty] | None | [5 empty] | Unknown |  | Unassigned
iScala (Mexico) |  | Retired | 05/03/16 - Adding iScala (Mexico) back to the inventory. It was discovered that this application was not completely retired. David Hernandez: "This server was running iScala however some time ago this is turned off and off line, it's only turn on to check historical." |  | Firas Almahamid | David Hernández | [7 empty] | Full | [5 empty] | Unknown |  | Unassigned |  | David.Hernandez@smith-nephew.com
jPrint |  | Retired | SAP Branch Printing |  | Imtiaz Iqbal | Marianne Morton | [7 empty] | Full | [5 empty] | Unknown | 38472.375 | Unassigned |  | Marianne.Morton@smith-nephew.com
Kitting |  | Retired | Application for Sales Reps to build product kits for customers | ASD (Advanced Surgical Devices) | Chris Cook | Paul Davison | [7 empty] | Full | [5 empty] | Unknown | 38717.375 | Unassigned |  | paul.davison@smith-nephew.com
Labeling Request Web App |  | Retired | Site used by Tech Comm for users to submit label requests. The Labeling Request web application is a one page form that allows users to submit new and updated Label request changes. The submissions are emailed to specific individuals in the Global Labeling and Telecom departments. 11/2/15 - GxP Assessed per Roger Heffington. | Supply Chain | Imtiaz Iqbal | Andres Bernard | [7 empty] | Full | [5 empty] | Unknown | 39082.375 | Unassigned |  | Andres.Bernard@smith-nephew.com
Laserfiche Document Management |  | Retired | Document Management |  | Imtiaz Iqbal | Marianne Morton | [7 empty] | Full | [5 empty] | Unknown | 38472.375 | Unassigned |  | Marianne.Morton@smith-nephew.com
LeadTracker |  | Retired | Tradeshow/ event lead information | ASD (Advanced Surgical Devices) | Chris Cook | Paul Davison | [7 empty] | Full | [5 empty] | Unknown | 39082.375 | Unassigned |  | paul.davison@smith-nephew.com
Lotus Notes - York GRC |  | Retired | Workflow Application. Used as an ERP system for Accounts Payable and Accounts Receivable | Group Functions | Imtiaz Iqbal | Paul Davison | [7 empty] | Limited | [5 empty] | Unknown | 36525.375 | Unassigned |  | paul.davison@smith-nephew.com
Manugistics |  | Retired | Supply Chain: Forecasting & Demand Management. Includes: OneView | Supply Chain | Imtiaz Iqbal | Amit Shokeen | [7 empty] | Full | [5 empty] | Unknown | 37256.375 | Unassigned |  | Amit.Shokeen@smith-nephew.com
Micropay |  | Retired | Payroll |  | Imtiaz Iqbal | Marianne Morton | [7 empty] | Full | [5 empty] | Unknown | 38472.375 | Unassigned |  | Marianne.Morton@smith-nephew.com
MyCareer |  | Retired | Performance and Talent Management. Decommissioned 7 Jan after confirmation from Nikki West and Jerry Poreca. |  | Tjebbes Feenstra | Paul Davison | [7 empty] | Full | [5 empty] | Unknown |  | Unassigned |  | paul.davison@smith-nephew.com
National Australia Bank (NAB) Online |  | Retired | Banking |  | Imtiaz Iqbal | Marianne Morton | [7 empty] | Full | [5 empty] | Unknown | 38472.375 | Unassigned |  | Marianne.Morton@smith-nephew.com
NEC PABX |  | Retired | PABX. Phone system for main office. Vendor SLA in place that requires 4 hour recovery window. |  | Imtiaz Iqbal | Tsutomu Hirooka | [7 empty] | Full | [5 empty] | Unknown | 38472.375 | Unassigned |  | Tsutomu.Hirooka@smith-nephew.com
OnBase SQL |  | Retired | 05/31/16 - Adding as a placeholder for now per request from Mark Beal. | IT | Dave Cranny | David Hernández | [13 empty] | Unknown | 42521.375 | Unassigned |  | David.Hernandez@smith-nephew.com
OneBridge |  | Retired | Onebridge Admin defines sync rules handheld to server databases. Proxy passes traffic through DMZ over Internet. 03/22/16 - Update from Al Whitney, no longer used. | ASD (Advanced Surgical Devices) | Chris Cook | Alvin Whitney | [7 empty] | Full | [5 empty] | Unknown | 39447.375 | Unassigned |  | Al.Whitney@smith-nephew.com
OptioDCS |  | Retired | Design Form Document (Invoice, Credit Notes, Customer Statements, etc...) | ERP | Imtiaz Iqbal | Paul Davison | [7 empty] | Full | [5 empty] | Unknown | 40543.375 | Unassigned |  | paul.davison@smith-nephew.com
Proship AWM TMS System |  | Retired | Transportation mgt system | Supply Chain | Derek Spillane | Amit Shokeen | [7 empty] | Full | [5 empty] | Unknown | 40551.375 | Unassigned |  | Amit.Shokeen@smith-nephew.com
Qmaster |  | Retired | Call Centre |  | Imtiaz Iqbal | Marianne Morton | [7 empty] | Full | [5 empty] | Unknown | 38472.375 | Unassigned |  | Marianne.Morton@smith-nephew.com
Safecom |  | Retired | Manages all Warwick Users Print jobs. 08/24/16 - Francisco/Paul Browett supplied answers to all questions about the application. Safecom 9.44.4.3. | ASD (Advanced Surgical Devices) | Imtiaz Iqbal | Amit Shokeen | [7 empty] | None | [5 empty] | Unknown | 40588.375 | Unassigned |  | Amit.Shokeen@smith-nephew.com
Salesrep (induction) form |  | Retired | Collects information and sends e-mail to recipients. Used for onboarding sales rep except in AWM | Commercial | Firas Almahamid | Andres Bernard | [7 empty] | Full | [5 empty] | Unknown | 39082.375 | Unassigned |  | Andres.Bernard@smith-nephew.com
SAP T&E |  | Retired | SAP T&E (Archived) | Enterprise | Imtiaz Iqbal | Santhosh Nair | [7 empty] | Full | [5 empty] | Unknown |  | Unassigned |  | Santhosh.Nair@smith-nephew.com
SEPA CGI |  | Retired | European banking app used by a small number of users and was set up quite a while ago for Mark Dunbar. Joerg Kiepert may be the only user left. This SSO is only accessible to members of one specific AD group. Integrated with SecureAuth | Group Functions | Firas Almahamid | Steve Horgan | [13 empty] | Unknown | 42395.375 | Unassigned |  | Stephen.Horgan@smith-nephew.com
SNAG (Smith and Nephew Arrangement Guardian) |  | Retired | Currently integrates with AD | ASD (Advanced Surgical Devices) | Tjebbes Feenstra | Paul Davison | [7 empty] | Full | [5 empty] | Unknown | 39813.375 | Unassigned |  | paul.davison@smith-nephew.com
SNAP |  | Retired | SN Account Profile - Customer information used by sales | ASD (Advanced Surgical Devices) | Chris Cook | Paul Davison | [7 empty] | Full | [5 empty] | Unknown | 37986.375 | Unassigned |  | paul.davison@smith-nephew.com
SNBio University |  | Retired | Replaced HealthPoint University. Wound sales training. Per Robert Jones, this is an iPad app and was developed by SNI business - no IT involvement. Not sure if there is a server or SaaS service associated. | AWM-US | Imtiaz Iqbal | Andres Bernard | [7 empty] | None | [5 empty] | Unknown | 40640.375 | Unassigned |  | Andres.Bernard@smith-nephew.com
SSO eRecruitment |  | Retired | Recruiting software | Group Functions | Imtiaz Iqbal | Paul Davison | [7 empty] | Full | [5 empty] | Unknown | 39629.375 | Unassigned |  | paul.davison@smith-nephew.com
Talend Open Studio |  | Retired | ETL tool used to extract copy data from SAP tables to an SQL 2005 server In Brussels. The data extracted is the details for IT expenses for SAP based countries, which is the being joined with the same data from other sources on the Spain BO server. 1/11/16 - Per Linda, this is obsolete. Bart is checking to confirm this has been or can be decommissioned. 1/20/16 - Linda confirmed. "This application can be taken offline as it's no longer in use. The server has other non BI apps on it, but the the Talend software was removed." |  | Chris Cook | Tomasz Fijalkowski | [7 empty] | Full | [5 empty] | Unknown | 40178.375 | Unassigned |  | Tomasz.Fijalkowski@smith-nephew.com
Telstra BRSS |  | Retired | Telecom Reporting |  | Imtiaz Iqbal | Marianne Morton | [7 empty] | Full | [5 empty] | Unknown | 38472.375 | Unassigned |  | Marianne.Morton@smith-nephew.com
Timelink (Historical only) |  | Retired | Replaced by Kronos ***Set to Retired Per Paul Davidson 7-JAN-16:ALPHAM |  | Tjebbes Feenstra | Paul Davison | [7 empty] | Limited | [5 empty] | Unknown | 36525.375 | Unassigned |  | paul.davison@smith-nephew.com
Toll Connect |  | Retired | Freight & Shipping |  | Imtiaz Iqbal | Marianne Morton | [7 empty] | Full | [5 empty] | Unknown | 38472.375 | Unassigned |  | Marianne.Morton@smith-nephew.com
Turnover V5.4 |  | Retired | AS400 tool - source migration mgt. 2016-06-16: Removed from European AS400s (DEVMAIN, DISLIVE and MANLIVE). Now only used for Canada PRMS (MOAS400-170, MOAS400). RESETTING APP TO ACTIVE - SERVERS ARE STILL related to this apps environment; this needs to be corrected prior to setting applications to retired in all cases. | AWM (Advanced Wounded M...) | Imtiaz Iqbal | Paul Davison | [7 empty] | None | [5 empty] | Unknown | 35795.375 | Unassigned |  | paul.davison@smith-nephew.com
UKSalesMessenger |  | Retired | Program that runs daily sending text messages to the UK Sales Force with the prior days sales | ASD (Advanced Surgical Devices) | Chris Cook | Paul Davison | [7 empty] | Full | [5 empty] | Unknown | 39082.375 | Unassigned |  | paul.davison@smith-nephew.com
Utility PLM Server |  | Retired | PLM | R&D | Bob Watkins | Ian Bennett | [7 empty] | Full | [5 empty] | Unknown | 36160.375 | Unassigned |  | ian.bennett@smith-nephew.com
uTrak |  | Retired | Print Reporting |  | Imtiaz Iqbal | Marianne Morton | [7 empty] | Full | [5 empty] | Unknown | 38472.375 | Unassigned |  | Marianne.Morton@smith-nephew.com
Valuenex |  | Retired | Analytical package - intellectual asset management - integral website - creates maps to identify white spaces where patents have not been filed (or threats) can load own patent data and do analysis (public domain) patent offices - create lists and do analysis - pricing $500/month - 1 license for trial. No connection to S&N. Web access. We upload data - Public. Free trials and training has been done. (Need to contact Chris Cook and Dan Foster). Can adjust subscription (off and on) IT SUPPORT = NONE | R&D | Imtiaz Iqbal | Andres Bernard | [13 empty] | Unknown | 42743.375 | Unassigned |  | Andres.Bernard@smith-nephew.com
Vertex Sales Tax L Series |  | Retired | Sales and use tax calculation | AWM (Advanced Wounded M...) | Imtiaz Iqbal | Paul Davison | [7 empty] | Limited | [5 empty] | Unknown | 35795.375 | Unassigned |  | paul.davison@smith-nephew.com
VueLogic, PrintLogic, Edit Logic |  | Retired | printLogic is a server-based ENOVIA MatrixOne web integration that allows users to batch print documents directly from their MatrixOne databases. editLogic allows you to open, edit and save Program Code directly to Matrix without ever opening the Business | ASD (Advanced Surgical Devices) | Mark Towne | Ramesh Balabhadruni | [7 empty] | Full | [5 empty] | Unknown | 38717.375 | Unassigned |  | Ramesh.Balabhadruni@smith-nephew.com
Winshuttle |  | Retired | Data Upload. 01/08/16 - Setting disposition to Delete. See history of this entry in the original EAP (sharepoint site). There was a reference to a Winshuttle instance in North Ryde, AUS. |  | Firas Almahamid | Santhosh Nair | [7 empty] | Full | [5 empty] | Unknown | 38472.375 | Unassigned |  | Santhosh.Nair@smith-nephew.com
Wound Tridek (old WCMS) |  | Retired | 04/28/15 - Per David Gamble, Scheduled for decommision May-2015 |  |  | David Gamble | [7 empty] | [Unknown] | [5 empty] | Unknown |  | Unassigned |  | David.Gamble@smith-nephew.com
3C SOFTWARE | 3C SOFTWARE | Planned | PABX SYSTEM | IT | Mpho Gwala | Mpho Gwala | [7 empty] | Partial | [5 empty] | Unknown |  | Unassigned |  | Mpho.Gwala@smith-nephew.com
Aliquant | SmithNephewBenefits.com | Retired | S&N Benefits administration - SAAS | Group Functions | Imtiaz Iqbal | Steve Horgan | [13 empty] | Unknown | 38352.375 | Unassigned |  | Stephen.Horgan@smith-nephew.com
Attune Logi (Finland) | Barcodescanner and LOT tracking | Retired | Barcodescanner and LOT tracking for Finland - decommed since SAP golive in May 2015; tracking information is available from a text file stored on network share |  | Firas Almahamid | [8 empty] | External | [5 empty] | Unknown | 38352.375 | Unassigned
Automated Chargeback Reconciliation | ACR, CAMVP, Chargebacks Analytics | Planned | Provides automated and assisted chargeback reconciliation between approved chargeback amounts and vendor chargeback deductions for AWM in the US. | Commercial | Manish Sahay | Andres Bernard | [7 empty] | Partial | [5 empty] | No | 44095.375 | Unassigned |  | Andres.Bernard@smith-nephew.com | Firas Almahamid
Blue Mountain | CMMS | Active | The Calibration Management software is used to schedule calibration and preventive maintenance activities, to maintain a history of the equipment calibration, to create a traceable inventory of calibrated equipment used in regulatory applications. | RAQA | Sri Tupil | Aileen Diola | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Windows 2016 | SQL 2016 | 8.0 (2012) | SaaS | No | 43185.375 | Invest |  | Aileen.Diola@smith-nephew.com | Sri Tupil
CA-Web | Corrective Action (Mansfield) | Active | Is a Correction Action Tracker use by the Quality Management team Hosted in a Legacy Think CLient version with MSAccess being replaced with this Hosted Web Based Solution. PROD: CHarlotte, NC, DR: Atlanta, GA. | RAQA | Sri Tupil | Aileen Diola | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | External | Not EOL | Windows 2012 | No DB | 8.0 (2012) | SaaS | No | 42217.375 | Tolerate |  | Aileen.Diola@smith-nephew.com | Sri Tupil
Calibration Manager | Calibration Manager-Plant Maintenance | Retired | Blue Mountain Quality Resource | Manufacturing | Imtiaz Iqbal | Amit Shokeen | [7 empty] | Limited | [5 empty] | Unknown | 38352.375 | Unassigned |  | Amit.Shokeen@smith-nephew.com
CARS | Contract Management System; CCMS | Retired | Chargebacks and Rebates application - similar to S&N TRACCS. Contract Management System. S&N AWB (formerly Healthpoint) began using the Revitas (formerly I-MANY) CARS CCMS platform in 2006. 09/13/17 - Per Steve McNeil, this is now completely retired. All historical data captured and stored on BPCS. | AWM (Advanced Wounded M...) | Chris Cook | Robert Jones | [7 empty] | External | [5 empty] | Unknown | 41311.375 | Unassigned |  | Robert.Jones@smith-nephew.com
CCure 9000 Security Management System | JC CCure 2000 | Active | Facility Access Control | Group Functions | Philip Sedgwick | Paul Davison | [13 empty] | No | 44256.375 | Unassigned |  | paul.davison@smith-nephew.com | Chris Cook
Citrix Netscaler VPX 10 Virtual Appliance | Netscaler | Retired | Gatwey servcei conencting CRM APP on IPad to CWR Server |  | Imtiaz Iqbal | Marianne Morton | [7 empty] | Limited | [5 empty] | Unknown | 41759.375 | Unassigned |  | Marianne.Morton@smith-nephew.com
Contract Express | CAT | Planned | This SaaS tool is used for the creation of new contracts in a controleed and automated function using Contract Templates, with a workflow in place to route any non-standard contracts through a formal legal review. This is initially a Prototype roll-out in 2020. | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Non windows | Other DB | No IIs | SaaS | No | 43998.375 | Unassigned |  | paul.davison@smith-nephew.com | Chris Cook
Contractor Notification | Non Employee Notification; Temp/Contractor Notification | Retired | The app users enter information about NonEmployee (Hires/Transfers and Terms). The data is then sent via email to various distribution lists. | Group Functions | Firas Almahamid | Andres Bernard | [7 empty] | Limited | [5 empty] | Unknown | 38726.375 | Unassigned |  | Andres.Bernard@smith-nephew.com
CPI | Computer Packages Inc. | Retired | http://cpi.arthrocare.com Intellectual Property Database | ASD (Advanced Surgical Devices) | Tjebbes Feenstra | David Gamble | [7 empty] | External | [5 empty] | Unknown | 40893.375 | Unassigned |  | David.Gamble@smith-nephew.com
DAP CONTROLLER | DAP CONTROLLER | Planned | DECT PHONES (CORDLESS PHONES) AP CONTROLLER | IT | Mpho Gwala | Mpho Gwala | [7 empty] | Partial | [5 empty] | No |  | Unassigned |  | Mpho.Gwala@smith-nephew.com
Dashboard | Dashboard | Retired | http://dashboard.smithnephew.com/launch.asp Dashboard for Sales Reporting On Memsrv240 | Data & Analytics | Imtiaz Iqbal | Andres Bernard | [7 empty] | Limited | [5 empty] | Unknown | 38717.375 | Unassigned |  | Andres.Bernard@smith-nephew.com
dataSTOR | dataSTOR | Active | This application is used to store an electronic copy of PODs, Invoices, Statements and other forms which might be needed to be located and sent to customers, auditors, suppliers etc. at a later stage | ERP | Dave Cranny | Sebastian Pasch | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Windows 2008R2 | SQL 2008R2 | No IIs | COTS | No | 42437.375 | Unassigned |  | Sebastian.Pasch@smith-nephew.com
Deployment Tracking and Analytics System (DTAS) | DTAS | Active | This application is used for monitoring SNN Implants usages VS competition. Hosted in Microsoft Azure. Project Vendor: Syssoft, New Delhi. Approved as a temporary solution until POWER India is completed. URL: www.dtas-snn.com | Commercial | Jerry Li | Malav Joshi | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL |  | Partial |  | Windows 2012 | SQL 2012 |  | Vendor Developed | No | 42430.375 | Unassigned |  | Malav.Joshi@smith-nephew.com | Firas Almahamid
DS Software - KES | Data Collection, Analysis and Management System (DCAM) and Calibration Management System (CalMan) | Planned | Data collect, analysis and management and calibration management software. | R&D | Adam Keech | Adam Keech | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL |  | Partial | Not EOL | Windows 2019 | Other DB |  | Vendor Dev'ed | No | 44092.375 | Unassigned |  | Adam.Keech@smith-nephew.com | Chris Cook
DXC eForms | HP eForms | Retired | Used to process Journal Requests including supporting documents. | Group Functions | Firas Almahamid | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Non windows | Other DB |  | SaaS | No | 41640.375 | Unassigned |  | paul.davison@smith-nephew.com
Employee Stock Purchase Plan | ESPP - Bank of New York | Retired | ESPP - Employee Stock Purchase Plan | Group Functions | Imtiaz Iqbal | Steve Horgan | [13 empty] | Unknown | 38352.375 | Unassigned |  | Stephen.Horgan@smith-nephew.com
EUDAMED PTC Windchill PLM | EUDAMED PLM | Planned | Enterprise Compliance - Quality and Regulatory | RAQA | Ian Bennett | Matthew Stephens | [13 empty] | No | 43985.375 | Unassigned |  | Matthew.Stephens@smith-nephew.com | Sri Tupil
Exhibitforce | Exhibitforce | Active | Event Suite - event management technology for tracking inventory, staffing, housing and overall trade show logistics. | Commercial | Manish Sahay | Andres Bernard | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial | Not EOL |  |  |  | SaaS | No | 44013.375 | Unassigned |  | Andres.Bernard@smith-nephew.com | Firas Almahamid
FDA Chat/Collaborate MVP | Master Validation Plan | Retired | In-house developed solution for managing audit communications with FDA. 10/16/15 - This application was developed in-house by end-user and deployed on a non-compliant Linux server. This application will be relocated to a new server in data center managed by IT. See Francisco for more details. | ASD (Advanced Surgical Devices) | Imtiaz Iqbal | Amit Shokeen | [7 empty] | Limited | [5 empty] | Unknown | 42248.375 | Unassigned |  | Amit.Shokeen@smith-nephew.com
Fidelity | www.401k.com | Retired | 401k and retirement benefit provider | Group Functions | Imtiaz Iqbal | Steve Horgan | [13 empty] | Unknown | 42273.375 | Unassigned |  | Stephen.Horgan@smith-nephew.com
Field Spend Capture | FSC | Retired | HCP Aggregate Spend mobile device application for collection of spend data from 1099 / Third Party Sales reps. | Group Functions | Firas Almahamid | Andres Bernard | [7 empty] | External | [5 empty] | Unknown | 40543.375 | Unassigned |  | Andres.Bernard@smith-nephew.com
Global Recruitment Application (Taleo) | eRecruitment | Retired | New, global recruiting service. Replaces OpenHire. | Group Functions | Imtiaz Iqbal | Steve Horgan | [13 empty] | Unknown | 41182.375 | Unassigned |  | Stephen.Horgan@smith-nephew.com
Global Wound Academy | GWA | Retired | Being replaced and upgraded - project due to complete end of June, 2013. ITLT Cert: 26-MAY-17 Product Vendor Support=Supported Delivery Manager Cert: 22JUN17 | Commercial | Santhosh Nair | Andres Bernard | [7 empty] | External | [5 empty] | Unknown | 38352.375 | Unassigned |  | Andres.Bernard@smith-nephew.com
HP Certification | Assurenet | Retired | HP finance tool. Steve Horgan and Tony Pockney. Integrated with SecureAuth. | Group Functions | Firas Almahamid | Steve Horgan | [13 empty] | Unknown | 42395.375 | Unassigned |  | Stephen.Horgan@smith-nephew.com
IBM Cognos Impromptu Adminsitrator | Impromptu | Retired | Application to map BPSC to Cognos cubes |  | Imtiaz Iqbal | Marianne Morton | [7 empty] | Limited | [5 empty] | Unknown | 41541.375 | Unassigned |  | Marianne.Morton@smith-nephew.com
IQ-Soft (Tuttlingen) | IQ-Soft , IQSoft | Active | This is a COTS application utilized by Tuttlingen site. This software have two modules; 1. Calibration Management used by Quality Management 2. Operating Equipment Management used by Downstream Engineering | RAQA | Sri Tupil | Aileen Diola | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial | Not EOL | Windows 2016 | Other DB | 8.0 (2012) | COTS | No | 38353.375 | Tolerate |  | Aileen.Diola@smith-nephew.com | Sri Tupil
IRAMEA-LATAM Data Warehouse (South Africa) | SADW | Active | Data Warehouse for the SABO reporting System | Data & Analytics | Stuart Robinson | Mark Elliott | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | [Unknown] |  | Windows 2012 | Other DB | No IIs | SNI dev'ed | No | 38718.375 | Tolerate |  | Mark.Elliott@smith-nephew.com | Stuart Robinson
Katalon Studio | Katalon Katalon TestOps | Active | "Katalon is a Desktop application. At Smith and Nephew Katalon is used to setup automated test scripts and execute scripts for Regression testing. A video file is generated for every test execution and validated by the tester. Katalon is a powerful solution that helps you automate Web, API, Mobile, and Desktop apps — with smart analytics and CI/CD integrations. " | R&D | Ian Bennett | Matthew Stephens | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial | Not EOL | Windows 2016 | No DB | No IIs | COTS | No |  | Tolerate |  | Matthew.Stephens@smith-nephew.com | Sri Tupil
Loopio | Loopio | Planned | Automated RFP responses | Commercial | Manish Sahay | Andres Bernard | [7 empty] | Partial | [5 empty] | Unknown |  | Unassigned |  | Andres.Bernard@smith-nephew.com
Master Control | Biotherapeutics Apps (Master Control) | Active | Electronic Document Management System (EDMS) for Controlled Biotherapeutic documents This software is used for Non Conformance, CAPA Management, Change Management, Calibration Management, Records Management Application was migrated to SaaS solution Jul 2017 | RAQA | Sri Tupil | Aileen Diola | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Windows 2016 | SQL 2016 | 8.0 (2012) | SaaS | No | 42919.375 | Invest |  | Aileen.Diola@smith-nephew.com | Sri Tupil
Medidata CTMS | Edge; Medidata Edge | Active | Manage and report on clinical studies | R&D | Sri Tupil | Matthew Stephens | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL |  | Not EOL | Windows 2016 | SQL 2016 | 8.0 (2012) | SaaS | No | 43449.375 | Invest |  | Matthew.Stephens@smith-nephew.com | Sri Tupil
MI Touch (CRM - EUCAN) | Pulse | Retired | CRM system for EUCAN ITLT Cert: 26-MAY-17 |  | Chris Cook | Richard Hepwood | [7 empty] | None | [5 empty] | Unknown |  | Unassigned |  | Richard.Hepwood@smith-nephew.com
MKS Implementer 2005 | Software Development Management (SDM) | Retired | AS/400 Change Management for US Wound | AWM (Advanced Wounded M...) | Imtiaz Iqbal | Paul Davison | [7 empty] | None | [5 empty] | Unknown | 35795.375 | Unassigned |  | paul.davison@smith-nephew.com
Modern Hire | Montage (former company name) | Active | Modern Hire is an interview platform offering on demand and live interview types (including text screen, video, live). Jobs are constructed in the platform, and candidates can complete via web/text/video etc. Interviews rate the submissions. This data is passed back to Workday. | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Non windows | Other DB | No IIs | SaaS | No | 43891.375 | Unassigned |  | paul.davison@smith-nephew.com | Chris Cook
MS Dynamics GP 10 | Great Plains - MS Dynamics GP 10 | Archive | ERP System. 07/08/16 - Per David H, system is not used for Archive. Backups were made and place on NAS storage locally. Need to confirm. |  | Firas Almahamid | Massimo Trambaioli | [7 empty] | Partial | [5 empty] | Unknown | 38352.375 |  |  | Massimo.Trambaioli@smith-nephew.com
NPWT Fleet Management Portal | RENASYS SMART PLUS Portal | Active | The portal will be a platform for users to track S&N medical devices from location to location. Depending on the type of user, one would be allowed to access the different functions associated with the device. | IT | Jerry Li | Rohit Gupta | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Windows 2019 | SQL 2014 | No IIs | SaaS | No | 44090.375 | Unassigned |  | Rohit.Gupta@smith-nephew.com | Firas Almahamid
OrgPlus Enterprise | Orgplus | Retired | Human Resources Organization Charting Tool | Human Resources | Tjebbes Feenstra | Steve Horgan | [7 empty] | External | [5 empty] | Unknown |  | Unassigned |  | Stephen.Horgan@smith-nephew.com
Ortho Data Warehouse Discoverer Reporting | DataHub | Retired | BI Reporting Tool (used by Ortho only) (aka DataHub) | Data & Analytics | Chris Cook | Tomasz Fijalkowski | [7 empty] | Limited | [5 empty] | Unknown | 40178.375 | Unassigned |  | Tomasz.Fijalkowski@smith-nephew.com
Pilgrim SmartSolve Training (ARTC) | Pilgrim SmartSolve (ArthroCare) | Retired | 1/12/16 - Changing name of system back to original: "Pilgrim SmartSolve (ARTC)". The name was changed w/o approval and has caused confusion with Global Complaints. 12/16/2015 11:39 Hello Allena Could you do additional changes: • Primary support: is the Vendor (Pilgrim) • Business owner: Schilder Jaap Mit freundlichen Grüssen/Best regards Antoine d'Overschie 12/16/2015 :Dear Service Desk Team Would you please • Change the CI Pilgrim SmartSolve (ARTC) to Pilgrim SmartSolve Complaint Management • Change the delivery owner from David Gamble to Al Whitney Thank you very much for your support Mit freundlichen Grüssen/Best regards Antoine d'Overschie IT Business Analyst Smith & Nephew Orthopaedics AG Schachenallee 29 5001 Aarau Switzerland Training; 04/28/15 - David Gamble changed from "Critical" to "Very Important" | RAQA | Bob Watkins | Andres Bernard | [7 empty] | External | [5 empty] | Unknown | 41875.375 | Unassigned |  | Andres.Bernard@smith-nephew.com
Pro Check Plus | ACIS | Retired | Check writing - Manages the addition of the MICR codes to the check. Currently have ACIS, will upgrade to Pro Check Plus. Vendor is On-Pay. | 0 | Imtiaz Iqbal | Paul Davison | [7 empty] | Limited | [5 empty] | Unknown | 38352.375 | Unassigned |  | paul.davison@smith-nephew.com
QAD MFG/Pro | QAD MFG/Pro (ArthroCare) | Archive | Enterprise Resource Planning: It is still online to satisfy FDA requirements (it has to stay up for 17 years after being decommissioned). The only support option is to call a vendor (Progress). | Manufacturing | Manas Singha | Andres Bernard | [7 empty] | None | [5 empty] | Unknown | 40847.3333 | Tolerate |  | Andres.Bernard@smith-nephew.com | Firas Almahamid
QlikView | QV | Retired | Dashboard | Local | Bob Watkins | Massimo Trambaioli | [7 empty] | Partial | [5 empty] | Unknown | 41851.375 | Unassigned |  | Massimo.Trambaioli@smith-nephew.com
Rave EDC | Medidata Rave; Medidata RaveX; RaveX EDC; Rave; RaveX | Active | Manage and report on clinical studies | R&D | Sri Tupil | Matthew Stephens | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL |  | Not EOL | Windows 2016 | SQL 2016 | 8.0 (2012) | COTS | No | 43449.375 | Invest |  | Matthew.Stephens@smith-nephew.com | Sri Tupil
Regulatory Affairs | Regula | Active | This is use for Regulatory Submission. Hosted in Baar. | RAQA | Sri Tupil | Aileen Diola | EOL | EOL | EOL | EOL |  | Not EOL | Not EOL | None |  | Windows 2008R2 |  | 7.5 (2008R2) | Vendor Dev'ed | No | 40819.375 | Tolerate |  | Aileen.Diola@smith-nephew.com | Sri Tupil
RIM | RIM | Retired | Finacial Reporting | Local | Imtiaz Iqbal | Guoliang Wu | [7 empty] | None | [5 empty] | Unknown | 40544.375 | Unassigned |  | guoliang.wu@smith-nephew.com
SCMNet | SCMNet (ArthroCare) | Retired | Agile-SAP Interface | ASD (Advanced Surgical Devices) | Imtiaz Iqbal | Ramesh Balabhadruni | [7 empty] | External | [5 empty] | Unknown | 40543.375 | Unassigned |  | Ramesh.Balabhadruni@smith-nephew.com
Sentry -Active Synch Server | MDM - Mobile iron | Retired | MDM - Adminstration view of devices |  | Imtiaz Iqbal | Marianne Morton | [7 empty] | Limited | [5 empty] | Unknown | 41517.375 | Unassigned |  | Marianne.Morton@smith-nephew.com
SLS | TM1 SLS | Planned | Captures US intercompany sales and OCOGS | Data & Analytics | Stuart Robinson | Sathiamurthy Samidurai | [7 empty] | Partial | [5 empty] | No | 44038.375 | Invest |  | Sathiamurthy.Samidurai@smith-nephew.com | Stuart Robinson
SNI_Archive Service | Serrala ; Archival Factory Set up ; System Retirement Program ; Decommission ; | Active | Through Archiving service , the data and metadata of legacy applications will be archived to AWS cloud . Each archival data is associated with retention period based on the domain and country they belong to. Archived data can be retrieved as reports for reference purposes through the archival tool. | Enterprise Technology | Mateusz Kolenda | Piotr Jarosz | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial | Not EOL |  | Other DB |  | SaaS | No | 43862.375 | Tolerate |  | Piotr.Jarosz@smith-nephew.com | Anna Falbogowska
Spectrum 10 | Spectrum | Active | Spectroscopic data collection and analysis Name updated due to new release and configuration | RAQA | Sri Tupil | Aileen Diola | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Windows 2012 |  | 8.0 (2012) | COTS | No | 38352.375 | Tolerate |  | Aileen.Diola@smith-nephew.com | Sri Tupil
StoreHippo | AWM e-portal | Active | E-Commerce Portal along with E-Learning online application. Target audience for this application is HCP. This will provide access to large number of consultants and physicians as well mini-hospitals, nursing where we don't have direct reach through our existing sales team and channels. This application is goign to address two areas i.e E-Commerece and E-Learning as detailed below E-commerce: Ability to view and buy AWM / TWC products from a catalogue. MOQ / MOV based commercial transaction A safe and secured user-key enabled registration process and payment Gateway Purchase will be restricted only to a Registered Medical Practitioner (RMP) or a third party (healthcare institutions like nursing homes, hospitals, etc.) with a valid Drugs License. Analytics: Product enquiries and revenues, geographic / customer wise purchase and analysis, financial monitoring, back-end analytics. Registration of product complaints and connect with a central number for any queries / FAQs (during specified business hours) Education: Ability to view and complete module-based educational courses and wound management protocols (in algorithm formats) with therapy modalities, products and information, replete with images, videos, textual and interactive content Certificate issuance of completion of these Smith & Nephew courses This is expected to continue for a long time. | Commercial | Jerry Li | Malav Joshi | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL |  | Partial |  | Non windows | Other DB | No IIs | Vendor Developed | No | 43101.375 | Unassigned |  | Malav.Joshi@smith-nephew.com | Firas Almahamid
Syngistix | Winlab32 | Active | WinLab32 software/Syngistix is a COST system for iCP. The system comprises 3 locally installed WinLab32 applications across 3 networked desktop machines connected to iCP instrumentation. All 3 systems save GxP data to the Hull shared drive NLAMSSMAPPVW28. The iCP software is sued for laboratory testing of class 3 medical device products, intermediates and raw materials. The system captures and analyzes QC test data obtained from a connected laboratory instrument. | RAQA | Sri Tupil | Aileen Diola | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Windows 2012 | No DB | No IIs | COTS | No | 43191.375 | Invest |  | Aileen.Diola@smith-nephew.com | Sri Tupil
Teams | Cegedim | Retired | Sales CRM database for AWM Europe. SaaS and Desktop app.02/23/16 - Update from Sebastian and Hugo, this is retired. | 0 | Firas Almahamid | Alison Conlon | [7 empty] | Limited | [5 empty] | Unknown | 38352.375 | Unassigned |  | Alison.Conlon@smith-nephew.com
Theobald | Theobald/GCS Database | Retired | 03/31/16 - Al Whitney/Lucie do not provide any IT support for this application. The associated server was Unknown. After investigating software installed on the server, Lucie found Theobald, SQL Server, Oracle on the server. She also stated that she is sending files from Manugistics to this server for processing 2x daily but is not aware of what is being done with the files. She also stated that she has been told by the business owner that it is in use and must not be decommissioned. Additonal Information About DR: The server that Theobald resides upon is not part of the DR. It was going to be used for a custom piece of software that was not ever put into production. As long as there is nothing else on this server, it can be retired after Sudoku goes live. Lucie | Supply Chain | Bob Watkins | Amit Shokeen | [7 empty] | None | [5 empty] | Unknown | 39630.375 | Unassigned |  | Amit.Shokeen@smith-nephew.com
Trial Interactive eTMF | eTMF; TransPerfect | Active | This is a cots system that is used for Clinical studies document management The Product Vendor is TransPerfect | RAQA | Sri Tupil | Aileen Diola | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None |  | Windows 2019 | No DB | No IIs | SaaS | No | 42933.375 | Tolerate |  | Aileen.Diola@smith-nephew.com | Sri Tupil
Unified Functional Testing | UFT | Active | UFT provides regression testing functionality for application testers |  | Stuart Robinson | Sathiamurthy Samidurai | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL |  |  | Windows 2012 | No DB | 8.0 (2012) | COTS | No | 43439.375 | Tolerate |  | Sathiamurthy.Samidurai@smith-nephew.com | Stuart Robinson
VSP Virtual Smartphone Platform | MDM mobile Iron | Retired | MDM servcie for iDevices , phones, tablets |  | Imtiaz Iqbal | Marianne Morton | [7 empty] | Limited | [5 empty] | Unknown | 41517.375 | Unassigned |  | Marianne.Morton@smith-nephew.com
Webtop | DHR | Retired | DHR etc links to Documentum. General support is routed to business owner | ASD (Advanced Surgical Devices) | Mark Towne | Ramesh Balabhadruni | [7 empty] | Limited | [5 empty] | Unknown | 39447.375 | Unassigned |  | Ramesh.Balabhadruni@smith-nephew.com
Woolloo Content Management Solution | Woolloo | Active | Brand Transforming App to managent marketing Assets | Commercial | Jerry Li | Sathiamurthy Samidurai | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | EOL | Not EOL | Partial |  |  |  | No IIs | COTS | No | 41851.375 | Migrate |  | Sathiamurthy.Samidurai@smith-nephew.com | Stuart Robinson
Worksoft Certify | Worksoft Certify (ArthroCare) | Retired | Automated Testing | ASD (Advanced Surgical Devices) | Imtiaz Iqbal | David Gamble | [7 empty] | External | [5 empty] | Unknown |  | Unassigned |  | David.Gamble@smith-nephew.com
Adobe iCloud | Adobe Creative | Archive | CLOUD Version of the Desk Top app; Designer Software: PDF edit/creation/photoshop etc | Enterprise Technology | Anna Falbogowska | Andres Bernard | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None |  | Non windows | Other DB | No IIs | COTS | No | 42004.375 | Tolerate | To SaaS | Andres.Bernard@smith-nephew.com | Firas Almahamid
BPCS - European HUB | DISLIVE | Retired | ERP Application for European Sales and Marketing sites, including: Denmark, Sweden, Norway, Italy and France (Le Mans and Courbevoie). ARCHIVED DATA ONLY - as of Q2 2015. | ERP | Philip Sedgwick | Paul Davison | EOL | EOL | EOL | EOL | EOL | EOL | EOL | None | Not EOL | Non windows | Other DB | No IIs | SNI dev'ed | Yes | 35194.375 | Eliminate | Cannot go cloud | paul.davison@smith-nephew.com
BPCS - Gilberdyke Extruded Films | MANLIVE | Retired | ERP Application for Gilberdyke Extruded Films Manufacturing. Product Vendor Support= UNSUPPORTED Delivery Manager CERT=22JUN17 Extruded Films BPCS moved onto SAP Dec 2016. Now only used for inquiry. Reduced criticality to Low. | ERP | Philip Sedgwick | Paul Davison | EOL | EOL | EOL | EOL | EOL | EOL | EOL | None | Not EOL | Non windows | Other DB | No IIs | SNI dev'ed | Yes | 34262.3333 | Eliminate | Cannot go cloud | paul.davison@smith-nephew.com
BPCS - Hull | MANLIVE | Retired | ERP Application for Hull AWM Manufacturing. | ERP | Philip Sedgwick | Paul Davison | EOL | EOL | EOL | EOL | EOL | EOL | EOL | None | Not EOL | Non windows | Other DB | No IIs | SNI dev'ed | Yes | 35493.375 | Eliminate | Cannot go cloud | paul.davison@smith-nephew.com
e-MANPOWER | eMANPOWER | Retired | Payroll application for S&N Greece Support Vendor=Singularlogic SA Product Vendor Support=Supported Acquition Source= Plus Orthopedics | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None |  | Windows 2016 | SQL 2017 | No IIs | COTS | No | 39768.375 | Eliminate | Rehost (L&S) | paul.davison@smith-nephew.com
ExactMAX | MAX | Archive | Bluebelt INVENTORY MANAGEMENT AND MOVEMENT | ERP | Massimo Trambaioli | Amit Shokeen | Not EOL | EOL | EOL | EOL | EOL | EOL | EOL | None |  | Windows 2008R2 | SQL 2008R2 | 7.5 (2008R2) | COTS |  | 43109.375 | Eliminate | Unknown | Amit.Shokeen@smith-nephew.com | Massimo Trambaioli
Fax to EDI - Order 2 Cash | Seeburger | Retired | Currently in AWM, Germany only ITLT Cert: 26-MAY-17 | Supply Chain | Jacek Karas | Pablo Iradier | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial |  | Non windows | No DB | No IIs | SaaS | Unknown | 41804.375 | Invest | To SaaS | Pablo.Iradier@smith-nephew.com
Optiqs360 | Global Q | Planned | Optimized User Interface while interacting with data from multiple systems such as PLM, QMS and SAP. Serve as a synopsis engine for data across multiple systems including Device Master Record, consolidated from multiple systems. | R&D | Ian Bennett | Matthew Stephens | [7 empty] | Partial | [5 empty] | No | 44165.375 | Invest | Replatform | Matthew.Stephens@smith-nephew.com | Sri Tupil
BPCS - Spain (Barcelona) | BAAS400 | Active | ERP Application. 01/19/16 - Per Alison, replaced by EPO but is still available for 20 years for historical reference. Reducing criticality. | ERP | Philip Sedgwick | Paul Davison | EOL | EOL | EOL | EOL | EOL | EOL | EOL | None | Not EOL | Non windows | Other DB | No IIs | SNI dev'ed | Yes | 38352.375 | Eliminate | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
BPCS - St Pete | WMD400 | Active | ERP Application for St Pete AWM. 10/1/2015 - Confirmed with Paul Davison - as of 2010, this application is no longer validated (GxP=N). Product Vendor Support = UNSUPPORTED Delivery Manager Cert: 22JUN17 ITLT Cert:26-JUN-17 St Pete BPCS moved onto SAP Sep 2017. Now only used for inquiry. Reduced criticality to Low. | ERP | Philip Sedgwick | Paul Davison | EOL | EOL | EOL | EOL | EOL | EOL | EOL | None | Not EOL | Non windows | Other DB | No IIs | SNI dev'ed | Yes | 38352.375 | Eliminate | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
EasyKit | RFID EasyKit | Active | RFID system | Supply Chain | Manas Singha | Amit Shokeen | EOL | EOL | EOL | EOL | Not EOL | Not EOL | Unknown | None |  | Windows 2008 | SQL 2012 | 7.0 (2008) | COTS | Unknown | 36891.375 | Tolerate | Cannot go cloud | Amit.Shokeen@smith-nephew.com | Massimo Trambaioli
EnterprizeBiz | EBIZ | Active | Application used for Sales, Purchase, Inventory and QA. Acquistion Source=Clariance | ERP | Massimo Trambaioli | Sushant Pawar | Not EOL | EOL | Unknown | Unknown | EOL | Not EOL | Unknown | Partial |  | Pre Windows 2003 | SQL 2000 | No IIs | Vendor Dev'ed | Unknown | 36982.4167 | Migrate | Unknown | Sushant.Pawar@smith-nephew.com | Massimo Trambaioli
EPO 4.6 (Solidcore only) | EPO; Solidcore | Active | Solidcore locks down any changes to all files on older legacy systems that no longer receive patching | Infosec | Jody Jenkins | Paul Funk | EOL | EOL | EOL | EOL | EOL | EOL | EOL | Partial | EOL | Windows 2008R2 | SQL 2008 | 7.0 (2008) | Vendor Dev'ed | Yes | 41278.375 | Eliminate | Unknown |  | Lawrence Zorio
Fishbowl | Fishbowl | Active | Inventory Management –Tracks all components, WIP, FG, & Field Inventory. Lot, revision, and expiration date traceability. -ACQ SOURCE: ROTATION MEDICAL | ERP | Manas Singha | Amit Shokeen | EOL | EOL | EOL | EOL | EOL | EOL | EOL | Partial |  | Windows 2008 | SQL 2008R2 | 7.0 (2008) | COTS | Unknown | 41275.375 | Tolerate | Go to DataCenter as a Service | Amit.Shokeen@smith-nephew.com | Massimo Trambaioli
Medical Education Logistics (KLEOS) | KLEOS | Active | Medical Education Logistics EMEA | Commercial | Manish Sahay | Andres Bernard | EOL | EOL | EOL | EOL | EOL | EOL | EOL | None | EOL | Windows 2003 | Other DB | Unknown | COTS | Yes | 44084.375 | Unassigned | Rehost (L&S) | Andres.Bernard@smith-nephew.com | Firas Almahamid
PRMS - Canada | MOAS400, MOAS400-170 | Active | ERP Application for Canada AWM. ITLT Cert: 26-MAY-17 Product Vendor Support=UNSUPPORTED Delivery Manager CERT=22JUN17 Canada PRMS moved onto SAP Sep 2017. Now only used for inquiry. Reduced criticality to Low. | ERP | Philip Sedgwick | Paul Davison | EOL | EOL | EOL | EOL | EOL | EOL | EOL | None | Not EOL | Non windows | Other DB | No IIs | SNI dev'ed | Yes | 35430.375 | Eliminate | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
1099-ETC | 1099 forms | Active | Create 1099 forms to vendors. Standalone desktop application used on 2 desktop computers: Frankie Brooks has one, using the 1042 module, Eddie Dearborn has another and uses the 1099 module. A new version is purchased each year. | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Non windows | No DB | No IIs | COTS | No | 38352.375 | Tolerate | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
1C | 1C Moscow | Active | ERP Platform for Russia Product Vendor Support=Supported Support Knowledge=25% System Doucmentation=0% Maint Agreement=Yes Delivery Manager Cert: 22JUN17 | ERP | Massimo Trambaioli | Amit Shokeen | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial | Not EOL | Windows 2012 | SQL 2012 | 7.0 (2008) | Vendor Dev'ed | No | 40543.375 | Tolerate | Cannot go cloud | Amit.Shokeen@smith-nephew.com | Massimo Trambaioli
3CLogic Cloud Contact Center | ServiceNow | Active | Advanced CTI integration with 3CLogic's Cloud Communications Platform. Providing cloud based telephony platform which integrates seamlessly with ServiceNow. It includes caller identification, call transfer and recording and metrics reporting. | IT | Dave Cranny | Terance Lindof | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial |  | Non windows | Other DB | No IIs | SaaS | No | 43739.375 | Invest | To SaaS | Terance.Lindof@smith-nephew.com
ADP Adjustmate | ADP Payroll | Active | Payroll software (Adjustments). Manual Cheque writing for ADP used for adjustments to payroll after the payroll run | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Non windows | No DB | No IIs | SaaS | No | 40816.375 | Migrate | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
ADP Connect | ADP interface, Payroll | Active | Interface application to map SAP to ADP Payforce application | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Non windows | No DB | No IIs | SaaS | No | 40543.375 | Migrate | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
ADP Payforce | ADP Payroll | Active | Payroll software (main payroll)- SaaS | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Non windows | No DB | No IIs | SaaS | No | 40908.375 | Migrate | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
ADP UK | ADP Payroll | Active | Payroll software (main payroll). SaaS | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Non windows | No DB | No IIs | SaaS | No | 38352.375 | Migrate | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
Ancile uPerform | RWD - Infopak | Active | Training Development tool for SAP. uPerform has been used extensively since 2006 (when it was a prior application called Infopak). It is a completely different type of tool than Learncenter. There are great synergies between the two but they are very different. uPerform at the highest level is a documentation creation tool that allows SMEs to record training documentation - effectively reducing/eliminating the requirement to have consultants or specialized training developers to create documentation. Once the documentation is created using the desktop application by the authors, the resulting documentation can be published to uPerform's End User website. Anyone who is on the SN network has visibility to the documentation. One work instruction document created by an author creates multiple outputs: html based, pdf, and a html-based simulation. One document with multiple outputs. In addition to transactional-based documentation, uPerform also offers the development of a document output called a Course. These are similar to "powerpoint" type courses that can contain embedded simulations with the option to include a knowledge check as well. It is a very robust application and has been used for all NAPO/EPO/GPO implementations as well as multiple training reference materials for many other areas - Ortho's Customer Service for example has all our training reference materials stored there. | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial | Not EOL | Windows 2012 | SQL 2014 | No IIs | COTS | No | 40209.375 | Tolerate | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
Application Life Cycle Management (ALM) | Quality Centre, HPQC, ALM | Active | Requirements Management, Test Management, Defect Management. This is being migrated to the AWS cloud. Server details as follows: 1. DEV_APP - 10.30.153.93 - EC2AMAZ-E74ECST.us-east-2.snicloud.net 2. DEV_SQL - 10.30.152.143 - EC2AMAZ-OEQSPFR.us-east-2.snicloud.net 3. PROD_APP - 10.30.121.20 - EC2AMAZ-L0V6FUQ.us-east-2.snicloud.net 4. PROD_SQL - 10.30.120.204 - EC2AMAZ-S02NVQU.us-east-2.snicloud.net | Group Functions | Lois Spencer | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial | Not EOL | Windows 2016 | SQL 2016 | No IIs | COTS | No | 38352.375 | Invest | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
Ariba | Ariba on demand, Ariba Spend Management, Procurement Transformation | Active | Global Indirect Procurement Operations | Procurement | Jacek Karas | Krzysztof Gaik | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial | Not EOL | Non windows | Other DB | No IIs | SaaS | No | 42982.375 | Invest | Cannot go cloud | Krzysztof.Gaik@smith-nephew.com | Massimo Trambaioli
ASSIST4 | Assist | Active | Customs Clearance | Supply Chain | Manas Singha | Yvonne Braun | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial |  | Windows 2012 | SQL 2012 | 8.0 (2012) | COTS | No | 38352.375 | Unassigned | To SaaS | Yvonne.Braun@smith-nephew.com | Massimo Trambaioli
Bartender(OSIRIS) | Bartender | Active | Barcoding Software | RAQA | Derek Spillane | Jacob Goitom | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial |  | Windows 2008R2 | Other DB | No IIs | COTS | Unknown |  | Tolerate | Rehost (L&S) | Jacob.Goitom@smith-nephew.com | Chris Cook
BizTalk OneButton (Switzerland) | OneButton, OneClick | Active | Business process management (BPM) software; 07/15 - Upgraded from Important to Critical by Randall. | ERP | Massimo Trambaioli | Antoine d'Overschie | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None |  | Windows 2008R2 | SQL 2008R2 | No IIs | Vendor Dev'ed | Unknown | 39083.375 | Tolerate | Unknown | Antoine.doverschie@smith-nephew.com | Massimo Trambaioli
Carlson Wagonlit Travel | CWT | Active | Went in as part of the Concur project; Steve Horgan and Mark Tompkins. Integrated with SecureAuth. | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Non windows | Other DB | No IIs | SaaS | No | 42395.375 | Tolerate | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
CCH | CCH Central | Active | Accounts production software used to produce UK (and Ireland) subsidiary statutory accounts for filing at Companies House as well as tagged accounts for HMRC. Main times of use is March to November. | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial | Not EOL | Windows 2016 | SQL 2016 | No IIs | COTS | No | 43881.375 | Tolerate | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
Centris | HCP Engagement Platform | Active | An end-to-end HCP engagement process and workflow based solution, to manage S+N's engagin with HCPs as faculties / experts as well as managing grants programs; including compliance reporting and effectiveness | Commercial | Manish Sahay | Andres Bernard | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial | Not EOL |  |  |  | SaaS | No | 44005.375 | Unassigned | Cannot go cloud | Andres.Bernard@smith-nephew.com | Firas Almahamid
Cognos (STRATPLAN) | TM1 Strategic Planning | Active | TM1 Strategic Planning Application | Data & Analytics | Stuart Robinson | Sathiamurthy Samidurai | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial |  | Windows 2016 | No DB | No IIs | SNI dev'ed | No | 43287.375 | Invest | Replatform | Sathiamurthy.Samidurai@smith-nephew.com | Stuart Robinson
Cognos Performance Mgmt (STGP) | TM1, STGP | Active | STGP and RUBIK are the new Sales Reporting using Cognos BI front-end using Cognos TM1 data source; 03/03/15 - Merging the "Cognos TM1" entry into this entry. ITLT Cert:26-JUN-17 | Data & Analytics | Stuart Robinson | Sathiamurthy Samidurai | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial |  | Windows 2016 | No DB | No IIs | SNI dev'ed | No | 41966.375 | Invest | Replatform | Sathiamurthy.Samidurai@smith-nephew.com | Stuart Robinson
CVS Concurrent Version System | CVS | Active | Bluebelt "Source code for product software development is maintained in CVS. CVS provides configuration management for source-code files for Navio Implant Databases and the Navio System (GUI) Language Pack. Used for Navio Product Development" | R&D | Ian Bennett | Matthew Stephens | Not EOL | EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial | Not EOL | Non windows | Other DB | No IIs | COTS | Yes | 41640.375 | Migrate | Rearchitect | Matthew.Stephens@smith-nephew.com | Sri Tupil
EdgeTRAC | "Tracelink (RocIT) Serialization Edge Solution" | Active | EdgeTRAC performs Shipment Verification edits against Delivery Orders and associates scanned/read serialized container data with Delivery Orders. EdgeTRAC transmits a shipment transaction to TraceLink to associate Unique Identifiers with Delivery/Sales Order Numbers | Supply Chain | Manas Singha | Amit Shokeen | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Windows 2012 | No DB | 8.0 (2012) | COTS | No | 43039.3333 | Tolerate | Unknown | Amit.Shokeen@smith-nephew.com | Massimo Trambaioli
Edicom | Edicom | Active | Certify invoices and distribute them to customers | Supply Chain | Firas Almahamid | Eduardo Lima | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial |  | Windows 2019 | Other DB | No IIs | COTS | No | 43150.375 | Tolerate | Rehost (L&S) | Eduardo.Lima@smith-nephew.com | Firas Almahamid
ESKER Accounts Payable | AP Automation | Active | ESKER Accounts Payable is a SaaS application used globally for the processsing of invoices sent by vendors. For DR and BCP, from Jairus Harper @ Esker: "We do have a business continuity plan as well as a Disaster Recovery plan that in a worst case scenario situation Esker would trigger. Per our Chief Counsel, BOD, and Auditors we are not allowed to share this information with customers." However, see attached documents - SOC2, EoDSecurity which contain some of this information. | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Non windows | Other DB | No IIs | SaaS | No | 43128.375 | Invest | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
EXNGN | EX | Active | ADLER ERP application for Logistics, Warehouse Management, Sales, Procurement & Finance transaction. Used in Ratnagiri & GBS Pune Location. Supported by Local IT Team (Anuradha Soorkottula & Priyanka Shinde). | ERP | Massimo Trambaioli | Sushant Pawar | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None |  | Non windows | Other DB | No IIs | SaaS | No | 36617.4167 | Tolerate | Cannot go cloud | Sushant.Pawar@smith-nephew.com | Massimo Trambaioli
Finance Approval Portal | Appian, eForms | Active | This application provides a workflow for the request, approval and processing of Finance related approval requests. DR Info: RTO and RPO is 15 mins. RTO does not allow that entry in CMDB. | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial | Not EOL | Non windows | Other DB | No IIs | SaaS | No | 43512.375 | Invest | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
Gemalto Classic Client Toolbox | Gemalto Card Reader Software | Active | Provides protection in accessing and managing secure, cloud-based, online filing of IP data. "It is used by our legal dept here in Hull by 1 person. IT does not have anything to do it or support it." Gemalto Classic Client Toolbox is used to provide protection in accessing and managing secure, cloud-based, online filing of IP data. It is on a single PC used by legal in Hull. | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Non windows | No DB | No IIs | SaaS | No | 42370.375 | Tolerate | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
Git Version control | Git | Active | Git Version control is used to maintain source code for product software development. Git provides configuration management for source code files used to develop Navio product software. | R&D | Ian Bennett | Matthew Stephens | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial | Not EOL | Non windows | Other DB | No IIs | COTS | No | 41640.375 | Migrate | Rearchitect | Matthew.Stephens@smith-nephew.com | Sri Tupil
Grand Avenue | Grand Avenue | Active | Rotation Medical Quality Management System | RAQA | Sri Tupil | Aileen Diola | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Windows 2012 | SQL 2012 | 8.0 (2012) | SaaS | No | 43084.375 | Tolerate | To SaaS | Aileen.Diola@smith-nephew.com | Sri Tupil
GSC Data Warehouse Admin Tool | Nomino | Active | Web-based admin screens to allow Global Supply Chain users to manage elements of the data in the Data Warehouse. Arlene has documentation from Paul Davison. | Data & Analytics | Manas Singha | Amit Shokeen | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial |  | Windows 2012 | SQL 2012 | 8.0 (2012) | SNI dev'ed | Unknown | 37621.375 | Tolerate | Rehost (L&S) | Amit.Shokeen@smith-nephew.com | Massimo Trambaioli
Hyperion Enterprise | Hyperion Enterprise SE, Hyperion Enterprise 6.4 | Active | US Financial Consolidation Reporting, used in Memphis. | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial | Not EOL | Non windows | No DB | No IIs | COTS | No | 42219.375 | Migrate | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
iDeal (Tender Registry) | Tender Registry System | Active | Hosted Website to enter, schedule, manage answers to tenders opportunities for AWM European markets. Feb, 2016 - Added support for ASD (EU, CAN, UK). Hosted at UK-ENG-Stevenage with DR at UK-ENG-Welwyn Garden. ITLT Cert: 26-MAY-17 Delivery Manager Cert: 14-JUN-17 | Commercial |  | Andres Bernard | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None |  |  |  |  | SaaS | No | 41597.375 | Tolerate | To SaaS | Andres.Bernard@smith-nephew.com | Firas Almahamid
IT2 | Treasury Solutions | Active | Treasury Software used by Treasury Department only in GHO. Urgent to resolve as processing very large amounts of cash usually within tight deadlines. Product Vendor Support=Supported Delivery Manager Cert=22JUN17 ITLT Cert:26-JUN-17 | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial | Not EOL | Windows 2012 | SQL 2008R2 | 8.0 (2012) | COTS | No | 41274.375 | Invest | Rehost (L&S) | paul.davison@smith-nephew.com | Chris Cook
Madison Rewards | GEM | Active | HR application; Integrated with SecureAuth. | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Non windows | Other DB | No IIs | SaaS | No | 42395.375 | Tolerate | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
Marketing Materials Management (ORBIS) | MRM ORBIS | Active | Marketing Materials Management and Approval. 12/22/15 - Per Mark Towne, Richard is the Delivery/Support Manager for this solution. ITLT Cert: 26-MAY-17 Delivery manager cert: 14-JUN-17 >October 2020: Upgraded October 16, 2020 from 18.4 to 20.3 . - Andres | Commercial | Manish Sahay | Andres Bernard | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None |  |  |  |  | SaaS | No | 41275.375 | Tolerate | To SaaS | Andres.Bernard@smith-nephew.com | Firas Almahamid
Metafile | Metaviewer | Active | Optical Data storage system. Sometimes referred to as 'Metaviewer' - client access application. | Group Functions | Philip Sedgwick | Paul Davison | EOL | EOL | EOL | Not EOL | EOL | EOL | Not EOL | None | EOL | Windows 2003 | SQL 2005 | 6.0 (2003) | COTS | Yes | 37986.375 | Eliminate | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
Metasys | Metasys | Active | The Metasys System controls the complete site. That include the Air Handler Units, Temperature Control and monitoring, Pressure Control and monitoring(Manufacturing Rooms), Humidity monitoring, Chillers, Boiler, etc. Manages the connection and oversite of the manufacturing equipment utilized in our Ft Worth manufacturing plant. | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Windows 2016 | SQL 2016 | No IIs | COTS | No | 43531.375 | Tolerate | Unknown | paul.davison@smith-nephew.com | Chris Cook
MODA | MODA | Active | Paperless environmental monitoring and data collection / management system used to track and trend data in our QC labs. | RAQA | Sri Tupil | Aileen Diola | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial |  | Windows 2012 | SQL 2012 | 8.0 (2012) | Vendor Dev'ed | No | 43281.375 | Invest | Rearchitect | Aileen.Diola@smith-nephew.com | Sri Tupil
MyConnect (AWM CRM - US) | Cegedim MI Touch; Mobile Intelligence; Insights | Active | CRM call reporting, product placed information, and sales forecast by account. Product Vendor Support Level=supported Delivery Manager Cert: 22-JUN-17 ITLT Cert:26-JUN-17 June 1, 2020: Insights (what we refer to it as) has its own login maintained inside the app and there is no authentication at all to the S&N network. We are working to replace Insights with SalesForce.com with a planned pilot in October and go-live in Feb 2021 so this is on the application to be retired list. | Commercial | Manish Sahay | Andres Bernard | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial |  |  |  |  | SaaS | No | 41732.375 | Tolerate | To SaaS | Andres.Bernard@smith-nephew.com | Firas Almahamid
Navigate | SABA LMS | Active | SaaS LMS platform to manage sales force training globally | Commercial | Manish Sahay | Andres Bernard | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial |  |  |  |  | SaaS | No | 43419.375 | Invest | To SaaS | Andres.Bernard@smith-nephew.com | Firas Almahamid
Nomina APSI-Sistemas | Nomina | Active | Local Payroll in Mexico | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial | Not EOL | Windows 2016 | No DB | No IIs | COTS | No | 43150.375 | Migrate | Unknown | paul.davison@smith-nephew.com | Chris Cook
OEE | Overall Equipment Effectiveness, Overall Equipment Efficiency | Active | Virtulized | Manufacturing | Derek Spillane | Carla Morris | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial |  | Windows 2012 | SQL 2012 | 8.0 (2012) | COTS | No | 38352.375 | Tolerate | Cannot go cloud | Carla.Morris@smith-nephew.com | Derek Spillane
OLMEC - UDI Printing | OLMEC | Active | Server authenticates user AD accounts to allow access to the OLMEC UDI Printing software | R&D | Ian Bennett | Matthew Stephens | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Non windows | No DB | 8.0 (2012) | COTS | Unknown | 43312.375 | Tolerate | Cannot go cloud | Matthew.Stephens@smith-nephew.com | Sri Tupil
Oracle Hyperion | Oracle Hyperion (ArthroCare), ESSBASE, | Active | Financial reporting aka. ESSBASE. Ex-ARTC application. Web URL: http://dfwshy00.sncorp.smith-nephew.com:28080/interop/ | Group Functions | Philip Sedgwick | Paul Davison | EOL | EOL | EOL | Not EOL | EOL | EOL | Not EOL | Partial | EOL | Windows 2008R2 | SQL 2005 | 7.5 (2008R2) | COTS | Yes | 42036.375 | Migrate | Rehost (L&S) | paul.davison@smith-nephew.com | Chris Cook
Paymetric Application System | PAS | Active | Credit Card Authorization processing interfaced with SAP EPR and PRD system. 12/1/15 - Paul Wilson requested delivery manager - was set to Tauseef. | ERP | Jacek Karas | Pablo Iradier | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial |  | Windows 2008R2 | No DB | No IIs | COTS | No | 38352.375 | Invest | Replatform | Pablo.Iradier@smith-nephew.com | Massimo Trambaioli
Payroll - Softland (Colombia) | Softland ERP nomina, Softland ERP payroll, nomina, payroll | Active | Payroll Calculations, Deductions, Payments. Client (accessed through RDP) for administrators; Web interface for ~180 employees to access wage statements. | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Windows 2016 | SQL 2016 | No IIs | COTS | No | 42418.375 | Migrate | Rehost (L&S) | paul.davison@smith-nephew.com | Chris Cook
Payroll ADP Interface | ADP interface, Payroll | Active | Interface to G/L only - not an app. Outsourced to ADP | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Non windows | No DB | No IIs | SaaS | No | 38352.375 | Migrate | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
Process Data Collection | PDC; Process Data | Active | Business Only Application - No IT support - Process Network - Connects equipment PLCs to a central database for traceability / reporting. The hardware has not been received yet so the CIs cannot be put in place. | Manufacturing | Derek Spillane | Carla Morris | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial | Not EOL | Unknown | Unknown |  | COTS | No | 43220.375 | Tolerate | Cannot go cloud | Carla.Morris@smith-nephew.com | Derek Spillane
PTC Creo | PRO/E | Active | Bluebelt Used to generate the 3 dimensional models of our products. These 3d model are then converted to two dimensional prints within Creo and exported as ODSs and .STEP files. These documents become part of the Design History file. | R&D | Ian Bennett | Matthew Stephens | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial | Not EOL | Windows 2012 | No DB | No IIs | COTS | No | 41640.375 | Tolerate | Replatform | Matthew.Stephens@smith-nephew.com | Sri Tupil
Pulse (CRM - EUCAN) | Mobile Intelligence; Cegedim CRM | Active | CRM system for AWM EU - only being deployed in Germany at this time ITLT Cert: 26-MAY-17 Product Vendor Support Level=Supported Delivery Manager Cert:14-JUN-17 | Commercial | Manish Sahay | Andres Bernard | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial | [5 empty] | No | 41812.375 | Migrate | To SaaS | Andres.Bernard@smith-nephew.com | Firas Almahamid
QuickBooks (BBT) | Donnelly-Boland | Active | Bluebelt. Used to record and manage indirect spend. Manual GL journals only. Bank account being closed down. Currently, data is maintained for purposes to be in sync with PRA and Invoicing. | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Non windows | Other DB | No IIs | SaaS | No | 42577.375 | Eliminate | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
QuickBooks (RM) | Donnelly-Boland | Active | Rotation Medical. Customer Invoicing, AP/AR - Financial Reporting | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Non windows | Other DB | No IIs | SaaS | No | 43084.375 | Tolerate | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
Recon LaunchPad (SSO) | Authentication Service | Active | Used by Memphis and Aarau. The application basically provides single sign-on functionality by redirecting the users to another web site passing the user credentials to authenticate to the web site. | Commercial | Manish Sahay | Andres Bernard | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial |  | Windows 2012 |  | 8.0 (2012) | SNI dev'ed | No | 42217.375 | Tolerate | Rehost (L&S) | Andres.Bernard@smith-nephew.com | Firas Almahamid
RICOH E-Invoice | Costa Rica e-Invoice Solution | Active | Satisfies Costa Rica Ministry of Finance legal requirement to route all S&N supplier and commercial invoices through their tax authority prior to issuing the invoice for payment or receipt. | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Non windows | Other DB | No IIs | SaaS | No | 43346.375 | Tolerate | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
SAGE VIP | Payroll | Active | South Africa Payroll system | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | EOL | EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial | Not EOL | Windows 2008R2 | No DB | 7.5 (2008R2) | COTS | Yes | 42005.375 | Invest | Replatform | paul.davison@smith-nephew.com | Chris Cook
Salesforce (BBT) | Salesforce.com | Active | Customer Relationship Management system for capital sales process, replenishment orders, capital service management, deployed system management. BlueBelt acquisition. Includes DrawLoop software - a PDF plug-in, supported Internet Creation. 07/27/16 - Details for this entry submitted by Amit. | Commercial | Manish Sahay | Andres Bernard | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None |  |  |  |  | SaaS | No | 40210.375 | Migrate | To SaaS | Andres.Bernard@smith-nephew.com | Firas Almahamid
Salient | Sales Incentive Compensation Reporting | Active | Salient calculates sales incentive compensation for the US Sports Med and ENT sales forces based upon actual sales data, and business rules managed by Finance. | Commercial | Manish Sahay | Andres Bernard | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial |  | Windows 2016 | SQL 2012 | 8.0 (2012) | Vendor Dev'ed | No | 43009.375 | Tolerate | Rehost (L&S) | Andres.Bernard@smith-nephew.com | Firas Almahamid
SAP Fieldglass | Fieldglass | Active | Contingent labor recruiting and expense tracking. | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Non windows | Other DB | No IIs | SaaS | No | 42248.375 | Tolerate | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
Schilling Cost Accounting | Schilling; Cost Accounting; Fixed Assets; Kostenrechnung; Anlagenbuchhaltung; Anbu; Comarch | Active | Cost Accounting and Fixed Assets application | Group Functions | Philip Sedgwick | Paul Davison | EOL | EOL | Not EOL | Not EOL | EOL | Not EOL | Not EOL | Partial | Not EOL | Non windows | Other DB | No IIs | COTS | Yes | 43101.375 | Tolerate | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
Skillsoft (Percipio) | Corporate Learning & Development | Active | Corporate Learning / Development | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Non windows | No DB | No IIs | SaaS | No | 38964.375 | Invest | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
Smart eHL | eHL, T&A, time and attendance | Active | Time and Attendance Hull; this vendor was acquired by Kronos. | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | EOL | Not EOL | Partial | EOL | Windows 2008R2 | SQL 2008 | 7.5 (2008R2) | COTS | Yes | 37256.375 | Migrate | Rehost (L&S) | paul.davison@smith-nephew.com | Chris Cook
Strategic Worldwide Assessment Tool (SWAT) | SteepRock, SWAT | Active | Needs assesment management Db. Service is paid for by global compliance. HCP Payments/Compliance. | Commercial | Manish Sahay | Andres Bernard | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None |  | Non windows | Other DB | No IIs | SaaS | No | 38352.375 | Tolerate | Cannot go cloud | Andres.Bernard@smith-nephew.com | Firas Almahamid
Sunshine/NPI Data | NUC360, OneKey | Active | HCP MDM system with HCP Search functionality for OneKey. | Commercial | Manish Sahay | Andres Bernard | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None |  | Non windows | Other DB | No IIs | SaaS | No | 40908.375 | Tolerate | Cannot go cloud | Andres.Bernard@smith-nephew.com | Firas Almahamid
SVN - Subversion Configuration Management | SVN | Active | Bluebelt "Binary product software is managed on the SVN. Used for Navio Product Development" | R&D | Ian Bennett | Matthew Stephens | Not EOL | EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial | Not EOL | Non windows | Other DB | No IIs | COTS | Yes | 41640.375 | Migrate | Rearchitect | Matthew.Stephens@smith-nephew.com | Sri Tupil
TeamMate | Internal Audit | Active | Internal Audit software. Moved to SaaS solution in 2018. Now used by Compliance as well as Internal Audit. Old TeamMate servers are kept in order to retrieve historical data. | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Non windows | Other DB | No IIs | SaaS | No | 41274.375 | Tolerate | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
TM1 (Global Cost Visibility) | TM1 GCV | Active | TM1 Global Cost Visibility Application | Data & Analytics | Stuart Robinson | Sathiamurthy Samidurai | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial |  | Windows 2016 | No DB | No IIs | SNI dev'ed | No |  | Invest | Replatform | Sathiamurthy.Samidurai@smith-nephew.com | Stuart Robinson
TM1 (Transfer Pricing) | TM1 TP | Active | TM1 Transfer Pricing Application | Data & Analytics | Stuart Robinson | Sathiamurthy Samidurai | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial |  | Windows 2016 | No DB | No IIs | SNI dev'ed | No |  | Invest | Replatform | Sathiamurthy.Samidurai@smith-nephew.com | Stuart Robinson
TreasuryXpress | BCS; Bank Communication System | Active | This SaaS tool acts as a middleware that receives payment files and delivers them to the banks and in reverse fetches bank statements from the banks and delivers to our ERPs. This is a key control making payments touchless through automation. DR info: RTO and RPO - 15 mins. | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Non windows | Other DB | No IIs | SaaS | No | 43998.375 | Invest | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
Trintech Cadency | Trintech; Cadency; Certification; PEC Tool | Active | This is a Period End Close tool which is used to carry out B/S reconciliations as part of the close controls in all countries. DR Info: RPO = 1 hour, RTO = 4 hours | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Non windows | Other DB | No IIs | SaaS | No | 43657.375 | Invest | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
TyMetrix | T360 | Active | eBilling - used by Legal PROD - http://tymetrixsso Staging - http://tymetrixssotest | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Non windows | Other DB | No IIs | SaaS | No | 40908.375 | Tolerate | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
VEI Label Verification | Label Verification | Active | Confirm the contents of the label match the shop order Support Vendor: Vision Engineering, INC. Who grants Access? Zach Wells: Zach.Wells@smith-nephew.com Tim Harrison: Tim.Harrison@smith-nephew.com | Manufacturing | Derek Spillane | Carla Morris | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial |  | Windows 2016 | SQL 2012 | No IIs | Vendor Dev'ed | Unknown | 43008.375 | Tolerate | Rearchitect | Carla.Morris@smith-nephew.com | Derek Spillane
Veritas | Rescop B.V. | Active | Validated Document Management System providing electronic signature capability being Piloted by PMO | Group Functions | Lois Spencer | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial | Not EOL | Non windows | No DB | No IIs | SaaS | No | 42186.375 | Tolerate | To SaaS | paul.davison@smith-nephew.com | Chris Cook
Vertex Sales & Use Tax Returns | Vertex | Active | Vertex Quantum Sales & Use Tax Returns. 05/09/16 - Updated name from "QUANTUM RETURNS" to "Vertex Sales & Use Tax Returns" per request/approval from Dorothy/Paul W. | ERP | Jacek Karas | Krzysztof Gaik | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial |  | Windows 2012 | SQL 2008 | No IIs | COTS | No | 38352.375 | Invest | To SaaS | Krzysztof.Gaik@smith-nephew.com | Massimo Trambaioli
VirginPulse | Max Pedometer Software, Virgin PulseÕs Sync Software, Virgin HealthMiles | Active | HealthMiles / GoZone iSync | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Non windows | Other DB | No IIs | SaaS | No | 41547.375 | Tolerate | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
Werma-Win | Werma; WermaWin | Active | Overview of machine status in a software control center | Supply Chain | Massimo Trambaioli | Amit Shokeen | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial | Not EOL | Windows 2012 | SQL 2012 | 8.0 (2012) | COTS | No | 42705.375 | Tolerate | Rehost (L&S) | Amit.Shokeen@smith-nephew.com | Massimo Trambaioli
Winflex | WinflexIPS | Active | DNC software. 01/20/16 - RTO, GxP - Updated from email request from Yvonne. | Manufacturing | Derek Spillane | Yvonne Braun | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Partial |  | Windows 2012 | No DB | 8.0 (2012) | COTS | No | 38352.375 | Unassigned | Unknown | Yvonne.Braun@smith-nephew.com | Massimo Trambaioli
Workday Human Capital Management | Workday | Active | Workday is a SaaS application to manage human capital management globally in S+N. It is supported internally by the HRIS team and is supported by external vendors. DR info: RPO = 1 hour, RTO = 12 hours | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | None | Not EOL | Non windows | Other DB | No IIs | SaaS | No | 41882.375 | Invest | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
Abacus | Payroll | Active | Payroll application HR | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | EOL | Not EOL | Not EOL | Not EOL | EOL | Not EOL | Full | EOL | Windows 2008R2 | Other DB | No IIs | COTS | Yes | 38352.375 | Migrate | Replatform | paul.davison@smith-nephew.com | Chris Cook
ADFS (Active Directory Federation Services) | ADFS | Active | End-user authentication services; Current: Exchange Online, InTune (Company Portal), Lync, Yammer, Sharepoint (Online and Compass) | Infosec | Jody Jenkins | Paul Funk | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2016 | SQL 2016 | 8.0 (2012) | COTS | No | 41591.375 | Unassigned | Unknown | paul.funk@smith-nephew.com | Lawrence Zorio
AlienVault SIEM | AlienVault SIEM | Retired | Analyse system logs to correlate threat events. | IT | Imtiaz Iqbal | Paul Funk | EOL | EOL | EOL | EOL | EOL | EOL | EOL | Full | EOL | Non windows | Other DB | No IIs | COTS | Yes | 43344.375 | Eliminate |  | paul.funk@smith-nephew.com
Authentication Service (SecureAuth) | SecureAuth; FIM; SSO; multifactor authentication/2 factor authentication | Active | End-user authentication services; provides authentication service for SN employees/contractors to applications internal and external (SaaS) solutions. It is the corporate solution for Single Sign On (SSO). Current: Authentication service for Remote Access, WorkDay Product Vendor Support = Supported Delivery Manager Cert: 26MAY17 ITLT Cert=19MAY17 | Infosec | Jody Jenkins | Paul Funk | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL |  |  |  | COTS | No | 40653.375 | Eliminate | Cannot go cloud | paul.funk@smith-nephew.com | Lawrence Zorio
AutoCAD | Powershape Powermill | Active | Facilities Drawings, manufacturing shop floor layouts; vendor supplied drawings and models for Case Development AUTODESK POWERSHAPE PREMIUM SUBSCRIPTION -- 3,280.00 AUTODESK POWERSHAPE PREMIUM SUBSCRIPTION -- 3,280.00 AUTODESK POWERMILL PREMIUM SUBSCRIPTIon -- 9,225.00 AUTODESK POWERMILL PREMIUM SUBSCRIPTION -- 9,225.00 AUTODESK POWERSHAPE PREMIUM SUBSCRIPTION -- 3,280.00 ANNUAL RENEWAL References S/N: 564-47864651 Expires: 6/19/2019 S/N:564-44606441 Expires: 6/10/2019 S/N: 564-44606342 Expires: 6/10/2019 S/N: 564-43092548 Expires: 6/7/2019 S/N: 564-43090172 Expires: 6/7/2019 | R&D | Ian Bennett | Matthew Stephens | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2008R2 | No DB | No IIs | COTS | No | 39813.375 | Invest | Replatform | Matthew.Stephens@smith-nephew.com | Sri Tupil
Automation Anywhere | AA, RPA, RPAAI | Active | Robotic Process Automation (RPA or RPAAI) software. | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2016 | SQL 2017 | No IIs | COTS | No | 43614.375 | Invest | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
AVON | RDP, Remote Access | Retired | Remote app for AVON users (Finance) - for HP remote access to local SW. | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2008R2 | No DB | No IIs | COTS | Yes | 38352.375 | Eliminate | Rehost (L&S) | paul.davison@smith-nephew.com
AZURE Backup | AZURE Backup | Active | Azure Backup service | Cloud | Mateusz Kolenda | Marek Laskowski | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Non windows | No DB | No IIs |  | No | 44105.375 | Unassigned |  | Marek.Laskowski@smith-nephew.com | Chris Cook
AZURE WAF | AZURE WAF | Active | A web application firewall is a specific form of application firewall that filters, monitors, and blocks HTTP traffic to and from a web service. | Cloud | Mateusz Kolenda | Marek Laskowski | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Non windows | No DB | No IIs | SaaS | No | 44105.375 | Unassigned |  | Marek.Laskowski@smith-nephew.com | Chris Cook
BackupExec | Backup Exec NetBackup | Active | Windows Backup | IT | Roman Wojtasik | Patryk Bromirski | EOL | EOL | Not EOL | Not EOL | EOL | EOL | EOL | Full | Not EOL | Windows 2003 | SQL 2005 | No IIs | Vendor Dev'ed | Yes | 38352.375 | Migrate | To SaaS | Patryk.Bromirski@smith-nephew.com | Anna Falbogowska
BI (CHINA) | BI, BIRS, MRS | Active | Local managerial reporting system | Data & Analytics | Jerry Li | Jinble Li | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2012 | SQL 2012 | No IIs | SNI dev'ed | No | 41456.375 | Invest | Rehost (L&S) | Jinble.Li@smith-nephew.com | Firas Almahamid
CISCO Umbrella | Umbrella | Active | Public DNS using Webfiltering. Proxy for internet browsing. Umbrella filters the traffic and blocks/whitelists sites. Has a deployed agent on end user compute Support vendor is Cisco | Infosec | Jody Jenkins | Paul Funk | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Non windows | Other DB | No IIs | SaaS | No | 42873.375 | Tolerate | Unknown |  | Lawrence Zorio
Concur GLIS | GLIS; General Ledger Information System | Active | Contains Standard Accounting Extract (SAE) and Attendee Detail Extract (ADE) data for the Concur T&E for general ledger activity. | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2012 | SQL 2012 | 8.0 (2012) | SNI dev'ed | No | 42109.375 | Invest | To SaaS | paul.davison@smith-nephew.com | Chris Cook
CONNECT | CONNECT portal, NPWT Portal, Pump CONNECT portal | Active | The portal allows External S&N Customers to access usage information reguarding the CONNECT NPWT pump from S&N. These devices are rented to patients, and the device reports back information related to it's use via AT&T's 3G machine to machine network. This usage information is then used for billing purposes. Engineering Contact: Allan Macrae in the UK | R&D | Ian Bennett | Matthew Stephens | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Non windows | Other DB | No IIs | Vendor Dev'ed | No | 42763.375 | Invest | Cannot go cloud | Matthew.Stephens@smith-nephew.com | Sri Tupil
Deepwatch | Deepwatch JumpBox | Active | These boxes will be used by our MSSP vendor Deepwatch for remote access to connect to our internal network. This is to do analysis on possible security issues, network lookup for security issues and general connections to be used by Engineers working for Deepwatch. | Infosec | Jody Jenkins | Paul Funk | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Non windows | No DB | No IIs | Vendor Dev'ed | No | 43132.375 | Eliminate | Unknown |  | Lawrence Zorio
DocuSign | DocuSign | Active | Electronic/digital signature service (Initially used with Ariba) | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Non windows | No DB | No IIs | SaaS | No | 42919.375 | Invest | To SaaS | paul.davison@smith-nephew.com | Chris Cook
DocuSign Part 11 | DocuSign Part 11 | Active | Electornic/digital signature compliant with 21 CFR Part 11 service (Initally validated with eTMF) | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Non windows | No DB | No IIs | SaaS | No | 42765.375 | Invest |  | paul.davison@smith-nephew.com | Chris Cook
ENCORE | (Lotus Notes) | Active | Web-based application to allow European markets to log their own complaints relating to product delivery - Dependent on A 305 | Supply Chain | Sri Tupil | Amit Shokeen | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2012 | SQL 2012 | 8.0 (2012) | Vendor Developed | No | 37621.375 | Unassigned |  | Amit.Shokeen@smith-nephew.com | Massimo Trambaioli
Exchange Online | Office 365 | Active | Cloud Based Messaging Environment; Note that this does not reflect the RTO requirement from the project team, set this to Critical<12 hrs b/c the published MS SLA is RTO:2 hrs, RPO:45 mins | Enterprise Technology | Jakub Keler | Ludwik Hreczycho | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Unknown | Unknown | No IIs | SaaS | No | 41665.375 | Unassigned | Cannot go cloud | Ludwik.Hreczycho@smith-nephew.com | Anna Falbogowska
FastPath | FastPath | Active | System Access Control (SAP and AX 2012) | ERP | Jacek Karas | Krzysztof Gaik | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2016 | Unknown | Unknown | SaaS | No | 43830.375 | Invest |  | Krzysztof.Gaik@smith-nephew.com | Massimo Trambaioli
FedEx Ship Manager (Client) | FedEx Cafe | Active | Shipment Manager. Client version, multiple instances of this product throughout the organization. | Supply Chain | Manas Singha | Amit Shokeen | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2012 | No DB | No IIs | Vendor Dev'ed | No | 38352.375 | Tolerate | To SaaS | Amit.Shokeen@smith-nephew.com | Massimo Trambaioli
FIS (Get Paid) | Get Paid | Active | Accounts Receivable Automation - Cash Application, Credit Management, Disputes and Collections Management | Commercial | Firas Almahamid | Santhosh Nair | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2019 | Windows 2012 | No IIs | SaaS | No | 44041.375 | Tolerate | To SaaS | Santhosh.Nair@smith-nephew.com | Firas Almahamid
Global Protect VPN | Global Protect | Active | Full VPN | Infosec | Jody Jenkins | Paul Funk | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Non windows | Other DB | No IIs | COTS | No | 43952.375 | Invest | Cannot go cloud | paul.funk@smith-nephew.com | Lawrence Zorio
HR Service Management | ServiceNow, SNOW, HRSM | Active | HR contact management system Changed DEL MGR from Steve to Richard Stinson Per Steve's approval - 22-sep-16 MCA | Group Functions | Dave Cranny | Terance Lindof | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Non windows | Other DB | No IIs | SaaS | No | 42430.375 | Invest | To SaaS | Terance.Lindof@smith-nephew.com
Hyperion GHO | HFM, GRS, SNHFM, EPM, Group Reporting System | Active | Financial Planning Software - used to submit data to GHO. PROD link: http://epm.sncorp.smith-nephew.com:19000/workspace/index.jsp. NOTE: Maintenance window for this application is 09:00-21:00 GMT Saturday (03:00-15:00 CST). Please schedule changes for this application within this timeframe. Any issues, contact Paul Davison. Product Vendor Support=Supported Delivery Manager Cert: 22JUN17 ITLT Cert:26-JUN-17 | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2008R2 | Other DB | 7.5 (2008R2) | COTS | Yes | 42219.375 | Invest | Repurchase | paul.davison@smith-nephew.com | Chris Cook
Internet Web Filter | Palo Alto URL Filtering | Active | This tool will help prevent malware and phishing attacks originating from the web and minimize risk during Internet browsing. | Infosec | Jody Jenkins | Paul Funk | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Non windows | Other DB | No IIs | SaaS | No | 41608.375 | Eliminate | Go to DataCenter as a Service |  | Lawrence Zorio
JIRA | Atlassian JIRA | Active | Jira is used for issue tracking and project management | R&D | Ian Bennett | Matthew Stephens | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Non windows | Other DB | No IIs | SaaS | No | 43814.375 | Invest |  | Matthew.Stephens@smith-nephew.com | Sri Tupil
Lasernet / Nemhandel | EDI order and invoicing | Active | EDI system - receiving orders from customers and send electronic invoices to customers | ERP | Dave Cranny | Sebastian Pasch | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | EOL | Not EOL | Full | Not EOL | Windows 2008R2 | Other DB | No IIs | COTS | Yes | 38352.375 | Unassigned |  | Sebastian.Pasch@smith-nephew.com
LEAF Patient Reporting System | LEAF Custom Reprting System | Active | System Creates LEAF System Customer Reports to support Compliance and usage of the Sensor | Commercial | Chris Nguyen | Chris Nguyen | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2016 | SQL 2016 |  | COTS | No |  | Unassigned |  | Chris.Nguyen@smith-nephew.com
LogicMonitor | LogicMonitor | Retired | Middleware for Network monitoring with VOLOGY | IT | Roman Wojtasik | Patryk Bromirski | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2016 | No DB | No IIs | SaaS | No | 43770.3333 | Unassigned |  | Patryk.Bromirski@smith-nephew.com | Anna Falbogowska
Mainsaver CMMS (UK) | CMMS | Active | Manufacturing Maintenance and Repair management software; Mainsaiver CMMS is used in Hull only *** Old (EOL) UK server lised here- has been moved to NL Stefan Szafran - IT SME | Manufacturing | Derek Spillane | Carla Morris | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2016 | SQL 2016 | No IIs | COTS | Unknown | 43344.375 | Tolerate | To SaaS | Carla.Morris@smith-nephew.com | Derek Spillane
McAfee ePO Console | McAfee Anti-Virus for Windows & Linux | Active | Supports disk encryption | IT | Jakub Keler | Bartosz Ostrowski | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2012 | SQL 2012 | 8.0 (2012) | Vendor Dev'ed | No | 43048.375 | Tolerate | Replatform | Bartosz.Ostrowski@smith-nephew.com | Anna Falbogowska
Mcosmos | Mitutoyo Cosmos | Active | Coordinate Measuring Machine (CMM) Software This is a COTS application/software use to run process, assess metrics and data and run report for the CMM lab equipment. This is used by the Quality Engineer team in Aarau Switzerland. Hardware that runs this software is purchased directly by the vendor. | Manufacturing | Derek Spillane | Aileen Diola | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2016 | No DB | No IIs | COTS | No | 38352.375 | Tolerate | Unknown | Aileen.Diola@smith-nephew.com | Sri Tupil
Microsoft InTune | InTune | Active | Mobile Device Management | Infosec | Jody Jenkins | Paul Funk | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Non windows | Other DB | No IIs | SaaS | No | 41833.375 | Invest | Unknown |  | Lawrence Zorio
Microsoft MFA/SSO | MFA/SSO | Planned | multi-factor authentication (MFA) and Single Sign On (SSO) | Infosec | Jody Jenkins | Paul Funk | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Unknown | Unknown | Unknown | SaaS | No | 43983.375 | Invest |  | paul.funk@smith-nephew.com | Lawrence Zorio
Microsoft OneDrive | OneDrive | Active | Online storage space in the cloud | Enterprise Technology | Jakub Keler | Ludwik Hreczycho | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Unknown | Unknown | No IIs | SaaS | No |  | Unassigned | Cannot go cloud | Ludwik.Hreczycho@smith-nephew.com | Anna Falbogowska
Microsoft Sentinel | SIEM | Active | Used to collect logs and correlate potential security events. | Infosec | Jody Jenkins | Paul Funk | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Non windows | Other DB | No IIs | SaaS | No | 43860.375 | Unassigned |  | paul.funk@smith-nephew.com | Lawrence Zorio
Microsoft Teams | Teams | Active | Collaboration and communitcation system | Enterprise Technology | Jakub Keler | Ludwik Hreczycho | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Unknown | Unknown | No IIs | SaaS | No | 43831.375 | Unassigned |  | Ludwik.Hreczycho@smith-nephew.com | Anna Falbogowska
Movemedical | Movemedical | Active | Movemedical is a single platform with a web and mobile application to manage the functionality of Sales Orders, Surgery Cases, Inventory and SoX Compliance. Sales reps will be able to use the mobile application to schedule surgeries, request inventory, view what is being shipped for surgery, track product usage from the surgery, request replenishments, view pricing, and begin the billing process. Users will be able to directly message other sales reps and their offices to eliminate excessive phones calls, text messages, and emails. Users will also be able to load attachments directly to a case or sales order. Sales offices will be able to use the web application to view upcoming surgeries within their sales area, source inventory needed for surgeries, as well as complete the shipping, receiving, inspection, and replenishment process. Both central loaners and field loaner offices will have the ability to utilize RFID to speed up these processes. Current processes will be further updated through the use of new SAP interfaces to provide real time pricing and additional inventory functions such as transfers, stock orders, and returns. | Commercial | Manish Sahay | Andres Bernard | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL |  |  |  | SaaS | No | 44075.375 | Unassigned |  | Andres.Bernard@smith-nephew.com | Firas Almahamid
MyMediset | LRC; Loaners | Active | Tracks assets on Loan, Repair or Consignment. Used in Europe, Australia, New Zealand. ITLT Cert:26-JUN-17 | ERP | Jacek Karas | Pawel Pietrzyk | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Non windows | No DB | No IIs | COTS | No | 41547.375 | Invest | Unknown | Pawel.Pietrzyk@smith-nephew.com | Massimo Trambaioli
Nexpose Metasploit | Metasploit | Active | email phishing | Infosec | Jody Jenkins | Paul Funk | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2016 | Other DB | No IIs | Vendor Dev'ed | No | 43497.375 | Invest | Repurchase | paul.funk@smith-nephew.com | Lawrence Zorio
Non-Employee Database | NED | Active | Web Application used to maintain NonEmployee data and send data extract to Learn.com | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2012 | SQL 2012 | 8.0 (2012) | SNI dev'ed | No | 40178.375 | Tolerate | Rehost (L&S) | paul.davison@smith-nephew.com | Chris Cook
NVR Security Camera System | NVR Security Camera System | Active | NVR Security Camera System This Server is a DVR Digital Video Recorder fro Camera system in Mansfield, HCL owns Support for the server but not the application | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2016 | SQL 2016 | 8.0 (2012) | COTS | No | 43221.375 | Tolerate | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
Opentext ECM | Livelink | Active | Enterprise Content Management, Archived Data Repository | RAQA | Sri Tupil | Aileen Diola | EOL | EOL | EOL | Not EOL | EOL | EOL | Not EOL | Full | EOL | Windows 2008R2 | SQL 2005 | 7.5 (2008R2) | COTS | Yes | 40574.375 | Eliminate | Cannot go cloud | Aileen.Diola@smith-nephew.com | Sri Tupil
PackSize | PackSize | Active | On-Demand packinging system | Supply Chain | Manas Singha | Amit Shokeen | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2016 | No DB | 8.0 (2012) | SaaS | No | 43351.375 | Tolerate | Go to DataCenter as a Service | Amit.Shokeen@smith-nephew.com | Massimo Trambaioli
Panorama (Palo Alto Firewall Management Platform) | Panorama | Active | Used to manage the Palo Alto firewalls throughout the S+N environment. | Infosec | Jody Jenkins | Paul Funk | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Non windows | Other DB | No IIs | Vendor Dev'ed | No | 43495.375 | Invest | Cannot go cloud | paul.funk@smith-nephew.com | Lawrence Zorio
PartMaker | swissCAM | Active | CAM system for automating the programming of mutli-axis Turn-Mill centers and Swiss-type lathes. license server - used by Memphis & Mansfield China uses the same software but does does not access this server for licensing, but use dongles instead. | Manufacturing | Derek Spillane | Carla Morris | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL |  | No DB | No IIs | COTS | Unknown | 38352.375 | Unassigned |  | Carla.Morris@smith-nephew.com | Derek Spillane
Procurement Service Management | ServiceNow, SNOW | Active | Supports Procurement processing | Procurement | Dave Cranny | Terance Lindof | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Non windows | Other DB | No IIs | SaaS | No | 42594.375 | Invest | Go to DataCenter as a Service | Terance.Lindof@smith-nephew.com
Qualys Vulnerability Scanner | Qualys Vulnerability Scanner | Active | Scan assets connected to the network for vulnerabilities and configuration standards. | Infosec | Jody Jenkins | Paul Funk | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Non windows | Other DB | No IIs | SaaS | No | 43344.375 | Eliminate | Unknown |  | Lawrence Zorio
RAMS (China) | RARRS, Regulatory Affairs Registration Request System, Regulatory Submission | Active | RARRS, Regulatory Submission; Manages the process of new/renew Registration request for China Commercial. Including the approval management, document management and tracking records. | RAQA | Sri Tupil | Aileen Diola | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2012 | SQL 2012 | 8.0 (2012) | Vendor Dev'ed | No | 41205.375 | Tolerate | Rearchitect | Aileen.Diola@smith-nephew.com | Sri Tupil
SAP S4HANA Mfg - ERP | S4H ERP | Active | SAP S4HANA Mfg - MP1 | Manufacturing | Jacek Karas | Krzysztof Gaik | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Non windows | Other DB | No IIs |  | No | 44197.375 | Unassigned |  | Krzysztof.Gaik@smith-nephew.com | Massimo Trambaioli
Security Incident & Event Monitor (SIEM) | SETA | Retired | Service will detect threats on critical and exposed devices in our various DMZs | IT | Imtiaz Iqbal | Harold Combs | EOL | EOL | EOL | EOL | EOL | EOL | EOL | Full | EOL | Non windows | Other DB | No IIs | COTS | Yes | 41333.375 | Eliminate |  | Harold.Combs@smith-nephew.com
SharePoint Online | Office 365 | Active | Cloud Based SharePoint Environment. 07/22/14 - Note that the RTO requirement from the project team was set to High<72 hrs, changed this to Critical<12 hrs only b/c the published MS SLA is RTO:4 hrs, RPO:2 hrs. | Enterprise Technology | Jakub Keler | Ludwik Hreczycho | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Unknown | Unknown | No IIs | SaaS | No | 41665.375 | Tolerate | Cannot go cloud | Ludwik.Hreczycho@smith-nephew.com | Anna Falbogowska
Skype for Business | Office 365 | Retired | Cloud Based Instant Messaging Environment; Note that the RTO requirement from the project team was set to Best Effort, changed this to Critical<12 hrs only b/c the published MS SLA is RTO:2 hrs, RPO:45 mins. 01/20/16 - Changed name from "Lync Online" to "Skype for Business". | Enterprise Technology | Jakub Keler | Ludwik Hreczycho | EOL | EOL | EOL | EOL | EOL | EOL | EOL | Full | EOL | Unknown | Unknown | No IIs | SaaS | Yes | 41819.375 | Unassigned | Cannot go cloud | Ludwik.Hreczycho@smith-nephew.com
Solidworks | Solidworks (ArthroCare) | Active | Computer Aided Design ITLT Cert:26-JUN-17 | R&D | Ian Bennett | Matthew Stephens | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2012 | No DB | No IIs | COTS | No | 38718.375 | Invest | Replatform | Matthew.Stephens@smith-nephew.com | Sri Tupil
Splunk (SIEM) | Splunk Heavy Forwarder | Retired | Security Event log monitoring | IT | Jody Jenkins | Paul Funk | EOL | EOL | EOL | EOL | EOL | EOL | EOL | Full | EOL | Non windows | Other DB | No IIs | COTS | Yes | 43506.375 | Eliminate |  | paul.funk@smith-nephew.com
STAN | Sales Tool for ANalytics, New SAE | Active | STAN (Sales Tool for Analytics) application is a verndor deveopled and hosted on AWS cloud being used by US commercial business. This application is a new US Wound datawarehouse which receives traced sales data, prescriber data and pharmacy data from multiple distributors and vendors. | Data & Analytics | Stuart Robinson | Sathiamurthy Samidurai | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Non windows | Other DB | No IIs | Vendor Developed | No | 44011.375 | Invest |  | Sathiamurthy.Samidurai@smith-nephew.com | Stuart Robinson
START | US Onboarding tool, US Roster tool | Active | START (Sales Training And Roster Tool) application is a SNI developed application hosted on AWS as RDS solution and being used by USA Commercial business team. This application is an Onboarding tool that holds geography alignment data, training data for our US Sales force personnel. | Data & Analytics | Stuart Robinson | Sathiamurthy Samidurai | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2012 | SQL 2012 | No IIs | SNI dev'ed | No | 43689.375 | Tolerate |  | Sathiamurthy.Samidurai@smith-nephew.com | Stuart Robinson
System Center Configuration Manager (SCCM) | SCCM | Active | IT tool for inventory,remote takeover,patch management,software distribution | IT | Jakub Keler | Bartosz Ostrowski | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2012 | SQL 2012 | No IIs | COTS | No | 41669.375 | Invest |  | Bartosz.Ostrowski@smith-nephew.com | Anna Falbogowska
Tenable VMS | Tenable VMS | Active | Tenable VMS | Infosec | Jody Jenkins | Paul Funk | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Non windows | Other DB | No IIs | SaaS | No | 43524.375 | Invest | To SaaS |  | Lawrence Zorio
The Receptionist | The Receptionist | Active | Digital receptionist | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Non windows | No DB | No IIs | SaaS | No | 43851.375 | Tolerate | To SaaS | paul.davison@smith-nephew.com | Chris Cook
Tops Pro | Tops Pro (ArthroCare) | Active | Packaging Design | R&D | Ian Bennett | Matthew Stephens | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2012 | No DB | No IIs | COTS | No | 40543.375 | Tolerate | Cannot go cloud | Matthew.Stephens@smith-nephew.com | Sri Tupil
Unily | Unily | Active | SAAS solution hosting Company Intranet | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Non windows | Other DB | No IIs | SaaS | No | 43683.375 | Invest | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
VAG Security | Building Access | Active | Brussels Building access contol system | Group Functions | Philip Sedgwick | Paul Davison | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2012 | SQL 2012 | 8.0 (2012) | COTS | No | 41091.375 | Eliminate | Cannot go cloud | paul.davison@smith-nephew.com | Chris Cook
Visionaire Case Processing of Images | K Drive, K-drive, EMC, Isilon | Active | Central storage for all patient case files (EMC Isilon) and applications that automate case processing (Segway and Initialize) and the Remote Sites (Aarau, Sydney, Noida). ITLT Cert:26-JUN-17 | R&D | Ian Bennett | Matthew Stephens | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Non windows | No DB | No IIs | Vendor Dev'ed | No | 41456.375 | Tolerate | Cannot go cloud | Matthew.Stephens@smith-nephew.com | Sri Tupil
Winshuttle | Winhuttle | Active | Workflow automation solution for master data management in SAP and mass uploads in to SAP. Not supported for transactional data extracts. | Data & Analytics | Stuart Robinson | Mahmood Mohammed | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Unknown | Unknown | Unknown | COTS | No | 40790.375 | Invest |  | Mahmood.Mohammed@smith-nephew.com | Stuart Robinson
X-Point | X-Point | Active | This is a COTS Complaint Reporting system used by the QA and Sales team in Japan | ERP | Sri Tupil | Aileen Diola | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Windows 2012 | Other DB | 8.0 (2012) | COTS | No |  | Tolerate |  | Aileen.Diola@smith-nephew.com | Sri Tupil
xMatters | xMatters | Active | Communication Tool for Major Incident. Disaster Recovery is done quarterly by the vendor. | IT | Justyna Koloch | Ankur Dubey | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Non windows | Other DB | No IIs | SaaS | No | 43192.375 | Migrate | To SaaS | Ankur.Dubey@smith-nephew.com | Anna Falbogowska
zScaler Private Access (ZPA) | Remote Access | Active | Network Remote Access | Infosec | Jody Jenkins | Paul Funk | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | Not EOL | Non windows | Other DB | No IIs | SaaS | No | 43348.375 | Tolerate | To SaaS |  | Lawrence Zorio
Compass | Compass | Retired | On-Premise Hosted SharePoint Global Intranet | Group Functions | Santhosh Nair | Andres Bernard | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2012 | SQL 2012 | 8.0 (2012) | SNI dev'ed | No | 41758.375 | Unassigned |  | Andres.Bernard@smith-nephew.com
Curacao PO System | Curacao Lotus Notes; Curacao PO | Retired | Purchase Order application used in Curacao | Procurement | Manas Singha | Amit Shokeen | Unknown | EOL | EOL | EOL | Unknown | Unknown | Unknown | Full |  | Windows 2008R2 | No DB | 7.5 (2008R2) | SNI dev'ed | Unknown | 38353.375 | Eliminate | Cannot go cloud | Amit.Shokeen@smith-nephew.com | Massimo Trambaioli
Cybozu | Cybozu | Archive | Workflow System | Commercial |  | Tsutomu Hirooka | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2016 | Other DB | No IIs | Vendor Dev'ed | Unknown | 42370.375 | Tolerate |  | Tsutomu.Hirooka@smith-nephew.com | Firas Almahamid
Demand Smoothie | Demand Smoothie Mambo | Retired | Demand planning solution for ARTC/ENDO. | Supply Chain | Manas Singha | Amit Shokeen |  | Not EOL |  |  | Unknown |  |  | Full |  | Windows 2012 | No DB | 8.0 (2012) |  | Unknown | 42339.375 | Migrate |  | Amit.Shokeen@smith-nephew.com
ECAP | ECAP | Retired | External web based entry form to be used by Smith & Nephew customer accounts. This will gather product information from surgeries to help facilitate warranties and warranty claims for PICO. Users need to be able to enter information into the website which will then be reviewable by internal Smith & Nephew employees through an internal admin site. External users do not need to be able to retrieve this information from website at a later time. | Commercial | Santhosh Nair | Andres Bernard | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL |  | Full |  | Windows 2012 | SQL 2012 |  |  | No | 41782.375 | Tolerate |  | Andres.Bernard@smith-nephew.com
Medical Education and Scientific Data | MedEd | Retired | www.smith-nephew.com/education Replacement of externally-hosted Kleos.md site | Commercial | Santhosh Nair | Andres Bernard | EOL | EOL | EOL | Not EOL | EOL | EOL | Not EOL | Full |  | Windows 2008R2 | SQL 2008R2 | 7.5 (2008R2) | COTS | Yes | 41592.375 | Migrate | To SaaS | Andres.Bernard@smith-nephew.com
Shin Eigyo System | Shin Eigyo System | Archive | Sales Order | Commercial | Tsutomu Hirooka | Tsutomu Hirooka | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2016 | Other DB | No IIs | Vendor Dev'ed | Unknown | 40179.375 | Tolerate |  | Tsutomu.Hirooka@smith-nephew.com | Firas Almahamid
VLOG | MHP | Retired | All 3 servers have a software installed called vlog from the vendor MHP. Vlog is a carrier label printing program that supports various different vendors like DHL, DPD, TNT, FedEx, UPS. So instead of using the vendor software a standard software is used that supports multiple carriers. Why has that been done… For UK, Germany and NL SAP is sending via EDI a txt file to the server. From there the business wrote a program on the MHP server to import those data into a SQL server (each vLog installation comes with a SQL server) and from there vlog picks it up to print the label on a label printer. Additional to that a keylogger tracks on each shipping desk if there is a delivery number scanned and enters the shipping desk number together with the delivery note number to the MHP Server SQL database. So the business process is that the person in the warehouse scan the SAP delivery and with the PGI in SAP a postal label is automatically printed next to his desk that he can use for the parcel. That is why we use a central tool supporting multiple carriers so if the SAP order said DPD a DPD label would come out and if the SAP order would have TNT in it, a TNT label is created. You can put me as delivery manager down. From a support perspective: • Vlog: the business has a support contract that includes remote support with MHP (each country has their own contract) • The import tool has been written by a business person in Germany and support of that tool is also done by the business themselves • The keylogger is also created by the business and supported by them • EDI support is done by S&N IT The fees for the software and installation has been paid by the business, IT just provided the servers and a helping hand where needed. | ERP | Manas Singha | Amit Shokeen | EOL | EOL | EOL | EOL | EOL | EOL | EOL | Full |  | Windows 2008R2 | SQL 2008R2 | 7.5 (2008R2) | SNI dev'ed | Unknown | 41000.375 | Eliminate | Cannot go cloud | Amit.Shokeen@smith-nephew.com
Web Order System | Web Order System | Archive | Sales Order | Commercial | Tsutomu Hirooka | Tsutomu Hirooka | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2016 | Other DB | No IIs | Vendor Dev'ed | Unknown | 40179.375 | Tolerate |  | Tsutomu.Hirooka@smith-nephew.com | Firas Almahamid
AIMS (China) | Asset Instrument Management Systems | Active | Asset Instrument Management Systems - SC management of instrument sets Product Vendor Support=UNSUPPORTED Delivery Manager Cert:22JUN17 | Supply Chain | Emily Yu | Emily Yu | EOL | EOL | EOL | Not EOL | EOL | Not EOL | Not EOL | Full |  | Windows 2008R2 | SQL 2008R2 | 7.5 (2008R2) | Vendor Dev'ed | Yes | 41238.375 | Migrate | Unknown | Emily.Yu@smith-nephew.com | Massimo Trambaioli
Archive System OS7 | DHR | Active | Digital data archiving system for healthcare - used in Aarau | RAQA | Sri Tupil | Aileen Diola | EOL | EOL | EOL | EOL | EOL | EOL | EOL | Full |  | Windows 2008R2 | SQL 2008R2 | 7.5 (2008R2) | Vendor Dev'ed | Yes | 36160.375 | Migrate | To SaaS | Aileen.Diola@smith-nephew.com | Sri Tupil
AX 2012 (POWER) | POWER | Active | ERP system supporting Finance and Supply Chain Operations Support manager change: Mohamed Dawood Product Vendor Support Level:=supported Delivery Manager Cert: 14-JUN-17 | ERP | Massimo Trambaioli | Balvant Kelaiya | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2012 | SQL 2012 | 7.0 (2008) | Vendor Dev'ed | No | 41739.375 | Invest | To SaaS | Swapnil.Kelaiya-off@smith-nephew.com | Massimo Trambaioli
Axapta 2009 (Dubai) | AX | Active | ERP system Support Knowledge=100% System Documentation=50% Maint Agreement=Yes Product Vendor Support=Supported Delivery Manager Cert=22JUN17 | ERP | Massimo Trambaioli | Balvant Kelaiya | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2008R2 | SQL 2012 | 7.5 (2008R2) | Vendor Dev'ed | Unknown | 38352.375 | Invest | To SaaS | Swapnil.Kelaiya-off@smith-nephew.com | Massimo Trambaioli
Axapta 2009 (India) | AX | Active | ERP System Product Vendor Support Level: Supported Delivery Manager Certified: 26-MAY-17 | ERP | Massimo Trambaioli | Balvant Kelaiya | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2008R2 | SQL 2012 | 7.5 (2008R2) | Vendor Dev'ed | Unknown | 40825.375 | Invest | To SaaS | Swapnil.Kelaiya-off@smith-nephew.com | Massimo Trambaioli
BOSS | BOSS; Business Operations Support System; ISA; Integration Services Automation | Active | Sales Force Rostering System. Aligns with CRM data for reporting. Locally hosted LAMP server | Commercial | Manish Sahay | Andres Bernard | EOL | EOL | Not EOL | EOL | Not EOL | EOL | Not EOL | Full |  | Windows 2008R2 | Other DB |  | Vendor Dev'ed | Yes | 40945.375 | Tolerate | To SaaS | Andres.Bernard@smith-nephew.com | Firas Almahamid
Captiva | DHR | Active | OCR and Imaging Software for DHR. Captiva (Input Accel) is our Memphis-based Device History Record (DHR) document scanning and indexing subsystem. Scanned DHR batches are exported to Open Text for subsequent document retrieval. Product Vendor Support=Supported Deliivery Manager Cert=22JUN17 | RAQA | Sri Tupil | Aileen Diola | EOL | EOL | EOL | EOL | EOL | Not EOL | EOL | Full |  | Windows 2008R2 | SQL 2008R2 | 7.5 (2008R2) | COTS | Yes | 39082.375 | Migrate | To SaaS | Aileen.Diola@smith-nephew.com | Sri Tupil
China commercial Eflow | BPM, MDM, DMDM, VMDM, RAMS | Active | Workflow platform for China commercial | Data & Analytics | Jerry Li | Oswin Liao | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2012 | SQL 2012 | 8.0 (2012) | Vendor Dev'ed | No | 41456.375 | Tolerate | Rearchitect | Oswin.Liao@smith-nephew.com | Firas Almahamid
Corporate Website | www.smith-nephew.com; EpiServer | Active | Global Internet content management system CMS for all public websites. URL: www.smith-nephew.com. Runs on EpiServer platform. 12/15/15 - Worked with Mike D to change the name from "Global Internet - EpiServer CMS" to "Corporate Website". | Commercial | Firas Almahamid | Andres Bernard | EOL | EOL | EOL | Not EOL | EOL | EOL | Not EOL | Full |  | Windows 2008 | SQL 2008 | 7.0 (2008) | COTS | Yes | 41205.375 | Migrate | To SaaS | Andres.Bernard@smith-nephew.com | Firas Almahamid
CyberArk EPM (Endpoint Privilege Management) | CyberArk EPM (Endpoint Privilege Management) | Active | Provides privilege elevation for non-privileged users on workstations removing the need for local admin privileges. | Infosec | Jody Jenkins | Paul Funk | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2016 | SQL 2016 | 8.0 (2012) | Vendor Dev'ed | No | 43388.375 | Invest | Rehost (L&S) |  | Lawrence Zorio
CyberArk PAM (Privileged Access Management) | CyberArk PAM (Privileged Access Management) | Active | Manages passwords for privileged accounts in the S&N environment. | Infosec | Jody Jenkins | Paul Funk | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2016 | SQL 2016 | 8.0 (2012) | Vendor Dev'ed | No | 43388.375 | Invest | Rehost (L&S) |  | Lawrence Zorio
eCatalogue | eCatalog; EpiServer; Catalogue; Catalog | Active | Online product catalog for sales representatives. Runs on the EpiServer platform. | Commercial | Manish Sahay | Andres Bernard | EOL | EOL | EOL | Not EOL | EOL | EOL | Not EOL | Full |  | Windows 2008 | SQL 2008R2 | 7.0 (2008) | COTS | Yes | 42374.375 | Migrate | To SaaS | Andres.Bernard@smith-nephew.com | Firas Almahamid
Electronic Instructions for Use | eIFU | Active | This is a public facing website to allow health care professionals download electronic PDF versions of our product instruction for use documents (IFUs). Healthcare product manufacturers are required to produce and provide Instructions for Use (IFU) documents for their reusable surgical instruments, medical devices and equipment and implantable biologics, materials and devices. | Manufacturing | Derek Spillane | Carla Morris | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2016 | SQL 2016 | 8.0 (2012) | SNI dev'ed | No | 43405.3333 | Tolerate |  | Carla.Morris@smith-nephew.com | Derek Spillane
Endo Loans | endoloans.smith-nephew.com | Active | Internal web form to allow sales reps to request orders electronically on their mobile device for Visualization Tower evaluations. It will be accessed through webaccess on their iPad. | Commercial | Manish Sahay | Andres Bernard | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2012 | SQL 2012 |  | SNI dev'ed | No | 42714.375 | Tolerate | Rehost (L&S) | Andres.Bernard@smith-nephew.com | Firas Almahamid
EquipCommand (ShockWatch) | ShockWatch | Active | Wireless fleet management system controls access, detects impacts, and monitors forklift equipment operation. | Supply Chain | Manas Singha | Amit Shokeen | Not EOL | EOL | Unknown | Unknown | Unknown | EOL | Unknown | Full |  | Windows 2012 | No DB | 8.0 (2012) | Vendor Dev'ed | Unknown | 38352.375 | Tolerate | Unknown | Amit.Shokeen@smith-nephew.com | Massimo Trambaioli
ERP LN | BAAN - Biotherapeutics. | Active | ERP application for Biotherapeutics. Includes both Finance and Manufacturing modules. 1-6-16: Delivery Manager was Steve McNeill. Changed to Robert Jones Support Knowledge = 75% System Documentation=50% Maint agreement =YES Product vendor support level=Supported Delivery Mangager CERT: 9-JUN-17 HP-LNDB - Production DB Server - 2008 OS & DB EOL ERP LN functions/modules • User Maintenance • Item Master • Business Partner Management • Sales and Purchase Orders • Manufacturing • Warehouse Management • Cash Management (AP and AR) • General Ledger Management • Finance Integrations including Treasury • Quality Release/blocking Currently utilized at the following locations: • US: Fort Worth, TX; Andover, MA • Curacao (shutting down in 6 months) • India • Costa Rica | ERP | Massimo Trambaioli | Carla Morris | Not EOL | EOL | Not EOL | Unknown | EOL | Unknown | Unknown | Full |  | Windows 2008R2 | SQL 2008R2 | 7.5 (2008R2) | Vendor Dev'ed | Unknown | 40870.375 | Migrate | Unknown | Carla.Morris@smith-nephew.com | Derek Spillane
eTemplate | Digital Templates | Active | Regulatory Affairs. 07/28/16 - Identified by Joy Du (App registered by Tom Steels). This system in externally (Internet) exposed. | RAQA | Sri Tupil | Aileen Diola | Not EOL | Not EOL | Not EOL | Not EOL | EOL | Not EOL | EOL | Full |  | Windows 2012 | SQL 2008R2 | 7.5 (2008R2) | Vendor Dev'ed | Yes | 39448.375 | Tolerate | Rearchitect | Aileen.Diola@smith-nephew.com | Sri Tupil
Event Manager | Infor Event Manager | Active | sdfsa | Supply Chain | Manas Singha | Amit Shokeen | Not EOL | EOL | EOL | EOL | EOL | Not EOL | Unknown | Full |  | Windows 2008R2 | Other DB | 7.0 (2008) | COTS | Unknown | 39814.375 | Invest | To SaaS | Amit.Shokeen@smith-nephew.com | Massimo Trambaioli
Global Labeling System (PRISYM) | PRISYM Medica | Active | Printing Product labels (PRISYM). 01/21/16 - Update from Al. Changing name to include "Prisym". As of 11/17/2020 1. PWF secure version – 6.10.33 2. PWF controls version – 6.10.32 3. Medica Web config version – 1.7.27 4. Importer version - ImporterService.exe – 5.5.0 5. Destination Print client version -DestinationPrintclient.exe – 2.9.13 6. Link updater - LinkUpdaterService.exe – 5.5.0 7. Web Directory - Custom.SmithAndNephew.BusinessLogic.dll – D:\Prisym Software\Patch 2.9.26 & Custom.SmithAndNephew.WebApp.dll – D:\Prisym Software\Patch 2.9.26 8. Back up of the 'Importer for Smith and Nephew' Directory - C:\Program Files (x86)\PRISYMid Ltd\Importer for Smith and Nephew (Back up's are available with the same folder) 9. Database Version – Microsoft SQL 2008 R2 10. Data Editor Version – 3.8.1(Client) 3.8.7(Server) 11. Windows Version – Microsoft Windows Server 2008 R2 Standard 12. IIS version – Version 7.5.7600.16385 Please find the requested info, Server Name OS IIS Version below- Production USMANSMWSPVW25 Windows Server 2008 R2 7.5.7600.16385 USMANSMWSPVW26 Windows Server 2008 R2 7.5.7600.16385 Quality USMAN-SMWSPVW14 Windows Server 2008 R2 7.5.7600.16385 USMAN-SMWSPVW15 Windows Server 2008 R2 7.5.7600.16385 USMANSMWSQVW16 Windows Server 2008 R2 7.5.7600.16385 | Manufacturing | Derek Spillane | Carla Morris | EOL | EOL | EOL | Not EOL | EOL | EOL | Unknown | Full |  | Windows 2008R2 | SQL 2008R2 | 7.5 (2008R2) | COTS | Unknown | 38352.375 | Migrate | Rearchitect | Carla.Morris@smith-nephew.com | Derek Spillane
Global Regulatory Submissions | GRS, Market Registrations, ENOVIA | Active | GRS is a COTS application used by the Regulatory business unit in Memphis for organizing and storing regulatory documents and data based on format and metrics and policies set by the FDA and other regulatory governing bodies. | RAQA | Sri Tupil | Aileen Diola | EOL | EOL | EOL | EOL | EOL | Not EOL | Not EOL | Full |  | Windows 2008 | SQL 2008R2 | 7.5 (2008R2) | Vendor Dev'ed | Yes | 42161.375 | Tolerate | Rearchitect | Aileen.Diola@smith-nephew.com | Sri Tupil
Hydra (Aarau) | Hydra | Active | Hydra is a COTS application used by Aarau site's HR and Quality Business Unit. For HR: The application/module Time Tracking ZPE is used to track manufacturing's shop floor resources time in and time out. The module is integrated to a time tracking/biometric device. For Quality: The application/module CAQ is used for RAW materials incoming inspection. The module is integrated to lab calibration/measuring equipments. The application is used to process data and information accross the business unit, store data and has reporting capabilities as well. | RAQA | Sri Tupil | Aileen Diola | EOL | EOL | EOL | EOL | EOL | EOL | EOL | Full |  | Windows 2003 | SQL 2000 | 6.0 (2003) | Vendor Dev'ed | Yes | 38352.375 | Invest | Replatform | Aileen.Diola@smith-nephew.com | Sri Tupil
Hydra (Tuttlingen) | Hydra | Active | Hydra is a COTS application used by Aarau site's HR, Maintenance, Manufacturing and Quality Business Unit. For HR: The application/module Time Tracking ZPE is used to track manufacturing's shop floor resources time in and time out. The module is integrated to a time tracking/biometric device. For Quality: The application/module CAQ is used for RAW materials incoming inspection. The module is integrated to lab calibration/measuring equipments. For Maintenance: The application/module ZKS is used for building access controls and is integrated to biometric door access equioments. For Manufacturing: The application/module BDE is used for shop floor controls. The application is used to process data and information accross the business unit, store data and has reporting capabilities as well. | RAQA | Sri Tupil | Aileen Diola | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2012 | SQL 2012 | 8.0 (2012) | COTS | No | 38352.375 | Tolerate | Rearchitect | Aileen.Diola@smith-nephew.com | Sri Tupil
Logility Voyager (SCP) | Sudoku | Active | Global Supply Chain planning and inventory optimization. Implemented as part of project: Sudoku. | Supply Chain | Manas Singha | Amit Shokeen | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2012 | SQL 2014 | 8.0 (2012) | Vendor Dev'ed | Unknown | 42644.375 | Invest | Go to DataCenter as a Service | Amit.Shokeen@smith-nephew.com | Massimo Trambaioli
Lotus Notes - Ft Worth AWM | Ft Worth PO System | Active | Lotus Notes installation running applications which will EOL with NAPO. Local PO System and CER System. For 2015 also has SOX implications but will not in 2016. 10/05/15 - Application created at request of Robert Jones. | ERP | Massimo Trambaioli | Amit Shokeen | EOL | EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2008R2 | SQL 2008R2 | 7.5 (2008R2) | Vendor Dev'ed | Yes | 38352.375 | Migrate | To SaaS | Amit.Shokeen@smith-nephew.com | Massimo Trambaioli
Medical Education and Evidence | MedEd; E&E | Active | www.smith-nephew.com/education Hosts SNI product training video, literature for HCPs. 70% of content requires credentials to access. ASD and advanced wound management (AWM). ITLT Cert: 26-MAY-17 Product Vendor Supprt=Supported Delivery Manager Cert= 22JUN17 | Commercial | Firas Almahamid | Andres Bernard | EOL | EOL | EOL | Not EOL | EOL | EOL | Not EOL | Full |  | Windows 2008R2 | SQL 2008R2 | 7.5 (2008R2) | COTS | Yes | 40909.375 | Migrate | To SaaS | Andres.Bernard@smith-nephew.com | Firas Almahamid
Microsoft Dynamics - Mobile Gateway | MS Dynamics | Active | 1) Create and submit surgery cases to local field offices to record or request loaner equipment 2) Create and submit sales orders and product replenishment orders to SAP. 03/09/16 - Per Dave M, this is now in scope for SOX. ITLT Cert:26-JUN-17 RESCO: 1) Create and submit surgery cases to local field offices to record or request loaner equipment 2) Create and submit sales orders and product replenishment orders to SAP | Commercial | Manish Sahay | Andres Bernard | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2016 | SQL 2016 | 8.0 (2012) | COTS | No | 40517.375 | Migrate | To SaaS | Andres.Bernard@smith-nephew.com | Firas Almahamid
Minitab | Minitab | Active | Minitab is a COTS application used by multiple business units in multiple SNI locations. This is a statistic software that can perform statistical calculations and generate reports and graphs. Data is manually entered into the application that allows Minitab to run statistical analysis. Data is not stored in Minitab and the output is in the form of document/ or excel like reporting. | RAQA | Sri Tupil | Aileen Diola | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  |  | SQL 2012 |  | COTS | No | 35795.375 | Invest | Repurchase | Aileen.Diola@smith-nephew.com | Sri Tupil
MLE (China) | Infor 10 | Active | Supply Chain: Forecasting & Demand Management, Replenishment Planning & RCCP | Supply Chain | Manas Singha | Amit Shokeen | Not EOL | EOL | EOL | EOL | EOL | Not EOL | Unknown | Full |  | Windows 2008R2 | No DB | 7.5 (2008R2) | COTS | Unknown | 41753.375 | Invest | To SaaS | Amit.Shokeen@smith-nephew.com | Massimo Trambaioli
MLE (Hull) | Infor MLE | Active | Supply Chain: Forecasting & Demand Management, Replenishment Planning & RCCP | Supply Chain | Manas Singha | Amit Shokeen | Not EOL | EOL | EOL | EOL | EOL | Not EOL | Unknown | Full |  | Windows 2008R2 | Other DB | 7.5 (2008R2) | COTS | Unknown | 38352.375 | Invest | To SaaS | Amit.Shokeen@smith-nephew.com | Massimo Trambaioli
Nicelabel | Nicelabel (ArthroCare) | Active | Product Labeling System https://lps.arthrocare.com Labeling Software - Validted with IE8 or Higher. 10/20/15 - Assessed by Roger Heffington, changing GxP from false to true. | Manufacturing | Derek Spillane | Carla Morris | Not EOL | EOL | Unknown | Unknown | EOL | Unknown | Unknown | Full |  | Windows 2008R2 | SQL 2008R2 | 7.5 (2008R2) | COTS | Unknown | 41184.375 | Migrate | Cannot go cloud | Carla.Morris@smith-nephew.com | Derek Spillane
Nicelabel Administration | Nicelabel Administration (ArthroCare) | Active | https://lps.arthrocare.com/lpsadmin Label Software Administration (Developed by ARTC) | Manufacturing | Derek Spillane | Carla Morris | Not EOL | EOL | Unknown | Unknown | EOL | Unknown | Unknown | Full |  | Windows 2008R2 | SQL 2008R2 | 7.5 (2008R2) | COTS | Unknown | 41121.375 | Migrate | Cannot go cloud | Carla.Morris@smith-nephew.com | Derek Spillane
NPWT Tracker | AWD Tracker | Active | Web based app for tracking NPWT sales (AWM npwt devices); retired w/ EPO Release. 1/11/16 - Per Chris Cook "Data is incorrect – it SHOULD have been replaced by SAP but that is not the case and it remains in use; managed out of a third party in Germany. Transfer that one to me please." Removed Linda Rosser as the Delivery Manager. ITLT Cert: 26-MAY-17 Business Owner is TBD - ECMDB Cannot Remove due to sec perm. | Commercial | Manish Sahay | Andres Bernard | EOL | EOL | EOL | EOL | EOL | EOL | EOL | Full |  | Windows 2008R2 | SQL 2008R2 | 7.0 (2008) | SNI dev'ed | Yes | 38352.375 | Migrate | Rehost (L&S) | Andres.Bernard@smith-nephew.com | Firas Almahamid
OHB (Document Management System) | OHB | Active | Custom built Document Management System based on SharePoint used by users in Aarau. | RAQA | Sri Tupil | Aileen Diola | EOL | EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Pre Windows 2003 | SQL 2000 | 6.0 (2003) | Vendor Dev'ed | Yes | 39447.375 | Migrate | To SaaS | Aileen.Diola@smith-nephew.com | Sri Tupil
Pilgrim SmartSolve Complaint Management | Complaint System, Complaint Reporting; Pilgrim; Global Compliants Management | Active | Pilgrim SmartSolve Complaint Management, version 9.1.44.02 is currently used by Advanced Wound Management, Advanced Surgical Devices (AWM, ASD respectively), and IRAMEA & LATAM business divisions. The Pilgrim Smart Solve application is a Smith & Nephew globally used commercial off-the-shelf configurable business complaint management system used for managing the lifecycle of a complaint. This lifecycle consists of intake, triage, Investigation, Reporting and Closure. This application has been configured for the processing of S&N complaints: • Intake of complaints • Triage of complaints • Investigation of complaints • Reporting of complaints • Electronic Submission of complaints to National Competent Authorities (NCA) • Closure of complaints • Management reporting of the Complaint life-cycle | RAQA | Sri Tupil | Aileen Diola | EOL | EOL | EOL | EOL | EOL | EOL | EOL | Full |  | Windows 2008R2 | SQL 2008R2 | 7.5 (2008R2) | Vendor Dev'ed | Yes | 41875.375 | Migrate | To SaaS | Aileen.Diola@smith-nephew.com | Sri Tupil
PricingTool | PricingTool | Active | Comercial forecast for princings conditions | Commercial | Manish Sahay | Andres Bernard | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2012 | SQL 2012 | 8.0 (2012) | SNI dev'ed | No | 42430.375 | Migrate | To SaaS | Andres.Bernard@smith-nephew.com | Firas Almahamid
RADB | CLS | Active | Is a vendor developed application used by SNI China Quality and Manufacturing business unit for Regulatory Submissions and Labeling System. Product Vendor Support=Supported Delivery Manager Cert: 22JUN17 | RAQA | Sri Tupil | Aileen Diola | Not EOL | EOL | EOL | EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2008R2 | SQL 2012 | 7.5 (2008R2) | Vendor Dev'ed | Yes | 42736.375 | Tolerate | Replatform | Aileen.Diola@smith-nephew.com | Sri Tupil
Sales Life Online | SLO | Active | Sales portal for global ASD sales force for storing electronic product marketing and specification documents. Implemented as part of Project Sunrise. | Commercial | Manish Sahay | Andres Bernard | EOL | EOL | EOL | EOL | EOL | EOL |  | Full |  | Windows 2008 | SQL 2008 | 7.0 (2008) | COTS | Yes | 42384.375 | Migrate | To SaaS | Andres.Bernard@smith-nephew.com | Firas Almahamid
SmartComplaints (Legacy) | Pilgrim ARTC | Active | Customer Complaints System. Pilgrim product. Maintained for historic purposes only. Replaced by Global Complaints (Pilgrim) solution. DR :INFO Smart Complaint[LC] (aka PILGRIM) Any DR done, If yes when was the last time :[LC] No IS DR feasible:[LC] Yes Any DR Plan available:[LC] No | RAQA | Sri Tupil | Aileen Diola |  | EOL |  |  | Unknown |  |  | Full |  | Windows 2003 | No DB | 6.0 (2003) |  | Unknown | 38352.375 | Eliminate |  | Aileen.Diola@smith-nephew.com | Sri Tupil
SOTI | SOTI | Active | RF Gun Management Console and configuration tool for Warehouses ADC is Product vendor Pablo Iradier - IT SME - SAP John Thomas - IT SME - Equipment | Supply Chain | Manas Singha | Amit Shokeen | Not EOL | EOL | Not EOL | Not EOL | EOL | Not EOL | Unknown | Full |  | Windows 2008R2 | SQL 2008R2 | 7.5 (2008R2) | COTS | Unknown | 42248.375 | Tolerate | Unknown | Amit.Shokeen@smith-nephew.com | Massimo Trambaioli
Supplemental Labeling | Slapshot; AWM Web | Active | Site to request a new label. 01/07/16 - Steve Pollard requested this be renamed from "Labeling" to "Supplemental Labeling". PrimalLogix product - includes Slapshot module and AWM Web module. | Manufacturing | Derek Spillane | Carla Morris | Not EOL | EOL | Unknown | Unknown | EOL | Not EOL | Unknown | Full |  | Windows 2008R2 | SQL 2008R2 | 7.5 (2008R2) | COTS | Unknown | 42217.375 | Eliminate | Unknown | Carla.Morris@smith-nephew.com | Derek Spillane
Tableau Bridge | Tableau Bridge | Active | Tableau Bridge is a Vendor developed application using Tableau online platform and used at global location by Operations team. The application is data visualization tool for advanced analytics Provides strong in geospatial analysis for Supply Chain | Supply Chain | Stuart Robinson | Sathiamurthy Samidurai | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2016 | Other DB | 8.0 (2012) | Vendor Dev'ed | No |  | Tolerate | To SaaS | Sathiamurthy.Samidurai@smith-nephew.com | Stuart Robinson
Tender Recording Analysis Normalization System | TRANS | Active | Tender registry solution for China. Vendor: GrapeCity, Inc No integration with other system | Commercial | Jerry Li | Las Lu | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2012 | SQL 2012 | 8.0 (2012) | Vendor Dev'ed | No | 42611.375 | Invest | Cannot go cloud | Las.Lu@smith-nephew.com | Firas Almahamid
Trackwise (EU) | Trackwise | Active | TrackWise is a COTS web-based tracking software tool for electronically logging, managing, and trending CAPA, Audit and Change at Aarau and Tuttlingen used by the Quality Business Unit. | RAQA | Sri Tupil | Aileen Diola | EOL | EOL | EOL | EOL | EOL | EOL | EOL | Full |  | Windows 2008R2 | SQL 2008R2 | 7.5 (2008R2) | Vendor Dev'ed | Yes | 38353.375 | Migrate | Repurchase | Aileen.Diola@smith-nephew.com | Sri Tupil
Trackwise (US) | Biotherapeutics Apps (Trackwise) | Active | Legacy Complaints management tool for the Plus business. TrackWise is a COTS web-based tracking software tool for electronically logging, managing, and trending quality and compliance issues and action items in accordance with cGxP standards. Used by Fort Worth and Curacao. 1-6-16: Delivery Manager was Steve McNeill. Changed to Robert Jones | RAQA | Sri Tupil | Aileen Diola | EOL | EOL | EOL | EOL | EOL | EOL | EOL | Full |  | Windows 2008R2 | SQL 2008R2 | 7.5 (2008R2) | Vendor Dev'ed | Yes | 38352.375 | Migrate | Repurchase | Aileen.Diola@smith-nephew.com | Sri Tupil
Trios Guardian | TA rheometer, TA Advantage Integrity | Active | Lab Application | RAQA | Sri Tupil | Aileen Diola | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2012 | SQL 2012 | 8.0 (2012) | Vendor Dev'ed | No | 43191.375 | Tolerate | Rearchitect | Aileen.Diola@smith-nephew.com | Sri Tupil
Calibration Manager(OSIRIS) | Cal Man | Active | Calibration Management Tool | RAQA | Aileen Diola | Jacob Goitom | EOL | EOL | EOL | EOL | EOL | EOL | EOL | Full |  | Windows 2008 | Other DB | No IIs | COTS | Unknown |  | Eliminate | Cannot go cloud | Jacob.Goitom@smith-nephew.com | Chris Cook
Mobile Inventory Management System | MIMS | Active | Long Description: The MIMS application allows our field sales reps visibility into their current inventory, customer accounts and delivered order status. A rep can use the application to create an order for their customer for inventory that they currently have in hand and are physically delivering to the customer. Each night the system data including inventory, accounts, sales districts are repopulated from feeds out of SAP. After the information is updated, any Draft or Pending PO order inventory is updated to reflect what has been allocated by the MIMS system but not yet in SAP. Key Interfaces: 'MobileOrderFormExtractLoad' Interface - executes SSIS packages to import data from SAP, the program then loads the data tables and executes some data maintenance stored procedures. 'MobileImsOutput' Interface - creates EDI order files to be placed in a shared folder where they can be retrieved and processed by Gentran for SAP. Short Description: Order entry system for sales reps providng delivered orders to customers. 03/09/16 - Per Dave M, this is now in scope for SOX. | Commercial | Manish Sahay | Andres Bernard | EOL | EOL | EOL | EOL | EOL | EOL | Not EOL | Full |  | Windows 2008R2 | SQL 2008 | No IIs | SNI dev'ed | Yes | 42233.375 | Invest | To SaaS | Andres.Bernard@smith-nephew.com | Firas Almahamid
Procurement Spend Management | PSM;Performance Spend Management:Supplier Scorecard | Active | Business Objects Spend Performance Management and Supplier Scorecards. Business owner update per:SRR0079440 | Procurement | Stuart Robinson | Sathiamurthy Samidurai | EOL | Not EOL | Not EOL | Not EOL | EOL | EOL | Not EOL | Full |  | Non windows | Other DB | No IIs | Vendor Dev'ed | Yes | 40543.375 | Migrate | Replatform | Sathiamurthy.Samidurai@smith-nephew.com | Stuart Robinson
SAP Business Warehouse | SAP BWP | Active | SAP Business Intelligence BWP sends data to TM1, PSM, Pilgrim, Endo Varicent and other apps. | Data & Analytics | Stuart Robinson | Sathiamurthy Samidurai | Not EOL | Not EOL | Not EOL | Not EOL | EOL | Not EOL | Not EOL | Full |  | Non windows | Other DB | No IIs | SNI dev'ed | Yes | 41546.375 | Migrate | Replatform | Sathiamurthy.Samidurai@smith-nephew.com | Stuart Robinson
SAP PRD (ORTHO) | SAP | Active | Legacy US commercial and US/UK ortho manufacturing platform ITLT Cert:26-JUN-17 | ERP | Jacek Karas | Krzysztof Gaik | Not EOL | Not EOL | Not EOL | Not EOL | EOL | EOL | Not EOL | Full |  | Non windows | Other DB | No IIs | COTS | Yes | 35795.375 | Tolerate | To SaaS | Krzysztof.Gaik@smith-nephew.com | Massimo Trambaioli
eFIP (electronic Field Inspection Procedure) | efip | Active | electronic Field Inspections and Recording | R&D | Ian Bennett | Matthew Stephens | Not EOL | Not EOL | EOL | EOL | Not EOL | EOL | Unknown | Full |  | Windows 2008R2 | Other DB | No IIs | SNI dev'ed | Yes | 41959.375 | Migrate | Cannot go cloud | Matthew.Stephens@smith-nephew.com | Sri Tupil
GDCFIP (GDC Field Inspection Printing) | gdcfip | Active | Field Inspection Printing interface for printing Matrix Inspection Procedures | R&D | Ian Bennett | Matthew Stephens | Not EOL | Not EOL | EOL | EOL | Not EOL | EOL | Unknown | Full |  | Windows 2012 | Other DB | No IIs | SNI dev'ed | Yes | 41952.375 | Eliminate | Cannot go cloud | Matthew.Stephens@smith-nephew.com | Sri Tupil
GSOP (Global Shop Order Printing) | GSOP | Active | shop floor interface for printing Matrix documents Includes Coastal Logic sw components VueLogic, PrintLogic, Edit Logic. ITLT Cert:26-JUN-17 | R&D | Ian Bennett | Matthew Stephens | Unknown | Not EOL | EOL | EOL | Not EOL | EOL | Unknown | Full |  | Windows 2008R2 | Other DB | No IIs | SNI dev'ed | Yes | 36160.375 | Migrate | Cannot go cloud | Matthew.Stephens@smith-nephew.com | Sri Tupil
Matrix10 | PLM | Active | Product Lifecycle Management System Change Management, Product Structure (BOM), Document Structure, File Vaulting, Shop Floor Print Pkg w/Work Authorization, Administrative Hierarchy. Runs on NAS ITLT Cert:26-JUN-17 | R&D | Ian Bennett | Requalann Pereira | Unknown | EOL | EOL | EOL | Not EOL | EOL | Not EOL | Full |  | Windows 2012 | Other DB | No IIs | COTS | Yes | 36160.375 | Migrate | Cannot go cloud | Requalann.Pereira@smith-nephew.com | Sri Tupil
Active Directory | Domain Controller, DNS, DHCP | Active | Domain Controller, DNS, DHCP Services | Infosec | Jody Jenkins | Paul Funk | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2016 | Other DB | No IIs | Vendor Dev'ed | Unknown | 40791.375 | Invest | Cannot go cloud | paul.funk@smith-nephew.com | Lawrence Zorio
AggSpend 360 | AGS360; Aggregate Spend 360 | Active | HCP Aggregate Spend repository, aggregation, and reporting tool. | Commercial | Manish Sahay | Andres Bernard | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Non windows | Other DB | No IIs | Vendor Dev'ed | No | 40908.375 | Tolerate | To SaaS | Andres.Bernard@smith-nephew.com | Firas Almahamid
Agile PLM | Agile PLM (ArthroCare) | Active | PLM system for ex-Arthrocare products | R&D | Ian Bennett | Matthew Stephens | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2012 | Other DB | No IIs | COTS | No | 39437.375 | Migrate | Rehost (L&S) | Matthew.Stephens@smith-nephew.com | Sri Tupil
Agile-Eigner PLM | PLM | Active | Agile Eigner Product Lifecycle Management solution from Oracle Database PLM ITLT Cert:26-JUN-17 | R&D | Ian Bennett | Antoine d'Overschie | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2008R2 | Other DB | No IIs | Vendor Dev'ed | Unknown | 35718.375 | Migrate | Unknown | Antoine.doverschie@smith-nephew.com | Massimo Trambaioli
Automic | AWA; Batch Automation | Active | Tool to automate batch Job Scheduling and monitoring in SAP PR1 & EPR | ERP | Jacek Karas | Krzysztof Gaik | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2008R2 | SQL 2016 | No IIs | COTS | No | 43252.375 | Invest | To SaaS | Krzysztof.Gaik@smith-nephew.com | Massimo Trambaioli
AWM Data Warehouse | Wound Data Warhouse (WDW) | Active | AWM Data Warehouse is a SNI developed application using Informatica platform and used at US and EUC by Wound buisness team. This Application provides Sales and Product information to the MLE Demand Planning Application and wound business for reporting ITLT Cert:26-JUN-17 | Data & Analytics | Stuart Robinson | Sathiamurthy Samidurai | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2012 | SQL 2012 | No IIs | SNI dev'ed | No | 40178.375 | Tolerate | Replatform | Sathiamurthy.Samidurai@smith-nephew.com | Stuart Robinson
BPCS - Japan | BPCS (AS400) | Active | ERP Application Product vendor support: Supported | ERP |  | Tsutomu Hirooka | Not EOL | Not EOL | Unknown | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Non windows | Other DB | No IIs | Vendor Dev'ed | Unknown | 38352.375 | Tolerate | Cannot go cloud | Tsutomu.Hirooka@smith-nephew.com | Firas Almahamid
Broomstreet Inventory Desk | Inventory Desk | Active | Consignement Tracking | Commercial | Santhosh Nair | Jacob Goitom | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Non windows | Other DB | No IIs | Vendor Dev'ed | No |  | Eliminate | Cannot go cloud | Jacob.Goitom@smith-nephew.com | Chris Cook
Broomstreet Mobile App | Sales Mobile App | Active | Sales Force Ordering Mobile App | Commercial | Santhosh Nair | Jacob Goitom | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Non windows | Other DB | No IIs | Vendor Dev'ed | No |  | Eliminate | Cannot go cloud | Jacob.Goitom@smith-nephew.com | Chris Cook
Broomstreet Sales CRM | Sales CRM | Active | Sales Team Sales CRM | Commercial | Santhosh Nair | Jacob Goitom | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Non windows | Other DB | No IIs | Vendor Dev'ed | No |  | Eliminate | Cannot go cloud | Jacob.Goitom@smith-nephew.com | Chris Cook
Central FTP | CFTP | Active | Internal and External FTP (file transfer) servcies. External (DMZ) leverages AS2 encryption (Axway, WS_FTP). Supports many internal business applications and processes. SAP, BPCS, PRMS, etc. ITLT Cert: 26-JUN-17 Del Cert:26JUN17 | ERP | Jacek Karas | Pawel Pietrzyk | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2012 | No DB | No IIs | COTS | Unknown | 36526.375 | Invest | Replatform | Pawel.Pietrzyk@smith-nephew.com | Massimo Trambaioli
CIMCO (China) | DNC | Active | DNC System | Manufacturing | Derek Spillane | Carla Morris | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2019 | Other DB | No IIs | COTS | Unknown | 41548.375 | Tolerate | Cannot go cloud | Carla.Morris@smith-nephew.com | Derek Spillane
CIMCO (Mansfield) | DNC | Active | DNC System | Manufacturing | Derek Spillane | Carla Morris | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2016 | Other DB | No IIs | COTS | Unknown | 41821.375 | Tolerate | Cannot go cloud | Carla.Morris@smith-nephew.com | Derek Spillane
CIMCO (Memphis) | DNC | Active | DNC System Upgraded to V8 .07.06 ~ 01/18/2020 Available through the Software Center | Manufacturing | Derek Spillane | Carla Morris | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2016 | SQL 2017 | No IIs | COTS | Unknown | 39814.375 | Tolerate | Cannot go cloud | Carla.Morris@smith-nephew.com | Derek Spillane
Cognos BI (Complaints Analytics) | CA | Active | Analytics of S&N complaints, allowing trend analysis | Data & Analytics | Stuart Robinson | Sathiamurthy Samidurai | Not EOL | EOL | Not EOL | Not EOL | Not EOL | EOL | Not EOL | Full |  | Windows 2012 | Other DB | No IIs | SNI dev'ed | Yes | 42835.375 | Eliminate | Rehost (L&S) | Sathiamurthy.Samidurai@smith-nephew.com | Stuart Robinson
Cognos BI (Sales Recon Datamart) | GBIP ODW | Active | Cognos instance for interface between GBIP platform and Ortho Data Warehouse (ODW) | Data & Analytics | Stuart Robinson | Sathiamurthy Samidurai | Not EOL | EOL | Not EOL | Not EOL | Not EOL | EOL | Not EOL | Full |  | Windows 2012 | Other DB | No IIs | SNI dev'ed | Yes | 43146.375 | Eliminate | Rehost (L&S) | Sathiamurthy.Samidurai@smith-nephew.com | Stuart Robinson
Commercial Contract Management | Model N | Active | [2/6/2018] The majority of CCM has been migrated to NAPO underlying processes. However, there is still the Indirect Sales component. An SSIS package runs on usmemsmdbpvw18 nightly to make this integration between Integrichain and Model N occur. Manage contract pricing, chargebacks, rebates, government pricing, Medicaid payments. Intakes chargeback claims from Integrichain. Has interfaces to/from ERP systems (ERP LN and BPCS), and outbound EDI transmissions to trade partners via SAP PI. PROD DC - Kansas City, MO DR DC - Dallas, TX Supported by Model - N | Commercial |  | Andres Bernard | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Non windows | Other DB | No IIs | SaaS | No | 42795.375 | Invest | Unknown | Andres.Bernard@smith-nephew.com | Firas Almahamid
Connect Plus | Connect Plus | Active | ETL for Dr.sum, Web Customer Support and Shipping Slip Management from SAP | IT |  | Tsutomu Hirooka | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2016 | No DB | No IIs | Vendor Dev'ed | Unknown | 41760.375 | Tolerate | Cannot go cloud | Tsutomu.Hirooka@smith-nephew.com | Firas Almahamid
Cortex | CBIT | Active | Cortex is a SNI developed application running on AWS cloud used by Marketing, Sales and Finance and used in Global location. This application provides Cloud based solution using AWS Technology, with MS Power BI as the BI tool and Commercial BI for AWM, Sports, Ortho for US, EMEA and APAC. Standardised Management reporting . | Data & Analytics | Stuart Robinson | Sathiamurthy Samidurai | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Non windows | Other DB | No IIs | SNI dev'ed | No |  | Invest |  | Sathiamurthy.Samidurai@smith-nephew.com | Stuart Robinson
Dr.Sum | Dr.Sum | Active | Business Intelligence for sales amount and inventory | Data & Analytics | Jerry Li | Chika Ishii | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | EOL | Not EOL | Full |  | Windows 2008R2 | SQL 2014 | No IIs | Vendor Dev'ed | Yes | 41609.375 | Migrate | To SaaS | Chika.Ishii@smith-nephew.com | Firas Almahamid
Eagle RF Express | Eagle RF | Active | Eagle RF Express RF-Gun Software | Supply Chain | Derek Spillane | Jacob Goitom | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Non windows | No DB | No IIs | COTS | Unknown |  | Tolerate | Rehost (L&S) | Jacob.Goitom@smith-nephew.com | Chris Cook
Embarcadero/Erwin Studio | Embarcadero Data Modelling | Active | Data & Analytics Engineers Data Modelling tool | R&D | Stuart Robinson | Sathiamurthy Samidurai | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | EOL | Not EOL | Full |  | Windows 2012 | No DB | No IIs | COTS | Yes | 41954.375 | Tolerate | Repurchase | Sathiamurthy.Samidurai@smith-nephew.com | Stuart Robinson
Enterprise Business Objects Reporting | Bobj | Active | Reporting tool that accesses GDW, ODW, and EPO Ax data sources | Data & Analytics | Stuart Robinson | Sathiamurthy Samidurai | EOL | EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2012 | SQL 2012 | No IIs | Vendor Dev'ed | Yes | 40178.375 | Migrate | Replatform | Sathiamurthy.Samidurai@smith-nephew.com | Stuart Robinson
Expert Document Imaging (EDI) | EDi | Active | Provides document managing solution to electronically store all surgery cases and AWM customer orders paperwork. System stores electronically patient surgery case information as well as accounts receivables documentation. | Commercial | Roberto Pujol | Eduardo Lima | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2016 | Other DB | No IIs | COTS | No | 40057.375 | Tolerate | Unknown | Eduardo.Lima@smith-nephew.com | Firas Almahamid
GBS Portal | ServiceNow, SNOW | Active | Employee front end to the IT ServiceNow tool to allow end user ticket logging and request ordering | Group Functions | Dave Cranny | Terance Lindof | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Non windows | Other DB | No IIs | SaaS | No | 42582.375 | Invest | To SaaS | Terance.Lindof@smith-nephew.com
Gentran Server for Unix | Gentran | Active | EDI; EDIFACTS (Component) ITLT Cert: 26-JUN-17 | ERP | Jacek Karas | Krzysztof Gaik | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Non windows | No DB | No IIs | COTS | No | 38352.375 | Invest | Rearchitect | Krzysztof.Gaik@smith-nephew.com | Massimo Trambaioli
Georgia Softworks | Georgia SoftWorks Universal Terminal Server (UTS) | Active | Enables Telnet SAP Console for Easykit RFID system | ERP | Jacek Karas | Krzysztof Gaik | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2008R2 | No DB | No IIs | COTS | No | 39681.375 | Invest | Rearchitect | Krzysztof.Gaik@smith-nephew.com | Massimo Trambaioli
Global Business Information Platform | GBIP DataWarehouse | Active | Oracle instances for Enterprise Data Warehouse (GBIP) environment. Name changed to Global Business Information Platform (RUBIK). 22-MAR-17 Per Troy Seals and Robert Heide ITLT Cert:26-JUN-17 | Data & Analytics | Stuart Robinson | Sathiamurthy Samidurai | EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Non windows | Other DB | No IIs | SNI dev'ed | Yes | 42912.375 | Tolerate | Replatform | Sathiamurthy.Samidurai@smith-nephew.com | Stuart Robinson
Global Data Warehouse | GDW | Active | Microsoft SQL - Global Business Warehouse system for Sales, Inventory, Contracts, Products. GDW is the data source for US, Japan, China, and ANZ ASD Endo reporting and analytics environment. Business Objects is the reporting tool interface. ITLT Cert:26-JUN-17 | Data & Analytics | Stuart Robinson | Sathiamurthy Samidurai | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2012 | SQL 2012 | No IIs | SNI dev'ed | No | 39082.375 | Migrate | Replatform | Sathiamurthy.Samidurai@smith-nephew.com | Stuart Robinson
Global Market Monitoring | GMM Trending Analysis | Active | 03/07 - TS - Received request to add this application to portfolio. | Data & Analytics | Stuart Robinson | Sathiamurthy Samidurai | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2012 | SQL 2012 | No IIs | SNI dev'ed | No | 39082.375 | Migrate | Replatform | Sathiamurthy.Samidurai@smith-nephew.com | Stuart Robinson
In-Market Sales System (dealer management system) | IMS/Eorder | Active | Distributor accounts management Transactions Inventories In-Market Sales Sales Plan Reports Territory Hierarchies Delivery Notes Dealer visit connect with POWeR AX for eordering connect with eflow for product\price\customer master data integration | Commercial | Jerry Li | Las Lu | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Non windows | Other DB | No IIs | SaaS | No | 42536.375 | Invest | To SaaS | Las.Lu@smith-nephew.com | Firas Almahamid
Informatica (SoNAR Data Intergration) | GBIP | Active | Informatica instance for Enterprise Data Warehouse (GBIP) environment. ITLT Cert:26-JUN-17 Name Formally Informatica (GBIP) Changed per SRR0082319 to reflect current name | Data & Analytics | Stuart Robinson | Sathiamurthy Samidurai | EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Non windows | Other DB | No IIs | SNI dev'ed | Yes | 42912.375 | Invest | Rehost (L&S) | Sathiamurthy.Samidurai@smith-nephew.com | Stuart Robinson
Informatica MDM Data Quality | IDQ | Active | Data quality tool allows business users to monitor data quality and perform data set discovery | Data & Analytics | Stuart Robinson | Sathiamurthy Samidurai | EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Non windows | Other DB | No IIs | SNI dev'ed | Yes | 42724.375 | Invest | Rehost (L&S) | Sathiamurthy.Samidurai@smith-nephew.com | Stuart Robinson
Informatica P360 | GDSN | Active | Informatica P360 is a COTS application from Informatica used globally by GHX US, IT data quality and master data management teams. The Informatica P360 application provides GDSN - Global GS1-driven standardized data format to allow manufacturers and customers to efficiently exchange product data and centrally maintained Single Product Hierarchy used across oraganization. GDSN is a Global GS1-driven initiative to provide a standardized data format / repository design to allow manufacturers and customers to efficiently exchange product data (at SKU-level). This is done using GDSN Data pool companies assigned in each market, or globally at company level. Our customers subscribe to get access to various data sources from that pool (paid). We subscribe to get access to customer metadata from the data pool. The objective is to drive efficiency and transparency in the Healthcare supply chain. This project will put in place a single, global, integrated approach to e-commerce which incorporates the immediate GS1/GDSN requirements and a business as usual standardized process to support future customer needs & market requirements either in response to a mandate or proactively to enhance our customers' experience. | Data & Analytics | Stuart Robinson | Sathiamurthy Samidurai | EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Non windows | Other DB | No IIs | SNI dev'ed | Yes | 42994.375 | Invest | Rehost (L&S) | Sathiamurthy.Samidurai@smith-nephew.com | Stuart Robinson
IT Configuration Management Database (CMDB) | EAP, Application Portfolio, ServiceNow, SNOW | Active | Repository acting as a data warehouse for IT, holding data relating to IT assets and descriptive relationships between such assets. | IT | Dave Cranny | Terance Lindof | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Non windows | Other DB | No IIs | SaaS | No | 42278.375 | Invest | To SaaS | Terance.Lindof@smith-nephew.com
IT Problem Management | ITPM, ServiceNow, SNOW | Active | Problem Management | IT | Dave Cranny | Terance Lindof | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Non windows | Other DB | No IIs | SaaS | No | 42216.375 | Invest | To SaaS | Terance.Lindof@smith-nephew.com
IT Service Management | ITSM, ServiceNow, SNOW | Active | Change Management, Incident Managerment, | IT | Dave Cranny | Terance Lindof | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Non windows | Other DB | No IIs | SaaS | No | 42216.375 | Invest | To SaaS | Terance.Lindof@smith-nephew.com
IT Software Asset Management (SAM) | SAM, ServiceNow | Active | The ServiceNow® Software Asset Management (SAM) application systematically tracks, evaluates, and manages software licenses, compliance, and optimization. You can reclaim unused software rights, purchase new software rights, and manage allocations for entitlements. | IT | Dave Cranny | Terance Lindof | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Non windows | Other DB | No IIs | SaaS | No | 43160.375 | Invest | To SaaS | Terance.Lindof@smith-nephew.com
Logility Voyager (SCP) - Data Integration | ODS, Integration | Active | Global Supply Chain planning and inventory optimization | Supply Chain | Manas Singha | Amit Shokeen | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Non windows | Other DB | No IIs | COTS | Unknown | 42644.375 | Invest | Rehost (L&S) | Amit.Shokeen@smith-nephew.com | Massimo Trambaioli
Motion Board | Motion Board | Active | Dashboard Application | Data & Analytics | Tsutomu Hirooka | Chika Ishii | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | EOL | Not EOL | Full |  | Windows 2008R2 | SQL 2014 | No IIs | Vendor Dev'ed | Yes | 42186.375 | Migrate |  | Chika.Ishii@smith-nephew.com | Firas Almahamid
Offline Counting | Stock counting; Consignemnts Audit tool | Active | Application used to perform stock audits at customer premises Support manager updated per Paul D and Francisco M. 16-NOV-17 | Supply Chain | Manas Singha | Amit Shokeen | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2016 | SQL 2017 | No IIs | SaaS | Unknown | 41521.375 | Tolerate | To SaaS | Amit.Shokeen@smith-nephew.com | Massimo Trambaioli
OpenText | rightfax | Active | RightFax digital fax | IT | Santhosh Nair | Jacob Goitom | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Non windows | No DB | No IIs | SaaS | Unknown |  | Invest | To SaaS | Jacob.Goitom@smith-nephew.com | Chris Cook
Oracle Enterprise Manager | OEM | Active | Oracle Enterprise Manager is a COTS application from Oracle used by IT team. The application provides environmental and database monitoring of GBIP SoNAR, Logility, P360 and IDQ applications | Data & Analytics | Stuart Robinson | Sathiamurthy Samidurai | EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Non windows | Other DB | No IIs | COTS | Yes | 42373.375 | Tolerate | Repurchase | Sathiamurthy.Samidurai@smith-nephew.com | Stuart Robinson
PMPA | PMI, PMI System, MarkLogic, Post Market Informatics | Active | PMPA hosts post market product performance information. Structured data as well as unstructured data including advance search and full-text search. It will include all CER's and PMS reports for the S&N company for all products. | Data & Analytics | Stuart Robinson | Sathiamurthy Samidurai | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Non windows | Other DB | No IIs | SNI dev'ed | No | 43083.375 | Invest | Replatform | Sathiamurthy.Samidurai@smith-nephew.com | Stuart Robinson
QAD ERP | QAD MFG | Active | Manufacturing ERP SDM: Jacob Goitom pending add to group | Manufacturing | Derek Spillane |  | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Non windows | Other DB | No IIs | COTS | Unknown |  | Tolerate | Rehost (L&S) |  | Chris Cook
Sales Analytics Engine | SAE | Active | Sales Force Compensation Engine - inputs disparate data sources, applies business rules and produces cleansed sales data for comp. 1-6-16: Delivery Manager was Steve McNeill. Changed to Robert Jones 4-26-2019 updated per INC0460366 | Data & Analytics | Stuart Robinson | Sathiamurthy Samidurai | Not EOL | EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2008R2 | SQL 2008R2 | No IIs | SNI dev'ed | Yes | 41639.375 | Eliminate | Replatform | Sathiamurthy.Samidurai@smith-nephew.com | Stuart Robinson
Salesforce (JPN) | Sales Cloud | Active | In-Market Sales System Support Vendor is salesforce.com | Commercial | Tsutomu Hirooka | Tsutomu Hirooka | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Non windows | Other DB | No IIs | Vendor Dev'ed | No | 42870.375 | Invest |  | Tsutomu.Hirooka@smith-nephew.com | Firas Almahamid
SAP Business Connector | SAP BC | Active | Mem GDC SAP interface server in network dedicated to Conveyor control (SAP to Forte ADS)have version 4.7 SAP BUSCON (latest is 4.8) both only work on Win 2003 platform. no newer OS solution from SAP BUSCON the path for upgrade would be PI (XI). -- Windows 2008 R2 Datacenter SP1 | ERP | Jacek Karas | Pawel Pietrzyk | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | EOL | Not EOL | Full |  | Windows 2008R2 | No DB | No IIs | COTS | No | 35795.375 | Migrate | To SaaS | Pawel.Pietrzyk@smith-nephew.com | Massimo Trambaioli
SAP Cloud Platform Intergration | SCPI | Active | Acts as a conduit or pipeline to enable two-way communication between SAP PR1 and the Spanish Tax Authority, in sending tax data from SAP PR1 to the Spanish Tax Authority and in receiving confirmation from them. No user level operations or access. | ERP | Jacek Karas | Pawel Pietrzyk | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Non windows | No DB | No IIs | COTS | Unknown | 43240.375 | Invest | To SaaS | Pawel.Pietrzyk@smith-nephew.com | Massimo Trambaioli
SAP Console | SAP Console | Active | RF Console (server) ITLT Cert:26-JUN-17 | ERP | Jacek Karas | Pawel Pietrzyk | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2008R2 | No DB | No IIs | COTS | Unknown | 38352.375 | Invest | Replatform | Pawel.Pietrzyk@smith-nephew.com | Massimo Trambaioli
SAP DMS (UK) | SAP | Active | AWD - SAP Document Management System ITLT Cert:26-JUN-17 | ERP | Jacek Karas | Krzysztof Gaik | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2008R2 | Other DB | No IIs | COTS | No | 38717.375 | Invest | To SaaS | Krzysztof.Gaik@smith-nephew.com | Massimo Trambaioli
SAP DMS (US) | SAP | Active | ASD (ENDO) - SAP Document Management System ITLT Cert:26-JUN-17 | ERP | Jacek Karas | Krzysztof Gaik | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2008R2 | Other DB | No IIs | COTS | No | 36953.375 | Invest | To SaaS | Krzysztof.Gaik@smith-nephew.com | Massimo Trambaioli
SAP EPR (GLOBAL) | SAP | Active | Global Manufacturing Operations platform ITLT Cert: 26-JUN-17 | ERP | Jacek Karas | Krzysztof Gaik | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Non windows | Other DB | No IIs | COTS | No | 36891.375 | Invest | To SaaS | Krzysztof.Gaik@smith-nephew.com | Massimo Trambaioli
SAP GRC (Virsa) | SAP ECC 6.0 (ArthroCare) | Active | SAP User Compliance Software | ERP | Jacek Karas | Krzysztof Gaik | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Non windows | Other DB | No IIs | COTS | No | 41274.375 | Invest | To SaaS | Krzysztof.Gaik@smith-nephew.com | Massimo Trambaioli
SAP P01 | SAP ECC 6.0 (ArthroCare) | Active | Arthrocare manufacturing operations platform | ERP | Jacek Karas | Krzysztof Gaik | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Non windows | Other DB | No IIs | COTS | No | 40909.375 | Invest | To SaaS | Krzysztof.Gaik@smith-nephew.com | Massimo Trambaioli
SAP Portal | Portal | Active | Portal | ERP | Jacek Karas | Pawel Pietrzyk | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Non windows | No DB | No IIs | COTS | Unknown | 39813.375 | Invest | Unknown | Pawel.Pietrzyk@smith-nephew.com | Massimo Trambaioli
SAP PR1 (Commercial EPO) | SAP | Active | SAP Commercial Instance (EPO). Global Commercial Operations platform. ITLT Cert:26-JUN-17 | ERP | Jacek Karas | Krzysztof Gaik | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Non windows | Other DB | No IIs | COTS | No | 41546.375 | Invest | To SaaS | Krzysztof.Gaik@smith-nephew.com | Massimo Trambaioli
SAP Process Integration (PIP) | PIP | Active | SAP PI; 10/28/15 - Added at request of Janet Hunter, Paul Wilson confirmed and requested all attributes be set to same as SAP PR1. ITLT Cert:26-JUN-17 | ERP | Jacek Karas | Pawel Pietrzyk | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Non windows | Other DB | No IIs | COTS | Unknown | 41546.375 | Invest | Replatform | Pawel.Pietrzyk@smith-nephew.com | Massimo Trambaioli
SAP Solution Manager (Global) | SOLMAN | Active | SAP Solution Manager (Global) ITLT Cert:26-JUN-17 | ERP | Jacek Karas | Pawel Pietrzyk | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Non windows | Other DB | No IIs | COTS | No | 39448.375 | Invest | Replatform | Pawel.Pietrzyk@smith-nephew.com | Massimo Trambaioli
SAP WP1 (WOUND) | SAP | Active | SAP WP1 (WOUND). Wound DMS is all that remains after MOVPO delivery. ITLT Cert:26-JUN-17 | ERP | Jacek Karas | Krzysztof Gaik | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Non windows | Other DB | No IIs | COTS | No | 38717.375 | Invest | To SaaS | Krzysztof.Gaik@smith-nephew.com | Massimo Trambaioli
ServiceNow Core | ServiceNow | Active | ServiceNow core platform | GBS-IT | Dave Cranny | Terance Lindof | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Non windows | Other DB | No IIs | SaaS | No | 42216.375 | Invest | To SaaS | Terance.Lindof@smith-nephew.com
Simulia Abaqus | Abaqus | Active | Product Development Design Optimization, Falure Analysis and Nondestructive testing. Engineering analysis tool. Material fatigue and stress tesing. (Delmia is the new name) | R&D | Ian Bennett | Matthew Stephens | Unknown | EOL | Not EOL | Not EOL | Not EOL | Not EOL | Unknown | Full |  | Windows 2008 | No DB | No IIs | COTS | Yes | 38352.375 | Tolerate | Replatform | Matthew.Stephens@smith-nephew.com | Sri Tupil
TOTVS | TOTUS | Active | ERP Platform for Brazil Product Vendor Support=Supported Users Internal is set to YES, & not number Delivery Manager Certification = 14-Jun-17 | ERP | Manas Singha | Eduardo Lima | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2019 | SQL 2016 | No IIs | COTS | No | 41609.375 | Tolerate | Rehost (L&S) | Eduardo.Lima@smith-nephew.com | Firas Almahamid
Unigraphics | Siemens NX | Active | CAD Modeling, Assembly, Drawing Creation, CAM Programming,CMM programming | R&D | Ian Bennett | Requalann Pereira | Not EOL | EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2008 | No DB | No IIs | COTS | Yes | 38352.375 | Invest | Replatform | Requalann.Pereira@smith-nephew.com | Sri Tupil
Vertex - Q Series | Q Series (ArthroCare) | Active | Q Series ITLT Cert:26-JUN-17 | ERP | Jacek Karas | Krzysztof Gaik | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2012 | SQL 2008 | No IIs | COTS | No | 40909.375 | Invest | To SaaS | Krzysztof.Gaik@smith-nephew.com | Massimo Trambaioli
Vertex - Q Series Returns | Q Series Returns (ArthroCare) | Active | Q Series Returns | ERP | Jacek Karas | Krzysztof Gaik | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2012 | SQL 2008 | No IIs | COTS | No | 40909.375 | Invest | To SaaS | Krzysztof.Gaik@smith-nephew.com | Massimo Trambaioli
Vertex - Rate Locator | Rate Locator (ArthroCare) | Active | Rate Locator | ERP | Jacek Karas | Krzysztof Gaik | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2012 | SQL 2008 | No IIs | COTS | No | 40909.375 | Invest | To SaaS | Krzysztof.Gaik@smith-nephew.com | Massimo Trambaioli
Vertex - Tax Decision Maker | Tax Decision Maker (ArthroCare) | Active | Tax Decision Maker | ERP | Jacek Karas | Krzysztof Gaik | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2012 | SQL 2008 | No IIs | COTS | No | 40909.375 | Invest | To SaaS | Krzysztof.Gaik@smith-nephew.com | Massimo Trambaioli
Vertex Sales Tax Q Series | Vertex | Active | Sales and use tax calculation | ERP | Jacek Karas | Krzysztof Gaik | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2012 | SQL 2008 | No IIs | COTS | No | 35795.375 | Invest | To SaaS | Krzysztof.Gaik@smith-nephew.com | Massimo Trambaioli
Windchill PLM | PTC Windchill PLM | Active | Product Lifeycle Management | R&D | Ian Bennett | Matthew Stephens | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2016 | Other DB | No IIs | COTS | No | 43313.375 | Invest | Rehost (L&S) | Matthew.Stephens@smith-nephew.com | Sri Tupil
Zebra Retail Solutions | Zebra Inventory, Hart Inventory | Active | Scanner devices capture inventory counts and results are posted on the web portal for reconciliation DR-Location=Secaucaus, NJ Prod-Location=Long Island, NY Product Vendor=Zebra Retail Solutions, LLC. ZEBRA IS SAAS SOLUTION | Supply Chain | Manas Singha | Amit Shokeen | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Non windows | Other DB | No IIs | SaaS | Unknown | 42795.375 | Invest | To SaaS | Amit.Shokeen@smith-nephew.com | Massimo Trambaioli
AWM Sales Portal | sales.smithnephewbio.com | Retired | Sharepoint based sales portal. Collection of 12 sites containing 7 workflow applications. | Commercial | Santhosh Nair | Andres Bernard | Not EOL | EOL | Not EOL | EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2008 |  |  | SNI dev'ed | Yes | 40909.375 | Migrate | Rehost (L&S) | Andres.Bernard@smith-nephew.com
iStability | iStability | Active | iSTability LIMS is Part11 compliant COTS application used by the quality team in Ft. Worth location. This is a turn-key laboratory information management system (LIMS) used for pharmaceutical stability testing programs and stability management. The application analyzes data statistc and produces stability report. Application provides stability testing against product samples | RAQA | Sri Tupil | Aileen Diola | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2012 |  | 8.0 (2012) | COTS | No | 43220.375 | Tolerate | Repurchase | Aileen.Diola@smith-nephew.com | Sri Tupil
Kofax (Topcall) | Topcall | Active | Fax Software ITL, Business Owner, updated per Email from Imtiaz(via Dave M); Support manager and Primary Support updated 31-NOV-17 | ERP | Jacek Karas | Pawel Pietrzyk | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Windows 2012 |  | 8.0 (2012) | COTS | No | 38352.375 | Tolerate | Repurchase | Pawel.Pietrzyk@smith-nephew.com | Massimo Trambaioli
PCDMIS | PCDMIS | Active | A COTS software provided by Browne&Sharpe, that is use for part inspection on shop floor by Quality MFG and is connected to a CMM apparatus. The software is locally installed in each users' individual computer. | RAQA | Sri Tupil | Aileen Diola | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  | Non windows |  |  | COTS | No | 38352.375 | Migrate | To SaaS | Aileen.Diola@smith-nephew.com | Sri Tupil
Esker Document Process Automation | Esker SOP Automation | Active | Order processing through faxing | Commercial | Firas Almahamid | Sathiamurthy Samidurai | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  |  |  | No IIs | SaaS | No | 43101.375 | Invest |  | Sathiamurthy.Samidurai@smith-nephew.com | Stuart Robinson
Global Ops Inventory Visibility (ATK) | ATK | Active | BI solution implemented and hosted by ATK. Intention long-term is to bring this in-house. | Data & Analytics | Stuart Robinson | Sathiamurthy Samidurai | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | EOL | Not EOL | Full |  |  |  | No IIs | SNI dev'ed | Yes | 42644.375 | Eliminate |  | Sathiamurthy.Samidurai@smith-nephew.com | Stuart Robinson
Ortho Data Warehouse | ODW | Active | Ortho Sales & Finance Business Warehouse System. ODW is the data source for US ASD Ortho reporting and analytics. Oracle Discoverer/Datahub is the reporting tool interface. ITLT Cert:26-JUN-17 | Data & Analytics | Stuart Robinson | Sathiamurthy Samidurai | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | EOL | Not EOL | Full |  |  |  | No IIs | SNI dev'ed | Yes | 40178.375 | Eliminate |  | Sathiamurthy.Samidurai@smith-nephew.com | Stuart Robinson
ARIA | ARIA | Archive | Care management platform, which links together patients and partnered providers in one system. It allows a care coordinator or lead physician full transparency into the patients episode of care, including deviations from their standard of care. | Digital | Sri Tupil | Marcos Margulies | [7 empty] | Full | [5 empty] | Unknown | 44226.375 | Unassigned |  | Marcos.Margulies@smith-nephew.com | James Fullarton
Austria Business Objects Reporting | Austria Bobj Historical Reporting | Retired | Business Objects Reporting tool. Local instance in Austria. Used for data archival/historical reporting pre Cognos EPO & GBIP | ASD multiple areas | Bob Watkins | Tomasz Fijalkowski | [7 empty] | Full | [5 empty] | Unknown | 40178.375 | Unassigned |  | Tomasz.Fijalkowski@smith-nephew.com
Axapta 2009 (Singapore) | Singapore Commercial | Active | Singapore Commercial | ERP | Massimo Trambaioli | Mulyanto Ng | [7 empty] | Full | [5 empty] | Unknown | 42036.375 | Unassigned |  | Mulyanto.Ng@smith-nephew.com | Massimo Trambaioli
Azure Cloud Platform | Azure | Active | Azure Cloud Platform is a Smith+Nephew Infrastracture as a Service solution. Use to host internal application. | Cloud | Mateusz Kolenda | Marek Laskowski | [7 empty] | Full | [5 empty] | No | 44105.375 | Unassigned |  | Marek.Laskowski@smith-nephew.com | Chris Cook
Azure DevOps | Azure board | Planned | Azure DevOps is a hosted service providing development and collaboration tools. | IT | Jacek Karas | Krzysztof Gaik | [7 empty] | Full | [5 empty] | Unknown |  | Unassigned | Cannot go cloud | Krzysztof.Gaik@smith-nephew.com | Massimo Trambaioli
AZURE DEVOPS TOOL | AZURE DEVOPS TOOL | Active | AZURE DEVOPS TOOL | IT | Mateusz Kolenda | Marek Laskowski | [7 empty] | Full | [5 empty] | No | 44105.375 | Unassigned |  | Marek.Laskowski@smith-nephew.com | Chris Cook
Azure reporting | Azure reporting | Planned | Azure reporting is a SNI developed application used globaly by all verticals. The application is used for reports like billing and backups on applications using Azure infrastructure. | Cloud | Mateusz Kolenda | Marek Laskowski | [7 empty] | Full | [5 empty] | No |  | Unassigned |  | Marek.Laskowski@smith-nephew.com | Chris Cook
Beacon / Main Org (SalesForce.com) | SFDC | Planned | Mobile enabled Account Planning SalesForce Software solution that provides US Sportsmed Sales Reps capability of planning opportunities to reach sales targets. | Commercial | Manish Sahay | Andres Bernard | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  |  |  |  | SaaS | No | 43857.375 | Invest | To SaaS | Andres.Bernard@smith-nephew.com | Firas Almahamid
Bizflow | Electronic Artwork Approval | Retired | Used for Electronic Artwork Approval (WM and HC) and Admin for Germany EDI | AWM (Advanced Wounded M...) | Mark Towne | Paul Davison | [7 empty] | Full | [5 empty] | Unknown | 37621.375 | Unassigned |  | paul.davison@smith-nephew.com
Business Objects (ASD-ARTC) | SAP Business Objects (ArthroCare) | Retired | Business Intelligence | ASD (Advanced Surgical Devices) | Mark Towne | Tomasz Fijalkowski | [7 empty] | Full | [5 empty] | Unknown | 41852.375 | Unassigned |  | Tomasz.Fijalkowski@smith-nephew.com
CIF (Customer Inquiry Form) | CIF; inSIGHTS Requests; CRM Requests; | Retired | Provides the ability for the sales force to notify the Ops team that customer information (either prescriber or facility) is incorrect in CRM. Provides mechanisms of communicating back and forth with the sales team until such time as the issue has been resolved. | AWM (Advanced Wounded M...) | Imtiaz Iqbal | Andres Bernard | [7 empty] | Full | [5 empty] | Unknown | 41275.375 | Unassigned |  | Andres.Bernard@smith-nephew.com
CPQ2WIN | Configure, Price and Quote (CPQ) | Active | Mobile enabled Configure-Price-Quote (CPQ) software solution that consolidates the necessary customer and product information in one platform and allows our Reps to create, configure and get approvals of customer quotations and capital requests. | Commercial | Manish Sahay | Andres Bernard | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full |  |  |  |  | SaaS | No | 43718.375 | Invest | To SaaS | Andres.Bernard@smith-nephew.com | Firas Almahamid
Crystal Reports | Crystal Reports | Retired | Site used by several departments to run predefined Crystal Reports. Also the user admin part of this application is used by other applications | Commercial | Firas Almahamid | Andres Bernard | [7 empty] | Full | [5 empty] | Unknown | 37621.375 | Unassigned |  | Andres.Bernard@smith-nephew.com
Crystal Reports Database (Sales Reps IDs) | Crystal Users | Retired | This Crystal database is a database that maps sales rep network IDs to SAP sales rep numbers. It has a web app that Sales Ops uses to maintain the data. The old Crystal Reports system uses this database and EDWODS data to filter reports by Sales Rep. Out of Vendor Support | Commercial | Imtiaz Iqbal | Andres Bernard | [7 empty] | Full | [5 empty] | Unknown | 36892.375 | Unassigned |  | Andres.Bernard@smith-nephew.com
Curtis-Fitch (Archive) | Curtis-Fitch | Retired | Archive for Procurement Contracts/Agreements Set app to retired per INC0324104 | ASD (Advanced Surgical Devices) | Steve Horgan | Paul Wilson | [7 empty] | Full | [5 empty] | Unknown |  | Unassigned |  | Paul.Wilson@smith-nephew.com
Data Warehouse (Dubai) | oracle DW | Retired | 05/15/15 - Oracle data warehouse reported by Requalann | Data & Analytics | Imtiaz Iqbal | Requalann Pereira | [7 empty] | Full | [5 empty] | Unknown | 43157.375 | Unassigned |  | Requalann.Pereira@smith-nephew.com
Digital Packaging Platform | DPP, Appian | Planned | Digitized Package Engineering Forms. Built on the APPIAN platform. | Digital | Derek Spillane | Carla Morris | [7 empty] | Full | [5 empty] | Unknown |  | Unassigned |  | Carla.Morris@smith-nephew.com | Derek Spillane
Documentum | DHR | Retired | Document storage solution for DHR (works with Captiva) | ASD (Advanced Surgical Devices) | Imtiaz Iqbal | Ian Bennett | [7 empty] | Full | [5 empty] | Unknown | 39447.375 | Unassigned |  | ian.bennett@smith-nephew.com
EDWODS Data Warehouse | EDW, ODS | Retired | EDWODS is a data warehouse for SAP sales data (billings and bookings) and master data (product, customer, etc) that has been around for a long time. Jim Schromm took custody of this system when someone left the company 7 years ago. We don't do any enhancements to this system but it receives data on a daily basis. GDW hooks into this system to retrieve data even though GDW was supposed to replace this system. It runs on SQL Server 2000. Out of vendor support. Some users interface with MS Access. | Data & Analytics | Imtiaz Iqbal | Paul Davison | [7 empty] | Full | [5 empty] | Unknown | 36892.375 | Unassigned |  | paul.davison@smith-nephew.com
Ennov PV-Works | Safety system, PV247 | Planned | PV-Works (human) is a software system designed to support pharmacovigilance business processes and technical services case handling practices. In addition, is used as a Safety system for tracking and documenting the sponsor review of Clinical study adverse events data and as required by ISO 14155 and ICH-GCP. | Product/Clinical | Sri Tupil | Aileen Diola | [7 empty] | Full | [5 empty] | No |  | Unassigned |  | Aileen.Diola@smith-nephew.com | Sri Tupil
ENT Material Order Form | ENT Material Order Form (ArthroCare) | Retired | ENT Trade Show Order Process | ASD (Advanced Surgical Devices) | Imtiaz Iqbal | Andres Bernard | [7 empty] | Full | [5 empty] | Unknown | 42163.375 | Unassigned |  | Andres.Bernard@smith-nephew.com
ERP (India - HISTORICAL REFERENCE) | Old ERP | Retired | OLD ERP - Production (application) WOUND domain (As per Government Rule in India, we need to keep server alive till - YR 2019) | Local | Firas Almahamid | Sushant Pawar | [7 empty] | Full | [5 empty] | Unknown | 42273.375 | Unassigned |  | Sushant.Pawar@smith-nephew.com
Esker VsiFax | Esker VsiFax (ArthroCare) | Retired | E-Fax Delivery. 01/28/16 - Update from Paul Wilson. This is no longer in use. Setting disposition to Retired. | ASD (Advanced Surgical Devices) | Tjebbes Feenstra | Paul Wilson | [7 empty] | Full | [5 empty] | Unknown |  | Unassigned |  | Paul.Wilson@smith-nephew.com
Eurodata | Windev | Retired | Custom-written application (in Windev 5.5) to review backorder information on European HUB BPCS. Now retired as European BPCS on SAP as of Q2 2015. | AWM (Advanced Wounded M...) | Tjebbes Feenstra | Paul Davison | [7 empty] | Full | [5 empty] | Unknown | 36525.375 | Unassigned |  | paul.davison@smith-nephew.com
FSC Report | Field Spend Capture, FSC | Retired | Web application that produces reports based on the FSC data. Used by Bob's team. Admin is Geoffrey Dutton. | Group Functions | Imtiaz Iqbal | Paul Davison | [7 empty] | Full | [5 empty] | Unknown | 42426.375 | Unassigned |  | paul.davison@smith-nephew.com
Global Internet - Public Websites (ARTC) | ArthroCare Public Websites | Retired | Marketing Websites | ASD (Advanced Surgical Devices) | Chris Cook | David Gamble | [7 empty] | Full | [5 empty] | Unknown |  | Unassigned |  | David.Gamble@smith-nephew.com
Global Operations Datahub | GODBA; GOBA; Global Operations Digital & Business Analytics Datahub | Planned | "GODBA is a Business Analytics extracts, stores and generates dashboards & Reports for Manufacturing and Supplychain applications. Application utilizes services like, RDS, ElasticBeanstalk, S3, Lambda, AD Connectivity & Glue etc..)" | Manufacturing | Stuart Robinson | [8 empty] | Full | [5 empty] | Unknown |  | Unassigned
HP Quality Center | Quality Centre, HPQC | Retired | Requirements Management, Test Management, Defect Management Update Per Chris Cook via CMDB Email 20-NOV-17 |  | Chris Cook | Jacquie Levasseur | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Jacquie.Levasseur@smith-nephew.com
HR Provisioning System | HR Provisioning System (ArthroCare) | Retired | User Provisioning | ASD (Advanced Surgical Devices) | Tjebbes Feenstra | David Gamble | [7 empty] | Full | [5 empty] | Unknown |  | Unassigned |  | David.Gamble@smith-nephew.com
HR Service Portal | ServiceNow, SNOW | Retired | Employee front end to the HR ServiceNow tool to allow end user ticket logging and request ordering Changed DEL MGR from Steve to Richard Stinson Per Steve's approval - 22-sep-16 MCA | Both ASD and AWM | Tjebbes Feenstra | Richard Stinson | [7 empty] | Full | [5 empty] | Unknown | 42430.375 | Unassigned |  | Richard.Stinson@smith-nephew.com
IP6 - Iberia KITS system | carrousel | Retired | IP6 - Iberia Warehouse sytem retired with SAP golive in 2014 | Manufacturing, Operations and Supply Cha | Chris Cook | Alison Conlon | [7 empty] | Full | [5 empty] | Unknown |  | Unassigned |  | Alison.Conlon@smith-nephew.com
LabelView | LabelView (ArthroCare) | Active | Legacy Product Labeling Software. 01/21/16 - Update from Al. This will be retired within next 60 days, moving to NiceLabel. Received notifcation that this app is still running on workstations with a retirement plan of 6 months from now. (< 2019) 09/15/2020 (Carla Morris)- Used at Plymoth West & Plymouth East - all products are being transitioned to Costa Rica by Q1 2020. Costa Rica already using Prisym... After transition of products to CR in Q1 2021 the plan is to leave the Plymouth locations dormant through May 2022 just in case an issue arrises with CR manufacturing (low risk). Seems to be 5 licenses only, installed on PCs, no SN IT support required, To discuss again with Gary Graham , Bobbie Johnson, Amaranatha Reddy, Francisco Marconcini, Charles Hayes in JQ4 2020/Q1 2021. | Manufacturing | Derek Spillane | Carla Morris | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Unknown | Not EOL | Full |  |  |  |  | COTS | Unknown | 42735.375 | Migrate | Rehost (L&S) | Carla.Morris@smith-nephew.com | Derek Spillane
Labview (BBT) | Labview | Retired | Bluebelt Prototyping platform. For developing testing platform. Generally used coupled with National Instruments Hardware. Merged with CORP version | ASD (Advanced Surgical Devices) | Imtiaz Iqbal | Ian Bennett | [7 empty] | Full | [5 empty] | Unknown | 42583.375 | Unassigned |  | ian.bennett@smith-nephew.com
LEAF Quality Management System | Parts & Vendor | Planned | Quality Management System for the LEAF System | R&D | Chris Nguyen | [8 empty] | Full | [5 empty] | Yes |  | Unassigned
Logo Accounting | LOGO | Archive | Accounting software in Turkey | Global | Firas Almahamid | Cagatay ASLAN | [7 empty] | Full | [5 empty] | Unknown |  | Unassigned |  | Cagatay.Aslan@smith-nephew.com
Lumino Platform | HIPAA Cloud | Active | HIPAA compliant AWS based Cloud Platform, running client facing applications | Digital | James Fullarton | Marcos Margulies | [7 empty] | Full | [5 empty] | Unknown | 44197.375 | Unassigned |  | Marcos.Margulies@smith-nephew.com | James Fullarton
Matlab (BBT) | Matlab | Retired | Bluebelt Numerical computational analysis program, used in the R&D stage of design. Primary used is for simulating physical models through algorithms and being able to change parameters quickly and for processing large amounts of data in a specific way. Consolidated into CORP version | ASD (Advanced Surgical Devices) | Imtiaz Iqbal | Ian Bennett | [7 empty] | Full | [5 empty] | Unknown | 42370.375 | Unassigned |  | ian.bennett@smith-nephew.com
Microsoft Cloud App Security | MCAS | Planned | Microsoft Cloud App Security enables you to take control of your cloud environment by providing you rich visibility, control over data travel, and sophisticated analytics to identify and combat cyberthreats across all your cloud services. | Infosec | Jody Jenkins | Paul Funk | [7 empty] | Full | [5 empty] | Unknown | 43831.375 | Unassigned |  | paul.funk@smith-nephew.com | Lawrence Zorio
Microsoft Defender/ATP | Defender/ATP | Planned | Provides anitvirus protection for desktops and servers and ATP for email | Infosec | Jody Jenkins | Paul Funk | [7 empty] | Full | [5 empty] | Unknown |  | Unassigned |  | paul.funk@smith-nephew.com | Lawrence Zorio
Microsoft FRX 6.7 | FRX | Retired | Provide accurate reports generated from pulling information directly from the general ledger and a reduction in error-prone double entry, simplified reporting with design wizards and customizable report templates that help people quickly create relevant financial reports, multiple output options, traditional and graphical, including Microsoft Office Excel or other spreadsheets, ASCII, FRx DrillDown Viewer, online analytical processing (OLAP), or extensible business reporting language (XBRL), and flexible report design so recipients can view information in an easy-to-understand format. This application is only being used for historical data for our previous ERP system (Microsoft Dynamics GP) | Both ASD and AWM | Alison Conlon | David Hernández | [7 empty] | Full | [5 empty] | Unknown | 38353.375 | Unassigned |  | David.Hernandez@smith-nephew.com
MLE (Barcelona) | MLE | Retired | Demand planning and purchasing software |  | Firas Almahamid | Alison Conlon | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Alison.Conlon@smith-nephew.com
Moogsoft | https://events5.hclmtaas.com/ | Active | This is the Event Management tool connected to Native Infrastructure Monitoring tools (SCOM/Azure Monitor) |  | Roman Wojtasik | Patryk Bromirski | [7 empty] | Full | [5 empty] | No |  | Unassigned |  | Patryk.Bromirski@smith-nephew.com | Anna Falbogowska
MSL Activities | MSL Contact Activity - MSL Independent Activities | Retired | Mini CRM / time management SharePoint based applications. Created separately but consolidated in the database. | Commercial | Santhosh Nair | Andres Bernard | EOL | EOL | Not EOL | Not EOL | EOL | EOL | Not EOL | Full |  |  |  |  | COTS | Yes | 41275.375 | Eliminate | Cannot go cloud | Andres.Bernard@smith-nephew.com
MSL Request | MSL Portal | Retired | Sales force tool to request the utilization of MSL's along with proper tracking, time mgmt, and many other efficiencies for the MSL team. | Commercial | Santhosh Nair | Andres Bernard | EOL | EOL | Not EOL | Not EOL | EOL | EOL | Not EOL | Full |  |  |  |  | COTS | Yes | 41275.375 | Eliminate | Cannot go cloud | Andres.Bernard@smith-nephew.com
Own The Tower | ownthetower.smith-nephew.com, Visualization Tower website | Retired | Internal web form to allow sales reps to request orders electronically on their mobile device for Visualization Tower evaluations. It will be accessed through webaccess on their iPad. | Global | Imtiaz Iqbal | Andres Bernard | [7 empty] | Full | [5 empty] | Unknown | 42714.375 | Unassigned |  | Andres.Bernard@smith-nephew.com
Password Manager Pro | PMP | Retired | Password vault tool for storing privilege account credentials. Includes service accounts for AD, Unix/Linux, Juniper (VPN gateway). Database is encrypted, browser interface uses HTTPS. | IT | Imtiaz Iqbal | Harold Combs | [7 empty] | Full | [5 empty] | Unknown | 40725.375 | Unassigned |  | Harold.Combs@smith-nephew.com
PLATO ERP | PLATO - Custom ERP for Turkey | Archive | Custom Developed ERP for Turkey (PLATO) | Local | Firas Almahamid | Cagatay ASLAN | [7 empty] | Full | [5 empty] | Unknown | 40544.375 | Unassigned |  | Cagatay.Aslan@smith-nephew.com
PrintLogic | PLM | Retired | 04/10/14 - New app identified during WARP by RR team. Product Lifecycle Management System Change Management, Product Structure (BOM), Document Structure, File Vaulting, Shop Floor Print Pkg w/Work Authorization, Administrative Hierarchy. Runs on NAS ITLT Cert:26-JUN-17 | ASD (Advanced Surgical Devices) | Mark Towne | Ramesh Balabhadruni | [7 empty] | Full | [5 empty] | Unknown | 38717.375 | Unassigned |  | Ramesh.Balabhadruni@smith-nephew.com
Red Carpet | Red Carpet | Retired | Onboarding. SaaS |  | Tjebbes Feenstra | David Gamble | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | David.Gamble@smith-nephew.com
Remote Access Service (ARTC) | Cisco VPN (ArthroCare) | Retired | VPN Access. 02/04/16 - Update from Alison, this has been retired. | ASD (Advanced Surgical Devices) | Alison Conlon | Alison Conlon | [7 empty] | Full | [5 empty] | Unknown |  | Unassigned |  | Alison.Conlon@smith-nephew.com
Robotic Process Automation | RPA | Retired | Automate and augment rule-based process to increase responsiveness. | Commercial | Firas Almahamid | Steve Horgan | [7 empty] | Full | [5 empty] | Unknown | 43419.375 | Unassigned |  | Stephen.Horgan@smith-nephew.com
Sales Rep Locator | US Commercial Sales Rep Locator | Retired | This is a mobile app (iOS and Android) that enables sales reps in the field to locate sales rep colleagues that work in a particular geography and/or customer(s). | Commercial | Firas Almahamid | Andres Bernard | [7 empty] | Full | [5 empty] | Unknown | 43374.375 | Unassigned |  | Andres.Bernard@smith-nephew.com
SAP Business One | SAP B1 | Active | ERP South Korea Product Vendor Support Level: Supported Support Knowledge: 0% Delivery Manager Cert: 14-JUN-17 | ERP | Massimo Trambaioli | Chang Keun Oh | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | ChangKeun.Oh@smith-nephew.com
SAP EDP | EPO Business Warehouse | Retired | BI solution that extracts data from SAP PR1, performs data transformation and sends processed data to applications like TM1, Pilgrim etc. | Both ASD and AWM | Imtiaz Iqbal | Tomasz Fijalkowski | [7 empty] | Full | [5 empty] | Unknown | 41640.375 | Unassigned |  | Tomasz.Fijalkowski@smith-nephew.com
SAP S4HANA Mfg - Fiori | S4H Fiori | Active | Landscape (DFH/QFH/PFH) for SAP S4HANA Mfg - Fiori. | ERP | Jacek Karas | Pawel Pietrzyk | [7 empty] | Full | [5 empty] | No |  | Unassigned |  | Pawel.Pietrzyk@smith-nephew.com | Massimo Trambaioli
SAP S4HANA Mfg - Solution Manager | S4H SolMan | Active | Landscape (DFS/PFS) for SAP S4HANA Mfg - Solution Manager. | ERP | Jacek Karas | Pawel Pietrzyk | [7 empty] | Full | [5 empty] | No |  | Unassigned |  | Pawel.Pietrzyk@smith-nephew.com | Massimo Trambaioli
SAP Solution Manager | SAP Solution Manager (ArthroCare) | Retired | Landscape Management | ASD (Advanced Surgical Devices) | Imtiaz Iqbal | Santhosh Nair | [7 empty] | Full | [5 empty] | Unknown |  | Unassigned |  | Santhosh.Nair@smith-nephew.com
SAP Web Dispatcher | SAP Web Dispatcher (ArthroCare) | Retired | Web Proxy RESETTING APP TO ACTIVE - SERVERS ARE STILL related to this apps environment; this needs to be corrected prior to setting applications to retired in all cases. | ASD (Advanced Surgical Devices) | Imtiaz Iqbal | Paul Wilson | [7 empty] | Full | [5 empty] | Unknown | 40909.375 | Unassigned |  | Paul.Wilson@smith-nephew.com
SAP Webdispatcher | SAP WD | Active | Development & Production | Procurement | Jacek Karas | Pawel Pietrzyk | [7 empty] | Full | [5 empty] | Unknown | 44204.375 | Unassigned |  | Pawel.Pietrzyk@smith-nephew.com | Massimo Trambaioli
ServiceNow GRC | Governance, Risk & Compliance | Planned | ServiceNow Application providing risk management, policy, compliance, controls monitoring and audit functionality for IT on ServiceNow Platform (which is APaaS - Application Platform as a Service) from ServiceNow. | IT | Lawrence Zorio | Terance Lindof | [7 empty] | Full | [5 empty] | Unknown | 44062.375 | Unassigned |  | Terance.Lindof@smith-nephew.com
Sharepoint Services | SharPoint | Retired | Various on-premise environments. | Commercial | Santhosh Nair | Andres Bernard | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL |  | Full |  |  |  |  | COTS | No | 37986.375 | Tolerate | Rehost (L&S) | Andres.Bernard@smith-nephew.com
SmartSolve eQMS CAPA | eQMS CAPA | Active | CAPA is a module within IQVIA's SmartSolve Enterprise Quality Management Software (eQMS) use mainly by the Quality Assurance Business Unit. CAPA stands for Corrective Action and Preventive Action. This tool is used to identify, resolve and avoid non conformances. The holistic framework helps to standardize, centrlaize and automate CAPA processes. This is a full SAAS provided by IQVIA Inc. • This application is use for: • Intake of CAPA • Triage of CAPA • Investigation of CAPAs • Reporting of CAPAs | RAQA | Sri Tupil | Aileen Diola | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | [5 empty] | No | 43843.375 | Invest | To SaaS | Aileen.Diola@smith-nephew.com | Sri Tupil
SmartSolve eQMS Change Management | eQMS Change Mngt | Planned | "Change mngt is a module within IQVIA's SmartSolve Enterprise Quality Management Software (eQMS) use mainly by the Quality Assurance Business Unit. This is a full SAAS provided by IQVIA Inc. This solution is used to automate and streamline change management process/workflow: • Intake of change • Triage of change • Investigation of change • Reporting of changes • Closure of change " | RAQA | Sri Tupil | Aileen Diola | [7 empty] | Full | [5 empty] | Unknown | 43920.375 | Unassigned |  | Aileen.Diola@smith-nephew.com | Sri Tupil
SmartSolve eQMS Complaint Management | eQMS Complaint Management | Active | Complaints is a module within IQVIA's SmartSolve Enterprise Quality Management Software (eQMS) use mainly by the Quality Assurance Business Unit. This solution is used to automate and streamline complaint handling and regulatory reporting. This is a full SAAS provided by IQVIA Inc. This application has been configured for the processing of S&N complaints: • Intake of complaints • Triage of complaints • Investigation of complaints • Reporting of complaints • Electronic Submission of complaints to National Competent Authorities (NCA) • Closure of complaints • Management reporting of the Complaint life-cycle | RAQA | Sri Tupil | Aileen Diola | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | [5 empty] | No | 43941.375 | Invest | To SaaS | Aileen.Diola@smith-nephew.com | Sri Tupil
SmartSolve eQMS Document Management | eQMS Doc Mngt | Planned | "Doc mngt is a module within IQVIA's SmartSolve Enterprise Quality Management Software (eQMS) use mainly by the Quality Assurance Business Unit. This is a full SAAS provided by IQVIA Inc. This solution is used to automate and streamline document management process/workflow: • Organize document lifecycle • Regulatory fillings • Document routing • Document approval " | RAQA | Sri Tupil | Aileen Diola | [7 empty] | Full | [5 empty] | Unknown | 43920.375 | Unassigned |  | Aileen.Diola@smith-nephew.com | Sri Tupil
SmartSolve eQMS NC | eQMS NC | Active | NC is a module within IQVIA's SmartSolve Enterprise Quality Management Software (eQMS) use mainly by the Quality Assurance Business Unit. NC stands for Non Conformances. The NC solution provides a closed-loop workflow to document, verify, disposition and investigate product and process noncoformances and noncompliances. This is a full SAAS provided by IQVIA Inc. This application is use to: • Intake of NC • Triage of NC • Investigation of NCs • Reporting of NCs | RAQA | Sri Tupil | Aileen Diola | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | [5 empty] | No | 43843.375 | Invest | To SaaS | Aileen.Diola@smith-nephew.com | Sri Tupil
SmartSolve eQMS QI Tool (Tibco Spotfire) | eQMS QI Tool | Active | QI Tool is a Quality Intelligence software powered by Tibco Spotfire provide by IQVIA Inc. The QI Tool is a full SAAS Enterprise-level Business Intelligence tool to provide reporting across large data sources with interactive dashboards where data can be analyzed in multiple ways. The Tool provides Key Quality Metrics/Analytics such as: •Interactive dashboards •On time and aging metrics •Frequence and Trending of data such as Failure Modes or Caus | RAQA | Sri Tupil | Aileen Diola | [7 empty] | Full | [5 empty] | Unknown | 44103.375 | Unassigned |  | Aileen.Diola@smith-nephew.com | Sri Tupil
SmartSolve eQMS Training Management | Training Mngt | Planned | "Training mngt is a module within IQVIA's SmartSolve Enterprise Quality Management Software (eQMS) use mainly by the Quality Assurance Business Unit. This is a full SAAS provided by IQVIA Inc. This solution is used to electronically manage training lifecycle for Quality. " | RAQA | Sri Tupil | Aileen Diola | [7 empty] | Full | [5 empty] | Unknown | 43981.375 | Unassigned |  | Aileen.Diola@smith-nephew.com | Sri Tupil
Solidworks (BBT) | Solidworks | Retired | Bluebelt Software used to perform CAD (Computer Aided Design) & CAM (Computer Aided Manufacturing) work by design engineering & manufacturing to design and manufacture Smith & Nephew products. Consolidated into CORP version | ASD (Advanced Surgical Devices) | Imtiaz Iqbal | Ian Bennett | [7 empty] | Full | [5 empty] | Unknown | 42583.375 | Unassigned |  | ian.bennett@smith-nephew.com
Spain Business Objects Reporting | Spain Historical Reporting | Retired | Local Spain Business Objects reporting. End users and reporting content consoldiated into the Enterprise Bobj (ASD Global) instance in 2016. Dbase server remains online for archival/historical reporting 06/29/17 - Mike H: Their reports and universes migrated from this legacy business objects server to our Business Objects (ASD-Global) environment application environment. After we migrated everything Hugo told me that Spain does not use business objects any longer, they use Cognos. Therefore they powered off Spain BO server and he asked us to hide their reports and universes in our ASD-Global environment. 06/29/17 -Oriol: Yes, it was completely removed. Legacy data will be obtained from BO ASD-Global, or legacy BPCS system itself. |  | Mark Towne | Tomasz Fijalkowski | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Tomasz.Fijalkowski@smith-nephew.com
TRACCS | Contract Management System; CCMS | Retired | Contracts & Rebates system. Contract Management System. S&N AWC/D-USA launched an internally built CCMS in 1998 (TRACCS). This system runs on an AS400 platform and is tightly coupled to the BPCS ERP platform. | Commercial | Imtiaz Iqbal | Paul Davison | [7 empty] | Full | [5 empty] | Unknown | 35795.375 | Unassigned |  | paul.davison@smith-nephew.com
Trial interactive eFeasibility | Survey application | Planned | Trial Interactive eFeasibility is a platform technology that allows electronic creation of surveys, email delivery of surveys, collection and reporting of survey data. Communication, response tracking, and data collection is also maintained in the system. Cloud based platform using a configured web-based file structure. |  | Bob Watkins | Danielle Blackwell | [7 empty] | Full | [5 empty] | Unknown |  | Unassigned |  | Danielle.Blackwell@smith-nephew.com | Sri Tupil
TSF | Smart TSF; dTSF | Archive | The Smart TSF website is designed for use with the S+N Taylor Spatial Frame. It allows surgeons to enter deformity and mounting parameters, and generate day-to- | Digital | Sri Tupil | Marcos Margulies | [7 empty] | Full | [5 empty] | Unknown | 44287.375 | Unassigned |  | Marcos.Margulies@smith-nephew.com | James Fullarton
WebOps | POWER | Active | Loaners and Consignments Application Support Manager=Mohamed Dawood Product Support Level=Supported Delivery Manager Cert: 14-JUN-17 | Supply Chain | Massimo Trambaioli | Balvant Kelaiya | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Not EOL | Full | [5 empty] | No | 41743.375 | Unassigned |  | Swapnil.Kelaiya-off@smith-nephew.com | Massimo Trambaioli
WinAutomation (DXC) | DXC RPA; DXC Robotics; | Retired | A Robotics tool used by DXC to perform high volume tasks automatically. LOC PROD = NGDC (HOU AUS) ====================================== From: Adewole, Fola Sent: Wednesday, September 26, 2018 7:40 AM To: Bernard, Andres <Andres.Bernard@smith-nephew.com> Subject: FW: Landscape Simplification Hi Andres, Hope you are well, I've been doing some research into "WinAutomation (DXC)" and from my correspondence with Steve Horgan, it sounds like it can be decommissioned. As the Support Manager could you please start the decommissioning process for this application. Kind Regards, Fola From: Horgan, Stephen Sent: 25 September 2018 19:19 To: Adewole, Fola <Fola.Adewole@smith-nephew.com> Subject: RE: Landscape Simplification We don't use WinAutomation anymore. Thank you Steve Horgan | Group Functions | Imtiaz Iqbal | Andres Bernard | [7 empty] | Full | [5 empty] | Unknown | 42370.375 | Unassigned |  | Andres.Bernard@smith-nephew.com
York Intranet | Bionet | Retired | 05/09/16 - Per David Gamble: "I just got information from Tom on this server. It is hosting a legacy York intranet site that is going to be active until they close that facility. " Bionet. | Local Europe | Imtiaz Iqbal | Andres Bernard | [7 empty] | Full | [5 empty] | Unknown |  | Unassigned |  | Andres.Bernard@smith-nephew.com
zScaler Private Access (ZPA) | US pension vendor interface | Retired | Employee Demographic data to benefits provider | Group Functions | Imtiaz Iqbal | Steve Horgan | [7 empty] | Full | [5 empty] | Unknown | 38352.375 | Unassigned |  | Stephen.Horgan@smith-nephew.com

## Validation
Finished (blue) | Yes | Yes | Not done | Scope Change (out of scope)
On track (green) | No | No | Done, no evidence provided | Schedule Change
Risk of delay (amber) |  | Done | Done with evidence provided | Migration Strategy Change
Imminent Delay (red) |  |  | N/A | Other
Not started (grey) |  |  |  | Scope Change
Out of scope (dark grey) |  |  |  | Scope Change (added to scope)
Reverted (light orange)

## Change Control v2
Change ID | Change Type | Application Name | Environment | Change | Updated By | Approved BY | Date
1 | Migration Strategy Change | SNID Archived Shipping Documents | DEV | Moved Treatment to Rehost and Wave to Wave 1 | Debojit | Amit S | 1900-01-02
1 | Migration Strategy Change | SNID Archived Shipping Documents | QA | Moved Treatment to Rehost and Wave to Wave 1 | Debojit | Amit S | 2020-12-09
2 | Scope Change (out of scope) (out of scope) | Dubai Axapta | QA | Out of scope | Mateusz P | Ken | 2020-12-11
2 | Scope Change (out of scope) (out of scope) | Dubai Axapta | PROD | Out of scope | Mateusz P | Ken | 2020-12-11
3 | Migration Strategy Change | Informatica MDM Data Quality | DEV | Changed Treatment Plan to REPLATFORM as per SNI SDM request (Sathia) & discussion with SNI leadership on 10th Dec | Debojit | Ken/Adrian | 2020-12-10
3 | Migration Strategy Change | Informatica MDM Data Quality | TEST | Changed Treatment Plan to REPLATFORM as per SNI SDM request (Sathia) & discussion with SNI leadership on 10th Dec | Debojit | Ken/Adrian | 2020-12-10
3 | Migration Strategy Change | Informatica MDM Data Quality | EVL | Changed Treatment Plan to REPLATFORM as per SNI SDM request (Sathia) & discussion with SNI leadership on 10th Dec | Debojit | Ken/Adrian | 2020-12-10
3 | Migration Strategy Change | Informatica MDM Data Quality | PROD | Changed Treatment Plan to REPLATFORM as per SNI SDM request (Sathia) & discussion with SNI leadership on 10th Dec | Debojit | Ken/Adrian | 2020-12-10
4 | Scope Change (added to scope) | QA Change Control | DEV | Added QA Change Control application to migration scope to mitigate comingling situation and Rehosting to Azure. | Debojit | Ken | 2020-12-14
4 | Scope Change (added to scope) | QA Change Control | QA | Added QA Change Control application to migration scope to mitigate comingling situation and Rehosting to Azure. | Debojit | Ken | 2020-12-14
4 | Scope Change (added to scope) | QA Change Control | PROD | Added QA Change Control application to migration scope to mitigate comingling situation and Rehosting to Azure. | Debojit | Ken | 2020-12-14
5 | Scope Change (out of scope) | Recon LaunchPad (SSO) | QA | According to cutover planning there is no QA environment for this App. Markes Out of Scope. | Debojit |  | 2021-01-11
6 | Scope Change (added to scope) | Inventures (SCAMPI) Web App | DEV | Added the DEV environment also, which was not part of the initial assessment which had QA and PROD only. | Debojit |  | 2021-01-11
7 | Scope Change (added to scope) | Reimbursement | DEV | Added the DEV environment also, which was not part of the initial assessment which had QA and PROD only. | Debojit |  | 2021-01-11
8 | Schedule Change | Bugzilla | PROD | Moved out of Wave 2 | Jyotsna | Matt Pie | 2021-01-15
9 | Schedule Change | CVS | PROD | Moved out of Wave 2 | Jyotsna | Matt Pie | 2021-01-15
10 | Schedule Change | Cockpit | PROD | Moved to Wave 8 | Jyotsna | Matt Pie | 2021-01-15
11 | Schedule Change | ID Prove | PROD | Moved to Wave 5 | Jyotsna | Yvonne | 2021-01-15
12 | Schedule Change | Winflex | PROD | Moved out of Wave 2 to Wave 4 because it has dependencies associated with Hydra & Assist4 which is scheduled for Wave 4 | Jyotsna | Yvonne/Matt Pie | 2021-01-15
13 | Schedule Change | Lutron | PROD | Moved out of W2-MG1 | Jyotsna |  | 2021-01-15
14 | Scope Change (out of scope) | InfinityQS ProFicient (SPC software) | PROD | Out of scope because this application is planned to be phased out before end of this year. | Jyotsna | Ken / Aileen | 2021-01-20
15 | Scope Change (out of scope) | FileZilla | PROD | Retired application now, moved out of scope. | Mateusz P | Ken | 2021-02-01
16 | Scope Change (out of scope) | Cockpit | PROD | Review because it is already in Azure as part of new build | Mateusz P | Ken | 2021-02-01
17 | Scope Change (out of scope) | Axapta (Dubai) | QA | Out of scope | Mateusz P | Ken | 2021-02-01
17 | Scope Change (out of scope) | Axapta (Dubai) | PROD | Out of scope | Mateusz P | Ken | 2021-02-01
17 | Scope Change (out of scope) | Axapta (India) | QA | Out of scope | Mateusz P | Ken | 2021-02-01
17 | Scope Change (out of scope) | Axapta (India) | DR | Out of scope | Mateusz P | Ken | 2021-02-01
17 | Scope Change (out of scope) | Axapta (India) | PROD | Out of scope | Mateusz P | Ken | 2021-02-01
17 | Scope Change (out of scope) | Axapta (Malaysia & Thailand) | DR | Out of scope | Mateusz P | Ken | 2021-02-01
17 | Scope Change (out of scope) | Axapta (Malaysia & Thailand) | PROD | Out of scope | Mateusz P | Ken | 2021-02-01
17 | Scope Change (out of scope) | Axapta (Singapore) | QA | Out of scope | Mateusz P | Ken | 2021-02-01
17 | Scope Change (out of scope) | Axapta (Singapore) | Prod | Out of scope | Mateusz P | Ken | 2021-02-01
18 | Migration Strategy Change | Electronic Instructions for Use | DEV | Changed Treatment Plan to REPLATFORM as part of DB consolidation | Jyotsna | Matt Pie / Carla | 2021-02-03
18 | Migration Strategy Change | Electronic Instructions for Use | QA | Changed Treatment Plan to REPLATFORM as part of DB consolidation | Jyotsna | Matt Pie / Carla | 2021-02-03
19 | Scope Change (out of scope) | Mobile Inventory Management System | DEV | Added the DEV and QA environments for this Application to the list which was not part of the list initially | Debojit |  | 2021-02-03
19 | Scope Change (out of scope) | Mobile Inventory Management System | QA | Added the DEV and QA environments for this Application to the list which was not part of the list initially | Debojit |  | 2021-02-03
20 | Other | Target DB Servers for SQL 2019 consolidation |  | Column N includes target DB servers for SQL 2019 consolidation. | Mateusz P | Mateusz P | 2021-02-04
21 | Scope Change (out of scope) | Lutron | PROD | Out of scope because of the latency requirements - to be verified again | Mateusz P | Ken | 2021-02-04
22 | Scope Change (out of scope) | Mcosomos | PROD | Out of scope - Desktop application. There is no app server. | Mateusz P |  | 2021-02-04
23 | Scope Change (out of scope) | Motion Board | PROD | To be decomissioned end of the year. To be confirmed it will be fully retired EOY (Mat P) | Mateusz P |  | 2021-02-04
24 | Scope Change (out of scope) | Trackwise (EU) | DEV | To be moved to AVS because of SQL 2005 and no upgrade possible. Ken approval to follow. Retirement date to follow. | Mateusz P |  | 2021-02-04
24 | Scope Change (out of scope) | Trackwise (EU) | VAL | To be moved to AVS because of SQL 2005 and no upgrade possible. Ken approval to follow. Retirement date to follow. | Mateusz P |  | 2021-02-04
24 | Scope Change (out of scope) | Trackwise (EU) | PROD | To be moved to AVS because of SQL 2005 and no upgrade possible. Ken approval to follow. Retirement date to follow. | Mateusz P |  | 2021-02-04
25 | Scope Change (out of scope) | Expres Visionaire | PROD | To be retired. | Mateusz P | Adrian | 2021-02-08
26 | Scope Change (out of scope) | Partmaker | PROD | License server to be decomissioned, hence app out of scope | Mateusz P | Adrian | 2021-02-08
27 | Schedule Change | Informatica (Wound Data Intergration) | PROD | Moved to W3-MG2 19th Mar cutover per request from Sathia | Debojit | Sathia / Ken | 2021-02-08
28 | Schedule Change | AWM Data Warehouse | PROD | Moved to W3-MG2 19th Mar cutover per request from Sathia | Debojit | Sathia / Ken | 2021-02-08
29 | Migration Strategy Change | Flex LM | PROD | Changed to REPLATFORM. Per SNI guidelines Windows 2008 Enterprise & Standard is not supported in SNi Azure Cloud | Debojit |  | 2021-02-09
30 | Migration Strategy Change | MIMICS | PROD | Changed to REPLATFORM. Per SNI guidelines Windows 2008 Enterprise & Standard is not supported in SNi Azure Cloud | Debojit |  | 2021-02-09
31 | Migration Strategy Change | Myriad | PROD | Changed to REPLATFORM. Per SNI guidelines Windows 2008 Enterprise & Standard is not supported in SNi Azure Cloud | Debojit |  | 2021-02-09
32 | Migration Strategy Change | SEAL Application | PROD | Changed to REPLATFORM. Per SNI guidelines Windows 2008 Enterprise & Standard is not supported in SNi Azure Cloud | Debojit |  | 2021-02-09
33 | Migration Strategy Change | Unigraphics | PROD | Changed to REPLATFORM. Per SNI guidelines Windows 2008 Enterprise & Standard is not supported in SNi Azure Cloud | Debojit |  | 2021-02-09
34 | Migration Strategy Change | Visionaire Case Processing of Images | QA | Changed to REPLATFORM. Per SNI guidelines Windows 2008 Enterprise & Standard is not supported in SNi Azure Cloud | Debojit |  | 2021-02-09
34 | Migration Strategy Change | Visionaire Case Processing of Images | LB | Changed to REPLATFORM. Per SNI guidelines Windows 2008 Enterprise & Standard is not supported in SNi Azure Cloud | Debojit |  | 2021-02-09
34 | Migration Strategy Change | Visionaire Case Processing of Images | PROD | Changed to REPLATFORM. Per SNI guidelines Windows 2008 Enterprise & Standard is not supported in SNi Azure Cloud | Debojit |  | 2021-02-09
35 | Schedule Change | Visionaire Case Processing of Images | QA | Moved to June Wave 6 as the Application migration project has to be aligned with AWS migration of Visionaire | Lukasz P | Requalann | 2021-02-16
35 | Schedule Change | Visionaire Case Processing of Images | LB | Moved to June Wave 6 as the Application migration project has to be aligned with AWS migration of Visionaire | Lukasz P | Requalann | 2021-02-16
35 | Schedule Change | Visionaire Case Processing of Images | PROD | Moved to June Wave 6 as the Application migration project has to be aligned with AWS migration of Visionaire | Lukasz P | Requalann | 2021-02-16
36 | Schedule Change | Informatica MDM Data Quality | QA | Moved to W4-MG1 as per Adrian | Mateusz P | Adrian | 2021-02-16
36 | Schedule Change | Informatica MDM Data Quality | DEV | Moved to W4-MG1 as per Adrian | Mateusz P | Adrian | 2021-02-16
36 | Schedule Change | Informatica MDM Data Quality | TEST | Moved to W4-MG1 as per Adrian | Mateusz P | Adrian | 2021-02-16
37 | Schedule Change | Informatica P360 | DEV | Moved to W4-MG1 as per Adrian | Mateusz P | Adrian | 2021-02-16
37 | Schedule Change | Informatica P360 | TEST | Moved to W4-MG1 as per Adrian | Mateusz P | Adrian | 2021-02-16
37 | Schedule Change | Informatica P360 | QA | Moved to W4-MG1 as per Adrian | Mateusz P | Adrian | 2021-02-16
38 | Scope Change (out of scope) | IQ-Soft (Aarau) | PROD | AVS scope. Ken's appoval to follow. | Mateusz P |  | 2021-02-16
39 | Scope Change (out of scope) | Visionaire Case Processing of Images | QA | To be moved to AWS in April, because of HIPAA data | Mateusz P | Adrian | 2021-02-16
39 | Scope Change (out of scope) | Visionaire Case Processing of Images | LB | To be moved to AWS in April, because of HIPAA data | Mateusz P | Adrian | 2021-02-16
39 | Scope Change (out of scope) | Visionaire Case Processing of Images | PROD | To be moved to AWS in April, because of HIPAA data | Mateusz P | Adrian | 2021-02-16
40 | Schedule Change | Tarife | PROD | Has to go with Assist4. Moved to W5-MG1 | Mateusz P | Adrian | 2021-02-16
41 | Scope Change (out of scope) | Informatica MDM Data Quality | EVL | EVL env out of scope | Mateusz P | Adrian | 2021-02-16
42 | Scope Change (out of scope) | Informatica P360 | EVL | EVL env out of scope | Mateusz P | Adrian | 2021-02-16
43 | Scope Change (added to scope) | Global Labeling System (PRISYM) | QA | Addition to the scope | Mateusz P | Ken | 2021-02-16
43 | Scope Change (added to scope) | Global Labeling System (PRISYM) | PROD | Addition to the scope | Mateusz P | Ken | 2021-02-16
44 | Scope Change (added to scope) | SNMAG_DWH | PROD | Addition to the scope | Mateusz P | Ken | 2021-02-16
45 | Other | Inventures (SCAMPI) Web App | DEV | SDM - Ian Bennett | Mateusz P | Ken | 2021-02-16
45 | Other | Inventures (SCAMPI) Web App | PROD | SDM - Ian Bennett | Mateusz P | Ken | 2021-02-16
45 | Other | Inventures (SCAMPI) Web App | QA | SDM - Ian Bennett | Mateusz P | Ken | 2021-02-16
46 | Other | Electronic Instructions for Use | PROD | SDM - Carla Morris | Mateusz P | Ken | 2021-02-16
46 | Other | Electronic Instructions for Use | DEV | SDM - Carla Morris | Mateusz P | Ken | 2021-02-16
46 | Other | Electronic Instructions for Use | QA | SDM - Carla Morris | Mateusz P | Ken | 2021-02-16
46 | Other | Electronic Instructions for Use | DR | SDM - Carla Morris | Mateusz P | Ken | 2021-02-16
47 | Schedule Change | FLEx LM | PROD | Moved to 30th May 2021 to include with Co-Mingled Apps. | Arun S |  | 2021-02-18
48 | Other | CIMCO Mansfield | DEV | Updated server names for CIMCO Mansfield DEV and PROD based on inputs from App SME Greg T | Debojit M |  | 2021-02-20
48 | Other | CIMCO Mansfield | PROD |  | Debojit M |  | 2021-02-20
49 | Schedule Change | CIMCO Memphis | DEV | Aligned CIMCO Memphis to Wave 6 with CIMCO China since server is being shared with CIMCO China | Debojit M |  | 2021-02-20
49 | Schedule Change | CIMCO Memphis | PROD | Aligned CIMCO Memphis to Wave 6 with CIMCO China since server is being shared with CIMCO China | Debojit M |  | 2021-02-20
50 | Schedule Change | dataSTOR | PROD | Moved to April cutover due to delays in planning from vendor. | Debojit M | Adrian C | 2021-02-23
51 | Schedule Change | OSISoft PI System | PROD | Rescheduled to Wave 5 MG1 to accomodate decision around China regulatory requirements. | Debojit M | Adrian C | 2021-02-23
52 | Schedule Change | SEAL Application | PROD | Rescheduled to Wave 4 MG1 to accomodate vendor dependency and engagement. | Debojit M | Mateusz P | 2021-02-23
53 | Schedule Change | TOTVS | DEV | Assigned to W3-MG2 instead of W3-MG1 to accomodate additional time to build firewall rules for DMZ & terminal server licensing. | Debojit M | Mateusz P | 2021-02-23
54 | Schedule Change | Mobile Inventory Management System | TEST | Moved to July per discussion with ITLT. May be included with additional apps as a REHOST. | Debojit M | Adrian C | 2021-02-24
54 | Schedule Change | Mobile Inventory Management System | PROD | Moved to July per discussion with ITLT. May be included with additional apps as a REHOST. | Debojit M | Adrian C | 2021-02-24
54 | Schedule Change | Mobile Inventory Management System | PROD (archive) | Moved to July per discussion with ITLT. May be included with additional apps as a REHOST. | Debojit M | Adrian C | 2021-02-24
54 | Schedule Change | Mobile Inventory Management System | DR | Moved to July per discussion with ITLT. May be included with additional apps as a REHOST. | Debojit M | Adrian C | 2021-02-24
55 | Scope Change (out of scope) | Winflex | PROD | Moved to Out Of Scope per discussion with Yvonee because of the File Server dependency. | Debojit M | Ken | 2021-02-24
56 | Migration Strategy Change | Winshuttle | DEV | DB Re-platform - SQL 2019 consolidation | Mateusz P |  | 2021-02-24
56 | Migration Strategy Change | Winshuttle | PROD | DB Re-platform - SQL 2019 consolidation | Mateusz P |  | 2021-02-24
56 | Migration Strategy Change | Winshuttle | QA | DB Re-platform - SQL 2019 consolidation | Mateusz P |  | 2021-02-24
56 | Migration Strategy Change | PricingTool | PROD | DB Re-platform - SQL 2019 consolidation | Mateusz P |  | 2021-02-24
56 | Migration Strategy Change | AWD Tracker | PROD | DB Re-platform - SQL 2019 consolidation | Mateusz P |  | 2021-02-24
56 | Migration Strategy Change | Metasys | PROD | DB Re-platform - SQL 2019 consolidation | Mateusz P |  | 2021-02-24
56 | Migration Strategy Change | Lasernet / Nemhandel | PROD | DB Re-platform - SQL 2019 consolidation | Mateusz P |  | 2021-02-24
56 | Migration Strategy Change | ID Prove | PROD | DB Re-platform - SQL 2019 consolidation | Mateusz P |  | 2021-02-24
56 | Migration Strategy Change | Spectrum 10 | PROD | DB Re-platform - SQL 2019 consolidation | Mateusz P |  | 2021-02-24
57
58
59
60
61
62
63
64
65
66
67
68