## Cutover Summary
Change Information
Wave Group | Wave 3
Move Group | Move Group 1
Migration Cutover Id | W3-MG1
Change Request Number | Multiple CRs
Change Submission Date | 29th Jan 2021
CAB Approval Date | 2021-02-17
Change Implementation Start Date | 17-02-2021 12:30:00 PM EST
Change Implementation End Date | 12-03-2021 12:00:00 PM EST
Change Outage Window Start | 5th Mar 9:30 PM US EST
Change Outage Window End | 7th Mar 9:30 PM US EST
Region | US | US | US | US | US | US | US | US | US | US | US | US
Vertical | Supply Chain | Commercial | Commercial2 | Data & Analytics | R&D | Commercial3 | Group Functions | RAQA | Commercial4 | Commercial5 | Commercial6 | Supply Chain2
Application | Connect Ship (UPS/DHL) | Endoloans | Global Returns Disposition Tool | GSC Data Warehouse Admin Tool | Inventures (SCAMPI) Web App | Nomino Security | Non-Employee Database | QA Change Control | Recon LaunchPad (SSO) | Reimbursement | Sales Request Forms | SNID Archived Shipping Documents
Application Environment | QA | PROD | PROD | PROD | PROD | PROD | PROD | Prod | PROD | PROD | PROD | PROD
Treatment Plan- App | Re-Host | Re-Host | Re-Host | Re-Host | Re-Host | Re-Host | Re-Host | Re-Host | Re-Host | Re-Host | Re-Host | Re-Host
Treatment Plan- DB | RePlatform | RePlatform | RePlatform | "NA Will remain on prem-in W3-MG1)" | RePlatform | RePlatform | RePlatform | RePlatform | NA | RePlatform | RePlatform | NA
MoveGroup Status | Confirmed | Confirmed | Confirmed | Confirmed | Confirmed | Confirmed | Confirmed | Confirmed | Confirmed | Confirmed | Confirmed | Confirmed
Server Name - App | USMAN-SMAPDVW32 | USMAN-SMWSPVW12 | USMAN-SMWSPVW12 | USMAN-SMWSPVW12 | USMEMSMAPPVW23, USMAN-SMWSPVW12(Admin) | USMAN-SMWSPVW12 | USMAN-SMWSPVW12 | USMAN-SMWSPVW12 | USMAN-SMWSPVW12 | USMEMSMAPPVW23, USMAN-SMWSPVW12(Reimbursement Admin) | USMAN-SMWSPVW12 | USMAN-SMWSPVW12
Server Name- DB | USMANSMDBDUW01 | USMAN-SMDBPVW12 | USMAN-SMDBPVW12 | UKRTH-SMDBPVW32 (Will remain on prem-in W3-MG1) | USMAN-SMDBPVW12 | SMRTHSQL2 (Cluster); UKRTHSMDBPW03; UKRTHSMDBPW04; | USMAN-SMDBPVW12 | SMRTHSQL2 UKRTHSMDBPW03 UKRTHSMDBPW04 | NA | USMAN-SMDBPVW12 | USMAN-SMDBPVW12 | NA
Application SDM | Amit Shokeen | Andres Bernard | Andres Bernard | Amit Shokeen | Requalann Pereira | Andres Bernard | Paul Davison | Aileen Diola | Andres Bernard | Andres Bernard | Andres Bernard | Amit Shokeen
Pre-Migration SNI Testing | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
GO No GO Decision | GO | GO | GO | GO | GO | GO | GO |  | GO | GO | GO | GO
Cutover Tasks
Backup for All Servers
Disable the Server in Backup Policy and Put in MM.
App Shutdown
Run SQL validation DB script, if applicable
Stop all the DB services for all DB servers. (Rehost only)
Final APP Server Sync to Azure
Final DB Server SYNC to Azure
Power on App Server on Azure
Power on DB server on Azure
Start DB services for all DB servers
Run SQL validation DB script, if applicable
Startup Application Services.
DNS update and point traffic to new host.
Configure Load Balancer and Application Gateway (if applicable)
Validate and test.
Enable Monitoring, Back Up and Update Management on remaining On-Prem servers
CMDB Tracker update
Migration Final Status
Project SME Mapping
Application | Connect Ship (UPS/DHL) | Endoloans | Global Returns Disposition Tool | GSC Data Warehouse Admin Tool | Inventures (SCAMPI) Web App | Nomino Security | Non-Employee Database | QA Change Control | Recon LaunchPad (SSO) | Reimbursement | Sales Request Forms | SNID Archived Shipping Documents
Application SDM | Amit Shokeen | Andres Bernard | Andres Bernard | Amit Shokeen | Requalann Pereira | Andres Bernard | Paul Davidson | Aileen Diola | Andres Bernard | Andres Bernard | Andres Bernard | Amit Shokeen
Application SME | Kamal.Mishra@smith-nephew.com | Maagedha.Shajahan@smith-nephew.com Soumen.Mallick@smith-nephew.com | Maagedha.Shajahan@smith-nephew.com Soumen.Mallick@smith-nephew.com | Maagedha.Shajahan@smith-nephew.com | Maagedha.Shajahan@smith-nephew.com Soumen.Mallick@smith-nephew.com | Maagedha.Shajahan@smith-nephew.com Soumen.Mallick@smith-nephew.com | Maagedha.Shajahan@smith-nephew.com Soumen.Mallick@smith-nephew.com | Maagedha.Shajahan@smith-nephew.com Soumen.Mallick@smith-nephew.com | Maagedha.Shajahan@smith-nephew.com | Maagedha.Shajahan@smith-nephew.com Soumen.Mallick@smith-nephew.com | Maagedha.Shajahan@smith-nephew.com Soumen.Mallick@smith-nephew.com | Kamal.Mishra@smith-nephew.com
HCL Migration - Infra | Rahul Sarin | Rahul Sarin | Rahul Sarin | Rahul Sarin | Rahul Sarin | Rahul Sarin | Rahul Sarin | Rahul Sarin | Rahul Sarin | Rahul Sarin | Rahul Sarin | Rahul Sarin
HCL Migration - Apps | Kishore Balimidi | Vidit Kumar | Raju Pottella | Raju Pottella | Deepak Sathya Babu | Vidit Kumar | Vidit Kumar | Vidit Kumar | Deepak Sathya Babu | Deepak Sathya Babu | Deepak Sathya Babu | Deepak Sathya Babu
Application cTASK SNOW Group
HCL OPS SME MAPPING
HCL Ops - Windows/Linux | Johnson.Susairaj@smith-nephew.com |  | +91 9841306591 | HCL-Windows@smith-nephew.com
HCL Ops - Network | Abdul.Sayeed@smith-nephew.com |  | +91 9342244325 | HCL-NetworkData@smith-nephew.com
HCL Ops - Monitoring | Sridhar.Venkatakrishnan@smith-nephew.com |  | +91 7305838202 | HCL-Tools@smith-nephew.com
HCL Ops - Backup | Dhachanamoorthy.Selvaraj@smith-nephew.com |  | +91 8122989025 | HCL-Backup@smith-nephew.com
HCL Ops - Apps | Dhinagaran.Kuppusamy@smith-nephew.com |  | +91 9901877221 | HCL-AMS@Smith-Nephew.com
SNI Security | Purushothaman.Sekar@smith-nephew.com |  | +91 9566117107 | HCL-NetworkSecurity@smith-nephew.com
DXC - Linux

## OEM (hidden)
S.No. | Category | Pre Migration Steps | Platform | Responsibility
1 | Migration - Initial Setup & Sync | Network Team to check and confirm on the Data center Interconnect Health (ER) | Azure Cloud | HCL Migration - Infra/Network Team
2 | Migration - Initial Setup & Sync | Backup Policy Creation in Azure | Azure Cloud | HCL Migration - Infra
3 | Migration - Initial Setup & Sync | Azure Resource Group Creation | Azure Cloud | HCL Migration - Infra
4 | Migration - Initial Setup & Sync | Subnet Creation | Azure Cloud | HCL Migration - Infra
5 | Migration - Initial Setup & Sync | Provision new Database VM in the Azure (Migration Prod Subscription) as per given detail by App Team | Azure Cloud | HCL Migration - Infra
6 | Migration - Initial Setup & Sync | Update the patches as required on new Database VM | Azure Cloud | HCL Migration - Infra
7 | Migration - Initial Setup & Sync | Allocate and create Disk Devices for for the DB Servers | Azure Cloud | HCL Migration - Infra
8 | Migration - Initial Setup & Sync | Create Disk Group for ASM (DATA & FRA) | Azure Cloud | HCL Migration - DBA
9 | Migration - Initial Setup & Sync | Configure IP and DNS entry (/etc/resolv.conf) for the DB Server | Azure Cloud | HCL Migration - Infra
10 | Migration - Initial Setup & Sync | Create the DNS Entry for the DR and DB Server | Azure Cloud | HCL Migration - Infra
11 | Migration - Initial Setup & Sync | Provide access to App/DBA. Provide Sudo permission if applicable | Azure Cloud | HCL Migration - Infra
12 | Migration - Initial Setup & Sync | Install Oracle 12.1.0.2 for oracle/grid binaries ( Need GUI Interface) and create ASM DB | Azure Cloud | HCL Migration - DBA
13 | Migration - Initial Setup & Sync | Perform pre-requisites set up for Data Guard | Azure Cloud | HCL Migration - DBA
14 | Migration - Initial Setup & Sync | Setup lisener.ora and tnsnames.ora file on cloud database host | Azure Cloud | HCL Migration - DBA
15 | Migration - Initial Setup & Sync | Edit /etc/oratab on cloud database host | Azure Cloud | HCL Migration - DBA
16 | Migration - Initial Setup & Sync | Setup the .oraenv file on cloud database host | Azure Cloud | HCL Migration - DBA
17 | Migration - Initial Setup & Sync | Setup the memory parameters for oracle on the cloud host | Azure Cloud | HCL Migration - DBA
18 | Migration - Initial Setup & Sync | Copy the init.ora file from on-premise db host to cloud db-host | Azure Cloud | HCL Migration - DBA
19 | Migration - Initial Setup & Sync | Check all the required permissions for the newly created Database | Azure Cloud | HCL Migration - DBA
20 | Migration - Initial Setup & Sync | Make sure all the filesystems in consitent level and fix any issues in the VM (Sanity check) /boot should be 50% free | On-Prem | DXC
21 | Migration - Initial Setup & Sync | Install / Configure OEM Agent for OEM DB Primary Server and DR DB Server | Azure Cloud | Srinivas
22 | Migration - Initial Setup & Sync | Take complete snapshot backup of App Server, DB Server and DR server | On-Perm | DXC
S.No. | Category | Migration Steps | Platform | Responsibility
22 | Cutover (Downtime Window) | Disable Monitoring and a backup for the App Server and DR Server | On-Perm | DXC
23 | Cutover (Downtime Window) | Create a dummy table in the Primary OEM DB server for validating DB consistency after migration. Perform log switch | On-Prem | Srinivas
24 | Cutover (Downtime Window) | Capture all the On-Perm Prod Server configuration as an Evidence | Azure Cloud | HCL Migration - Infra/DXC
25 | Cutover (Downtime Window) | Perform database Backup for emrepprd database from on-premise | On-Prem | Srinivas
26 | Cutover (Downtime Window) | Move the Database Backup from On-Perm to Azure for restoration | Azure Cloud | HCL Migration - Infra
27 | Cutover (Downtime Window) | Validate the On-prem system and ensure no process is active and running | On-Prem | Srinivas
28 | Cutover (Downtime Window) | Disable the Data guard Log shipping and Log Transfer for OEM Prod DB Server | On-Prem | Srinivas
29 | Cutover (Downtime Window) | Disable the archive log destination on Primary database for On-Prem Prod database. Shutdown the OEM instances(emrepprd) on-prem prod database environment (i) SQL> shutdown immediate Note : Don’t Shutdown the VM which is in On-Perm as it is hosting other DBs as well | On-Prem | Srinivas
30 | Cutover (Downtime Window) | Power On the migrated server in Azure after the Source Server Shutdown is confirmed | Azure Cloud | HCL Migration - Infra
31 | Cutover (Downtime Window) | Validate the DNS entry in /etc/resolv.conf file | Azure Cloud | HCL Migration - Infra
32 | Cutover (Downtime Window) | AD Team to bind new IP with hostname / aliases | On-Prem/Azure Cloud | HCL Ops Infra/ HCL Migration - Infra
33 | Cutover (Downtime Window) | Ping Hostname and FQDN from Network to ensure both are responding to primary IP. | Azure Cloud | HCL Migration - Infra
34 | Cutover (Downtime Window) | Check CPU and RAM Allocation at Azure | Azure Cloud | HCL Migration - Infra
35 | Cutover (Downtime Window) | Login to the server using root via SSH | Azure Cloud | HCL Migration - Infra
36 | Cutover (Downtime Window) | Validate the disk details as per Source | Azure Cloud | HCL Migration - Infra
37 | Cutover (Downtime Window) | Validate the NFS Service if it is not running start the service | Azure Cloud | HCL Migration - Infra
38 | Cutover (Downtime Window) | Make sure the NFS mount points are avaialble if there was any in Source | Azure Cloud | HCL Migration - Infra
39 | Cutover (Downtime Window) | Check all required ports are open in both DB and APP server. Required ports will be provided by APP/DB team | Azure Cloud | HCL Migration - Infra
40 | Cutover (Downtime Window) | Confirm the App team once all validation pass | Azure Cloud | HCL Migration - Infra
41 | Cutover (Downtime Window) | Take the Database Backup in source server | On-Perm | Srinivas
42 | Cutover (Downtime Window) | Copy the Database backup from Source to target | Azure Cloud | HCL Migration - Infra
43 | Cutover (Downtime Window) | Restore the Database and Restart Oracle Database services, Listeners ( lsnrctl start ) - SQL> startup | Azure Cloud | HCL Migration - DBA
44 | Cutover (Downtime Window) | Validate if the database is up and running fine and all connections looking good - (ps -ef¦grep pmon) | Azure Cloud | HCL Migration - DBA
45 | Cutover (Downtime Window) | Check the permission for TNSORA file for DB admins for modification | Azure Cloud | HCL Migration - DBA
46 | Cutover (Downtime Window) | Configure Data Guard between Prod and DR DB and enable synchronization | Azure Cloud | HCL Migration - DBA
47 | Cutover (Downtime Window) | Take the required backup of the application in app server | On-Perm | Srinivas
48 | Cutover (Downtime Window) | Disable Doubletake(DR replication) for server PROD USATL-SMAPPUL02 (Primary OMS App Server) | On-Perm | Roger Pearson / David Pfaffenroth | David.Pfaffenroth@smith-nephew.com
49 | Cutover (Downtime Window) | Initiate the Azure Migrate | Azure Cloud | HCL Migration - Infra
50 | Cutover (Downtime Window) | Bring the source App server down | On-Perm | DXC
51 | Cutover (Downtime Window) | Change the IP address of the App Server | Azure Cloud | HCL Migration - Infra
52 | Cutover (Downtime Window) | Create a DNS Record for the App server | On-Prem/Azure Cloud | HCL Ops Infra/ HCL Migration - Infra
53 | Cutover (Downtime Window) | Validate the App Server in Target | Azure Cloud | HCL Migration - Infra
54 | Cutover (Downtime Window) | Reconfigure cloud DB details repository to the cloud OEM | Azure Cloud | Srinivas
55 | Cutover (Downtime Window) | Validate the OMS instance (emrepprd_dr) and its connections with Oracle Database also enable log shipping | Azure Cloud | Srinivas
56 | Cutover (Downtime Window) | Validate the logs and check for any errors ( Log file location is listed in the Configuration Tab) | Azure Cloud | Srinivas
57 | Cutover (Downtime Window) | Create any schedule job if required in DB Server (Crontab) | Azure Cloud | Srinivas
58 | Cutover (Downtime Window) | Install agent, Configure Backup Policy and initiate Backup on both APP and DB server | Azure Cloud | HCL Migration - Infra
59 | Cutover (Downtime Window) | Install and configure Monitoring in both App & DB Server | Azure Cloud | HCL Migration - Infra
60 | Cutover (Downtime Window) | Un-install tool agents used in On-permises (System Center EP Protection, SCCM, SCOM, Backup) | Azure Cloud | HCL Migration - Infra
61 | Cutover (Downtime Window) | Perform one full infra validation | Azure Cloud | HCL Migration - Infra
62 | Cutover (Downtime Window) | Run the Smoke Test cases and do a complete Sanity on the application | Azure Cloud | Srinivas/ App Migration Team
63 | Cutover (Downtime Window) | Coordinate with SDM/SME's for Unit Test cases and support during the Acceptance Testing | Azure Cloud | Srinivas/ App Migration Team
64 | Post-Cutover | Rename the App Server to (Migratedon_date) in Vcenter for the Application Server | On-Perm | DXC
65 | Post-Cutover | Capture the server configuration in azure this include CPU, Mem, Disk, Network and Ports | Azure Cloud | HCL Migration - Infra
66 | Post-Cutover | Update the IP sheet | Azure Cloud | HCL Migration - Infra
67 | Post-Cutover | Update the DNS sheet | Azure Cloud | HCL Migration - Infra
68 | Post-Cutover | Change the status of the change request | Azure Cloud | HCL Migration - Infra
69 | Post-Cutover | Send Migration confirmation email to all stakeholders, informing that the application is live in Azure Cloud | Azure Cloud | App Migration Team
70 | Post-Cutover | Get the Business Sign Off on the Testing | Azure Cloud | App Migration Team
71 | Post-Cutover | Get the Sign Off from SDM | Azure Cloud | App Migration Team
72 | Post-Cutover | Get Sign off from Ken | Azure Cloud | App Migration Team
73 | Migration - Initial Setup & Sync | Clone PRIMARY Database VM to DR Database VM in Diff Zone - Allocate and create Disk Devices for for the DB Servers - Create Disk Group for ASM (DATA & FRA) | Azure Cloud | HCL Migration - Infra
74 | Migration - Initial Setup & Sync | Configure Hostname/IP and DNS entry (/etc/resolv.conf) for the New DR DB Server | Azure Cloud | HCL Migration - Infra
75 | Migration - Initial Setup & Sync | Create a DNS Recored for the DR server | Azure Cloud | HCL Migration - Infra
76 | Migration - Initial Setup & Sync | Provide access to App/DBA. Provide Sudo permission if applicable | Azure Cloud | HCL Migration - Infra
77 | Migration - Initial Setup & Sync | Install Oracle 12.1.0.2 for oracle/grid binaries ( Need GUI Interface) , create ASM DB, preform pre-requisites set up for data guard (If Applicable) | Azure Cloud | HCL Migration - DBA
78 | Migration - Initial Setup & Sync | Setup lisener.ora and tnsnames.ora file on cloud database host | Azure Cloud | HCL Migration - DBA
79 | Migration - Initial Setup & Sync | Setup lisener.ora and tnsnames.ora file on cloud database host | Azure Cloud | HCL Migration - DBA
80 | Migration - Initial Setup & Sync | Edit /etc/oratab on cloud database host | Azure Cloud | HCL Migration - DBA
81 | Migration - Initial Setup & Sync | Setup the .oraenv file on cloud database host | Azure Cloud | HCL Migration - DBA
82 | Migration - Initial Setup & Sync | Setup the memory parameters for oracle on the cloud host | Azure Cloud | HCL Migration - DBA
83 | Migration - Initial Setup & Sync | Copy the init.ora file from on-premise db host to cloud db-host | Azure Cloud | HCL Migration - DBA
84 | Migration - Initial Setup & Sync | Check all the required permissions for the newly created Database | Azure Cloud | HCL Migration - DBA
85 | Migration - Initial Setup & Sync | Make sure all the filesystems in consitent level and fix any issues in the VM (Sanity check) | On-Prem | DXC
86 | Cutover (Downtime Window) | Create a dummy table in the Primary OEM DB server for validating DB consitency after migration. Perform log switch | On-Prem | Srinivas
87 | Cutover (Downtime Window) | Capture all the On-Perm DR Server configuration as an Evidence | Azure Cloud | HCL Migration - Infra/DXC
88 | Cutover (Downtime Window) | Validate the On-prem system and ensure no process is active and running | On-Prem | Srinivas
89 | Cutover (Downtime Window) | Disable the Dataguard Log shipping and Log Transfer for server usmem-smdbpul06 ( on-prem OEM DR Database Server) dgmgrl>edit database 'emrepprd_dr' set state='APPLY-OFF'; dgmgrl>edit database 'emrepprd' set state='TRANSPORT-OFF';Note : Don’t Shutdown the VM which is in On-Prem as it is hosting other DBs as well | On-Prem | Srinivas
90 | Cutover (Downtime Window) | Disable the archive log destination on Primary database for On-Prem DR database.Shutdown the OEM instances(emrepprd_dr) on-prem DR database environment (i) SQL> shutdown immediate Note : Don’t Shutdown the VM which is in On-Perm as it is hosting other DBs as well | On-Prem | Srinivas
91 | Cutover (Downtime Window) | Perform database Backup for emrepprd database to Create Physical Standby database on Cloud emrepprd_dr | Azure Cloud | HCL Migration - DBA
92 | Cutover (Downtime Window) | Move the Database Backup from Prod to DR Server | Azure Cloud | HCL Migration - Infra
93 | Cutover (Downtime Window) | Power On the migrated server in Azure after the Source Server Shutdown is confirmed | Azure Cloud | HCL Migration - Infra
94 | Cutover (Downtime Window) | Validate the DNS entry in /etc/resolv.conf file | Azure Cloud | HCL Migration - Infra
95 | Cutover (Downtime Window) | AD Team to bind new IP with hostname / aliases | On-Prem/Azure Cloud | HCL Ops Infra/ HCL Migration - Infra
96 | Cutover (Downtime Window) | Ping Hostname and FQDN from Network to ensure both are responding to primary IP. | Azure Cloud | HCL Migration - Infra
97 | Cutover (Downtime Window) | Check CPU and RAM Allocation at Azure | Azure Cloud | HCL Migration - Infra
98 | Cutover (Downtime Window) | Login to the server using root via SSH | Azure Cloud | HCL Migration - Infra
99 | Cutover (Downtime Window) | Validate the disk details as per Source | Azure Cloud | HCL Migration - Infra
100 | Cutover (Downtime Window) | Validate the NFS Service if it is not running start the service | Azure Cloud | HCL Migration - Infra
101 | Cutover (Downtime Window) | Make sure the NFS mount points are avaialble if there was any in Source | Azure Cloud | HCL Migration - Infra
102 | Cutover (Downtime Window) | Check all required ports are open in both DB and APP server. Required ports will be provided by APP/DB team | Azure Cloud | HCL Migration - Infra
103 | Cutover (Downtime Window) | Confirm the App team once all validation pass | Azure Cloud | HCL Migration - Infra
104 | Cutover (Downtime Window) | Restore the Database and Restart Oracle Database services, Listeners ( lsnrctl start ) - SQL> startup | Azure Cloud | HCL Migration - DBA
105 | Cutover (Downtime Window) | Configure data guard and enable syncronization | Azure Cloud | HCL Migration - DBA
106 | Cutover (Downtime Window) | Validate if the database is up and running fine and all connections looking good - (ps -ef¦grep pmon) | Azure Cloud | HCL Migration - DBA
107 | Cutover (Downtime Window) | Check the permission for TNSORA file for DB admins for modification | Azure Cloud | HCL Migration - DBA
108 | Cutover (Downtime Window) | Reconfigure cloud DB details repository to the cloud OEM | Azure Cloud | Srinivas
109 | Cutover (Downtime Window) | Validate the OMS instance (emrepprd_dr) and its connections with Oracle Database also enable log shipping | Azure Cloud | Srinivas
110 | Cutover (Downtime Window) | Validate the logs and check for any errors ( Log file location is listed in the Configuration Tab) | Azure Cloud | Srinivas
111 | Cutover (Downtime Window) | Create any schedule job if required in DB Server (Crontab) | Azure Cloud | Srinivas
112 | Cutover (Downtime Window) | Install agent, Configure Backup Policy and initiate Backup for File systems. | Azure Cloud | HCL Migration - Infra
113 | Cutover (Downtime Window) | Install and configure Monitoring on the servers, App & DB (if required). | Azure Cloud | HCL Migration - Infra
114 | Cutover (Downtime Window) | Add server to the patch & update management group | Azure Cloud | HCL Migration - Infra
115 | Cutover (Downtime Window) | Un-install tool agents used in On-permises (System Center EP Protection, SCCM, SCOM, Backup) | Azure Cloud | HCL Migration - Infra
116 | Cutover (Downtime Window) | Perform one full infra validation | Azure Cloud | HCL Migration - Infra
117 | Cutover (Downtime Window) | Run the Smoke Test cases and do a complete Sanity on the application | Azure Cloud | Srinivas/ App Migration Team
118 | Cutover (Downtime Window) | Coordinate with SDM/SME's for Unit Test cases and support during the Acceptance Testing | Azure Cloud | Srinivas/ App Migration Team
119 | Post-Cutover | Rename the App Server to (Migratedon_date) in Vcenter for the Application Server | On-Perm | DXC
120 | Post-Cutover | Capture the server configuration in azure this include CPU, Mem, Disk, Network and Ports | Azure Cloud | HCL Migration - Infra
121 | Post-Cutover | Update the IP sheet | Azure Cloud | HCL Migration - Infra
122 | Post-Cutover | Update the DNS sheet | Azure Cloud | HCL Migration - Infra
123 | Post-Cutover | Change the status of the change request | Azure Cloud | HCL Migration - Infra
124 | Post-Cutover | Send Migration confirmation email to all stakeholders, informing that the application is live in Azure Cloud | Azure Cloud | App Migration Team
125 | Post-Cutover | Get the Business Sign Off on the Testing | Azure Cloud | App Migration Team
126 | Post-Cutover | Get the Sign Off from SDM | Azure Cloud | App Migration Team
127 | Post-Cutover | Get Sign off from Ken | Azure Cloud | App Migration Team

## Test Plan
Application Name | Test Type | Test Scenario
Connectivity Test
Application Smoke Test
Connectivity Test
Application Smoke Test
Connectivity Test
Application Smoke Test

## Cutover(MoveGroup) Scope
HOME
S.no | Servername | IP Address | Migration Method | Azure Hostname | Azure IP Address | Application count | Domain / Workgroup/LDAP(Unix family) | Migration Scope (Y/N) | Environment | Operating System Version | Server Description | Application Name (Primary) | Application Name (Secondary) | Application Name (Third) | Application Name (Others) | Application Owner | DMZ Zone | Dependency | Current Location | Cluster | Public IPs | SSL Offload at Server or LB | NFS/File Share dependencies | Server Status | DNS Record (Alias Entry in Private or Public DNS) | Web URL (URLs published need to know mapped with IP) | Public IP's | Week Day Cutover | Wave Group # | Move Group # | Test | Dev | QA | PROD | Server Handover to APPS (In case of new fresh build) | Tentative Cutover Date | Migrated Date | Migration Method (P2V or V2V) | Azure Migrate (Agentbase / Agentless) | Access requested | Access validation | Azure Region | AZ Subscription | AZ Resource Group | Azure VM Type | Blob SA | Standalone / Cluster / Network LB | Azure Load Balancer | Azure AvailabilitySet/(Azure)Availability Z | Azure vNET | Public IP Addresses | LISTENING Ports | Rights to add server to AD | Local Admin Rights | Disk space issue on source servers | services needed on source server to Azure Migrate | Operating System Version | CPU | Memory | Type of Disk (Premium/Standard) | Disk size Allocated (GB) | Disk size Used (GB) | DB / APP | DB Technology | DB_Version | Identify LUNs > 2TB on source servers | Identify RDM LUNs on source servers | Identify cluster server configuration | Identify unsupported OS | Server Reboot | Mount point validation | Migration Owner | Azure Migrate Initial Sync start date/time | Azure Migrate Initial Sync End date/time | Azure Migrate delta sync start date/time | Azure Migrate delta sync end date/time | Time Taken | Delta size copied (GB) | Temp IP Used for Migration | Test IP | Test VLAN | Resolution Pending with | Target DC | Expected Resolution Direction | Decomm. Approval Date | Decomm. status | Comments
1
2
3
Note on V2: Praveen Shanmugaraju: Server which is accesible from outside SNI Network
Note on Z2: Praveen Shanmugaraju: Is there multiple Alias on IPs
Note on AA2: Praveen Shanmugaraju: Any URL is there for the application and its IP (private/public)
Note on AB2: Praveen Shanmugaraju: Fill the IP during migration
Note on AR2: Praveen Shanmugaraju: Prod or Non-Prod Migration subscription
Note on AS2: Praveen Shanmugaraju: RG will be based on 1. Application 2. Environment Naming: APP_Nonprod_Test App_Prod
Note on AT2: Praveen Shanmugaraju: General purpose Compute optimized Memory optimized Storage optimized High performance compute Link: https://docs.microsoft.com/en-us/azure/virtual-machines/sizes
Note on AU2: Praveen Shanmugaraju: Any extra storage account required
Note on AX2: Praveen Shanmugaraju: Don’t fill this data as need discussion with SNI
Note on AY2: Praveen Shanmugaraju: Prod or Non-Prod Migration Vnet
Note on AZ2: Praveen Shanmugaraju: If column V have a IP then we need a IP in Azure say (Yes/No)
Note on BB2: Praveen Shanmugaraju: Do you have access as superuser to do modification (Yes/No)
Note on BC2: Praveen Shanmugaraju: Do you have access as superuser to do modification (Yes/No)
Note on BD2: Praveen Shanmugaraju: If any drive/Filesystem getting 90% full then capture that
Note on BE2: Praveen Shanmugaraju: Leave blank
Note on BP2: Praveen Shanmugaraju: Any RAW disk if YES then how many disk
Note on BR2: Praveen Shanmugaraju: Current OS is supported or Not (Yes/No)
Note on BS2: Praveen Shanmugaraju: Any Application requirment for server Reboot
Note on BT2: Praveen Shanmugaraju: Cross validation of Mount point with On-Perm

## Backout Plan
HOME
Task Id | Application Name | Rollback tasks
1 | All In Scope | Remove Target server from domain
2 | All In Scope | Shut down the new server and rename Virtual Server as "Failed Migration" and uncheck Power On option from vNIC
3 | All In Scope | Power on Source Servers
4 | All In Scope | Re-join Source server to domain
5 | All In Scope | Notify to perform application startup as needed
6 | All In Scope | Application team will start services on all servers.
7 | All In Scope | Verify that application startup steps have completed
8 | All In Scope | Notify the customer to perform functional testing / UAT
9 | All In Scope | Customer performs functional testing / UAT and checks the application functioning
10 | All In Scope | Remove the additional Firewall rules
11 | All In Scope | Verify that Firewall is accessible and administrator has admin rights on firewall
12 | All In Scope | Ensure all information for application is available(source, Destination, port, protocol, Zone)
13 | All In Scope | Remove the addional Firewall rules and tested all the application is available(source, Destination, port, protocol, Zone)
14 | All In Scope | Verify Routes, NAT rules are in revert for application was migrated, remove if present on firewall
15 | All In Scope | Make sure all the application- Prior to cutover- are funtional
16 | All In Scope | Sign-off on the roll-back
17 | All In Scope | Update the migration tracker with rolled-back servers w/ reason for roll-back
Overall approach is to Backout only in the case of a catastrophic failure. Otherwise issues will be resolved on migrated App/Server in Azure.

## Change Log
Date | What Changed | Owner