## Prod
S.No. | Category | Migration Steps | Platform | Servers | Responsibility
1 | T-1 Before Initial Replication | Create Local user Azurmigrator in Source Server | On-Prem | USMAN-SMWSPVW12 | HCL Migration - Infra
2 | T-1 Start Initial Replication | Initial Replication and validations | On-Prem | USMAN-SMWSPVW12 | HCL Migration - Infra
3 | T-0 Cutover (Downtime Window) | Take a full incremental backup and Snapshot of the Application Server | On-Prem | USMAN-SMWSPVW12 | HCL Ops Infra
4 | T-0 Cutover (Downtime Window) | Take Applicationn Database Backup | On-Prem | USMAN-SMWSPVW12 | HCL Ops Infra
5 | T-0 Cutover (Downtime Window) | Capture all the On-Perm Server configuration as an Evidence | On-Prem | USMAN-SMWSPVW12 | HCL Migration - Infra/HCL Ops
6 | T-0 Cutover (Downtime Window) | Disable the server from monitoring (Maintenance Mode) | On-Prem | USMAN-SMWSPVW12 | HCL Ops Infra
7 | T-0 Cutover (Downtime Window) | Disable Backup for the server from On-Perm Backup Tool | On-Prem | USMAN-SMWSPVW12 | HCL Ops Infra
8 | T-0 Cutover (Downtime Window) | Shutdown On-prem .NET/IIS Services for GSC Data Warehouse in Prod server VM. | On-Prem | USMAN-SMWSPVW12 | HCL App Migration Team
9 | T-0 Cutover (Downtime Window) | Validate that no Application process/service/job is active and running | On-Prem | USMAN-SMWSPVW12 | HCL App Migration Team
10 | T-0 Cutover (Downtime Window) | Shutdown any application services. | On-Prem | USMAN-SMWSPVW12 | SNI / HCL Apps Team
11 | T-0 Cutover (Downtime Window) | Initiate Migration - Monitor the progress of the migration at Azure for the Application server | On-Prem/Azure Cloud | USMAN-SMWSPVW12 | HCL Migration - Infra
12 | T-0 Cutover (Downtime Window) | Review the report from Azure Migrate once Final Replication is complete | Azure Cloud | USMAN-SMWSPVW12 | HCL Migration - Infra
13 | T-0 Cutover (Downtime Window) | Power On the migrated server in Azure after the Source Server Shutdown is confirmed | Azure Cloud | USMAN-SMWSPVW12 | HCL Migration - Infra
14 | T-0 Cutover (Downtime Window) | Re-IP the migrated server in Azure | Azure Cloud | USMAN-SMWSPVW12 | HCL Migration - Infra
15 | T-0 Cutover (Downtime Window) | Validate the DNS entry on the server | Azure Cloud | USMAN-SMWSPVW12 | HCL Migration - Infra
16 | T-0 Cutover (Downtime Window) | AD Team to bind new IP with hostname / aliases (If Required) | On-Prem/Azure Cloud | USMAN-SMWSPVW12 | HCL Ops Infra/ HCL Migration - Infra
17 | T-0 Cutover (Downtime Window) | Ping Hostname and FQDN from Network to ensure both are responding to primary IP. | Azure Cloud | USMAN-SMWSPVW12 | HCL Migration - Infra
18 | T-0 Cutover (Downtime Window) | Check CPU and RAM Allocation at Azure | Azure Cloud | USMAN-SMWSPVW12 | HCL Migration - Infra
19 | T-0 Cutover (Downtime Window) | Login to the server using RDP | Azure Cloud | USMAN-SMWSPVW12 | HCL Migration - Infra
20 | T-0 Cutover (Downtime Window) | Validate the disk details as per Source | Azure Cloud | USMAN-SMWSPVW12 | HCL Migration - Infra
21 | T-0 Cutover (Downtime Window) | Update the host file (/etc/hosts) with new IP in VM (if required) | Azure Cloud | USMAN-SMWSPVW12 | HCL Migration - Infra
22 | T-0 Cutover (Downtime Window) | Check all required ports are open in APP server. | Azure Cloud | USMAN-SMWSPVW12 | HCL Migration - Infra
23 | T-0 Cutover (Downtime Window) | Confirm the App team once all validation pass | Azure Cloud | USMAN-SMWSPVW12 | HCL Migration - Infra
24 | T-0 Cutover (Downtime Window) | Validate GSC Data Warehouse Application Artifacts Exists on path - D:\inetpub\wwwroot\WoundAppsWebsite\GSC Data Warehouse WebSite | Azure Cloud | USMAN-SMWSPVW12 | HCL App Migration Team
25 | T-0 Cutover (Downtime Window) | Verify and Update the config file - D:\inetpub\wwwroot\WoundAppswebsite\dbdw.inc file in the deployment artifact for the correct DB server details. | Azure Cloud | USMAN-SMWSPVW12 | HCL App Migration Team
26 | T-0 Cutover (Downtime Window) | Verify all the settings of IIS like Authentication,ASP,Logging,MIME Types are properly configured. | Azure Cloud | USMAN-SMWSPVW12 | HCL App Migration Team
27 | T-0 Cutover (Downtime Window) | Start .NET/IIS Services for GSC Data Warehouse in Prod server on cloud VM Box and validate. | Azure Cloud | USMAN-SMWSPVW12 | HCL App Migration Team
66 | T-0 Cutover (Downtime Window) | Validate the DNS entry for URL 1. http://woundapps.smith-nephew.com/GSCDataWarehouse with new Server IP and update if required. | On-Prem | USMAN-SMWSPVW12 | HCL Windows Team
28 | T-0 Cutover (Downtime Window) | Test Basic Application Functionality (UI working). Access the application URL's through browser to check the application home page. | Azure Cloud | USMAN-SMWSPVW12 | HCL App Migration Team
29 | T-0 Cutover (Downtime Window) | Verify system logs and application for any error. | Azure Cloud | USMAN-SMWSPVW12 | HCL App Migration Team
30 | T-0 Cutover (Downtime Window) | Validate the maintenance plans and scheduled time of the same (should match with the On-prem setup) | Azure Cloud | USMAN-SMWSPVW12 | HCL App Migration Team
31 | T-0 Cutover (Downtime Window) | Run the Smoke Test cases and do a complete Sanity on the application | Azure Cloud | USMAN-SMWSPVW12 | HCL App Migration Team
32 | T-0 Cutover (Downtime Window) | Configure Backup Policy and initiate Backup for File systems. | Azure Cloud | USMAN-SMWSPVW12 | HCL Migration - Infra
33 | T-0 Cutover (Downtime Window) | Install and configure Monitoring on the servers, App & DB (if required). | Azure Cloud | USMAN-SMWSPVW12 | HCL Migration - Infra
34 | T-0 Cutover (Downtime Window) | Add server to the patch & update management group | Azure Cloud | USMAN-SMWSPVW12 | HCL Migration - Infra
35 | T-0 Cutover (Downtime Window) | Un-install tool agents used in On-permises (System Center EP Protection, SCCM, SCOM, Backup) | Azure Cloud | USMAN-SMWSPVW12 | HCL Migration - Infra
36 | T-0 Cutover (Downtime Window) | Delete Local user Azurmigrator in Azure Server | Azure Cloud | USMAN-SMWSPVW12 | HCL Migration - Infra
37 | T-0 Cutover (Downtime Window) | Perform one full infra validation | Azure Cloud | USMAN-SMWSPVW12 | HCL Migration - Infra
38 | T-0 Cutover (Downtime Window) | Coordinate with SDM/SME's for Unit Test cases and support during the Acceptance Testing | Azure Cloud | USMAN-SMWSPVW12 | HCL App Migration Team
39 | Post-Cutover | Update the IP sheet | Azure Cloud | USMAN-SMWSPVW12 | HCL Migration - Infra
40 | Post-Cutover | Rename the On-Prem Server to "_MigratedonDate" in vCenter and Disconnect the NIC Card | On-Prem | USMAN-SMWSPVW12 | HCL OPS - Wintel
41 | Post-Cutover | Send Migration confirmation email to all stakeholders, informing that the application is live in Azure Cloud | Azure Cloud | USMAN-SMWSPVW12 | HCL App Migration Team
42 | Post-Cutover | Get the Business Sign Off on the Testing | Azure Cloud | USMAN-SMWSPVW12 | HCL App Migration Team
43 | Post-Cutover | Get the Sign Off from SDM | Azure Cloud | USMAN-SMWSPVW12 | HCL App Migration Team
44 | Post-Cutover | Get Sign off from Ken | Azure Cloud | USMAN-SMWSPVW12 | HCL App Migration Team

## Test Plans
Application Name | Test Type | Test Scenario
SNID | Connectivity Test | Verify the VPN Client able to access Azure network by working with Application teams.
Verify the VPN tunnel working from any remote sites by working with the Application Teams
Verify the application reachability from the site which is already migrated to SD WAN
Check the trace route to the server.
| Application Smoke Test | Validate User Credentials
Verify if website is deployed successfully.

## Infra Test Cases
Project Name: |  |  |  | SNI Cloud Migration |  |  | Depends On |  |  | Infra
GEO / Client Name: (Application SDM) |  |  |  | Amit Shokeen |  |  | Complexity |  |  | Simple
Application Name : |  |  |  | GSC Data Warehouse Admin Tool |  |  | Test Type |  |  | Infra
Version No. |  |  |  | 1 |  |  | Test Scenario |  |  | Checking Network Connection and Accessibility
Test Cycle No. |  |  |  | 1 |  |  | Environment: |  |  | Prod
Target Server details (Azure)
Hostname with FQDN: USMAN-SMWSPVW12.sncorp.smith-nephew.com |  |  |  | IP Address:
Sl No. | Test Case ID | Test Case Description | Test Conditions (Pre-Requisites) | Test Data | Execution Steps | Expected Result | Observed Result (Details to be provided if failed) | Outcome ( Pass / Fail) | Defect ID Ref. | Severity | Action | Sign-off
[11 empty] | (With Date) | (With Date)
1 | TC1 | Verify the Target server is accesssible form On-Perm Jump Server | On-Perm Jump Server information and Access On-Perm Server name: USASHSMINPVW01.sncorp.smith-nephew.com | Login to RDP Jump Server and open command prompt and run ping test on the target IP addess | Open the RDP from your laptop | Ping reply with no data loss |  | Pass
[5 empty] | Enter the hostname with FQDN of the Jump Server |  |  | Pass
[5 empty] | Provide your AD Credentials for login |  |  | Pass
[5 empty] | Open Cmd prompt and execute ping test of Target Server |  |  | Pass
2 | TC2 | Verify the VPN Client (Zscaler) able to access Azure network by working with Application teams | Zscaler VPN | Open RDP of your Target Server with FQDN from laptop using Zscaler | Open Zscaler and connect your VPN | RDP will connect the server |  | Pass
|  |  | Policy Update in Zscaler |  | Open the RDP from your laptop |  |  | Pass
|  |  | IP Address of the Target Server |  | Enter the hostname with FQDN |  |  | Pass
|  |  | DNS Registration |  | Provide your AD Credentials for login |  |  | Pass
3 | TC3 | Verify the VPN tunnel working from any remote sites by working with the Application Teams | On-Perm Europe Server information and Access On-Perm Server name: chaarsmdbpw02.sncorp.smith-nephew.com | Login to RDP Server and open command prompt and run ping test on the target IP addess | Open the RDP from your laptop | Ping reply with no data loss |  | Pass
[5 empty] | Enter the hostname with FQDN of the Jump Server |  |  | Pass
[5 empty] | Provide your AD Credentials for login |  |  | Pass
[5 empty] | Open Cmd prompt and execute ping test of Target Server |  |  | Pass
4 | TC4 | Verify the application reachability from the site which is already migrated to SD WAN (Branch Location) | On-Perm SDWAN Server information and Access. On-Perm Server name: prs04.sncorp.smith-nephew.com | Login to RDP Server and open command prompt and run ping test on the target IP addess | Open the RDP from your laptop | Ping reply with no data loss |  | Pass
[5 empty] | Enter the hostname with FQDN of the Jump Server |  |  | Pass
[5 empty] | Provide your AD Credentials for login |  |  | Pass
[5 empty] | Open Cmd prompt and execute ping test of Target Server |  |  | Pass
5 | TC5 | Check the trace route to the server from SD WAN | On-Perm SDWAN Server information and Access. On-Perm Server name: prs04.sncorp.smith-nephew.com | Login to RDP Server and open command prompt and run traceroute for the target IP addess | Open the RDP from your laptop | Traceroute will end up with proper hops |  | Pass
[5 empty] | Enter the hostname with FQDN of the Jump Server |  |  | Pass
[5 empty] | Provide your AD Credentials for login |  |  | Pass
[5 empty] | Open Cmd prompt and execute tracerouteof Target Server |  |  | Pass
6 | TC6 | Check connectivity between Application and database server | Target Database and Application Server IP and access | Login to RDP Server and open command prompt and do ping test between Application and Database Servers | Open the RDP from your laptop | Ping reply with no data loss |  | NA
[5 empty] | Enter the hostname with FQDN |  |  | NA
[5 empty] | Provide the login credentials created on the server |  |  | NA
[5 empty] | Execute Ping test between Application and Database servers |  |  | NA
Prepared by: |  |  |  | Rahul Sarin |  |  |  | Tested by: |  |  | Rahul Sarin
Date: |  |  |  | 2020-02-10 |  |  |  | Date:

## Backout Plan
Task Id | Application Name | Rollback tasks
1 | All In Scope | Remove Target server from domain
2 | All In Scope | Shut down the new server and rename Virtual Server as "Failed Migration" and uncheck Power On option from vNIC
3 | All In Scope | Power on Source Servers
4 | All In Scope | Re-join Source server to domain
5 | All In Scope | Notify to perform application startup as needed
6 | All In Scope | Application team will start services on all servers.
7 | All In Scope | Verify that application startup steps have completed
8 | All In Scope | Notify the customer to perform functional testing / UAT
9 | All In Scope | Customer performs functional testing / UAT and checks the application functioning
10 | All In Scope | Remove the additional Firewall rules
11 | All In Scope | Verify that Firewall is accessible and administrator has admin rights on firewall
12 | All In Scope | Ensure all information for application is available(source, Destination, port, protocol, Zone)
13 | All In Scope | Remove the addional Firewall rules and tested all the application is available(source, Destination, port, protocol, Zone)
14 | All In Scope | Verify Routes, NAT rules are in revert for application was migrated, remove if present on firewall
15 | All In Scope | Make sure all the application- Prior to cutover- are funtional
16 | All In Scope | Sign-off on the roll-back
17 | All In Scope | Update the migration tracker with rolled-back servers w/ reason for roll-back
Overall approach is to Backout only in the case of a catastrophic failure. Otherwise issues will be resolved on migrated App/Server in Azure.