## Prod
S.No. | Category | Migration Steps | Platform | Servers | Responsibility
1 | T-2 | Perform all required tasks (vault, rg, monitoring,update,WD) in the Azure Platform in Core and migration susbscriptions | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration - Infra
2 | T-2 | Requirement Document: Collect the target server information for new VM (OS & DB versions), Disks types and size, CPU, RAM, Public IP, Ports | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration - Infra
3 | T-2 | New SQL VMs are already provisioned in azure under SQL Consolidation project. The database server will be re-platformed on to those target servers. | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration - Infra
4 | T-2 | Update the patches as required on new DB VM in Azure | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration - Infra
5 | T-2 | Install any other required features on VM as required by Apps team or DB team | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration - Infra
6 | T-2 | Data Copy to the new Azure VM. Database and other data to be backed up and copied over to the new Database servers in Azure. | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration - Infra
7 | T-1 | Backup Policy Creation in Azure | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration - Infra
8 | T-1 | Azure Resource Group Creation | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration - Infra
9 | T-1 | Migration Team to validate target platform readiness in the Azure subscription | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration - Infra
10 | T-1 Data Base | Assess source database before upgrading your SQL Server instance using Data Migration Assistant (DMA) instance | On-Prem | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL MS-SQL Database consolidation Team
11 | T-1 Data Base | Review the compatibility issues by analyzing the impacted object and its details for every issue identified under Breaking changes, Behavior changes, and Deprecated features. | On-Prem | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL MS-SQL Database consolidation Team
12 | T-1 Data Base | Review feature recommendations across the Performance, Storage, and Security areas. | On-Prem | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL MS-SQL Database consolidation Team
13 | T-1 Data Base | Take confirmation from application SDM for target SQL Database version , application and database compatibility | On-Prem | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL MS-SQL Database consolidation Team
14 | T-1 Data Base | Capture details of Instance and Database Configuration | On-Prem | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration Infra DBA Team
15 | T-1 Data Base | Analyze capacity of Source SQL server database and Scale up (if required) SQL Server DB Server at Azure | On-Prem | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL MS-SQL Database consolidation Team
16 | T-1 Data Base | Share the details of target SQL DB Instance | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL MS-SQL Database consolidation Team
17 | T-1 Data Base | Validate SQL server product and features installed on new DB server. | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration Infra DBA Team
18 | T-1 | Add local user "Azuremigrator" in the VM (not AD user ) | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration - Infra
19 | T-1 | Initial Data sync from On-permises to Azure (complete server) | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration - Infra
20 | T-1 | Migration Team to prepare the VM for Final sync | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration - Infra
32 | T-1 | SQL jobs to be created along with the underlying SSIS package on the DB server | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL App Migration Team
21 | T-0 Cutover (Downtime Window) | Take a full incremental backup and Snapshot of the Application Server | On-Prem | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Ops Infra
22 | T-0 Cutover (Downtime Window) | Take Application and Database server Backup | On-Prem | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Ops Infra
23 | T-0 Cutover (Downtime Window) | Capture all the On-Perm Server configuration as an Evidence | On-Prem | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration - Infra/HCL Ops
24 | T-0 Cutover (Downtime Window) | Disable the server from monitoring (Maintenance Mode) | On-Prem | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Ops Infra
25 | T-0 Cutover (Downtime Window) | Disable Backup for the server from On-Perm Backup Tool | On-Prem | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Ops Infra
33 | T-0 Cutover (Downtime Window) | Shutdown On-prem .NET/IIS Services for GRDT in Prod server VM. | On-Prem | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL App Migration Team
34 | T-0 Cutover (Downtime Window) | Validate that no Application process/service/job is active and running | On-Prem | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL App Migration Team
35 | T-0 Cutover (Downtime Window) | Shutdown any application services. | On-Prem | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Ops Infra
26 | T-0 Cutover (Downtime Window) | Run a set of SQL scripts on the on-prem database prior to the migration after application shutdown | On-Prem | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL MS-SQL Database consolidation Team
27 | T-0 Cutover (Downtime Window) | Perform on-premises SQL database backup after apps shutdown | On-Prem | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration Infra DBA Team
28 | T-0 Cutover (Downtime Window) | Copy the backup file into the Azure virtual machine & Restore the Data Base | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration Infra DBA Team
29 | T-0 Cutover (Downtime Window) | Migrate SQL Logins and database User from on-premises SQL Database Instance | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration Infra DBA Team
30 | T-0 Cutover (Downtime Window) | Verify Database status | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration Infra DBA Team
31 | T-0 Cutover (Downtime Window) | Put SQL database in offline mode at source | On-Prem | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration Infra DBA Team
32 | T-0 Cutover (Downtime Window) | SQL jobs and maintenance plans to be created along with the underlying SSIS package on the DB server | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Infra DBA Team
36 | T-0 Cutover (Downtime Window) | Final Delta Sync/Initiate Migration - Monitor the progress of the migration at Azure for the Application server | On-Prem/Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration - Infra
37 | T-0 Cutover (Downtime Window) | Review the report from Azure Migrate once Final Replication is complete | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration - Infra
38 | T-0 Cutover (Downtime Window) | Power On the migrated server in Azure after the Source Server Shutdown is confirmed | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration - Infra
39 | T-0 Cutover (Downtime Window) | Re-IP the migrated server in Azure | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration - Infra
40 | T-0 Cutover (Downtime Window) | Validate the DNS entry on the server | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration - Infra
41 | T-0 Cutover (Downtime Window) | AD Team to bind new IP with hostname / aliases (if required) | On-Prem/Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Ops Infra/ HCL Migration - Infra
42 | T-0 Cutover (Downtime Window) | Ping Hostname and FQDN from Network to ensure both are responding to primary IP. | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration - Infra
43 | T-0 Cutover (Downtime Window) | Check CPU and RAM Allocation at Azure | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration - Infra
44 | T-0 Cutover (Downtime Window) | Login to the server using RDP | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration - Infra
45 | T-0 Cutover (Downtime Window) | Validate the disk details as per Source | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration - Infra
46 | T-0 Cutover (Downtime Window) | Check System Properties for CPU and RAM as per source at OS Level | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration - Infra
47 | T-0 Cutover (Downtime Window) | Activate Windows Online if not Activated | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration - Infra
48 | T-0 Cutover (Downtime Window) | Check Disk Management and make sure all disk size is fine as per source | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration - Infra
49 | T-0 Cutover (Downtime Window) | Check all the network configuration as per source and Disable IPV6 Configuration. | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration - Infra
50 | T-0 Cutover (Downtime Window) | Check the NIC Orders by going to Advance Settings of Network Configuration | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration - Infra
51 | T-0 Cutover (Downtime Window) | Rename the NICs as per the IP and Network Configuration (same as source) | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration - Infra
52 | T-0 Cutover (Downtime Window) | Remove all the Hardware Related Software depending on the Hardware (P2V Only) | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration - Infra
53 | T-0 Cutover (Downtime Window) | Check RDP is working or not. | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration - Infra
54 | T-0 Cutover (Downtime Window) | Update the host file (/etc/hosts) with new IP in VM (if required) | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration - Infra
55 | T-0 Cutover (Downtime Window) | Check all required ports are open in APP server. | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration - Infra
56 | T-0 Cutover (Downtime Window) | Confirm the App and DB team once all validation pass | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration - Infra
57 | T-0 Cutover (Downtime Window) | Run the set of SQL scripts on the Azure database immediately after the migration and before application is turned on | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL MS-SQL Database consolidation Team
58 | T-0 Cutover (Downtime Window) | Perform a textual comparison of corresponding outputs from the step 1 and 2 and validate if there are no discrepancies between the pre- and post-migration states. | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL MS-SQL Database consolidation Team
59 | T-0 Cutover (Downtime Window) | Verify if we are able to connect (locally and remotely) to SQL DB Instance with sysadmin privilege. | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration Infra DBA Team
60 | T-0 Cutover (Downtime Window) | Verify the SQL Server log for any error that is due to migration. | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration Infra DBA Team
61 | T-0 Cutover (Downtime Window) | Validate GRDT Application Artifacts Exists on path - D:\GRDT | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL App Migration Team
62 | T-0 Cutover (Downtime Window) | Verify and Update the config file - D:\GRDT\appsettings.json file in the deployment artifact for the correct DB server details. | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL App Migration Team
63 | T-0 Cutover (Downtime Window) | Verify all the settings of IIS like Authentication,ASP,Logging,MIME Types are properly configured. | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL App Migration Team
64 | T-0 Cutover (Downtime Window) | Start .NET/IIS Services for GRDT on cloud VM and validate. | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL App Migration Team
66 | T-0 Cutover (Downtime Window) | Validate the DNS entry for URL 1. https://grdt.smith-nephew.com/ 2. http://grdt.smith-nephew.com/ with new Server IP and update if required. | On-Prem | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Windows Team
67 | T-0 Cutover (Downtime Window) | Test Basic Application Functionality (UI working). Access the application URL's through browser to check the application home page. | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL App Migration Team
68 | T-0 Cutover (Downtime Window) | Verify system logs and application for any error. | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL App Migration Team
69 | T-0 Cutover (Downtime Window) | Validate whether the SQL server jobs are enabled and check the scheduled time of the job (should match with the On-prem setup) | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | Soumen/Bharat/HCL App Migration Team
70 | T-0 Cutover (Downtime Window) | Validate the maintenance plans and scheduled time of the same (should match with the On-prem setup) | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | Soumen/Bharat/HCL App Migration Team
71 | T-0 Cutover (Downtime Window) | Validate the below services should be in Started and Automatic state - SQL server - SQL server agent - SQL server Integration services | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | Soumen/Bharat/HCL App Migration Team
72 | T-0 Cutover (Downtime Window) | Run the Smoke Test cases and do a complete Sanity on the application | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL App Migration Team
73 | T-0 Cutover (Downtime Window) | Install and configure Monitoring on the servers, App & DB (if required). | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration - Infra
74 | T-0 Cutover (Downtime Window) | Add server to the patch & update management group | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration - Infra
75 | T-0 Cutover (Downtime Window) | Un-install tool agents used in On-permises (SCCM, SCOM, Backup) | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration - Infra
76 | T-0 Cutover (Downtime Window) | Delete Local user Azurmigrator in Azure Server | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration - Infra
77 | T-0 Cutover (Downtime Window) | Perform one full infra validation | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration - Infra
78 | T-0 Cutover (Downtime Window) | Configure Backup Policy and initiate Backup for File systems. | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration - Infra
84 | T-0 Cutover (Downtime Window) | Coordinate with SDM/SME's for Unit Test cases and support during the Acceptance Testing | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL App Migration Team
85 | Post-Cutover | Verify if the database is performing (processor/memory usage is as expected), database backup and monitoring configured | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL MS-SQL Database consolidation Team
86 | Post-Cutover | Update the IP sheet | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL Migration - Infra
87 | Post-Cutover | Rename the On-Prem Server to "_MigratedonDate" in vCenter and Disconnect the NIC Card | On-Prem | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL OPS - Wintel
88 | Post-Cutover | Send Migration confirmation email to all stakeholders, informing that the application is live in Azure Cloud | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL App Migration Team
89 | Post-Cutover | Get the Business Sign Off on the Testing | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL App Migration Team
90 | Post-Cutover | Get the Sign Off from SDM | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL App Migration Team
91 | Post-Cutover | Get Sign off from Ken | Azure Cloud | USMAN-SMWSPVW12 USMAN-SMDBPVW12 | HCL App Migration Team

## Infra Test Cases
Project Name: |  |  |  | SNI Cloud Migration |  |  | Depends On |  |  | Infra
GEO / Client Name: (Application SDM) |  |  |  | Andres Bernard |  |  | Complexity |  |  | Simple
Application Name : |  |  |  | Global Returns Disposition Tool |  |  | Test Type |  |  | Infra
Version No. |  |  |  | 1 |  |  | Test Scenario |  |  | Checking Network Connection and Accessibility
Test Cycle No. |  |  |  | 1 |  |  | Environment: |  |  | Prod
Target Server details (Azure)
Hostname with FQDN: USMAN-SMWSPVW12.sncorp.smith-nephew.com |  |  |  | IP Address:
Sl No. | Test Case ID | Test Case Description | Test Conditions (Pre-Requisites) | Test Data | Execution Steps | Expected Result | Observed Result (Details to be provided if failed) | Outcome ( Pass / Fail) | Defect ID Ref. | Severity | Action | Sign-off
[11 empty] | (With Date) | (With Date)
1 | TC1 | Verify the Target server is accesssible form On-Perm Jump Server | On-Perm Jump Server information and Access On-Perm Server name: USASHSMINPVW01.sncorp.smith-nephew.com | Login to RDP Jump Server and open command prompt and run ping test on the target IP addess | Open the RDP from your laptop | Ping reply with no data loss |  | Pass
[5 empty] | Enter the hostname with FQDN of the Jump Server |  |  | Pass
[5 empty] | Provide your AD Credentials for login |  |  | Pass
[5 empty] | Open Cmd prompt and execute ping test of Target Server |  |  | Pass
2 | TC2 | Verify the VPN Client (Zscaler) able to access Azure network by working with Application teams | Zscaler VPN | Open RDP of your Target Server with FQDN from laptop using Zscaler | Open Zscaler and connect your VPN | RDP will connect the server |  | Pass
|  |  | Policy Update in Zscaler |  | Open the RDP from your laptop |  |  | Pass
|  |  | IP Address of the Target Server |  | Enter the hostname with FQDN |  |  | Pass
|  |  | DNS Registration |  | Provide your AD Credentials for login |  |  | Pass
3 | TC3 | Verify the VPN tunnel working from any remote sites by working with the Application Teams | On-Perm Europe Server information and Access On-Perm Server name: chaarsmdbpw02.sncorp.smith-nephew.com | Login to RDP Server and open command prompt and run ping test on the target IP addess | Open the RDP from your laptop | Ping reply with no data loss |  | Pass
[5 empty] | Enter the hostname with FQDN of the Jump Server |  |  | Pass
[5 empty] | Provide your AD Credentials for login |  |  | Pass
[5 empty] | Open Cmd prompt and execute ping test of Target Server |  |  | Pass
4 | TC4 | Verify the application reachability from the site which is already migrated to SD WAN (Branch Location) | On-Perm SDWAN Server information and Access. On-Perm Server name: prs04.sncorp.smith-nephew.com | Login to RDP Server and open command prompt and run ping test on the target IP addess | Open the RDP from your laptop | Ping reply with no data loss |  | Pass
[5 empty] | Enter the hostname with FQDN of the Jump Server |  |  | Pass
[5 empty] | Provide your AD Credentials for login |  |  | Pass
[5 empty] | Open Cmd prompt and execute ping test of Target Server |  |  | Pass
5 | TC5 | Check the trace route to the server from SD WAN | On-Perm SDWAN Server information and Access. On-Perm Server name: prs04.sncorp.smith-nephew.com | Login to RDP Server and open command prompt and run traceroute for the target IP addess | Open the RDP from your laptop | Traceroute will end up with proper hops |  | Pass
[5 empty] | Enter the hostname with FQDN of the Jump Server |  |  | Pass
[5 empty] | Provide your AD Credentials for login |  |  | Pass
[5 empty] | Open Cmd prompt and execute tracerouteof Target Server |  |  | Pass
6 | TC6 | Check connectivity between Application and database server | Target Database and Application Server IP and access | Login to RDP Server and open command prompt and do ping test between Application and Database Servers | Open the RDP from your laptop | Ping reply with no data loss |  | NA
[5 empty] | Enter the hostname with FQDN |  |  | NA
[5 empty] | Provide the login credentials created on the server |  |  | NA
[5 empty] | Execute Ping test between Application and Database servers |  |  | NA
Prepared by: |  |  |  | Rahul Sarin |  |  |  | Tested by: |  |  | Rahul Sarin
Date: |  |  |  | 2020-02-10 |  |  |  | Date:

## Test Plans
Application Name | Test Type | Test Scenario
SalesRequestForm | Connectivity Test | Verify the VPN Client able to access Azure network by working with Application teams.
Verify the VPN tunnel working from any remote sites by working with the Application Teams
Verify the application reachability from the site which is already migrated to SD WAN
Check the trace route to the server.
| Application Smoke Test | Validate User Credentials
Verify if website is deployed successfully.

## Backout Plan
Task Id | Application Name | Rollback tasks
1 | All In Scope | Remove Target server from domain
2 | All In Scope | Shut down the new server and rename Virtual Server as "Failed Migration" and uncheck Power On option from vNIC
3 | All In Scope | Power on Source Servers
4 | All In Scope | Re-join Source server to domain
5 | All In Scope | Notify to perform application startup as needed
6 | All In Scope | Application team will start services on all servers.
7 | All In Scope | Verify that application startup steps have completed
8 | All In Scope | Notify the customer to perform functional testing / UAT
9 | All In Scope | Customer performs functional testing / UAT and checks the application functioning
10 | All In Scope | Remove the additional Firewall rules
11 | All In Scope | Verify that Firewall is accessible and administrator has admin rights on firewall
12 | All In Scope | Ensure all information for application is available(source, Destination, port, protocol, Zone)
13 | All In Scope | Remove the addional Firewall rules and tested all the application is available(source, Destination, port, protocol, Zone)
14 | All In Scope | Verify Routes, NAT rules are in revert for application was migrated, remove if present on firewall
15 | All In Scope | Make sure all the application- Prior to cutover- are funtional
16 | All In Scope | Sign-off on the roll-back
17 | All In Scope | Update the migration tracker with rolled-back servers w/ reason for roll-back
Overall approach is to Backout only in the case of a catastrophic failure. Otherwise issues will be resolved on migrated App/Server in Azure.