## PilotWave App Cutover Roster
Cutover | Application Name | Region | Application Environment | Server Name – App | Server Name - DB | Treatment | Vertical | CutOver Date & Downtime Window | Migration Id | Change Number | Business Owner Approval for Production Downtime
1 | Paymetric | US | QA | USMANSMPMDVW01 |  | RE-HOST | ERP | 6th Nov 8PM EST - 7th Nov 8AM EST | PW-MG1 | CHG0057982 (Completed)
1 | Abacus | Europe | TEST | TBD(New Build) |  | RE-PLATFORM | Group Functions | 6th Nov 8PM EST - 7th Nov 8AM EST | PW-MG1 | CHG0057982 (Completed)
2 | Oracle Enterprise Manager | US | TEST | USMEM-SMAPTVL13 | USMEM-SMDBTVL12 | RE-HOST/RE-PLATFORM | Data & Analytics | 12th Nov 8PM EST - 13th Nov 8PM EST | PW-MG2 | CHG0058065 (Completed)
2 | HR Notification | US | DEV | USMAN-SMWSDVW07 | USMAN-SMDPDVW16((Hosts LDAPUpdate TEST as well) | RE-PLATFORM | Group Functions | 12th Nov 8PM EST - 13th Nov 8PM EST | PW-MG2 | CHG0058065 (Completed)
2 | HR Notification | US | QA | USMAN-SMWSQVW05 | USMAN-SMDPDVW16((Hosts LDAPUpdate TEST as well) | RE-PLATFORM | Group Functions | 12th Nov 8PM EST - 13th Nov 8PM EST | PW-MG2 | CHG0058065 (Completed)
2 | LDAPUpdate | US | TEST |  | USMAN-SMDPDVW16(Hosts HR Notification DEV & QA) | RE-PLATFORM | Commercial | 12th Nov 8PM EST - 13th Nov 8PM EST | PW-MG2 | CHG0058065 (Completed)
3 | SNID Archive Documents | US | QA | USMAN-SMWSQVW05 |  | RE-PLATFORM | Supply Chain | 20th Nov 8PM EST - 21st Nov 8PM EST | PW-MG3 | Rescheduled to Wave 1
3 | Tops Pro | US | PROD | USAUS-SMLIPVW02 |  | RE-HOST | R&D | 20th Nov 8PM EST - 21st Nov 8PM EST | PW-MG3 | CHG0058356 (Completed) | Approval received from Matt and Kenneth
3 | Paymetric | US | PROD | USMANSMPMPVW01 |  | RE-HOST | ERP | 20th Nov 8PM EST - 21st Nov 8PM EST | PW-MG3 | CHG0058356 (Completed) | Approval Received from Pablo and Fernando
3 | LDAPUpdate | US | PROD |  | USMAN-SMDBPVW12 | RE-PLATFORM | Commercial | 20th Nov 8PM EST - 21st Nov 8PM EST | PW-MG3 | CHG0058356 (Completed) | Approval received from Andres
4 | Oracle Enterprise Manager | US | PROD | USATL-SMAPPUL02 | USATL-SMDBPUL02(Active) / USATL-SMDBPUL04(StandBy)/ USMEM-SMDBPUL06 (DR) | RE-HOST/RE-PLATFORM | Data & Analytics | 4th Dec 8 PM EST - 5th Dec 8 PM EST | PW-MG4 | CHG0058661(Completed) | Approval received from Sathia
4 | HR Notification | US | PROD | USMAN-SMWSPVW12 | USMAN-SMDBPVW12 | RE-PLATFORM | Group Functions | 4th Dec 8 PM EST - 5th Dec 8 PM EST | PW-MG4 | CHG0058619 (Completed) | Approval received from Paul
4 | KepServerEx (Amsterdam) | Europe | PROD | UKHULSMDBPVW02 | UKHULSMDBPVW04 | RE-HOST | Manufacturing | 4th Dec 8 PM EST - 5th Dec 8 PM EST | PW-MG4 | CHG0058619 (Completed) | Approval received from Carla

## Pilot Applications List
Application | Server Count | Treatment | Verticle | SDM Name
Oracle Enterprise Manager | 5 | RE-HOST | Data & Analytics | Sathiamurthy Samidurai
Paymetric | 2 | RE-HOST | ERP | Pablo Iradier
Tops Pro | 1 | RE-HOST | R&D | Matthew Stephens
HR Notification | 5 | RE-PLATFORM | Group Functions | Paul Davison
SN ID Archive Documents | 3 | RE-PLATFORM | Supply Chain | Amit Shokeen
KepServerEx (Amsterdam) | 2 | RE-HOST | Manufacturing | Carla Morris
LDAPUpdate | 2 | RE-PLATFORM | Commercial | Andres Bernard
Abacus | 1 | RE-PLATFORM | Group Functions | Paul Davison

## Change Log
Date | Change | Updated By
2020-10-14 | Initial Draft | Debojit
2020-10-21 | Removed ConnectShip, Added SNID Archive document as per inputs from Amit Shokeen | Debojit
2020-10-23 | a. OEM DEV cutover – 11/12 (moved from 11/6) b. OEM DR Cutover – 11/20 (moved from 11/12) c. OEM PRD Cutover – 12/4 (moved from 11/20) d. SNI ID Archive QA Cutover - 11/20 (Moved from 11/12) e. SNI ID Archive PROD Cutover - 12/4 (Moved from 11/20) f. HR Notification PROD Cuover – 12/4 (Moved from 11/20) | Debojit
2020-10-28 | Removed SNID Archive Documents - DEV from Migration roster as requested by SDM (Amit) | Debojit
2020-10-30 | Moved HR Notification QA to PW-MG2 as Database is being shared between DEV and QA | Debojit
2020-11-02 | Moved LDAPUpdate TEST to PW-MG2 to accomodate OS/DB version changes | Debojit
2020-11-02 | Added "Pilot Applications List" tab | Debojit
2020-11-03 | Added DR Server mentioned by Sathia for OEM to the list | Debojit
2020-11-05 | Moved DR and PROD StandBY server for OEM to PW-MG4 cutover | Debojit
2020-11-16 | Added Status columns for Cutover, Standardization and Testing Status | Debojit
2020-11-17 | Added KepServerEX Application to PW-MG4 schedule | Arun