## Cutover Summary
Change Information
Wave Group |  |  | Wave 3
Move Group |  |  | Move Group
Migration Cutover Id |  |  | W3-MG1
Change Request Number |  |  | Multiple CRs
Change Submission Date
CAB Approval Date
Change Implementation Start Date
Change Implementation End Date
Change Outage Window Start
Change Outage Window End
Region
Vertical
Application
Treatment Plan- App
Treatment Plan- DB
MoveGroup Status
Application Environment
Server Name - App
Server Name- DB
Pre-Migration SNI Testing
GO No GO Decision
DNS update and point traffic to new host.
Validate and test.
Project SME Mapping
Application
Application SDM
Application IT Owner
Application SME
Application UAT Contact
HCL Migration - Infra
HCL Migration - Apps
Application cTASK SNOW Group
HCL OPS SME MAPPING
HCL Ops - Windows/Linux | Johnson.Susairaj@smith-nephew.com | +91 9841306591 | HCL-Windows@smith-nephew.com
HCL Ops - Network | Abdul.Sayeed@smith-nephew.com | +91 9342244325 | HCL-NetworkData@smith-nephew.com
HCL Ops - Monitoring | Sridhar.Venkatakrishnan@smith-nephew.com | +91 7305838202 | HCL-Tools@smith-nephew.com
HCL Ops - Backup | Dhachanamoorthy.Selvaraj@smith-nephew.com | +91 8122989025 | HCL-Backup@smith-nephew.com
HCL Ops - Apps | Dhinagaran.Kuppusamy@smith-nephew.com | +91 9901877221 | HCL-AMS@Smith-Nephew.com
SNI Security | Purushothaman.Sekar@smith-nephew.com | +91 9566117107 | HCL-NetworkSecurity@smith-nephew.com
DXC - Linux
TASKS SUMMARY

## Wave 3 Apps
Applications | Databaes Technlogy | Environment | SDM | ITLT | Cutover ID | Cutover Date | On Prem App Server/s | Treatment App Server | On Prem DB Server/s | Treatment DB Server | Database Name | Target Database Server Name | App SME | Infra SME | Dependency | GXP | Domain | Region | Migration Strategy | Status | Remarks
AWM Data Warehouse |  | PROD | Sathiamurthy Samidurai | Stuart Robinson | W3-MG2 | 2021-03-19 | NA |  | UKRTH-SMDBPVW32 |  |  |  | Venkat/Isha | Srikanth Venkatasen |  | No | Data & Analytics | US | RE-HOST
Cognos STGP |  | DEV | Sathiamurthy Samidurai |  | W3-MG2 | 2021-03-19 | USMEM-SMAPEVW35 |  |  |  | NA |  | Venkat/Isha/Shirisha | Srikanth Venkatasen |  | Yes | Data & Analytics | US | RE-HOST
Cognos STGP |  | QA | Sathiamurthy Samidurai |  |  |  | USATL-SMAPQUW05 | [5 empty] | Venkat/Isha/Shirisha | Srikanth Venkatasen |  | Yes | Data & Analytics | US | RE-HOST
Cognos STGP |  | PROD | Sathiamurthy Samidurai |  |  |  | USATLSMAPPPW07 | [5 empty] | Venkat/Isha/Shirisha | Srikanth Venkatasen |  | Yes | Data & Analytics | US | RE-HOST
Cognos_STRATPLAN |  | DEV | Sathiamurthy Samidurai |  | W3-MG2 | 2021-03-19 | USMEM-SMAPEVW35 |  |  |  | NA |  | Venkat/Isha/Shirisha | Srikanth Venkatasen |  | Yes | Data & Analytics | US | RE-HOST
Cognos_STRATPLAN |  | QA | Sathiamurthy Samidurai |  |  |  | USATL-SMAPQUW05 | [5 empty] | Venkat/Isha/Shirisha | Srikanth Venkatasen |  | Yes | Data & Analytics | US | RE-HOST |  | Arun to schedule a call with Mat Pie to discuss Re-migration and constraint to only have DB server 2008 R2 in Azure.
Cognos_STRATPLAN |  | PROD | Sathiamurthy Samidurai |  |  |  | USATLSMAPPPW07 | [5 empty] | Venkat/Isha/Shirisha | Srikanth Venkatasen |  | Yes | Data & Analytics | US | RE-HOST |  | Arun to schedule a call with Mat Pie to discuss Re-migration and constraint to only have DB server 2008 R2 in Azure.
Connect Ship (UPS/DHL) |  | QA | Amit Shokeen | Massimo Trambaioli | W3-MG1 | 2021-03-05 | USMAN-SMAPDVW32 | Re-Host | USMANSMDBDUW01 | Re-Platform | progistics_test | USAZRSMDBQVW02 | Kishore | Rahul Sarin |  | No | Supply Chain | US | RE-HOST |  | App team to schedule a call with SAP team and Amit Shaukeen. ETA 9th Feb.
Connect Ship (UPS/DHL) |  | PROD | Amit Shokeen | Massimo Trambaioli | W3-MG2 | 2021-03-19 | USMAN-SMAPPVW51 | Re-Host | USMANSMDBPCW08; USMANSMDBPCW07 | Re-Host | progistics | USAZRSMDBPVW04 USAZRSMDBPVW05 Azure Cluster name: SQLProdUSEAST02 (10.32.4.31) | Kishore | Rahul Sarin |  | No | Supply Chain | US | RE-HOST |  | Pending on Rajeev Sharma from Apps Teams. App team is sharing the details with Sap team for validation.
dataSTOR |  | PROD | Sebastian Pasch |  | W3-MG2 | 2021-03-19 | ZASNFS2 | Re-Platform | ZASNFS2 | Re-Platform | datastor datastor_test | USAZRSMDBPVW02, USAZRSMDBPVW03 | Raju | Praveen Shanmugaraju |  | No | ERP | EMEA | RE-HOST |  | -Arun to followed up for Sebastian Decision. 9th Feb.-Done
Endo Loans |  | PROD | Andres Bernard | Firas Almahamid | W3-MG1 | 2021-03-05 | USMAN-SMWSPVW12 | Re-Host | USMAN-SMDBPVW12 | Re-Platform |  | USAZRSMDBPVW02 USAZRSMDBPVW03 (SQLProdUSEAST01) | Vidit | Rahul Sarin |  | No | Commercial | US | RE-HOST
Enterprise Business Objects Reporting |  | PROD | Sathiamurthy Samidurai | Stuart Robinson | W3-MG2 | 2021-03-19 | USMANSMAPPUW16 |  | SQL Cluster Address - USMANSMDBPUW35 USMANSMDBPUW31; USMANSMDBPUW32 |  |  |  | Shirisha | Srikanth Venkatasen |  | No | Data & Analytics | US | RE-HOST |  | DB Servers are on SQL Cluster. SQL Cluster cant be rehost. Discussion with Sathia on 5th Feb to plan how replatform can be done and support from his team.
Expert Document Imaging (EDI) |  | PROD | Eduardo Lima | Firas Almahamid |  |  | PRSEDI |  | To be moved to Wave 6 as per the SDM – Eduardo Lima |  |  |  | Deepak |  |  | No | Commercial | US | RE-HOST |  | DB Servers are on SQL Cluster. SQL Cluster cant be rehost. Discussion with Sathia on 5th Feb to plan how replatform can be done and support from his team.
Express Visionaire |  | PROD | Requalann Pereira | Sri Tupil |  |  | USMEMSMAPDVW28 ; USMANSMDBPCW4B |  | MEMSRV491 |  |  |  | Deepak |  |  | No | R&D | US | RE-PLATFORM |  | DB Servers are on SQL Cluster. SQL Cluster cant be rehost. Discussion with Sathia on 5th Feb to plan how replatform can be done and support from his team.
Global Data Warehouse |  | PROD | Sathiamurthy Samidurai | Stuart Robinson | W3-MG2 | 2021-03-19 | NA |  | SQL Cluster Address - USMANSMDBPUW35 USMANSMDBPUW31; USMANSMDBPUW32 |  |  |  | Venkat/Isha | Srikanth Venkatasen |  | No | Data & Analytics | US | RE-HOST |  | DB Servers are on SQL Cluster. SQL Cluster cant be rehost. Discussion with Sathia on 5th Feb to plan how replatform can be done and support from his team.
Global Market Monitoring |  | PROD | Sathiamurthy Samidurai | Stuart Robinson | W3-MG2 | 2021-03-19 | NA |  | SQL Cluster Address - USMANSMDBPUW35 USMANSMDBPUW31; USMANSMDBPUW32 |  |  |  | Venkat/Isha | Srikanth Venkatasen |  | No | Data & Analytics | US | RE-HOST |  | DB Servers are on SQL Cluster. SQL Cluster cant be rehost. Discussion with Sathia on 5th Feb to plan how replatform can be done and support from his team.
Global Returns Disposition Tool |  | PROD | Andres Bernard | Firas Almahamid | W3-MG1 | 2021-03-05 | USMAN-SMWSPVW12 | Re-Host | USMAN-SMDBPVW12 | Re-Platform | GRDT | USAZRSMDBPVW02, USAZRSMDBPVW03 | Raju | Rahul Sarin |  | No | Commercial | US | RE-HOST
GSC Data Warehouse Admin Tool |  | PROD | Amit Shokeen | Massimo Trambaioli | W3-MG1 | 2021-03-05 | USMAN-SMWSPVW12 | Re-Host | UKRTH-SMDBPVW32 (Will remain on prem-in W3-MG1) | NA Will remain on prem-in W3-MG1) | DBDataware house | NA Will remain on prem-in W3-MG1) | Raju | Rahul Sarin |  | No | Data & Analytics | US | RE-HOST |  | Note: App Server (USMAN-SMWSPVW12) will be migrated in W3-MG1. DB server (UKRTH-SMDBPVW32) will remain on prem in W3-MG1. It will be migrated in W3-MG2. For two weeks, App will remain on cloud, DB will remain on prem.
Informatica (Wound Data Intergration) |  | PROD | Sathiamurthy Samidurai | Stuart Robinson | W3-MG2 | 2021-03-19 | NLAMSSMAPPVW21 |  | UKRTH-SMDBPVW32 |  |  |  | Venkat/Isha | Srikanth Venkatasen |  | No | Data & Analytics | US | RE-HOST
Mcosomos |  | PROD | Aileen Diola |  |  |  | CHAARSMFSPW03 |  |  |  | NA |  | Vidit | Rahul Sarin |  | No | Manufacturing | EMEA | RE-HOST |  | Out of scope - Desktop application. There is no app server. Updated in Master tracker.
Mobile Inventory Management System |  | PROD | Andres Bernard | Firas Almahamid | W3-MG2 | 2021-03-19 | USMANSMWSPVW15; |  | USMANSMDBPW14; USMANSMDBPW15; |  |  |  | Deepak | Karuppanan, Rajeshkannan |  | Yes | Commercial | US | RE-HOST
Mobile Inventory Management System |  | DR | Andres Bernard | Firas Almahamid | W3-MG2 | 2021-03-19 | UKRTHSMWSQVW15; |  | UKRTHSMDBQPW14 |  |  |  | Deepak | Karuppanan, Rajeshkannan |  | Yes | Commercial | US | RE-HOST
Inventures (SCAMPI) Web App |  | PROD | Requalann Pereira |  | W3-MG1 | 2021-03-05 | USMEMSMAPPVW23, USMAN-SMWSPVW12(Reimbursement Admin) |  | USMAN-SMDBPVW12 |  | Scampi |  | Deepak | Rahul Sarin |  | Yes | R&D | US | RE-PLATFORM
Mobile Inventory Management System |  | Test | Andres Bernard | Firas Almahamid | W3-MG1 | 2021-03-05 | EQVSWB01 |  | AUVSDB00 |  |  |  | Deepak | Karuppanan, Rajeshkannan | [6 empty] | Call scheduled with Matt Pie for 9th Feb
Mobile Inventory Management System |  | Archive-Prod | Andres Bernard |  | W3-MG1 | 2021-03-05 | USMANSMWSPVW15 |  | EQVSDB00 |  |  |  | Deepak | Karuppanan, Rajeshkannan | [6 empty] | Call scheduled with Matt Pie for 9th Feb
Nomino Security |  | PROD | Andres Bernard | Firas Almahamid | W3-MG1 | 2021-03-05 | USMAN-SMWSPVW12 | Re-Host | SMRTHSQL2 (Cluster); UKRTHSMDBPW03; UKRTHSMDBPW04; | Re-Platform |  | USAZRSMDBPVW02 USAZRSMDBPVW03 (SQLProdUSEAST01) | Vidit | Rahul Sarin |  | No | Commercial | US | RE-HOST
NPWT Tracker |  | PROD | Andres Bernard | Firas Almahamid | W3-MG2 | 2021-03-19 | CHAARSMAPPW02 |  | CHAARSMAPPW02 |  | AWDTracker AWDTest |  | Vidit | Karuppanan, Rajeshkannan |  | No | Commercial | EMEA | RE-HOST
OSISoft PI System |  | PROD | Requalann Pereira | Sri Tupil | W3-MG2 | 2021-03-19 | SUZS06PI; SUZS07OPC; | Re-Platform | UKHULSMDBPVW02 | Re-Host | PIFD, Database Snapshots. |  | Raju |  |  | No | Manufacturing | EMEA | RE-PLATFORM |  | Arun followed up on 8th Feb.
Non-Employee Database |  | PROD | Paul Davidson | Chris Cook | W3-MG1 | 2021-03-05 | USMAN-SMWSPVW12 | Re-Host | USMAN-SMDBPVW12 | Re-Platform |  | USAZRSMDBPVW02 USAZRSMDBPVW03 (SQLProdUSEAST01) | Vidit | Rahul Sarin |  | No | Group Functions | US | RE-HOST
QA Change Control |  | Prod | Aileen Diola | Sri Tupil | W3-MG1 | 2021-03-05 | USMAN-SMWSPVW12 | Re-Host | SMRTHSQL2 UKRTHSMDBPW03 UKRTHSMDBPW04 | Re-Platform |  | USAZRSMDBPVW02 USAZRSMDBPVW03 (SQLProdUSEAST01) | Vidit | Rahul Sarin |  | Yes | RAQA | US | RE-HOST(App)/RE-PLATFORM(DB)
Recon LaunchPad (SSO) |  | PROD | Andres Bernard | Firas Almahamid | W3-MG1 | 2021-03-05 | USMAN-SMWSPVW12 |  |  |  | NA |  | Deepak | Rahul Sarin |  | No | Commercial | US | RE-HOST
Reimbursement |  | PROD | Andres Bernard | Firas Almahamid | W3-MG1 | 2021-03-05 | USMEMSMAPPVW23, USMAN-SMWSPVW12(Reimbursement Admin) |  | USMAN-SMDBPVW12 |  |  |  | Deepak | Rahul Sarin |  | No | Commercial | US | RE-HOST
SEAL Application |  | PROD | Krzysztof Gaik | Massimo Trambaioli | W3-MG2 | 2021-03-19 | UKHUL-SMAPPVW10 | Re-Platform | NA. No DB for the SEAL Application. | Re-Platform | NA |  | Raju | Praveen Shanmugaraju |  | No | ERP | EMEA | RE-HOST |  | SEAL application is currently on OS below 2008 R2. This is agreed by Pablo & Ken to be REPLATFORM. Pablo to share the cost details with Ken and get Ken's approval. PMO Team to keep a track on this and share us the final go. Arun to followup on Pablo/Krzsof on 8th Feb.
Sales Request Forms |  | PROD | Andres Bernard | Firas Almahamid | W3-MG1 | 2021-03-05 | USMAN-SMWSPVW12 |  | USMAN-SMDBPVW12 |  |  |  | Deepak | Rahul Sarin |  | No | Commercial | US | RE-HOST
TM1 Cognos Configuration |  | DEV | Sathiamurthy Samidurai | Stuart Robinson | W3-MG2 | 2021-03-19 | USMEM-SMAPEVW35 |  |  |  | NA |  | Venkat/Isha/Shirisha | karuppanan, Rajeshkannan |  | Yes | Data & Analytics | US | RE-HOST |  | HCL Infra and App team to discus with Suman/ Matt for Docker To get clarity from MS. Testing on 9th Feb . Srikant.
TM1 Cognos Configuration |  | QA | Sathiamurthy Samidurai | Stuart Robinson |  |  | USATL-SMAPQUW05 | [5 empty] | Venkat/Isha/Shirisha | karuppanan, Rajeshkannan |  | Yes | Data & Analytics | US | RE-HOST
TM1 Cognos Configuration |  | PROD | Sathiamurthy Samidurai | Stuart Robinson |  |  | USATLSMAPPPW07 | [5 empty] | Venkat/Isha/Shirisha | karuppanan, Rajeshkannan |  | Yes | Data & Analytics | US | RE-HOST
TM1(Global Cost Visibility) |  | DEV | Sathiamurthy Samidurai |  | W3-MG2 | 2021-03-19 | USMEM-SMAPEVW35 |  |  |  | NA |  | Venkat/Isha/Shirisha | karuppanan, Rajeshkannan |  | Yes | Data & Analytics | US | RE-HOST
TM1(Global Cost Visibility) |  | QA | Sathiamurthy Samidurai |  |  |  | USATL-SMAPQUW05 | [5 empty] | Venkat/Isha/Shirisha | karuppanan, Rajeshkannan |  | Yes | Data & Analytics | US | RE-HOST
TM1(Global Cost Visibility) |  | PROD | Sathiamurthy Samidurai |  |  |  | USATLSMAPPPW07 | [5 empty] | Venkat/Isha/Shirisha | karuppanan, Rajeshkannan |  | Yes | Data & Analytics | US | RE-HOST
TM1(Transfer Pricing) |  | DEV | Sathiamurthy Samidurai |  | W3-MG2 | 2021-03-19 | USMEM-SMAPEVW35 |  |  |  | NA |  | Venkat/Isha/Shirisha | karuppanan, Rajeshkannan |  | Yes | Data & Analytics | US | RE-HOST
TM1(Transfer Pricing) |  | QA | Sathiamurthy Samidurai |  |  |  | USATL-SMAPQUW05 | [5 empty] | Venkat/Isha/Shirisha | karuppanan, Rajeshkannan |  | Yes | Data & Analytics | US | RE-HOST
TM1(Transfer Pricing) |  | PROD | Sathiamurthy Samidurai |  |  |  | USATLSMAPPPW07 | [5 empty] | Venkat/Isha/Shirisha | karuppanan, Rajeshkannan |  | Yes | Data & Analytics | US | RE-HOST
SNID Archived Shipping Documents |  | PROD | Amit Shokeen | Massimo Trambaioli | W3-MG1 | 2021-03-05 | USMAN-SMWSPVW12 | [5 empty] | Deepak | Rahul Sarin |  | No | Supply Chain | US | RE-HOST
TOTVS |  | PROD | Eduardo Lima | Firas Almahamid |  |  | SEN-PROD01; SEN-PROD02; SEN-PROD03; SEN-PROD04 |  | SEN-PROD02 |  |  |  | Shweta/Kishore |  |  | No | ERP | US | RE-HOST
Trackwise (EU) |  | DEV | Aileen Diola | Sri Tupil |  |  | CHAARSMAPPW03 |  | CHAARSMAPPW03 |  |  |  | Vidit | Srikanth Venkatasen |  | No | RAQA | EMEA | RE-HOST |  | OOS by Aileen, PMO Team to follow and get the approval from Ken.
Trackwise (EU) |  | VAL | Aileen Diola | Sri Tupil |  |  | CHAARSMAPPW04 |  | CHAARSMAPPW04 |  |  |  | Vidit | Srikanth Venkatasen |  | No | RAQA | EMEA | RE-HOST |  | OOS by Aileen, PMO Team to follow and get the approval from Ken.
Trackwise (EU) |  | PROD | Aileen Diola | Sri Tupil |  |  | CHAARSMAPPW05 |  | CHAARSMDBPW02 |  |  |  | Vidit | Srikanth Venkatasen |  | No | RAQA | EMEA | RE-HOST |  | Confirmed by AIleen to take it OOS. PMO Team to follow up with Ken and get the approval and update the Move Group Tracker accordingly.
Visionaire Case Processing of Images |  | QA | Requalann Pereira | Sri Tupil |  |  | USMAN-SMWSQVW02 | [5 empty] | Deepak |  |  | No | R&D | US, EMEA, APAC | RE-HOST
Visionaire Case Processing of Images |  | LB | Requalann Pereira | Sri Tupil |  |  | USMEM-SMAPPVW22 | [5 empty] | Deepak |  |  | No | R&D | US, EMEA, APAC | RE-HOST
Visionaire Case Processing of Images |  | PROD | Requalann Pereira | Sri Tupil |  |  | USMEMSMAPPVW08; USMEM-SMAPPVW21; USMEM-SMAPPVW23; CHAARSMAPPW08; CHAARSMFSPW02; AUSYDSMAPPW01; AUSYDSMFSPW02; NOISRV001; NOISRV002; NOISRV003; |  | USMAN-SMWSDVW04; USMANSMAPDVW30; USMEM-SMAPDVW29;AUSYDSMAPDW01; |  |  |  | Deepak |  |  | No | R&D | US, EMEA, APAC | RE-HOST
Visual SVN |  | PROD | Requalann Pereira | Sri Tupil |  |  | EQVSRD00 | [5 empty] | Raju |  |  | No | R&D | US | RE-HOST
Flex LM |  | PROD | Requalann Pereira |  |  |  | MEMSRV403; MEMSRV434; | [8 empty] | No | R&D | US | RE-HOST
MIMICS |  | PROD | Requalann Pereira |  |  |  | MEMSRV434; | [8 empty] | Yes | R&D | US | RE-HOST
Myriad |  | PROD | Requalann Pereira |  |  |  | MEMSRV403 | [8 empty] | No | R&D | US | RE-HOST
Unigraphics |  | PROD | Requalann Pereira |  |  |  | MEMSRV403; MEMSRV434; | [8 empty] | No | R&D | US | RE-HOST
TOTVS |  | DEV | Eduardo Lima | Firas Almahamid | W3-MG1 | 2021-03-05 | SEN-HOMOL01; SEN-HOMOL02 |  | SEN-HOMOL02 |  |  |  | Shweta/Kishore | Rahul Sarin |  | No | ERP | US | RE-HOST |  | Arun has requested the SDM to expedite response on Infra team queries.

## Change LOG
Date | Update | Owner
2021-02-02 | Connect Ship (UPS/DHL) App Server Name were corrected as per team inputs in daily call. | Arun Sharma
2021-02-04 | Updated correct inventory for AWM, WDI, BOBJ, GDW & GMM | Saurabh Gairola
2021-02-08 | WDI and AWM Data Warehouse now rescheduled for W3-MG2. | Arun Sharma
2021-02-08 | Trackwise Removed from Cutover-MG. Its Out of scope as per Aileen Request.( Update from Master Tracker) | Arun Sharma
2021-02-08 | MIMS Dev is Test.QA is Archive -prod. Updated App Server details as well | Arun Sharma
2021-02-08 | MIMS Prod and DR server inventory updates as per Deepak request | Arun Sharma
2021-02-09 | MCOSMOS is Out of scope. Removed from W3-MG2 ( Update from Master Tracker) | Arun Sharma