## Sheet1
Take application database backup | On-Prem | HCL Infra team
Check SQL server product and features installed on new DB server | Azure Cloud | HCL Infra team
Check the SSMS connectivity on new DB server | Azure Cloud | HCL Infra team
Connect to the SQL database server | Azure Cloud | HCL Infra team
Create a new database with the same name as On-prem | Azure Cloud | HCL Infra team
Recover the data from the database backup file | Azure Cloud | HCL Infra team
Check the database functionality (data retrieval, SQL jobs, Maintenance plans) | Azure Cloud | HCL App team

## Sheet2
UKRTHSMDBPVW29
As we can see that two task schedulers jobs are running in the server with OEE application specific service accounts enabled ,please share those credentials for enabling/disabling jobs during the cutover. Task Scheduler Jobs: Restart OEE server service Start OEE Service on boot. Service Accounts User Name : UKRTHSMDBPVW29\OEE_Service SNCORP\hurlx | Richard will join the call during cut over and put his pass words for Jobs of Task sheduler.
In IIS there are four urls which are configured as web apps for dash boards please clarify us how these dash boards are being used. http://localhost/IdhammarDashboards http://localhost/IdhammarDashboards2/ http://localhost/IdhammarDashboards3/ http://localhost/LaunchDashboard/
We can see that Report server DB instance running on the DB please clariy us how it being used. Please clarify all below DB’s are being used for OEE itself. Dashboard Dashboard2 Dashboard3 IdhammarOEE6 ReportServer ReportServerTempDB | Action Item for Robert - What report servers ar ebeing used for OEE
We can see that multiple SQL Agent Jobs are running on the Sql server please clarify me how these are being used for the application.
We can see that under control panel OEE Client,OEE Dashboard,OEE Server are installed on server. All these software will comes along with the OEE installable package that resides in the path : C:\Program Files (x86)\Idhammar Systems\OEE Client. Or is there any external other package being used to get create then on the server.
Is there any specific reason team viewer being used inside the server. | Needs to uninstall before cutover
Transfer License to the new cloud server | Action Item for Robert wil support during cutover
Back up Retention Polocy that configured on on-prem server | Rahul