## SalesRequestForms
S.NO. | Requirements | Track Leads Response
1 | Access Details – Server OS – App User access, Database Access / OS – Service Accounts, permissions, access. | 1. SNOW - sys accounts 2. App Access - AD Authentication - User to be added at the backend. Alternate way to add user in the sql db. 3. Admin access to database.
2 | Dependencies & External Systems, Integration Endpoints, Notifications - SMTP | 1. Data being pulled from Oracle database (Source) to SQL DB (Target) - Datahub SONAR jobs running to load in oracle Db (Source) - Maintained via Yash Tech. 2. Oracle Connections are configured within the App Config files. 3. Queries to pull the data are part of App Transaction to pull the data to SQL DB. 4. Email ID - Setup in Config files.
3 | Source Code – Version, Tag | 1. Bitbucket Access Available 2. Repo Setup, No Version Control- One time activity done on 2019. 3. That is the latest Code for deployment during Migration.
4 | Deployment Mechanism, Releases Timings, Any Code Freeze period | 1. Comitting changes in the repo. 2. Manual Deployment Steps. - Creating Artifacts 3. Deploying directly on to the server.
5 | Web Server Details – Path, Config files, instances. | 1. IIS, Config files and Paths are available.
6 | All Configurations placeholders, files, system details. | 1. Oracle, SQL, SMTP Connections details.
7 | Database Details, Schema, Clients, Connections, Data sources. | 1. One Database Server for each env. 2. Database Name - SN_Salesrequestforms. 3. No other datasources other than Oracle Connections 4. One Database Schema
8 | App URLs, App Server details – Path, Instances, JVM parameters, JDK, etc. | 1. One URL for each env. 2. JDK, JVM comes within the .NET Installation Pack.
9 | SOPs for Application Maintenance.
10 | Any ongoing critical Incidents.
11 | Any Challenges/issues from Support team perspective.
12 | Additional details/requirements to perform the migration
13 | Pre requisites – If any specifically, other than access.
14 | Is it a 32-bit or 63-bit OS?
15 | Are there any scheduled downtime, we should be aware of?
16 | Any kind of Task Scheduler?
17 | What is the OS service Pack?
18 | Standalone DB or Cluster?
19 | Stakeholders, App Owners, SME's
20 | Downtime Approval and Communication?

## HR notification
S.NO. | Requirements | Track Leads Response
1 | Access Details – Server OS – App User access, Database Access / OS – Service Accounts, permissions, access. | 1. SNOW - sys accounts - Windows 2012 2. App Access - AD Authentication - By Default - No Roles needed 3. Access to database. - Table access, One Schema. Config files in the app 4. New App handed over to HCL
2 | Dependencies & External Systems, Integration Endpoints, Notifications - SMTP | 1. Data being updated via forms 2. SQL Connections are configured within the App Config files. 3. Email ID - Setup in Config files. - SMTP Config
3 | Source Code – Version, Tag | 1. Bitbucket Access Available - Will be provided by App Support Team 2. Repo Setup, No Version Control 3. That is the latest Code for deployment during Migration.
4 | Deployment Mechanism, Releases Timings, Any Code Freeze period | 1. Comitting changes in the repo. 2. Manual Deployment Steps. - Creating Artifacts 3. Deploying directly on to the server.
5 | Web Server Details – Path, Config files, instances. | 1. IIS 7.5, Config files and Paths are available. - No Documentation available, but a walkthrough sessions can be setup with App Support
6 | All Configurations placeholders, files, system details. | 1. SQL, SMTP Connections details.
7 | Database Details, Schema, Clients, Connections, Data sources. | 1. One Database Server for each env. 2. Database Name - TempContractorOwn. Few Tables 3. No Integration - Like Batch Jobs, ftp etc. 4. SQL Server 2012
8 | App URLs, App Server details – Path, Instances, JVM parameters, JDK, etc. | 1. One URL for each env. 2. JDK, JVM comes within the .NET 4.0 Installation Pack maintained by windows team 3. No SSL Configuration
9 | SOPs for Application Maintenance. | Recently transitioned app so transition doc created as per KT. Runbook is available.
10 | Any ongoing critical Incidents. | NA
11 | Any Challenges/issues from Support team perspective. | Not yet as the incidents raised are very less
12 | Additional details/requirements to perform the migration | Nil
13 | Pre requisites – If any specifically, other than access. | TBD
14 | Is it a 32-bit or 63-bit OS? | 64 bit
15 | Are there any scheduled downtime, we should be aware of? | Weekend Downtime Acceptable
16 | Any kind of Task Scheduler? | No
17 | What is the OS service Pack? | No Pack
18 | Standalone DB or Cluster? | standalone
19 | Stakeholders, App Owners, SME's | HR,Tony Howard - Business App Owner,Ritesh Prakash,Paul Davison - SDM
20 | Downtime Approval and Communication? | TBD

## Connectship
S.NO. | Requirements | Track Leads Response
1 | Access Details – Server OS – App User access, Database Access / OS – Service Accounts, permissions, access. | 1. SNOW - Sys accounts 2. App Access - AD Authentication. 3. Admin access to database.
2 | Dependencies & External Systems, Integration Endpoints, Notifications - SMTP | 1. It is Connected to link XPS installed at SAP-PR1 . The link must point to new azure location. 2. DB is configured in application Setup itself, which is poiniting to the DB server. DB will point to existing DB server. 3. Printers, which are currentely available on APP server must installed on new azure location.
3 | Source Code – Version, Tag | 1. Vendor's application- Exe setup will be provided by vendor for installation. 2. Azure copmatible .setup will be installed with the help of vendor OR steps will be given to install.
4 | Deployment Mechanism, Releases Timings, Any Code Freeze period | Vendor will install the compatible .exe file OR steps will be given by vendor to install it on azure.
5 | Web Server Details – Path, Config files, instances. | NA
6 | All Configurations placeholders, files, system details. | NA
7 | Database Details, Schema, Clients, Connections, Data sources. | SQL DB:- server=USMANSMDBPCW8B.sncorp.smith-nephew.com;database=Progistics
8 | App URLs, App Server details – Path, Instances, JVM parameters, JDK, etc. | Application Setup will be given by vendor compatible to cloud environment.
9 | SOPs for Application Maintenance. | SOP, Rubnook, KBAs are available.
10 | Any ongoing critical Incidents. | NA
11 | Any Challenges/issues from Support team perspective. | NA
12 | Additional details/requirements to perform the migration | NO
13 | Pre requisites – If any specifically, other than access. | NO
14 | Is it a 32-bit or 63-bit OS? | 64
15 | Are there any scheduled downtime, we should be aware of? | No
16 | Any kind of Task Scheduler? | NA
17 | What is the OS service Pack? | 2012R2
18 | Standalone DB or Cluster? | Standalone
19 | Stakeholders, App Owners, SME's | Mark Perry(Vendor), Amit Shokeen(SDM), Sumanth/Kamal(SME)
20 | Downtime Approval and Communication? | Will be available on demand. Every one Communicated regarding cloud migration

## LDAP Update
S.NO. | Requirements | Track Leads Response
1 | Access Details – Server OS – App User access, Database Access / OS – Service Accounts, permissions, access. | 1. SNOW - sys accounts 2. App Access - AD Authentication 3. Access to database.
2 | Dependencies & External Systems, Integration Endpoints, Notifications - SMTP | 1. Data being updated via forms 2. SQL Connections are configured within the App Config files. 3. Email ID - Setup in Config files.
3 | Source Code – Version, Tag | 1. Bitbucket Access Available 2. No Version Control 3. That is the latest Code for deployment during Migration.
4 | Deployment Mechanism, Releases Timings, Any Code Freeze period | 1. Comitting changes in the repo. 2. Manual Deployment Steps. - Creating Artifacts 3. Deploying directly on to the server.
5 | Web Server Details – Path, Config files, instances. | 1.Config files and Paths are available.
6 | All Configurations placeholders, files, system details. | 1. SQL, SMTP Connections details.
7 | Database Details, Schema, Clients, Connections, Data sources. | 1. One Database Server for each env. 2. Database Name - LDAP
8 | App URLs, App Server details – Path, Instances, JVM parameters, JDK, etc. | 1. No url available for this application as we have only backend. 2. JDK, JVM comes within the .NET Installation Pack maintained by windows team
9 | SOPs for Application Maintenance. | Transition doc created as per KT
10 | Any ongoing critical Incidents. | NA
11 | Any Challenges/issues from Support team perspective. | No
12 | Additional details/requirements to perform the migration | Nil
13 | Pre requisites – If any specifically, other than access. | TBD
14 | Is it a 32-bit or 63-bit OS? | 64
15 | Are there any scheduled downtime, we should be aware of? | NA
16 | Any kind of Task Scheduler? | Yes. Job has been configured in Task Scheduler
17 | What is the OS service Pack? | No Pack
18 | Standalone DB or Cluster? | standalone
19 | Stakeholders, App Owners, SME's | Andres Bernard, Maagedha Shajahan
20 | Downtime Approval and Communication? | TBD
Notes:
It’s a vendor developed deployable COTS product.
Set-up will be provided compatible with new environment to install it on Azure.
Installation steps will be given And/Or vendor will be deploy the set-up on request.
Console application is created on .NET and hosted on the same VMs where LDAP Backend Database is hosted for both Prod and Dev
SNI Developed
Batch Job running daily in .NET - Scheduled in Task Scheduler on the Server
There is no direct connections to any external app. Instead Other apps are referring the LDAP url for the authentication details.
Need to raise request for database access - Separate request to be raised
Console app will get authenticated via AD, it will pull the data from AD and put it in LDAP Database in the SQL Backend.

## TopsPro
S.NO. | Requirements | Track Leads Response
1 | Access Details – Server OS – App User access, Database Access / OS – Service Accounts, permissions, access. | 1. No sys accounts 2. No App Access 3. End user Workstation installtion 4. 2012 R2 Standard
2 | Dependencies & External Systems, Integration Endpoints, Notifications - SMTP | NA
3 | Source Code – Version, Tag | Source Code - NA COTS application Version - 6.5
4 | Deployment Mechanism, Releases Timings, Any Code Freeze period | NA
5 | Web Server Details – Path, Config files, instances. | License Server : USAUS-SMLIPVW02
6 | All Configurations placeholders, files, system details. | Path for configuration files and license file : C:\Program Files (x86)\TOPSAPPS\TOPSPro
7 | Database Details, Schema, Clients, Connections, Data sources. | NA
8 | App URLs, App Server details – Path, Instances, JVM parameters, JDK, etc. | 1. One URL for each env. 2. JDK, JVM comes within the .NET Installation Pack.
9 | SOPs for Application Maintenance. | NA
10 | Any ongoing critical Incidents. | NO
11 | Any Challenges/issues from Support team perspective. | NO
12 | Additional details/requirements to perform the migration | NO
13 | Pre requisites – If any specifically, other than access. | NA
14 | Is it a 32-bit or 64-bit OS? | 64 Bit
15 | Are there any scheduled downtime, we should be aware of? | NO
16 | Any kind of Task Scheduler? | NO
17 | What is the OS service Pack? | Version - 6.3
18 | Standalone DB or Cluster? | NA
19 | Stakeholders, App Owners, SME's | NA
20 | Downtime Approval and Communication? | NA
Desktop Software, Connects to License Server.
License Server is accessible via RDP
1 Prod env
No URL, Client access
Hostname must be configured with the same name in Azure Cloud
Stakeholders?
Remotely Connecting to the License Server

## Pilot Inventory
Application | Count | Treatment | Verticle | Dependencies/integrations | PROD |  | TEST |  | QA |  | DEV |  | EVAL |  | DR |  | LB | Cluster IP
| 24 |  |  |  | APP Server | DB Server | APP Server | DB Server | APP Server | DB Server | APP Server | DB Server | APP Server | DB Server | APP Server | DB Server
Oracle Enterprise Manager | 5 | RE-PLATFORM | Data & Analytics | CoHosted: Cognos BI (Complaints Analytics)-Prod RSG-Out Of Scope Services Informatica MDM Data Quality-Prod Informatica P360-Prod Global Business Information Platform-Prod | USATL-SMAPPUL02 | USATL-SMDBPUL02 | USMEM-SMAPTVL13 | USMEM-SMDBTVL12 | [7 empty] | USATL-SMDBPUL04
Paymetric | 2 | RE-HOST | ERP |  | USMANSMPMPVW01 |  |  |  | USMANSMPMDVW01
Tops Pro | 1 | RE-HOST | R&D |  | USAUS-SMLIPVW02
HR Notification | 6 | RE-PLATFORM | Group Functions | SNID Archived shipping documents ECAP ENCORE Endo Loans Global Return Disposition Tool GSC Datawarehouse Admin Tool Inventures Web App Nomino Security QA Change Control Recon LaunchPad(SSO) Reimbursement Sales Request Forms Non-Employee Database | USMAN-SMWSPVW12 | USMAN-SMDBPVW12 | USMAN-SMWSQVW05 | USMAN-SMDPDVW16 |  |  | USMAN-SMWSDVW07 | USMAN-SMDPDVW16
Connect Ship (UPS/DHL) | 6 | RE-PLATFORM | Supply Chain | SAP, warehouse Printers. | USMAN-SMAPPVW51 | USMANSMDBPCW08 USMANSMDBPCW07 |  |  |  |  | USMAN-SMAPDVW32 | USMANSMDBDUW01 | [5 empty] | USMANSMDBPCW8b
KepServerEx (Amsterdam) | 2 | RE-HOST | Manufacturing |  | UKHULSMDBPVW02 | UKHULSMDBPVW04
LDAPUpdate | 2 | RE-PLATFORM | Commercial | With LDAPUpdate few other applications are co-hosted in the same server. -> Contracts -> ECAP -> Endo Loans -> Inventures (SCAMPI) Web App -> Kitting -> LeadTracker -> Reimbursement -> Salient |  | USMAN-SMDBPVW12 |  | USMAN-SMDPDVW16
Abacus |  | RE-PLATFORM |  | Remarks: VM Build will be taken care by Infra and App hosting and support will be taken care by SNI SME's as recorded in the assessment as well.

## Rehost_Migration_Steps
S.No. | Migration Steps | Platform | Planning Week
1 | Confirm the downtime duration and time from SDM | On-Prem | T5
2 | Access details to be verified for OS, App Server, Database | On-Prem | T4
3 | Validate the current system on-prem and get a confirmation from SDM on application stability | On-Prem | T4
4 | Verify the Application server configurations, JVM, instances, logs, etc | On-Prem | T4
5 | Verify the database schemas, connection strings, datasources, config files, etc | On-Prem | T4
6 | Verify all the configuration specified within the application artifact | On-Prem | T4
7 | Verify if any Hard coded configuration is done anywhere within the artifact deployed | On-Prem | T4
8 | Run the Smoke Test cases and do a complete Sanity on the application | On-Prem | T4
9 | Check the IIS configurations, Paths, config files, doc root, site configurations, etc | On-Prem | T4
10 | Verify the integrations points and check all ftp location, ips, and the placeholders in the application server | On-Prem | T4
11 | Verify the Batch jobs running and their schedule, ftp details and other integrations points | On-Prem | T4
12 | Verify the DR environment,if any and the switchover steps | On-Prem | T4
13 | Prepare and validate the roll back steps and confirm with SDM | On-Prem | T4
14 | Get the Final confirmation from SDM/SME's for Cloud Migration & the application stability and to switch off On-Prem | On-Prem | T2 | Latency or I/O speeds
15 | Verify all configuration placeholders (IIS, .NET, DB Listeners) after the OS image has been installed to Azure Cloud | Azure Cloud | T4
16 | Restart all services in sequence (IIS, .NET, DB Listeners) after the OS image has been installed to Azure Cloud. | Azure Cloud | T4
17 | Follow the SOP's and validate all integration points with other applications and On-prem systems like - SAP | Azure Cloud | T2
18 | Validate the artifact deployed is running properly and the application is stable | Azure Cloud | T2
19 | Validate the logs and check for errors | Azure Cloud | T2
20 | Execute the batch jobs and validate the data | Azure Cloud | T2
21 | Check the database performance, indexing | Azure Cloud | T2 | Number of VM
22 | Run the Smoke Test cases and do a complete Sanity on the application | Azure Cloud | T1 | Number of DB
23 | Coordinate with SDM/SME's for Unit Test cases and support during the Acceptance Testing | Azure Cloud | T1 | Network bandwidth
24 | Shutdown services in On-Prem servers | On-Prem | T0 | Number of RAMS
25 | Validate the On-prem system and ensure no process is active and running | On-Prem | T0 | Number of Cores
26 | Sent out Migration confirmation to all stakeholders, informing that the application is live in Azure Cloud | Azure Cloud | T0 | SANS
27 | Get the Sign Off from SDM | Azure Cloud | T0 | Number of IP's
Number of Firewall Ports
"Application Migration" Definition of Done
1 | Application architecture diagram Initial Draft Creation. |  |  | URL's (internal Users)
2 | Application SOP baselined (SNI operation, App support team version). |  |  | URL's (External Users)
3 | Application Roll back plan documented and approved by ALL (infra/SNI) |  |  | Identify List of Users/Admins or Group of users are able to access this applicaitin using their accounts/cerdentials
4 | Application re-image (Re-host cases) OR installed (Re-Platform cases) move completed to new Host. |  |  | Physical location of apps files
5 | Application Data are moved (Data integrity test) - Expreess Route or manual VPN based jobs |  |  | Physical location of data files
6 | All services (automtic/manual) are runnign/listening |  |  | System Environment Variable, e.g. JAVA, .net home, etc
7 | Checklist- Able to switch on/off App instances/services/batch jobs/Deomon/operation/Agents/Cron jobs etc. |  |  | Max Pool size
8 | Checklist - All confuguration are in place AS IS (re-host cases) or created (re-platform cases). |  |  | Max Cache size
9 | new internal URL's can be accessed by SNI users
10 | new Public URL's can be accessed by external (partners) users
11 | Testing - Application is loading and performing (landing page, and other fucntions, etc.)
12 | Having all files readable and accessible on the cloud with no issues on I/O CRUD (create, read, update and delete) operation.
13 | Collect evidence of Traffic hitting new server.
14 | Collect evidence of Traffic are not seen going to Old On-Prem Server.
15 | No leftover private/temp data on the server.
16 | Application SOP updated (+1 version) and sign off from SNI operation + App support team
17 | Architecture diagram created and updated.
18 | Access revoked before handing over to Opertions/App Support
19 | Business team approves
20 | Ken Approval

## RePlatform_Migration_Steps
S.No. | Migration Steps | Platform | Planning Week
1 | Access details to be verified for OS, App Server, Database | On-Prem | T5
2 | Validate the current system on-prem and get a confirmation from SDM on application stability | On-Prem | T4
3 | Confirm the downtime duration and time from SDM | On-Prem | T4
4 | Verify the Application server configurations, JVM, instances, logs, etc | On-Prem | T4
5 | Verify the database schemas, connection strings, datasources, config files, etc | On-Prem | T4
6 | Verify all the configuration specified within the application artifact | On-Prem | T4
7 | Verify if any Hard coded configuration is done anywhere within the artifact deployed | On-Prem | T4
8 | Run the Smoke Test cases and do a complete Sanity on the application | On-Prem | T4
9 | Check the IIS configurations, Paths, config files, doc root, site configurations, etc | On-Prem | T4
10 | Verify the integrations points and check all ftp location, ips, and the placeholders in the application server | On-Prem | T4
11 | Verify the Batch jobs running and their schedule, ftp details and other integrations points. | On-Prem | T4
12 | Verify the DR environment,if any and the switchover steps | On-Prem | T4
13 | Prepare and validate the roll back steps and confirm with SDM | On-Prem | T4
14 | Verify the Source Code Location, Latest TAG & Artifact for deployment | On-Prem | T4
15 | Verify the Deployment mechanism, all manual steps to be verified with App Support team and the SDM/SME's | On-Prem | T4
16 | Verify all configuration placeholders (IIS, .NET, DB Listeners) where the new ip change to be taken care | On-Prem | T4
17 | Get the Final confirmation from SDM/SME's for Cloud Migration & the application stability and to switch off On-Prem | On-Prem | T2
18 | Setup & configure the SQL Database with necessary schemas, after the OS Build is ready in Azure Cloud | Azure Cloud | T2
19 | Configure the clustering services with new IP/Hostname as applicable. | Azure Cloud | T2
20 | Run the Data Migration for SQL Database from On-Prem | Azure Cloud | T2
21 | Validate all tables, views, joins, Constraints, indexing. | Azure Cloud | T2
22 | Re-Build the artifact with the new Database IP/Hostnames using Pipelines/Manual steps as applicable | Azure Cloud | T2
23 | Deploy the artifact in the application server | Azure Cloud | T2
24 | Verify all configuration placeholders (IIS, .NET, DB Listeners) | Azure Cloud | T2
25 | Restart all services in sequence (IIS, .NET, DB Listeners) | Azure Cloud | T2
26 | Follow the SOP's and validate all integration points with other applications and On-prem systems like - SAP | Azure Cloud | T2
27 | Validate the artifact deployed is running properly and the application is stable | Azure Cloud | T2
28 | Validate the logs and check for errors | Azure Cloud | T2
29 | Execute the batch jobs and validate the data | Azure Cloud | T2
30 | Check the database performance, indexing | Azure Cloud | T2
31 | Run the Smoke Test cases and do a complete Sanity on the application | Azure Cloud | T1
32 | Coordinate with SDM/SME's for Unit Test cases and support during the Acceptance Testing | Azure Cloud | T1
33 | Shutdown services in On-Prem servers | On-Prem | T0
34 | Validate the On-prem system and ensure no process is active and running | On-Prem | T0
35 | Sent out Migration confirmation to all stakeholders, informing that the application is live in Azure Cloud | Azure Cloud | T0
36 | Get the Sign Off from SDM | Azure Cloud | T0